# Annual Work Plan 2014

Rev5, 30 Dec 2013

Development of a robust Standardization, Quality Assurance, Accreditation and Metrology (SQAM) Infrastructure in Malawi

Country: MALAWI

Theme 1: Sustainable and Equitable Economic Growth and Food Security

UNDAF Outcome 1.3:	Productive poor benefit from decent work, income generation and pro-poor private sector growth by 2016;

UNDAF Output 1.3.3	National Export Strategy clusters are supported through enterprise and skills development, financial services, cooperatives development, promotion of structured markets and national quality infrastructure;

Expected CPD Output(s): 	New business-to-business opportunities for Malawi products;

Expected Project Output(s) 		1. Strengthened capacity of the Malawi Bureau of Standards to deliver business services and to achieve financial sustainability;

2. Technical Regulations reviewed to promote efficient, effective and accountable delivery of information in accordance with SQAM legislation and regulations;

3. Structurally enhanced capacity of the Malawi Bureau of Standards for conformity assessment services;

4. Strengthened, proactive and responsive National Enquiry Points (NEP) to the information and notification requirements of WTO/TBT/SPS agreements;

5. Sanitary and Phytosanitary (SPS) infrastructure improved and mainstreamed into National polices;

6. Capacity of Small and Medium sized Enterprises (SME), and particularly women and youth led enterprises, strengthened to comply with quality requirements; and

7. MBS compliant with International Regulations established.

Implementing Partner:		Malawi Bureau of Standards (MBS)

Responsible Parties:			UNIDO, UNDP, MBS

Note:

The conversion rate EUR/USD applied for the AWP 2014 is the official UN exchange rate of 0.736 as of December 2013.

## Annual Work Plan

##### 01 January – 31 December 2014

| EXPECTED CP OUTPUTS and indicators including annual targets | PLANNED ACTIVITIES List all activities including M&E to be undertaken during the year towards stated CP outputs | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount US$ |
| OUTPUT 1: Strengthened capacity of the Malawi Bureau of Standards to deliver business services and to achieve financial sustainability |
| Number of National Quality Policies (NQP), fast-tracked and approved by Cabinet. Baseline: 1 draft Target: 1 approved National Quality Policy. Level of increased organizational effectiveness of MBS Baseline: to be determined at project inception Target: MBS revised structure and procedures created and operationalized. Percentage increment of business services per year provided to Malawian organisations, both public and private, Baseline: 100 Standards developed, 142 Certified products and Services, 3046 Samples Tested, 800 Verification Audits -Metrology Services) Target: 30 % increase in services/per year Percentage increase in revenue growth per year Baseline: 20%/year Target: 30%/year | 1.0 National Quality Policy |  |  |  |  | MoIT MBS UNDP UNIDO | UNDP | 71300 - Local Consultant 75700- Training, Workshops and Confer 75700 - Training, Workshops and Confer | 15 000 5 000 6 000 |
|  | - The finalisation of the activity is being concluded as part of the NORAD project |  |  |  |  |  |  |  |  |
|  | - Dissemination of the NQP was provided for under Output 8 but will roll over from 2013 |  |  |  |  |  |  |  |  |
|  | - Development of a National Quality Strategy (NQS) |  |  |  |  |  |  |  |  |
|  | Project Visibility event As from AWP2014, all visibility events are provided for under Output 8 as part of the Communications and Visibility activity |  |  |  |  |  |  |  | 0 |
|  | Review and set-up of organisational structures, service delivery procedures and knowledge management within MBS |  |  |  |  | MBS MoIT UNDP | UNDP | 74100 - Professional Services | 25 800 |
|  | - Functional review of the MBS |  |  |  |  |  |  |  |  |
|  | - Improved organisational business management systems -Enterprise Resource Planning (ERP) |  |  |  |  |  |  |  |  |
|  | Market survey on the demand for testing and calibration in Malawi |  |  |  |  | MBS UNDP | EU |  | 0 |
|  | - Continuation of activity from 2013 |  |  |  |  |  |  |  |  |
|  | Preparation of a business plan and monitoring system for MBS. |  |  |  |  | MBS UNIDO | EU |  | 0 |
|  | - Collaboration between MBS Management and CTA |  |  |  |  |  |  |  |  |
|  | Development of a "marketing unit" within MBS. |  |  |  |  | MBS UNIDO | EU | 71200 - International Consultants | 21 223 |
|  | - This activity need to follow from the functional review and will consider MBS marketing policy and the development of a marketing strategy |  |  |  |  |  |  |  |  |
|  | Enhancement and updating of MBS website |  |  |  |  | MBS UNDP |  |  | 0 |
|  | - Continuation from 2013 |  |  |  |  |  |  |  |  |
|  | Preparation and implementation of a "training plan" for MBS. |  |  |  |  | MBS UNIDO | EU | 75700 - Training, Workshops and Confer | 81 522 |
|  | - International training in testing/calibration and key MBS functions. This primarily through study tours, attendance of conferences, workshops. |  |  |  |  |  |  |  |  |
| Sub-Total |  |  |  |  |  |  |  |  | 154 545 |
| OUTPUT 2: Technical Regulations reviewed to promote efficient, effective and accountable delivery of information in accordance with SQAM legislation and regulations |
| Number of Technical Regulations reviewed and aligned to International regulations and legislation Baseline: 8; Target: 12 Number of organizations promoting clear technical regulations Baseline: 8; Target: 12 | 2.1 Documentary and field survey of the Malawian situation with regards to technical regulations and enforcement. |  |  |  |  | MBS UNDP UNIDO |  |  | 0 |
|  | NOTE: Delay implementation till USAID project concludes, Evaluate manner in which outputs will be achieved during mid-term review. USAID project is fielding a consultant in Q1 to do situational analysis. Enforcement is however not necessarily included in scope of that work. |  |  |  |  |  |  |  |  |
|  | 2.2 Awareness campaigns and training on "Better regulation". |  |  |  |  | MBS UNDP UNIDO |  |  | 0 |
|  | NOTE: Delay implementation till USAID project concludes, Evaluate manner in which outputs will be achieved during mid-term review. |  |  |  |  |  |  |  |  |
|  | 2.3 Data gathering on TR, analysis and consolidation. Preparation of a strategy and a plan for the institutionalisation of "Better Regulation" in Malawi. |  |  |  |  | MBS UNDP UNIDO |  |  | 0 |
|  | NOTE: Delay implementation till USAID project concludes, Evaluate manner in which outputs will be achieved during mid-term review. |  |  |  |  |  |  |  |  |
|  | 2.4 Preparation of a strategy and a plan for the institutionalisation of "Better Regulation" in Malawi |  |  |  |  | MBS UNDP UNIDO |  |  | 0 |
|  | NOTE: Delay implementation till USAID project concludes, Evaluate manner in which outputs will be achieved during mid-term review. |  |  |  |  |  |  |  |  |
| Sub-Total |  |  |  |  |  |  |  |  | 0 |
| OUTPUT 3: Structurally enhanced capacity of the Malawi Bureau of Standards for conformity assessment services |
| Number of Metrology Institutes constructed Baseline: 0; Target:1 Percentage increase in demand and supply of MBS business services (standards, training services, testing and calibration. Baseline: 21%/year; Target: 30% /year Number of accreditations granted by an accreditation body full member of IAF. Baseline: 0; Target: 1 Number of MBS management systems certification body accreditations granted by an accreditation body full member of IAF for the international standards; ISO 9001 ISO 22000 and HACCP. Baseline: 0; Target: 1 Number of MBS testing laboratories accreditation granted by an accreditation body full member of ILAC for the international standards. Baseline: 0; Target: 2 Number of MBS calibration laboratories accreditation granted by an accreditation body full member of ILAC for the international standards. Baseline: 0; Target: 2 Number of MBS training units established Baseline: 0 ; Target: 1 | 3.1a Construction of the Metrology building (incl main Chichiri and satellite Maone site). |  |  |  |  | MBS MoIT | GoM |  | 0 |
|  | - Award of the contract to the Architect (design, oversight) [215m MKW] |  |  |  |  |  |  |  |  |
|  | - Design and Approval of plans, |  |  |  |  |  |  |  |  |
|  | - Securing financing for actual construction, [1.4bn MKW (indicative)] |  |  |  |  |  |  |  |  |
|  | - Tender processes for building contractor and contract award |  |  |  |  |  |  |  |  |
|  | - Construction commences |  |  |  |  |  |  |  |  |
|  | 3.1b Develop within MBS an accredited product certification body |  |  |  |  | MBS UNIDO UNDP | EU | 71200 - International Consultants 72100 - Contractual Services Companies 75700 - Training, Workshops and Confer | 25 951 27 174 9 000 |
|  | - Management system for the application the ISO/IEC 17065; Definition of objectives and requirements; initial evaluation (gap analysis); planning |  |  |  |  |  |  |  |  |
|  | - Training on the application of ISO/IEC 17065 for all personnel working for the certification body for product certification. (approx. 20 participants). |  |  |  |  |  |  |  |  |
|  | - Management system for the application the ISO/IEC 17065. Design and development; implementation; evaluation. |  |  |  |  |  |  |  |  |
|  | - Internal independent auditing for accreditation under the supervision of a certified auditor. |  |  |  |  |  |  |  |  |
|  | - Accreditation services provided by an accreditation body full member of IAF. (secure the service provider in Q4 in view of accreditation during Q1, 2015). |  |  |  |  |  |  |  |  |
|  | Develop within MBS a management systems certification body for: ISO 9001 (quality management systems); ISO14001 (environmental management systems); ISO 22000 (food safety management systems) |  |  |  |  | MBS UNDP | EU | 71200 - International Consultants 72100 - Contractual Services Companies 75700 - Training, Workshops and Confer | 25 951 27 174 9 000 |
|  | - In recognition of MBS having an ISO/IEC 17021 system in place, gap analysis by MBS to inform training; |  |  |  |  |  |  |  |  |
|  | - Training on the application of ISO/IEC 17021 for all personnel working for the certification body for the three management systems. (approx. 30 participants). |  |  |  |  |  |  |  |  |
|  | - Review of the MBS Management system for the application the ISO/IEC 17021, expand to include ISO14001 and ISO22000 |  |  |  |  |  |  |  |  |
|  | Internal independent auditing for accreditation under the supervision of a certified auditor; initial focus on ISO9001 |  |  |  |  |  |  |  |  |
|  | Accreditation services provided by an accreditation body full member of IAF. (secure the service provider in Q4 in view of accreditation during Q1, 2015, initial scope limited to ISO9001) |  |  |  |  |  |  |  |  |
|  | 3.3 Upgraded and accredited testing laboratories in MBS. |  |  |  |  | MBS UNIDO |  | 72200 - Equipment 71200 - International Consultants 72100 - Contractual Services Companies 75700 - Training, Workshops and Confer | 271 739 34 375 27 174 13 109 |
|  | - Procurement of selected equipment (ICT and Scientific) |  |  |  |  |  |  |  |  |
|  | - UNIDO to provide copies of guidelines for implementation of ISO/IEC17025 |  |  |  |  |  |  |  |  |
|  | - Training on the application of ISO/IEC 17025 for calibration and testing. |  |  |  |  |  |  |  |  |
|  | - Management system for the application the ISO/IEC 17025; Definition of objectives and requirements; initial evaluation; planning (gap analysis). Specific output is the recommended scope for testing services to be accredited. (microbiology/ pesticides/ food chemistry/ engineering). |  |  |  |  |  |  |  |  |
|  | - Management system for the application the ISO/IEC 17025. Design and development; implementation; evaluation. |  |  |  |  |  |  |  |  |
|  | Initiate quality control/ compliance activities to address gaps: Training in uncertainties Calibration of equipment Reference materials Environmental conditions Proficiency testing |  |  |  |  |  |  |  |  |
|  | 3.4 Upgraded and accredited calibration laboratories in MBS. |  |  |  |  | MBS UNIDO | EU | 72200 - Equipment 71200 - International Consultants 72100 - Contractual Services Companies 75700 - Training, Workshops and Confer | 543 478 34 375 27 174 13 109 |
|  | - Procurement of selected equipment (IT and Scientific), in consideration also of the NORAD project inception phase. Consumable items such as calibration stickers, printer, seals, etc are also required |  |  |  |  |  |  |  |  |
|  | - UNIDO to provide copies of guidelines for implementation of ISO/IEC17025. |  |  |  |  |  |  |  |  |
|  | - Training on the application of ISO/IEC 17025 for calibration and testing. |  |  |  |  |  |  |  |  |
|  | - Management system for the application the ISO/IEC 17025; Definition of objectives and requirements; initial evaluation; planning (gap analysis). Specific output is the recommended scope for calibration services to be accredited. |  |  |  |  |  |  |  |  |
|  | - Management system for the application the ISO/IEC 17025. Design and development; implementation; evaluation. |  |  |  |  |  |  |  |  |
|  | - Initiate activities to address gaps: Training of drivers/ operators (ref mobile equipment). Training in uncertainties of measurement Calibration of equipment Environmental conditions Intercomparisons |  |  |  |  |  |  |  |  |
|  | Enhance the MBS training business unit mainly for management systems standards, complying with ISO 29990. [This activity to follow the functional review] |  |  |  |  | MBS UNIDO | EU | 71200 - International Consultants | 13 125 |
|  | - Survey on Malawian market for training on standards during the realization of the training activities of Output R6. |  |  |  |  |  |  |  |  |
|  | - Contact and registry of available trainers |  |  |  |  |  |  |  |  |
|  | - Establishment of procedures for compliance with ISO 29990, including training |  |  |  |  |  |  |  |  |
|  | 3.6 Establish a pool of Malawian auditors. |  |  |  |  | MBS UNIDO | EU | 71200 - International Consultants | 8 750 |
|  | - Establishment of a methodology to select, approve, register and monitor the performance of auditors. |  |  |  |  |  |  |  |  |
|  | - Invitations to Malawi auditors and recent trainees to join the MBS pool of auditors. |  |  |  |  |  |  |  |  |
|  | - Establishment of a set of services for the pool of auditors, like: information, availability of updated curricula with a list of audits performed; participation on a community of practice. |  |  |  |  |  |  |  |  |
|  | 3.7 Collaboration with the Malawi Laboratory Association to strengthen the association as an integral part of the national quality infrastructure, notably in view of testing and calibration services. |  |  |  |  | MBS UNDP | UNDP | 75700 - Training, Workshops and Confer | 1 500 |
|  | - Consultative workshop with the MLA |  |  |  |  |  |  |  |  |
| Sub-Total |  |  |  |  |  |  |  |  | 1 110 391 |
| OUTPUT 4: Strengthened, proactive and responsive National Enquiry Points (NEP) to the information and notification requirements of WTO/TBT/SPS agreements |
| Number of databases established and made available to the general public that provide all Malawi technical regulations (TR), drafted and approved national standards. Baseline: 0; Target: 1 Number of TR not notified during the drafting stage. Baseline: n/a (to be determined during the inception phase of the project). Target: Zero TR that are not notified Number of publicly accessible services for exporting companies on foreign TR, standards and conformity assessment dispositions of countries that import from Malawi. Baseline: 0; Target: 1 | Identify, store, update, create and use the information on foreign TR, standards and conformity assessment dispositions of countries that import from Malawi NOTE: 3x SPS enquiry points: -MBS -Dept of Agricultural Research Services -Dept of Animal Health |  |  |  |  | MBS UNIDO | EU | 71200 - International Consultants | 16 065 |
|  | NOTE: Delay implementation till USAID project concludes, Evaluate manner in which outputs will be achieved during mid-term review. |  |  |  |  |  |  |  |  |
| Sub-Total |  |  |  |  |  |  |  |  | 16 065 |
| OUTPUT 5: Sanitary and Phytosanitary (SPS) infrastructure improved and mainstreamed into National polices |
| Number of SPS infrastructure action plans approved and implemented Baseline: 0; Target: 1 Number of Reports on the review and upgrade of SPS legislation in Malawi discussed and approved by stakeholders. Baseline: 0; Target: 1 | Review the national SPS infrastructure |  |  |  |  | MBS UNIDO | EU | 71200 – International Consultants | 27 679 |
|  | Develop a road map to improve the Malawian SPS infrastructure. |  |  |  |  | MBS UNIDO | EU | 71200 – International Consultants | 14 755 |
|  | Review and recommendations for the upgrade of legislation for the SPS infrastructure |  |  |  |  | MBS UNIDO | EU | 71200 – International Consultants | 12 228 |
| Sub-Total |  |  |  |  |  |  |  |  | 44 663 |
| OUTPUT 6: Capacity of Small and Medium sized Enterprises (SME), and particularly women and youth led enterprises, strengthened to comply with quality requirements |
| 6.1 Number of HACCP / ISO 22000 Food safety management systems in place in a selected number of SMEs. Baseline: 0; Target: 15 Number of ISO 9001 Quality management systems in place in a selected number of SMEs. Baseline: 0; Target: 10 Number of SME able to comply with specific quality requirements in export markets. Baseline: 0; Target: 10 Number of Trainers-cum-counsellors and auditors: training in HACCP / ISO 22000 Food safety management systems and approved as trainers and auditors. Baseline: 0; Target: 18 | 6.1 Preparation of an overall training and technical assistance programme for SMEs, in particular female and youth headed SMEs |  |  |  |  | MBS UNDP MoIT | EU | 75700 - Training, Workshops and Confer | 20 109 |
|  | - inception workshop Southern (roll over to Q1 2014), and to consider also workshops in Central and Northern |  |  |  |  |  |  |  |  |
|  | - Produce training and TA programme |  |  |  |  |  |  |  |  |
|  | 6.2 Technical assistance to 15 SMEs, in particular female and youth headed SMEs, to comply with HACCP / ISO 22000 Food safety management systems |  |  |  |  | MBS UNIDO |  |  | 0 |
|  | - Selection criteria, process |  |  |  |  |  |  |  |  |
|  | - Formulation of ToRs for technical assistance |  |  |  |  |  |  |  |  |
|  | 6.3 Technical assistance to 10 SMEs, in particular female and youth headed SMEs, to comply with ISO 9001 Quality management systems. |  |  |  |  | MBS UNIDO |  |  |  |
|  | - Selection criteria, process |  |  |  |  |  |  |  |  |
|  | - Formulation of ToRs for technical assistance |  |  |  |  |  |  |  |  |
|  | 6.4 Trainers-cum-counsellors and auditors: Training in HACCP / ISO 22000 Food safety management systems. |  |  |  |  | MBS UNIDO | EU | 71200 – International Consultants | 6 793 |
|  | - ID trainers, train the trainers |  |  |  |  |  |  |  |  |
|  | 6.5 Training in ISO 9001 Quality management systems for trainers-cum-counsellors and auditors. |  |  |  |  | MBS UNIDO | EU | 71200 – International Consultants | 6 793 |
|  | - ID trainers, train the trainers |  |  |  |  |  |  |  |  |
| Sub-Total |  |  |  |  |  |  |  |  | 33 696 |
| OUTPUT 7: MBS compliant with International Regulations established |
| Number of internationally recognized certificates issued Baseline: 0; Target: 5 Number of business plans produced Baseline: 0; Target: 1 | 7.1 TA for the preparation of the organisational and operational internal bylaws and business plan for the Malawian accreditation body. (MBS/CTA) |  |  |  |  | MBS UNIDO | EU |  | 0 |
| Sub-Total |  |  |  |  |  |  |  |  | 0 |
| OUTPUT 8: Programme Management |
| Operational Management Team | 8.1 Operational Management Team |  |  |  |  |  |  |  |  |
|  | -International Technical Assistance and related costs |  |  |  |  | UNIDO | EU | 77300 - Salary and related costs–TA/IP | 248 446 |
|  | - HQ travel |  |  |  |  | UNIDO | EU | 71600 – Travel | 14 841 |
|  | - National Project Assistant |  |  |  |  | UNDP MBS | EU | 77100 - Salary and related costs–TA/NP | 11 500 |
|  | - Fast Internet connection |  |  |  |  | MBS UNDP | EU | 72800 - Information Technology Equipmt | 42 500 |
|  | - Insurance for equipment |  |  |  |  | MBS UNDP | EU | 74500 - Miscellaneous | 81 522 |
|  | - Consumables- Office Supplies |  |  |  |  | MBS/CTA UNDP | EU | 72500 - Supplies | 10 870 |
|  | - Vehicle costs (normal use and maintenance) |  |  |  |  | MBS/CTA UNDP | EU | 73400 - Rental and Maintenance | 6 522 |
|  | - Vehicle costs (leasing) |  |  |  |  | MBS/CTA UNDP | EU | 73400 - Rental and Maintenance | 10 870 |
|  | - Audit |  |  |  |  | UNDP | EU | 74100 - Professional Services | 2 500 |
| Communications and Visibility | 8.2 Communications and Visibility |  |  |  |  |  |  |  |  |
|  | - Communication and Visibility (Launch Event) planned to coincide with the announcement about the new building |  |  |  |  | MBS/CTA UNDP | EU | 75700 - Training, Workshops and Confer | 50 000 |
|  | - Brochures, Press Releases, Media and Communication, Stickers |  |  |  |  | MBS/CTA UNDP |  | 74200 - Communications and Audiovisual | 20 000 |
| Programme Assurance, Coordination and Management | 8.3 Programme Assurance, Coordination and Management |  |  |  |  |  |  |  |  |
|  | - Programme Assurance |  |  |  |  | UNDP | UNDP | 77100/61200 - Salary and related costs–TA/NP 61300 - Salary and related costs–TA/IP | 36 000 41 000 |
|  | - Field Visits and Spot Checks |  |  |  |  | UNDP | UNDP | 72300 - Materials & Goods 71600 – Travel | 2 000 2 200 |
|  | - Bank Charges |  |  |  |  | UNDP | UNDP | 74500 – Miscellaneous | 1 000 |
|  | - Telephone/Mobiles |  |  |  |  | UNDP | UNDP |  | 4 000 |
|  | - Teleconference System for MBS |  |  |  |  | UNDP | UNDP | 72400 – Communication | 2 000 |
|  | - Quarterly Steering Committee Meetings and Monthly Project Management Meetings |  |  |  |  | UNDP | UNDP | 72300 - Materials & Goods 71600 – Travel | 2 000 2,000 |
|  | - Mid-Year Review Retreat |  |  |  |  | UNDP | UNDP | 75700 - Training, Workshops and Confer | 3 250 |
|  | - AWP 2015 Retreat |  |  |  |  | UNDP | UNDP | 75700 - Training, Workshops and Confer | 3 250 |
| Administrative Cost | UNDP/UNIDO (GMS 7%) |  |  |  |  |  |  |  | 196 910 |
| Sub-Total |  |  |  |  |  |  |  |  | 696 479 |
| GRAND TOTAL |  |  |  |  |  |  |  |  | $2,055,839 |

# Footnotes

The main project results mentioned on page 4 and 5 of the EU-UNDP Contribution Agreement on SQAM project dated 31.08.2012 and the project outputs of UNDP-Govt. of  Malawi  (Malawi Bureau of  Standards) Project Support Document dated 3/10/2012 are exactly the same; however, the wording in the project documents are different. For reporting and monitoring of project  results, the UNDP-Govt. of  Malawi document and its related logical framework applies.

# Text boxes

Narrative

There is a clear need for rapid and sustainable economic growth if Malawi is to achieve the Millennium Development Goals (MDGs) and the overall objective of poverty reduction on a meaningful scale. Trade has the potential to be an engine for growth that may lift many Malawians out of poverty. However, the country faces barriers that prevent it from benefiting fully from the world trading system. Internal barriers, e.g. inadequate knowledge and limited accessibility to information on export opportunities, excessive red tape, inadequate financing, poor quality infrastructure, pose major obstacles to Malawi’s trade expansion and diversification efforts. Such quantifiable supply-side constraints substantively add to operational costs and undermine trade development and export competitiveness in Malawi.

The Malawi Bureau of Standards (MBS) is the national enquiry point required by the World Trade Organization (WTO) under the Agreement on Technical Barriers to Trade. MBS sets and implements standards and conducts conformity tests on selected imports and exports. There is a strong perception that market demand for conformity services, particularly with regards to testing and calibration services for the private sector, is higher than currently available. However, exporters from Malawi are at present disadvantaged by the lack of internationally accredited testing facilities for certification of products for export. Certificates from MBS are only accepted in the region and exporters incur in high costs to obtain certification overseas. More generally, MBS has limited infrastructure to meet demands for the provision of SQAM services within Malawi.

Against this background, the “Development of the SQAM Infrastructure in Malawi” project is meant to enhance the ability to export goods from Malawi by reducing the need for re-testing, re-inspection, re-certification abroad through acceptance of measurements, tests, conformity assessment results issued in Malawi. The purpose of the project is to contribute to a more adequate, effective and sustainable National Quality Infrastructure (NQI) in Malawi in accordance with international and regional principles and practices (e.g. Common Market for Eastern and Southern Africa (COMESA), Southern African Development Community (SADC)), by supporting the improvement of the performance of the Malawi Bureau of Standards (MBS). This will have direct implications in terms of benefits for Malawi enterprises through improved business services provided by the National Quality Infrastructure and indirectly, and in the long term, in terms of improved protection of consumer rights of Malawian citizens.

The main activities that will be carried out during 2014 include:

- Development of a National Quality Strategy to follow the National Quality Policy

- Functional review of MBS to inform business improvement and further development of business and information management systems (including website);

- Conclusion of market survey on the demand for calibration and testing services and survey of opportunities for training services to be offered;

- Preparation of a marketing and training units in MBS;

- Review SPS infrastructure status and prepare roadmap for its strengthening;

- Progress by GoM in development of the new MBS facilities including construction to commence;

- Strengthening MBS technical and human capacity (equipment, systems, training) for conformity assessment services towards eventual accreditation of services in the following areas:

  - Product Certification

  - Management Systems Certification

  - Testing Services

  - Calibration Services

- Strengthening quality requirements in SMEs, in particular woman and youth led enterprises

- Programme management, quality assurance, monitoring and coordination

Estimated annualized budget (EU and UNDP):				$ 2,055,839

(inclusive of GMS)

Allocated resources:

Government		$1,136,363

UNDP Regular 		$ 152,000

EU			$ 1,903,839

Unfunded budget:	$ 0

AWP Period:			01 January 2014

31 December 2014

Programme Component:	Poverty Reduction and MDGs

Intervention Title:	SQAM Infrastructure Project

Atlas Award ID: 	00069207

Project ID: 			00083913

Duration:			1 year