Inclusive Growth Monthly Meeting – 11 July 2013

| ACTION POINT TRACKING MATRIX 9th July 2013 Action Point Tracker: Cinzia Tecce |
| --- |
| AGENDA | ACTION POINT | RESPONSIBLE PERSON (S) | DEADLINE/TIMELINE | COMMENT | STATUS AS OF 08 MAY 2013 |
| SQAM Project Implementation | UNIDO Advance | Cinzia/Naomi | End of June | Awaiting feedback from UNIDO if funds have reached their accounts | UNDP HQ – Treasury - transferred the first tranche of funds to UNIDO on June 19th |
|  | National Quality Policy | Cinzia/Augustine | End of July | NQP approved by Cabinet | Prepare for dissemination NORAD additional funding of 2 Million EUR was dependant on approval of NQP. |
|  | Metrology Design Expert | Cinzia | End of June | Expert submitted designs for the NML and layouts for equipment/lab benches | Final Metrology Designs delivered end of April. MBS provided final clearance in June MBS received approval from GoM in June to use a Private Architect for the Architectural Drawings of the NML. The Technical designs form the basis for the architectural drawings MBS is in the phase of launching the bids for the Architectural Drawings |
|  | Interim Progress Report 2013 for EUD | Cinzia | Mid July | Report in Draft form | Pre-financing of 758,096 EUR was received by UNDP in 2012 First interim payment for the SQAM Project is due by July 2013 An interim report is being prepared for submission to the EU. This will determine replenishment of funds |
|  | CTA | Cinzia | Mid July | Interviews closed but offer rejected by the recommended candidate | 17 applications and 5 shortlisted. Interviews took place week two of May. Interview panel was composed of UNDP (Cinzia as per clearance by DRR(P), UNIDO (Ouseph) and MBS (Chokazinga) An offer was made in late June to the recommended candidate. Offer was declined Remaining candidates not suitable for an offer. UNIDO is pre-qualifying additional candidates for interview |
|  | Project Management Meeting | Agnes/Augustine/Cinzia | Mid July | A first Project Management Meeting with implementing partners has been organized | First Project Management Meeting to take place on July 11 |
|  | Advance and Financial Reporting | Augustine | Early July | A first narrative and financial report was submitted | A first progress report was delivered to UNDP |
| PSD Project Funding and Implementation | DFID Financing Agreement | Cinzia | June | Finalized | First installment of 500£ to be received by end of October 2013 |
|  | Recruitment of TA Manufacturing under Output 1 | Cinzia/Augustine | July | Short-listing completed | Short-listing of candidates is complete. HR is arranging for written tests and interviews |
|  | TIP (Trade, Industry and PSD) SWAp Meetings | Augustine/Cinza | June/July | All 6 TWG Meetings completed in June | MoIT is organizing SWG meeting for mid July |
|  | Selection of MICF Fund Manager | Cinzia/Agnes | ASAP | RFP advertised | RFP advertised and three proposals received Evaluation team set-up Enquiry sent to HQ procurement on clarification of possible conflict of interest for one bidder Evaluation team will resume evaluation after feedback received from HQ |
|  | TORs for Industrial Policy | Cinzia/Augustine/Agnes | ASAP | RFP advertised | RFP advertised and three proposals received The scanned version of the RFP had omitted the last two pages (including last two annexes) In preparation for RFP to be re-advertised |
|  | Outstanding Payments from 2012 | Augustine/Agnes | ASAP | - | Augustine to provide an update |
|  | Formalize Q3 Work Plan | Augustine/Cinzia | ASAP | First Project Management Meeting held in June | Work with MoIT for allocation of WP for Q3 and for follow-up to first Project Management Meeting |
| EIF | UNDP to support formulation of 1 NES project under the EIF Tier-2 Window | Cinzia/Augustine | ASAP | Concept Note finalized and approved by EIF Geneva | Ministry has identified consultants for formulation. The MoIT is in the phase of preparing the contract |
| FIMA | FIMA Closure | Bill/Agnes | ASAP | - | Agnes to provide an update |
|  | UNCDF initiatives in Malawi | Bill | - | - | Bill to provide an update on status of UNCDF initiatives (Financial Literacy final draft, Status of MAP ToR) |
| GSB Closure | GSB Closure | Agnes | ASAP | - | To arrange for closure of GSB |