Private Sector Development Monthly Meeting

| ACTION POINT TRACKING MATRIX 8th May 2013 Action Point Tracker: Cinzia Tecce |
| --- |
| AGENDA | ACTION POINT | RESPONSIBLE PERSON (S) | DEADLINE/TIMELINE | COMMENT | STATUS AS OF 08 MAY 2013 |
| SQAM Project Implementation | MBS Advance Request for Q2 | Timothy/Augustine/ | Mid April | MBS expressed frustration on inefficiencies of UNDP | Advance request for Q2 finalized and submitted to PMRU for processing |
|  | MBS Specimen Signatory | Timothy/Augustine | ASAP | -none | Finalized |
|  | UNIDO Advance | Cinzia/Naomi | End of February | Awaiting feedback from UNIDO | UNIDO HQ is in contact with UNDP HQ for transfer of funds. Transfer has not been done yet due to unspent balance from UNIDO on Global Project Request An appeal was sent to UNIDO with the request to possibly consider to use UNIDO own resources while waiting for UNDP funds for sake of progress |
|  | Metrology Design Expert | Cinzia | End of March | Expert submitted the designs and layouts for equipment/lab benches | Final Metrology Designs delivered end of April. Awaiting for MBS final clearance MBS is also awaiting for approval from GoM to use a Private Architect for the Architectural Drawings in which the Technical designs feed into |
|  | Progress Report for EUD | Cinzia | 8 April | Report samples received by UNDP Brussels | Progress Report delivered to the EUD on April 30 as per deadline Next report due by mid June 2013 |
|  | CTA | Cinzia |  | Vacancy advertised on UNIDO website only | 17 applications and 5 shortlisted. CVs sent to and cleared by MBS. Interviews to take place week two of May. Interview panel is composed of UNDP (Cinzia as per clearance by DRR(P), UNIDO (Ouseph) and MBS (Chokazinga) |
| PSD Project Funding and Implementation | DFID Financing Agreement | Cinzia | ASAP | The Agreement was further discussed with the RR and DRR(P) | Draft Agreement reviewed by the the RR and DRR(P) with focus on schedule of payment and request for additional reporting Cinzia to share revised Agreement with DFID as per input provided by the RR and DRR(P) |
|  | Identification of Signatories of FACE Forms at MoIT and MoF | Agnes/Augustine/Timothy | ASAP | -Letters prepared for MoF and MoIT | Agnes and Augustine to follow-up with MoIT and MoF |
|  | Recruitment of TA Manufacturing under Output 1 | Cinzia/Augustine | 12 April | Position Creation and Classification cleared by HQ | Advert to be posted on UNDP website by UNDP HR |
|  | Selection of MICF Fund Manager | Cinzia | ASAP | RFP advertised | RFP advertised. Deadline for Submission of Proposals is 20 May 2013 COB |
|  | TORs for Industrial Policy | Cinzia | ASAP | TORs revised | TORs drafted by MoIT and revised TORs resubmitted to MoIT for final clearance |
|  | Distribution of NES | Timothy/Augustine | ASAP | - | Distribution List prepared MoIT to collect NES printed copies |
|  | Outstanding Payments from 2012 | Timothy/Augustine | ASAP | - | Timothy to provide an update |
|  | Formalize Q2 Work Plan | Augustine/Timothy/Cinzia | ASAP | - | Resources requirement for Q2 already provided and based on the signed AWP and in consultation with the MoIT To transpose details in Q2 Work Plan Arrange Management Meeting with MoIT |
| EIF | UNDP to support formulation of 1 NES project under the EIF Tier-2 Window | Cinzia/Augustine | ASAP | Concept Note finalized and approved by EIF Geneva | Ministry in phase of recruitment of consultants for formulation. Bid opening of proposals was set for April 4th. MoIT to communicate to UNDP finalization of the same for payment of consultants |
| FIMA | FIMA Closure | Bill/Agnes/Timothy/ | ASAP | - | Agnes to provide an update |
| GSB Closure | GSB Closure | Timothy | ASAP | - | To arrange for closure of GSB |
|  | Micro-Loan Foundation Payment of Annual Management Fee | Cinzia/Timothy/Agnes | ASAP | - | Cinzia preparing an Extension of contract for ARR clearance following internal meeting and discussions on the subject matter |