Private Sector Development Monthly Meeting

| ACTION POINT TRACKING MATRIX 14th March 2013 Action Point Tracker: Cinzia Tecce |
| --- |
| AGENDA | ACTION POINT | RESPONSIBLE PERSON (S) | DEADLINE/TIMELINE | COMMENT | STATUS AS OF 12 FEBRUARY 2013 |
| SQAM Project Implementation | AWP (Jan-Dec 2013) | Cinzia/Augustine | 15 February | Delays caused by overdue consensus on Inter-Agency Agreement between UNDP/ UNIDO | Joint AWP signed by UNDP and MBS. AWP now with UNIDO for signing RR a.i. decided to proceed with project implementation while awaiting for UNIDO signature to avoid further delays UNIDO made minor adjustments to TORs for CTA. The Job Advert has been shared with UNDP HQ for advertisement CTA is expected to be on board in Q2 |
|  | UNIDO/UNDP IIA | Cinzia | February | IIA signed on February 6th 2013 | Finance Dept was instructed to transfer first installment to UNIDO First installment not yet received by UNIDO but is with HQ. Finance is following-up |
|  | Metrology Design Expert | Cinzia | February | Expert fielded | Expert fielded on March 3rd and debriefing organized on March 9th Final Metrology Designs will be delivered by the expert by the end of March |
|  | Progress Report for EUD | Cinzia/Timothy | 30 March | Report samples received by UNDP Brussels | Progress Report to be delivered to the EUD by end of April |
| PSD Project Funding and Formulation | Signing of Prodoc, LPAC Meeting Minutes and AWP | Cinzia/Augustine/Patrick | 15 March | Patrick Kamwendo has been following up with MoF | Prodoc, LPAC Meeting Minutes and AWP signed by UNDP (Prodoc also signed by MoIT) on 5th February and delivered on Feb 6th to MoF Several follow-up meeting have been organized with MoF Awaiting signing from MoF |
|  | ATLAS uploading | Augustine | February | All documents uploaded in ATLAS | PSD Prodoc and AWP uploaded in ATLAS |
|  | DFID Financing Agreement | Cinzia | 18 March | Global Corporate Agreement and Guidelines in place and received from Partnership Bureau | Agreement drafted and being reviewed by DFID |
| FIMA | Closure of FIMA | Bill/Agnes/Timothy | ASAP | - | Agnes to provide update on FIMA closure |
|  | Pending issues on FIMA | Agnes | ASAP | - | Agnes to provide update on Pending FIMA issues |
| EIF | UNDP to support formulation of 1 NES project under the EIF Tier-2 Window | Cinzia | ASAP | Concept Note finalized and approved by EIF Geneva | The PSD Specialist and the EIF team have worked on a concept note to be submitted to EIF Tier-2 funding Window The Concept Note on Anchor Farms within the NES Priority Clusters has been approved Ministry in phase of recruitment of consultants for formulation |
|  | UNDP Geneva EIF Tier-1 Capacity Assessment for trade mainstreaming | Cinzia/Augustine | February | Further to UNDP Mission to Malawi, UNDP Geneva committed 100,000 USD for Capacity Assessment for Trade Mainstreaming | MoIT declined support from EIF Secretariat for the allocated 100,000 USD for Capacity Assessment in Trade Mainstreaming since the activities to be carried out – according to the Ministry – are a duplicate of the NES and functional and operational review to be carried out by DFID |
| GSB Closure | GSB Closure | Timothy | ASAP | - | To arrange for closure of GSB At the last meeting it was decided that no Final GSB SCM will be required to take place |
|  | Micro-Loan Foundation Payment of Annual Management Fee | Cinzia/Timothy/Agnes | ASAP | - | Under GSB 2012 AWP there was an allocation of 9,000 (Management fee for Micro-Loan Foundation up to April 2013) which has not been paid. To be paid by the PSDP. |