Private Sector Development Monthly Meeting

| ACTION POINT TRACKING MATRIX 14th February 2013 Action Point Tracker: Cinzia Tecce |
| --- |
| AGENDA | ACTION POINT | RESPONSIBLE PERSON (S) | DEADLINE/TIMELINE | COMMENT | STATUS AS OF 12 FEBRUARY 2013 |
| SQAM Project Implementation | AWP (Jan-Dec 2013) | Cinzia/Augustine | 15 February | Delays caused by overdue consensus on Inter-Agency Agreement between UNDP/ UNIDO | Joint AWP drafted and circulated to MBS and UNIDO for final validation prior to signing UNIDO is reviewing TORs for CTA, will commence recruitment asap. The CTA is expected to be on board in Q2 |
|  | UNIDO/UNDP IIA | Cinzia | February | UNIDO Mission fielded in early February | IIA signed on February 6th 2013 Finance Dept was instructed to transfer first installment to UNIDO |
|  | Selection of Metrology Design Expert | Cinzia | February | The pre-condition set by UNIDO on the release of the expert is to have the IIA signed | Expert identified and cleared by MBS (Ron Cook) Expert will be fielded on March 3rd Preparations underway for fieldwork |
|  | EU ROM-ing Mission to Malawi | Cinzia | February | Contacts established with EU Brussels consultants | ROM-ing monitoring visit to Malawi scheduled for 18-26 February. Mission Agenda agreed with consultants and meetings penciled in |
| PSD Project Funding and Formulation | Signing of Prodoc, LPAC Meeting Minutes and AWP | Cinzia/Augustine | February | Meeting with MoF was cancelled. Patrick Kamwendo paid a courtesy call to PS and ST | Prodoc, LPAC Meeting Minutes and AWP signed by UNDP (Prodoc also signed by MoIT) Awaiting signing from MoF |
|  | ATLAS uploading | Augustine | February | All documents uploaded in ATLAS | PSD Prodoc and AWP uploaded in ATLAS |
|  | DFID Financing Agreement | Cinzia | 15 February | Draft Global Corporate Agreement and Guidelines in place and received from Partnership Bureau | Agreement being drafted |
| FIMA | Closure of FIMA | Bill/Agnes/Timothy | ASAP | UNDP to organize TPR Meeting | FIMA TPR arranged for February 15th. MoF to provide feedback on availability of ST |
|  | Pending issues on FIMA | Agnes | ASAP | - | Agnes to provide update on Pending FIMA issues |
| EIF | UNDP to support formulation of 1 NES project under the EIF Tier-2 Window | Cinzia | ASAP | Concept Note finalized and approved by EIF Geneva | The PSD Specialist and the EIF team have worked on a concept note to be submitted to EIF Tier-2 funding Window The Concept Note on Anchor Farms within the NES Priority Clusters has been approved Ministry in phase of recruitment of consultants for formulation |
|  | UNDP Geneva EIF Tier-1 Capacity Assessment for trade mainstreaming | Cinzia/Augustine | February | Further to UNDP Mission to Malawi, UNDP Geneva committed 100,000 USD for Capacity Assessment for Trade Mainstreaming | MoIT submitted a letter to EIF Secretariat for request of the allocated 100,000 USD for Capacity Assessment in Trade Mainstreaming |
| GSB Closure | Organize Final SC for GSB | Timothy | ASAP | - | To arrange for closure of GSB To arrange for Final GSB SCM |
|  | Micro-Loan Foundation Payment of Annual Management Fees | Cinzia/Timothy/Agnes | ASAP | - | Under GSB 2012 AWP there was an allocation of 9,000 (Management fee for Micro-Loan Foundation up to April 2013) which has not been paid. To be added as a discussion item at the GSB SC Meeting |