| TYPE OF MEETING | DATE | PARTICIPATION |
| --- | --- | --- |
| MONTHLY PROJECT MANAGEMENT MEETING (occurs every Third Thursday of the Month at 2h00 pm in UNDP Offices unless indicated otherwise) The Back-to Back Meetings with the SC Meetings occur in the MoIT offices ) | 14 January 2016* 18 February 2016 17 March 2016 21 April 2016 19 May 2016 16 June 2016 21 July 2016 18 August 2016 15 September 2016 20 October 2016 17 November 2016 15 December 2016* *tbd | Members of the Project Management Team C. Phangaphanga, MoIT, Deputy Director of Industry, Chair NN, UNDP RSG Portfolio Head, Co-Chair C. Musonzo, MoIT Deputy Director Trade C. Tecce, UNDP PSD Specialist J. Hara, MoIT, Senior Economist S. Sindi, MoIT, Assistant Director of Industry M. Sauzande, MoIT, Assistant Director of Industry M. Mehrlaender, UNDP Programme Analyst T. Kavalo, UNDP Programme Analyst C. Kachiwala, MoIT, Principal Industrial Officer L. Mwaungulu, MoIT, Industrial Officer P. Kawonga, UNDP Programme Associate |
| QUARTERLY STEERING COMMITTEE MEETINGS (occurs every last month of the Quarter on the third Friday at 9h00 am in the Ministry of Industry and Trade unless indicated otherwise) | 18 March 2016 17 June 2016 16 September 2016 16 December 2016* *tbd | Members of the Steering Committee C. Chiunda, PS, MoIT, Chair C. Flore, DRR (P), UNDP, Co-Chair C. Kambauwa, Chief Director, MoIT NN, RSG Portfolio Head, UNDP K. Chisale, Director of Industry, MoIT C. Chatima, Director of Trade, MoIT C. Phangaphanga, Deputy Director of Industry, MoIT C. Musonzo, Deputy Director of Trade, MoIT C. Tecce, PSD Specialist, UNDP M. Mehrlaender, Programme Analyst, UNDP T. Kavalo, Programme Analyst, UNDP C. Kaferapanjira, CEO, MCCCI G. Chimteka, MoF K. Johnstone, DFID |
| MID-YEAR AWP REVIEW MEETING | 10 June 2016 | Project Management Team |
| 2016 AWP RETREAT | 02 December 2016 | Project Management Team |

| TYPE OF REPORT | RECIPIENT | RESPONSIBLE PARTY | DEADLINE FOR SUBMISSION |
| --- | --- | --- | --- |
| PSD Project Quarterly and Annual Technical and Financial Progress Report (the Quarterly reports shall include the Work Plan for the following Quarter) | UNDP | MoIT (Output 1) MICF (Output 2) | 9 January 2016 - (Q4 2015 Report) 1 April 2016 - (Q1 2016 Report) 1 July 2016 - (Q2 2016 Report) 7 October 2016 - (Q3 2016 Report) 13 January 2017 - (Q4 2015 Report) |
| PSD Project Quarterly and Annual Technical and Financial Progress Reports | DFID | UNDP | 15 January 2016 - (Annual Report 2015) 8 April 2016 - (Q1 2015 Report) 8 July 2016 - (Q2 2015 Report) 14 October 2016 - (Q3 2015 Report) 20 January 2017 - (Annual Report 2015) |

***

# Text boxes

PSD PROJECT

- CALENDAR OF MEETINGS - Secretariat: Ministry of Industry and Trade

PSD PROJECT

- REPORTS SUBMISSION CALENDAR -