SOCIAL COHESION   AND   CONFLICT PREVENTION

Progress Report

January –   December, 2016

December 2016

Contents

Acronyms										3

Executive Summary									4

Situational Background/Context							5

Assessment of project results during implementation period				6

Planned and implemented activities 		             			          15

Lessons learnt								                      16

Future work plan								          17

ACRONYM

AWP		Annual Work Plan

PAC		Public Affairs Committee

UNDP		United Nations Development Programme

EXECUTIVE   SUMMARY

All the eleven activities planned for the year 2016 as highlighted in the work plan were successfully implemented and executed within the EU/UNDP budget. Enhancing  public  dialogue  on  contested  issues  through  the 5th All-inclusive  Stakeholders  Conference  has  yielded  positive  results  after  submitting  the  outcomes emanating therefrom and presented them to the head of State and the Legislature. The  newspaper articles  have  continued  to  carry  stories  of  PAC conference  since  February  to date ( See  attached  Newspaper  articles, Documentaries  from Times, MBC). The other activities such as WIF and Early Warning and Early Response Structure are capacity building activities that will continuously be undertaken as an empowerment program in PAC.  Thirty Women-In- faith , a  network  of  women in Peace Building drawn  from  mother  bodies continued to gain  skills  on  mediation  and  conflict  prevention through  national trainings. The WIF has been recognized as the only network in Malawi mobilized for peace building and contributing to UNSCR 1325(2000). The  volunteer  structure also continued to gain  more  understanding  as  a  result  of  the  activities  implemented  in  this  quarter. Interface  meeting  with  Head  of  State and the Speaker of the National Assembly to  hand  over  conference  recommendations  and actionable resolutions  have  continued  to  enhance debate  as  far  as  holding  leaders  accountable  is  concerned. Shuttle  diplomacy  assisted  to  secure  appointment  with  the  Head  of  State. In  executing  the  work plan  gender mainstreaming and integration of gender issues  has  been  always  taken  on  board  unlike  the  previous  years of  PAC  operations  with  other  partners. Internal capacity building was a priority in the year where the Annual General meeting was held and ushered in the new Executive Board Members for the next three years.

Following  these  interventions, the  overall  impact   is  that PAC  continue  to  hold  the  government    accountable  based  on public demand  to  table conference resolutions. Secondly  PAC  has contributed  to  conflict  prevention  by  way  of  avoiding  mass  demonstration  since  the  issues  of  economy  and  political  direction  have  been  put  on  a  structured  debate  within  the  project. Maize scarcity was closely monitored and minimized. The government  established  a  Technical  Committee  to  dialogue  with  PAC  on  resolution  demonstrating  that  as  a  facilitators  of  public  dialogue  and  conflict  management  the  organization  is in  so  doing  gaining  skills  and  capacity  to  deal  with  contested  issues.

A critical issue is that of building capacity of the new board members who were just elected in position towards the end of the year  for them to appreciate the organization philosophy.  One  of  the  critical  lessons  learnt  is  that  to  develop  conference  resolutions  requires  a  process  approach  and  very expensive to engage consultancy. Based  on  the  recent  implementation , politicians  once  in  power  ignore  commitments  and  values  enshrined  in  their  manifestos and the commitment from the 19 issues discussed prior to elections in 2014 Tripartite General Election.

1. SITUATIONAL BACKGROUND/CONTEXT

The  2014  elections  were  a  landmark  event   in  the  history  of  the  country  for  it  was  the  first  time  to  hold  tripartite  elections. Nonetheless, public  perceptions point  to the  fact  that event  left  a  political  dent  as  far  as  social  cohesion  is  concerned. As  such demands for federalism,   coalitions,  and  lack of  inclusivity  at  cabinet  level  emerged  as critical  issues  to  be  tackled  for  the enhancement  of  social  cohesion in  Malawi  in  the  aftermath  of   tripartite  elections . On  the  economic  front, the  DPP-led  government  which  emerged  as  a  winner  in  the  2014  race  continued    to  deal  with  cashgate  matters - taking  over the  momentum  from   PP- led  government. In  the  process, requests for an audit  exercise  on  previous  government  expenditures  revealed a  financial  gap  to  the  tune  of  MK577 Billion misused during the DPP led government implicating most of the DPP Officials. As  such, the  levels  of trust  and  confidence  both  from  the  public  and  donors have  continued  to  remain  low  to  the  extent  that  budget  support  has  not  been  forthcoming. This  has  been  compounded  by  the  manner  in  which  the  Malawi  Savings  Bank  was  sold, the  parliamentary  coalition  between  UDF  and  DPP  was  formed  , and  the  trip  to  UN  General  Assembly  which  had  a  huge  delegation  at  the  time  Malawi  faces  economic  challenge. The continued abuse of power and public resources by the DPP led government pose a threat to the economy of the country. Also the impact of corruption on the political and socioeconomic landscape in Malawi is a barrier to development and diverts resources away from poverty eradication efforts and sustainable development

The  current  Malawi’s  economic  and  political  crisis  has  been faced  with   discussions  among  various  stakeholders  as  to  what  can  be  done  to  turn  around  this  country before  the  system  completely  collapses. While  some  have  argued  that  the  current  situation  will  be  dealt  with  by  the status quo, others  have  taken  a  view  that  the  situation  needs  to  be  addressed  now in  a  constructive debate. In  both  cases, the  common  factor  is  that  the current  situation  needs  solutions  whether  radical  or  moderate depending  on  how  key  stakeholders  feel  about it. Others have suggested that religious leaders under PAC need to strategize  to interrogate  institutions such as the Ant Corruption Bureau failure to providing checks and balances.  And the inter party disagreements in the opposition political parties poses a challenge to the strengthening of strong opposition that can perform in Parliament.

PAC  believes  in  constitutional  values  to  let  stakeholders  express  views  without  hindrance  through  public  dialogue  once  such  situations  arise. History  has  it  that  since  transition  in  1992, every  regime  has  been  tested  by  PAC’s  public  dialogue which  contributes  to  an  overall  goal  of  holding  leaders  accountable and urging them to be transparent. In view  of  this, the  concept  outlined  activities  that  are  based  on  outcomes of  2012 and 2014  conferences. These  activities  have been   further  premised  on  the demand  for transformative  leadership in  line  with the development  of  19  issues presented  to  12  Presidential  Candidates  in  2014.  To  this  end, the implementation  of activities  have a twin  objective  of  enhancing  public  dialogue,   conflict  prevention and promote  democratic governance principles(transperancy, accountability, participation, rule of law etc).

In line with the above, the project is designed to support existing structures, specifically the Public Affairs Committee (PAC), in providing platforms for collaborative dialogue, peace building and conflict prevention. Hence the focus on contested issues through Inclusive conferences, the Women in Faith Peace Building Network capacity building, and the Youth Early Warning and Early response initiatives in PAC. This is in line with the constitutional provision, section 13(l), which calls for the “adoption of mechanisms for peaceful settlement of conflicts through, among other strategies; conciliation, and mediation to ensure that the country is secure and democratically mature”. Following the implementation of the 2015 AWP which resulted amongst others in the training of Women in Faith, Youth early warning monitors and continued collaborative dialogues, UNDP/EU continued to support PAC in the roles of Advocacy, dialogue and facilitating collaborative leadership. Particular focus for 2016 has been on strengthening national level mediation and dialogue facilitation capacities, and also the development of a shared minimum national agenda. The AWP will also continue to support the pilot conflict early warning and early reporting structures at the district level, in order to make them more effective in their role in conflict prevention and the Women in Faith capacity building program and increased understanding of women participation in PAC activities. In addition, 2016 has been a year to rethink on strategies of enhancing sustainability of PAC secretariat.

2. ASSESSMENT OF PROJECT   RESULTS

Below is the result summary of the outputs in the Annual Work Plan submitted to UNDP.

OUTPUT 1: Potentially violent disputes resolved through mediation and consensus on key national priorities reached, through facilitation and advocacy by Public Affairs Committee.

  - DEVELOPED   A   SHARED   MINIMUM  AGENDA  ON  CONTESTED  ISSUE: ECONOMIC  AND  POLITICAL DIRECTION

    - 5th All-Inclusive  Stakeholders  Conference  on  Economic  and  Political  Direction  of  Malawi

In  response  to  the  public   outcry   on  the  state  of  economic and political affairs  in  the  country , signified  by  the Government’s public acknowledgement and call for a search for effective solutions, the Public Affairs Committee (PAC) convened a 5th  All Inclusive Stakeholder Conference at Mount Soche Hotel in Blantyre from the 17th to the 18th February 2016 with a theme: Defining Solutions to Economic and Political Direction of Malawi.  Delegates to the conference were drawn from various  sectors of the Malawian society. They comprised representatives from constitutional bodies, traditional leaders, representatives of faith-based as well as secular civil society organizations, political parties, representatives from Malawi’s nascent peace architecture, the National Assembly, faith leaders, the Judiciary, Law Society of Malawi, Malawi Congress of Trade Unions , Interest groups, Government and state House, academia, business community, the media, Security agencies and Women in Faith.  More  than 250 delegates participated in the conference.

The conference was convened amid growing concerns with a deteriorating economy and apparent lack of decisive action on the part of government to address the situation. It was further inspired by the realization that short term political and partisan concerns in managing the economy were effectively making it impossible to create a shared long term strategy for economic transformation and for deepening and broadening democratic governance in Malawi. In  short, there  was  public  dissatisfaction and contestation over national economic governance that had the potential of causing disruptive public action. The 5th  All Inclusive Conference provided a platform through which policy dialogues would be held between Government and stakeholders and would also serve as an accountability forum for  enhancing  public  dialogue  in  Malawi .

In order to address the theme of the conference six topics were  identified to anchor the discussions. These included: State of the Malawi Economy; Politics and Governance; Impact of the Economic Situation on the Business Sector; Health Sector; Agriculture and food security and Progress report on setting up the National Planning Commission. Most of the issues that were raised through these topics resonated with aspects of transformative leadership that formed a menu of 19 issues to which presidential candidates of the 2014 elections expressed their commitment and undertook to address in the post election period if they won office.

The immediate outcome  of  the  conference  was  a  Communique  which  highlighted  the  general  conference  observations  and  position  of  the  Public  Affairs  Committee. The   impact   included:

- Opposition  parties  became  organized  to  exercise  a  strong  oversight  on  the  budget  since  the  conference  preceded   the parliamentary sitting.

- Accessibility  of  maize  in  the  country  improved  as  a  result  of  the conference;

- Opposition  parties  for  held  joint  rallies  to  pressure  government  on  issues  of  national  importance  such  maize.

    - Pre-consultations -  PAC  governance

While  this  component  was titled  “ Pre-consultation”  in  the  work plan, during  implementation it assumed  the  name  of  “post-conference  consultations”  following  delays  in  transfer  of  funds  to  the extent  that  such  consultation  could  not  take  effect prior  to  the  conference. Three  PAC  Governance consultations  were  therefore  held between 13-21 April 2016  to develop  a conference communique  and  modality  for  disseminating  such  a  document. On  average , these  meetings  were  attended  by  at  least  14 participants  drawn from  Board of   Trustees, Executive  Committee  and  representatives  of  mother  bodies. The  role  of  the secretariat  was  to  present  proposals  for  consideration  to  the  meetings. Among  other  things , the  meeting  agreed  to  set  up  a  technical  team  and clusters  to  develop  actionable  resolutions   with  proposed  timeframes  to be  presented  to  the  Head  of  State.

    - Technical  Teams  and  Cluster  meetings  on  Actionable  Resolutions

A Task Team   of   PAC   Governance   met  in  March  2016 to  examine  modalities  of  dialogue  between  PAC  and  the  Head  of  State  following  the  issuance  of  Communique  of  the  5th All-Inclusive  Stakeholders  Conference  held  on  17-18  February, 2016.  The  team  agreed  on : Principles  governing  the   dialogue proposed  by  the  Head  of  State, structure,   and  a  mechanism if  the  leadership  fails  to  implement  actionable  resolutions. The  meeting  further  endorsed  the  initiative   to  establish  clusters  on  Economy, Health, Political Governance and  Agriculture  to  develop  and  critique  the  proposed  resolutions. It  should  be  noted  that  the Head  of  State  had   set  date  of  29  March 2016  as  a day  to  engage  PAC  officials. The  date  was  confirmed to  PAC  secretariat and  even  the composition  of  governments’ team.  This meeting  was postponed  following  advice  from  Presidential  Advisor  that   PAC would  press  on  H.E  on  reduction  of  Presidential  Powers  and  that  the meeting  would  give  the leadership  pressure  and let  alone  affect  his  health. In this regard  reference  was  made  to  the way  the  Late  Bingu  Wa Mutharika  collapsed  as  a  result  of   PAC  recommendations in  2012.

2.1.3.1   Dialogue

The   Team   agreed   the following points:

- In  principle dialogue  is  acceptable

- PAC  has  responsibility  to  dialogue  with  H.E  and  not  anybody  else  delegated by  him.

- PAC and  Government  will  be  equal  partners in  dialogue

- Resolutions  will  not  be  altered  by  the  state  house  as  a  result  of  their  observation  prior  to  the  meeting  with  H.E

- PAC  should  serve  as  a  messenger  because  it  was  the  conference  that raised  issues -  in  actual  sense  the state  will  be  indirectly  dialoguing  with  the  public

2.1.3.2. Structure   of   the  Presentation  to  H.E

The  team  agreed on  the structure  of  the  presentation as  follows:

- Introduction

- All recommendations  as  received  by  the  conference  based  on  the  adopted  procedure

- Actionable  resolutions  as  developed  by  clusters  identified  by  PAC:

- Issues

- Description  of  an  issue

- Proposed Solutions

- Timeframe  for  implementation

- Sharing outcome  of  previous  intervention – Consultation  on  Federalism

2.1.3. 3. Process   of   developing and   refining   Actionable   Resolutions

Cluster Meetings

Between 7th  March and  4th  April, 2016,  five  cluster  meetings  were  held  in  Lilongwe  and  Blantyre to  critique the  proposed  resolutions developed by the four  presenters  on Economy, Political  Governance, Health  and Agriculture. Three  of  these  meetings  had  no cost  implications  for  the groups  met at  their own  time  and  day  of  their convenience. On  24  March, 2016   both  presenters  and  groups met in   Blantyre  to  share  criticisms   which  were  expected  to  be taken  on  board.  This was  followed by  a  meeting held  on  4 April, 2016  held  in Blantyre  to  validate  the revised  papers  which  are  attached  to this  report.

The  Team  felt that  recommendations that came  from  the  conference   should  be  the  same  gathering  that  should  assess  governments  performance. To  this  end, it  was  agreed  that  a  5+1 All-Inclusive   Stakeholders  Conference  be  held  targeting  the same  delegates  that  attended  the  5th All-Inclusive  Conference  to  determine  governments  commitment on implementation.

    - Interface meeting : PAC  -  Head  of State

On  21  April, 2016  thirteen  PAC  officials  met the  Head  of  State  and  Governance at  Lilongwe  State  House  where they presented  all  conference  recommendations  and  actionable  resolutions. Twelve   government   officials were  in  attendance.   A 29 paged  document  was  delivered  to  the  Head  of  State focusing  more  on  actionable resolutions  leaving  conference recommendations  to  be  read  by  the  President  at  his  own  free  time.  For  full  details, attached  is  PAC  Chairpersons  presentation.

    - Shuttle diplomacy

Dealing  with  the  issue  of  political  and economic  direction  required  a  lot  of  shuttle diplomacy  and  interface  meetings  with  DPP  and  government  officials. Prior  to  the  conference  PAC  held  at  least  6  interface/shuttle  diplomacy  meetings  to  secure  the  attendance  of government  officials  and  to  clarify  the  objective  of  the  meeting. The  presence  of  government  officials  at  conference  contributed  to  the success  of  the  event.

The  need  for  shuttle  diplomacy   further   emerged  when  the  Head  of  State  cancelled  the  original  appoint  of  29  March  2016  at  2.00 Pm. At  least  4  meetings  were  held  with  Presidential  Advisor  sharing  draft  documents  in  advance  of  the  meeting  of  21 April  2016.

    - Interface meeting with Speaker of National Assembly

On 1st June 2016, PAC Board had an interface meeting with the Speaker of Parliament at Parliament buildings. The aim was to thank him for sending representatives to the PAC 5th All inclusive conference held in February, 2016 at Mt. Soche Hotel in Blantyre which demonstrates the values of public dialogue as one pillar for conflict prevention. Another reason for the meeting was to officially share the conference recommendations (which were the ideas that emerged from group discussions and plenary submissions based on an adopted procedure by the conference) and the actionable resolutions (are based on the analysis of the general recommendations, they are the consolidated issues, justifications, proposed solutions and proposed timeframes)

    - Enhanced capacity and elect new PAC Body of governance, AGM –Elect Office  Bearers

In fulfilling PAC Constitutional provision Section 15.2 ‘…Members of the Executive Committee shall hold their positions for a period of three years and shall be eligible for election---‘. Hence the AGM was held on 20th December, 2016 for the election of the new Executive Board Members under the theme “Taking a Stand on Corrupt practices in Malawi”. In order to address the theme there was one presentation titled ‘Corruption: Impact on Political and Socioeconomic Landscape in Malawi’. That was followed by the plenary where religious leaders interrogated the theme and querried how they can be of help to tramp out corrupt practices in the country. That was also the basis of the Communique as an output of the AGM.

Members present were: ------ and those absent were Members Absent for the 2016 AGM:

Seventhday Baptist, Baptist Convention of Malawi, Evangelical Church of Malawi

Providence Industrial Church of Malawi, United Methodist Church

- AGM  preparatory  meetings  of  Joint PAC  Governance

Prior to the AGM, there was a Pre-AGM meeting of the Board of Trustees, Executive Boardmembers, Mother Bodies and Secretariat  to brief on :

- 2013 AGM minutes

- Criteria for the new admission to PAC Membership

- Fundraising: suggestions for the  increase in membership fee

- Voting proceedures

- Confirmation on AGM Moderators

- Election management

The immediate outcome of the AGM were:

- The communiqué which highlighted the issues of corruption and its impact

- The re-election of the Chair and Publicity Secretary, the ushering in of the new members.

- For the first time women were nominated and subjected to voting(Previously women were not nominated as candidates) After voting, two women were voted in and one women being a Muslim she was allowed to be a member without being voted in. This was an affirmative action on inclusivity . Attached is the Election results

2.2 ENHANCED PEACE   THROUGH  VIOLENCE  PREVENTION  INITIATIVES

In the year January - December, 2016, PAC implemented two WIF trainings and two activities at local level. These are: Monitoring of Early Warning and Early Response Youth Volunteers and Review meetings for the same youth volunteers.

2.2. 1. Monitoring of Early Warning and Early Response

In 2016 PAC organized review meetings for the youth volunteers in order to take stock of how they have been performing in terms of identifying, managing/resolving and reporting conflicts. These review meetings were held at regional level. Meetings for the southern and central regions were held in April, 2016 while the review meeting for the northern region was held in August, 2016.

Review meetings targeted volunteers trained in 2014 and the committees at regional and district levels that were monitoring the activities at local level. A total of 131 people participated in the review meetings. Out of 131, 37 were women representing 28.2%. The reviews were centered at assessing how volunteers were collecting and analyzing data; how they were providing information to relevant authorities including PAC secretariat and how in certain circumstances were managing and resolving conflicts.

Monitoring visits activity was done from 3 – 9 March, 2016. Districts covered were Thyolo, Blantyre, Machinga, Mangochi, Ntcheu, Dedza, Lilongwe, Kasungu, Mzimba, Mzuzu, Rumphi and Karonga. Fifty youth volunteers were interviewed during the monitoring exercise  of  which 38 were men and 12 were  women representing 78% and 24 % respectively. As  regards  review  meetings, ninety two  youth volunteers  attended of  which 61  were  men  and  31  women   in southern and central regions representing 67 % and 34 % respectively.

Achievements

- It was observed that volunteers provided timely and appropriate interventions at local level as such early warning systems were able to prevent conflicts from intensifying.

- Volunteers were able to analyze the causes of the conflicts in their communities.

- Early warning systems involved women as such information provided by women was also submitted to relevant authorities.

- Volunteers used the skills for different types of conflicts ranging from political to social.

- Coordination among PAC volunteers has improved through implementation of the project at local level.

Challenges

- It was reported that mobility was a problem as such in most cases volunteers were failing to get first hand information as they would arrive at a place when conflict had already happened.

- It was observed that more work was done around 2014 elections, some volunteers thought the trainings only targeted political conflicts during elections.

- Some trained volunteers moved from flash points making it difficult for the newly identified volunteers to apply early warning and early response systems.

- Few women among the volunteers.

Recommendations

- There is need for a mechanism to deal with mobility problems among volunteers. A suggestion was made about the provision of bicycles.

- There is need to increase the number of youth volunteers in the districts as different types of conflicts are happening. For example, religious conflicts in Rumphi and Mangochi, Conflicts over land in Thyolo , Mulanje and Karonga.

- There is need to trained volunteers who will be newly recruited.

- There is need for co-existence activities in the district which are registered more conflicts like Thyolo, Mulanje, Rumphi, Mangochi and Karonga.

- A deliberate effort has to be made to recruit more women because in most cases women are the ones who suffer most in conflicts because of their triple roles (reproductive, productive and community) they have in life.

      - Successes

- Tools of conflict mapping helped them identify conflicts, analyze causes of conflict, know the networks and how conflicts were coordinated.

- More reports were submitted to PAC secretariat and district Multi Party Liason Committees (MPLC).

- Networking of youth volunteers with district MPLC made PAC visible at district level and it also improved the organization’s image.

- Visibility of PAC at district level through social cohesion project has made some PAC volunteers participate in District Executive Committee (DEC) and MPLC meetings.

Recommendations

- There is need for mechanism to support the volunteers with bicycles to ease mobility

- .Put in place a deliberate effort to increase the number women at local level, bearing in mind the triple roles affecting women participation in activities

- How to identify appropriate response to the conflict (in order to ensure that right type of response is provided to a specific conflict).

- Accuracy in the documentation of the information about the conflict. Accuracy in anticipating conflict and the credibility attached to the prediction has an impact on the action taken on the conflict.

Follow up activities :

- To expand the number of volunteer base, to incorporate new members and train them  in each district to monitor and deal with escalating number of conflicts

- To roll out activities to districts such as Thyolo, Mulanje, Karonga, Rumphi, Mangochi

- Training to address lack of knowledge on the Malawi Gender Related Laws (with an aim of linking projects supported by UN).

2.2.2. Women in faith Peace Building Network

In 2014 PAC established the Women in Faith with the aim of building capacity of women to enhance their roles in peace building and conflict prevention. 30 women being trained were drawn from the five mother bodies that form the organisation as faith based.

In 2016 from January to December three activities were implemented as follows: a)The 2 days review meeting for the Women in Faith Peace Building Network held at Mount Soche Hotel in Blantyre from 15 – 16 March, 2016; and  two trainings held on 12-14 April,2016 at Mzuzu Hotel in Mzuzu City and on 22-24 August, 2016 at Hotel Victoria in Blantyre respectively.

With support from EU/UNDP, PAC provided capacity building platform for collaborative dialogue, peace building, early warning early response and conflict prevention (in line with the Constitutional provision section 12(1) and 13(1) which calls for the ‘adoption of mechanisms for peaceful settlements of conflicts through among other strategies; reconciliation, and mediation to ensure that the country is secure and democratically mature’. The WIF also contributes to UNSCR 1325 passed in 2000 and the Malawi Gender Equality Policy that promote the empowerment of women and participation.  To increase visibility of WIF, a presentation on communication strategy was highlighted and a draft strategy is in place

- The WIF plans to domesticate the UNSCR 1325 ; to further disseminate Gender Related Acts  to assist in conflict prevention, early warning and responses, Understanding Gender Related Laws: Prevention of Domestic Violence Act; Deceased Estates(Will, Inheritance and Protection)Act; Gender Equality Act, the Marriage, Divorce and Family Relations Act, 2015; Anti- Trafficking Law

promote Religious Co-existence between Muslims and Christians Developed Regional Plans for Sensitization and Advocacy

Achievements

- Improved knowledge, skills and understanding of peace building, mediation, conflict prevention and advocacy

- Information sharing increases knowledge and ideas

- Women-In-faith are getting engaged in peace monitoring and mediation within their communities and religious activities

- Voluntary activities raises visibility among stakeholders

Commitment to domesticate the UNSCR 1325 and raise awareness on the importance of participation and representation of women in peace building and mediation at all levels using religions and community forums

Examples of Notable achievements

There has been a great improvement of knowledge gained through the trainings and the transfer of knowledge to others based on WIF Regional sensitization activities conducted on voluntary basis.

- Increased collaboration and networking among central region women who have attached themselves to Lingazi Police Victim Support Unit

- Northern region women have advanced the issue of diaper disposals working with the Councillor and Health department in Mzuzu. They were asked to assist them with the by Laws and be responsible to discuss with foreigners who are disposing diapers along the roads.

- Increased level of volunteerism; Central region and Southern region conducted sensitization meetings for the World Women Day of Prayer committees and Muslim women meetings in Lilongwe and Blantyre respectively.

- Southern region group had a sensitization program on issues of peace building on Blantyre Synod Radio Station

- Religious Coexistence improved as both Christian and Muslim women work together in the sensitization meetings

- Volunteerism: WIF have enhanced their own regional activities in creating awareness through their religions. For example  an intervention in Salima.

- Central region group visited a Private School in Salima (Mackenzie School) to encourage both parents and children on the importance of education. As means of settling disputes and   misunderstanding that led to high dropout rate of children influenced by their parents. The school has now normalized and children are now attending classes.

In Mzuzu they introduced themselves to the District team on health issues caused by disposals of diapers,

Work with chiefs in Mzuzu to address the issue of a criminal who was killing people using a torch. Now the criminal is in custody);

- Increased levels of sensitization:

- Central region group mobilized 35 world day of prayer women group and sensitized them on early warning signs, prevention of violence and peace building, and UNSCR 1325.

a) Southern region committee sensitized a group of Muslim Women in peace building, conflict prevention and mediation UNSCR principles

b) WIF Agnes (a Moslem) presenting on conflict tree analysis to a group of Christian women in Lilongwe

Follow-up activities:

- To increase knowledge, skill through training to produce TOTs in peace building, conflict prevention, advocacy, dialogue and transformation.

- Publicity and Visibility of WIF in Malawi and develop communication strategy

- To develop and compile simplified and translated version of the peace building training Manual for TOTs’ use in their local communities

- Conduct Regional trainings to reach out to more religions in the regions/districts

- Work with Youth Early warning structures

- Support WIF local activities

- Monitor women activities in their regions

- Reach out to more women in districts to address issues of Gender Based Violence and Gender Related Acts passed in Malawi

    - Publicity ad Publication

Within the quarter,  a  communiqué, documentaries, Zodiak snapshot  live  broadcast  of  the  conference  and  Newspaper  cuttings  were  produced  as  part  of  documentation. Improvements  on  website  and  designing and  printing  of  profile  were  also  implemented. Activities were covered in radios and TV as they were implemented.

2.3 PROGRAMME MANAGEMENT AND SUPPORT CAPACITIES ACQUIRED AND IMPLEMENTED

    - Strengthening capacity at secretariat

Staff  has  been  somewhat  motivated  and  implemented  the  above  captioned  activities. The participation in The  secretariat  also  purchase  new  equipment  such  offices  furniture based  on  2015  UNDP  snapshot  audit.

- Training  in  accounting, programme  management  and  advocacy

- Purchase of new equipment e.g.  computers

- Implementing Partner meetings strengthened partnerships, presentation and reporting of activities. Mainstreaming of SDGs and championing of the Global development agenda 2030

3. LESSONS   LEARNED

- There is need to have identification (IDs) for youth volunteers and Women in Faith Network. Some youth volunteers and WIF were having problems to get information from the communities or any other structures because of having no identification.

- Regular communications about the project makes people not forget about what they are supposed to do. There is need for regular communication with youth volunteers so that they continue monitoring conflicts in their respective communities.

- There is need to support WIF own community activities especially in monitoring and publicity

- There are different perceptions when dealing with conflicts.

- One conflict can lead to another conflict. For instance, politicization of land distribution in Thyolo has led Chiefs siding with a political party on land issues which has resulted into political issue.

- It was acknowledged that the intervention and the formation of the WIF is making a difference within the community. Some women are being recognized and asked to take part in mediating some disputes within their catchment areas. The women are now getting involved in decision making processes and have started to be included in sharing of responsibilities. One woman has been included in the Executive Board of PAC.

- However, the network would still endeavour to work hard to promote peace, conduct early warning monitoring and also conflict resolution with skills gained in Gender related laws, advocacy strategy.

- The monitoring exercise has helped to identify and get more information on some unresolved conflicts which need intervention and these are: Religious conflicts in Mangochi and Rumphi; Land conflicts in Thyolo and Ntcheu.

- Future Work Plan

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME |  |  |  | REMARKS | PLANNED BUDGET |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Amount($) |
| Output 1 Enhance facilitation, mediation skills and collaborative efforts Indicator 1:Progress towards development of a shared minimum national agenda on national issues Baseline 1: None Target 1: Draft shared minimum national agenda on emerging issues MoV: Progress reports. Indicator 2: Number of stakeholder engagements facilitated by PAC on national issues Baseline 2: 1 Target 2: 4 MoV: Interface reports, Progress reports. | Activity Result for Output 1.1: Enhanced capacity of Insider Mediators and Dialogue facilitators Action: - PAC orientation and strategy workshop - Monitoring emerging interfaith conflicts in Malawi - Dialogue facilitation and mediation training for mediators - Shuttle diplomacy efforts among national leaders on issues of national concern - 1 High level, Round Table sessions on Collaborative Leadership and Dialogue Activity Result for Output 1.2: Developed a shared minimum national agenda on emerging issues - PAC governance and review meetings - 1 collaborative dialogue fora on emerging issues - interfaith based advocacy through mother bodies agencies - Consultancies Activity Result for Output 1.3: Enhanced peace through violence prevention initiatives Action: - Training of trainers for Women in faith in peace building facilitation skills - Support to WIF community voluntary initiatives - 3 Regional dialogue facilitation training of women in religions - 3 refresher trainings for youth conflict early warning and early response monitors - 4 districts violence prevention initiatives in collaboration with District Peace Committees. Refresher Training of early warning and early response structure - Monitoring WIF Community initiatives - Publications and Publicity |  |  |  |  | New PAC governance orientation and development of strategy for mediation, shuttle diplomacy and collaborative leadership and dialogue To collaborate with mother body agencies on emerging issues advocacy To enhance the capacity of women in faith and youth structures on conflict prevention and promote their local initiatives. Women in faith voluntarily to roll out activities through already existing women groups in churches and mosques. Skill building for youth volunteer structure on early warning and early response. District prevention initiatives on reported conflicts in Karonga, Rumphi, Mangochi and Thyolo. PAC to voluntarily monitor youth initiatives on conflict early warning and early response. PAC to voluntarily monitor women in faith community initiatives. Photocopying newspaper cuttings, design and printing newsletter, documentaries, press statements, website management, annual reports and leaflets. | BPPS/EU UNDP BPPS/EU BPPS/EU BPPS/EU UNDP BPPS/EU UNDP BPPS/EU BPPS/EU BPPS/EU BPPS/EU | 75710-Conference-$3,521 72311-Fuel $2,292 72425-Comm $41 72505-Stationery $68 73105-Rent $10,398 75710-Conference- $9,589 75710 Conference-$3,288 72311 Fuel-$1,809 72425-Comm $41 72505 Stationery-$205 75710 Conference-$13,699 75710 Conference-$ 3,397 72311 Fuel- $1,911 72425 Comm $41 73410 Vehicle Maint-$4,110 75710-Confrence $22.849 72311-Fuel $5,719 72425-Comm $123 72505-Stationery $411 75710 Conference-$2,356 72311 Fuel- $1,855 72425 Fuel-$41 72505 Stationery $205 73120-Utilitise $658 72435 Email $3,836 71310 Consultancy $4,110 Internal PAC resources 75710 Conference $26,170 72311 Fuel $2,797 72425 Comm $41 72505 Stationery $137 73015- Leased Vehicle $616 71310-Constultancy $3,836 73410 Vehicle Maint- $2,466 Internal PAC resources Internal PAC resources 75710 Conference $7,014 72311 Fuel $7,625 72425 Comm $164 73105 Leased Vehicle $2,466 72505 Stationery $411 71310 Consultancy $1,096 75710 Conference $15,781 72311 Fuel $10,979 72425 Comm $123 72505 Stationery $411 73105 Leased Vehicle $1,849 71310 Consultancy $822 $15,488 |
| Sub Total |  |  |  |  |  |  |  |  |
| Output 2 Programme management and support capacities acquired and implemented Indicators: Project delivery rate Baseline: 80% Targets: 95% MOV: Delivery Analysis report, progress and annual report | Activity Result for Output 2.1: Capacity of PAC secretariat strengthened. Action: - Support to PAC secretariat Activity Result 2.2: Effective project management services Actions: - Provide Technical support - Monitoring and evaluation of project activities - Spot checks - Facilitate project audits |  |  |  |  | Enhancing operationalization of secretariat to implement the project. UNDP |  | $103,135 |
| Sub Total |  |  |  |  |  |  |  |  |
| TRAC |  |  |  |  |  |  |  | 150,000 |
| BCPR/EU |  |  |  |  |  |  |  | 150,000 |
| GRAND TOTAL (USD) |  |  |  |  |  |  |  | 300,000 |

ATTACHMENT

2016 AGM RESULTS

2016 AGM ELECTION RESULTS SHEET

| POSITION | NAME | NO. OF VOTES | VOID & VOTES |
| --- | --- | --- | --- |
| Chairperson | Rev. Dr. Felix Chingota | 63 * | 6 |
| Vice Chairperson | Bishop Alinafe Kalemba Rev John J. Gondwe Bro. Osman Karim | 21 14 34* |  |
| Secretary | Rev Innocent Chikopa Rev Fr. Dr Mark Mkandawire | 26 41* |  |
| Publicity Secretary | Fr Peter Mulomole Sheikh Dinala Chabulika | 51* 18 |  |
| Treasurer | Fr Emmanuel Makalande Bishop Gilford I. Matonga | 38* 30 |  |
| Members | Rev Matilda Matabwa Rev Maureen T. Tchuwa Sheikh Jafaar Kawinga Bishop Francis Kaulanda Mr Martin Chiphwanya Mrs Loney Laja | 12* 14* 9 9 23* *Affirmative Action for Muslim inclusivity | 2 |

Total number of Religious leaders to vote was 69 delegates

SIGNED BY ELECTIONS MANAGEMENT TEAM

Name:-----------------------------------------------------------------------------Signature:------------------------------------

Name:-----------------------------------------------------------------------------Signature:------------------------------------

Name:-----------------------------------------------------------------------------Signature:------------------------------------

Name:-----------------------------------------------------------------------------Signature:------------------------------------