UNITED NATIONS DEVELOPMENT PROGRAMME

REPUBLIC OF NAMIBIA

Barrier Removal to Namibian Renewable Energy Programme (NAMREP)

Phase II

Summary: The NAMREP project aims to (a) improve livelihoods and income generation opportunities of rural people by providing them access to off-grid solar energy technologies (for lighting, radio/TV, water pumping, small electric tools and refrigeration) and (b) reduce the dependency of increasingly expensive imported fuels by promoting solar water heating (to the household, and institutional and commercial sectors) and solar water pumping in the agricultural sector through the removal of barriers capacity and institutional barriers, public awareness and social acceptability barriers, and financial and technical barriers. Thus NAMREP will also contribute to climate stabilization by reducing or avoiding CO2 emissions in the order of 233,700 tonnes of CO2 (over a 15-year period). The project is implemented in two phases. The first phase, which is almost completed, has focussed on technical assistance to achieve barrier removal including considerable capacity building in government, NGOs, finance and other sectors, institutional development, reduction of financial barriers, building public awareness and technological barrier reduction. These activities have paved the way for an accelerated implementation of the solar technologies stimulated by financing schemes for appropriate product delivery mechanisms in the second phase. The first phase started in 2004 for a 2.5-year period until 2006 and has received USD 2.6 million from GEF. The proposed Phase II will start by the end of 2006 and continue for another 2.5 years. The total budget is an estimated US$ 16.44 million (Phase I: US$ 6.21 million, Phase II: US$ 10.20 million) with US$ 2.6 million solicited now from GEF to cover incremental cost of Phase II (US$ 2.6 million have been received for Phase I in 2003). The project outcomes are five-fold and will focus on: (1) capacity building in the public and private sectors and in NGOs, (2) establishing a framework of policies, regulations and action ins support of renewable energy and off-grid electrification, (3) increased public awareness and social acceptability of solar energy technologies, (4) Appropriate financing and product delivery schemes set up and expanded and (5) learning, evaluation and adaptive management.

TABLE OF CONTENTS

TABLE OF CONTENTS	2

ACRONYMS	3

Section A. ELABORATION OF THE NARRATIVE	4

1.	Situation analysis	4

1.1 	Context and global significance	4

1.2	Institutional, sectoral and policy context	5

1.3 	Baseline and barrier analysis	5

1.4	Stakeholder analysis	8

2.	Project strategy	9

2.1	Project rationale and conformity	9

2.2 	Project objective, outputs and activities	11

2.3 	Project indicators, assumptions and risks	18

2.4	 Expected global, national and local benefits	20

2.5	 Country ownership: country eligibility and country drivenness	20

2.6	 Sustainability and replicability	21

3.	Management Arrangements	22

3.1	Links with other initiatives	22

3.2	Project management	24

4.	MOnitoring and evaluation plan	25

5.	Legal context and other agreements	29

Section B. STrategic Results Framework	30

1.	Incremental cost analysis (Phase I and PHASE II)	30

2.	lOGICAL FRAMEWORK ANALYSIS	30

Section C. Total Budget and workplan	31

Section D.  ADDITIONAL INFORMATION	32

I.  STAKEHOLDER INVOLVEMENT PLAN	32

II.    CORRESPONDENCE OF NAMREP WITH REEECAP ACTIVITIES	33

ACRONYMS

APR-PIR	Annual Project Report – Project Implementation Report

CO2		carbon dioxide

CART 		Centre for Applied Research and Technology

CTA		Chief Technical Advisor

DKK		Danish crown

ECB		Electricity Control Board

GEF		Global Environment Facility

GHG		greenhouse gas

GRN		Government of Namibia

kWh		kilowatt-hour

MAWRD	Ministry o Agriculture, Water and Rural Development

MME		Ministry of Mines and Energy

MoU		Memorandum of Understanding

MW		megawatt

NAMREP	Barrier Removal to Namibian Renewable Energy Programme

NHE		National Housing Enterprise

NPD		National Project Director

NGO		non-governmental organization

PoN		Polytechnic of Namibia

PMU		Project Management Unit

PSC		Project Steering Committee

PVP		photovoltaic water pump

RDE		Royal Danish Embassy

RE		renewable energy

REEE		renewable energy and energy efficiency

REEECAP	Renewable Energy and Energy Efficiency

RET		renewable energy technology

SENS		Sustainable Energy Namibian Society

SET		solar energy technology

SHS		solar home system

SRF		Solar Revolving Fund

SWH		solar water heater

UNFCCC	United Nations Framework Convention on Climate Change

UNDP		UN Development Programme

USD		US dollar

US$		US dollar

VAT		value-added tax

W		Watt

Wp		peak Watt

WVTC		Windhoek Vocational Training Centre

- Section A. ELABORATION OF THE NARRATIVE

- Situation analysis

- This chapter provides an overview of the significance of the NAMREP project in the Namibian and global context, which is followed by an analysis of the baseline situation and identification of key stakeholders.

- 1.1 	Context and global significance

Geographical and socio-economic context

- With a land area of 824,269 km2 and a population of only 1.8 million, Namibia is a very sparsely populated country. It is a lower middle-income country with a GDP per capita close to USD 1,800. However, this figure masks a skewed income distribution and a majority of the population, particularly those in rural areas, continues to live in conditions of relative poverty.

- The state-owned national power utility NamPower has been responsible for Namibia’s electricity generation, imports and exports.  The power sector is in the process of reform and power distribution is now in the hands of Regional Electricity Distributors (REDs). According to the 2005 Rural Electrification Master Plan, only 1/3 of Namibia’s population has access to electricity (67% for urban areas and 10% for rural areas). Of Namibia’s 2,855 rural settlements (260,000 households) about 2,400 are not electrified. Some 131 settlements are officially designated as off-grid by the Master Plan, meaning that some 27,000 households will not have access to the national grid for at least 20 years.

- Namibia’s high population growth has three main implications for the energy sector. First, not only does the backlog in energy services for households need to be corrected but additional services need to be provided for new households in both urban and rural areas. Second, Namibia’s growing economy will require energy services to facilitate this growth. The third important consideration relates to the impact of energy usage and production on the environment. Much of the current conventional energy consumption relies on non-renewable hydrocarbon fuels of finite quantity, which have to be fully imported to Namibia.

- The growing need for power for lighting, refrigeration and cooking is currently not being met using grid electricity. Where this need is met, it is done through the use of relatively expensive and fossil-based alternatives such as diesel, paraffin, candles, coal and fuelwood. Given the low rural incomes, coupled with the rising cost of grid electrification, the decreasing value of the Namibian dollar and the dispersed nature of non-electrified settlements, grid expansion deep into rural areas is not a viable option. South Africa is rationalising its power industry and may raise the price of power exports to Namibia, so the government has indicated the possibility of sharp rises in the power tariffs in the near future. All these factors have a number of implications. Firstly, massive investments are required for the grid to reach the rural populations, but the government is lacking these funds. Secondly, the likelihood of low electricity consumption levels will jeopardise cost recovery on grid connections in remote rural areas.

Global environmental context

- According to Namibia’s First National Communication to the UNFCCC (2002), Namibia is a net absorber of greenhouse gases. CO2 removals (in forests and other biomass stocks) equalled 5.7 million tonnes. Of the total emissions of 1.8 million tonnes of CO2 the energy sector contributed practically all.

- 1.2	Institutional, sectoral and policy context

- The Ministry of Mines and Energy (MME) facilitates and regulates the responsible development and sustainable utilization of these resources. Within the Ministry, the Energy Directorate is responsible for renewable energy research and implementation of renewable energy projects. The Ministry of Mines and Energy established the Energy Policy Committee (EPC) to drive the policy making process and the development of an Energy Policy White Paper in 1998. As an energy policy framework, the White Paper formulated the following goals: effective governance, security of supply, social upliftment, investment and growth, economic competitiveness and efficiency, and sustainability. The strategy regarding renewable energy can be summarised as follows:

- Development challenges. There is an urgent need to provide improved access to better energy services in rural areas. There is strong demand for electricity for lighting and small appliances by households and public services and for water pumping, given the fact that Namibia’s water resources are scarce This need can often be met by solar home systems and solar water pumps as least-cost solutions, complementary to grid electrification. Water heating in urban areas makes extensive use of electric geysers that can be replaced by solar water heaters. Harnessing the country’s solar, biomass and wind resources for grid-connected power generation will increase the country’s dependence on imported power and improve environmental sustainability.

- Institutional challenges. At present renewable energy is on an unequal footing with conventional fuels and electricity. Key institutional challenges include the establishment of an adequate policy and planning framework, development of human resources and public awareness, adequate financing schemes and improved cooperation between ministries and public institutions on renewable energy.

- 1.3 	Baseline and barrier analysis

Problem description and barrier analysis

- Namibia has one of the best solar regimes in Africa with sunshine available throughout the year. The solar technologies with most scope in Namibia are solar home systems (SHS), solar water heaters (SWH) and photovoltaic pumps (PVP). There are several companies in Namibia that provide solar energy systems. In addition, one manufacturer produces solar cookers, while some camping equipment dealers provide solar cookers.

- A SHS provides a basic electricity service for off-grid households and, depending on its size, can provide power for lights, radio, TV and small electric tools and equipment or even refrigeration. There is a clear demand for SHS ranging from 50Wp for basic household services to 350Wp for small shops, such as grocery shops or shebeens, although the relative high investment is often a barrier for many low-income households. The off-grid areas also offer potential for solar-hybrid mini-grid systems. SWHs are used in urban areas and in rural areas by clinics, hostels and commercial farms. SWH have low maintenance and have a lifetime of 10 to 15 years and are often more cost effective than electric geysers with break-even points of 3-5 years.

- Three types of PVPs are available in Namibia, AC submersibles, DC submersibles and DC hammerheads. AC and DC submersibles are imported from USA, Europe or South Africa, while DC hammerheads are manufactured in Namibia. PVPs operate most cost-effectively as compared with diesel pumps on boreholes with a head not exceeding 150 metres with relatively low water delivery demand (up to 15 m3 per day). Namibia has some 15,700 boreholes that fulfil this criterion and this is a significant potential. However, of the around 8,500 water points installed by MAWRD, only 1% is PVP.

- The current annual sales of solar energy technologies (SETs) have been estimated in the baseline study and subsequent market surveys performed under the NAMREP project, Phase I:

Table A: Total Number of SETs (SHS, SWH, PVP) Sold Per Year

| Solar Home Systems | 2001 | 2002 | 2003 | 2004 | 2005 | 2006* |
| --- | --- | --- | --- | --- | --- | --- |
| CASH SALES | 291 | 294 | 298 | 380 | 478 | 800 |
| SALES SRF (LOANS) | 068 | 81 | 42 | 33 | 345 | 592 |
| TOTAL SALES CASH + LOANS | 359 | 375 | 340 | 413 | 823 | 1392 |

* for 2006 sales are estimated based on data available for the first quarter of the year (Jan-March 2006)

- These figures show that, although growing, the solar energy market is still very small. In fact, the more widespread application of these technologies has been hindered by various barriers, which are summarised below. Since the start of NAMREP Phase I in 2004 a market for solar energy technologies (SETs) has begun to develop. But the more widespread application of these technologies is still hampered by a number of capacity, institutional, technical, financial, information and cultural barriers. As reported in the phase I evaluation report most barriers have been mitigated during the implementation of NamRep phase I though not yet fully removed.

- Capacity barriers: General scarcity of human capacity and resources in the private sector, NGOs and in government institutions to identify, design, appraise, manage, advocate and implement sustainable energy projects:

- Private sector: Lack of skilled technicians in the rural areas to install, maintain and repair solar energy systems and a spatial concentration of SET suppliers in the cities, away from the demand centres, leading to high installation and maintenance cost; Lack of skills to develop business plans for the supply and the manufacture of SETs;

- NGOs: Lack of adequate information/knowledge on and limited skilled human capacity in the area of SETs to enable NGOs to undertake meaningful advocacy and promotional work and to design, manage and evaluate SET projects;

- Government: Limited skills to assess appropriate SETs applications, to assess and enforce compliance with standards and codes of practice and to develop and implement SET projects.

- Institutional and policy barriers: No optimization in ministries’ and agencies’ recurrent and capital expenditures over full-cycle costs taking SETs into account; No consideration of SET options in energy supply for infrastructure and for productive uses; Decision-making by ministries regarding energy choices in an uncoordinated way; Existence of a non-level playing field between grid electricity and off-grid electricity

- Public awareness and social acceptability:

- PVPs: Lack of information on life-cycle cost-benefits in comparison to other technologies; Lack of information on performance and operation; Environmental implications of using PVPs compared to diesel pumps; Unawareness of financing and loan schemes

- SHSs: Considered inferior to grid electricity; Unawareness of financing and loan schemes;

- PV refrigeration: Unawareness about availability and cost-benefits;

- SWHs: Cost of SWHs not added in the value of the house; Unawareness of financial programmes

- Rural energy demand: Lack of information on demand for modern energy carriers for social and productive uses and of opinion of end-users regarding SETs

- Financial barriers: High first-cost of SETs; Lack of well-marketed, affordable and easily accessible financing schemes for purchase, installation and maintenance; Lack of familiarity of current and potential financiers with appraising SET loans; Limited knowledge of local financiers about local, regional and international lending facilities dedicated to clean development; Lack of confidence in return of investment for end-users (and loan performance); Inadequate guarantee mechanisms to service and replace faulty or failing SET systems; Inadequate financial incentives for local renewable energy entrepreneurs to bulk procure, sell, install and maintain SETs.

- Technical barriers: Non-existence of norms, standards and codes of practice for performance, manufacturing, installation and maintenance of SETs; Non-existence of an independent SET testing facility; Lack of techno-economic data comparing different energy technologies for different energy services; Limited availability of adequately trained human resources within engineering, electric utilities, academia, government, financial institutions and NGOs to undertake and provide least-cost energy planning in the provision of energy services.

- Baseline scenario

- In the baseline scenario (without NAMREP), the energy situation in Namibia will continue to be characterized by the following aspects:

- Households and/or communities will have no access to financial resources to develop their locally available solar energy sources and families will remain dependent on the use of inefficient technology (such as candles and batteries for lighting) as energy sources in rural communities or adopt fossil fuel based technologies (such as diesel generators). This has the consequence of limiting evening activities to a minimum and reducing opportunities for income generation or improvements in the quality of education, health, and public service delivery (all of which are significantly improved by a suitable supply of electricity).

- Grid extension will continue to be the standard electrification approach of the government, supplemented with diesel generators for off-grid power supply, although at low coverage at the rural level (because of the vastness of Namibia’s rural areas) and despite of the increasingly large cost of power generation and importation. Few government resources will be directed to SET investment, and the majority of available resources will be dedicated to conventional grid extension. Private investment in renewable energy will not occur because (a) solar energy systems are not perceived as an attractive investment, (b) the regulatory and institutional arrangements promoting solar energy to be distributed are not in place, (c) the market demand for SETs remains small and (d) of the lack of adequate financing availability for SETs.

- The baseline course of action will not only have substantial implications for local communities and the national economy, but will lead to negative global environmental impacts, as the main sources of energy, whether grid connected or isolated, will continue to rely on fossil fuel based sources.  The consequences in terms of GHG emissions to the atmosphere are calculated in Section B, dealing with the incremental cost and logical framework analysis.

- 1.4	Stakeholder analysis

- Various stakeholders from government, private sector and NGOs, representing energy and non-energy sectors (agriculture, tourism, environment, rural development, public works and buildings) are involved. A list of stakeholders is given in the table below.

| Government and ministries: - Ministry of Mines and Energy (MME) - Ministry of Environment and Tourism (MET) - National Planning Council (NPC) - Ministry of Finance - Ministry of Agriculture, Water and Rural Development (MAWD) - Ministry of Trade and Industry - Ministry of Higher Education, Training and Employment (MHETEC) - Ministry of Works, Transport and Communications - Ministry of Women Affairs and Child Welfare (MWACW) - Solar Revolving Fund (managed by Konga Investments) - Regional Councils | NGOs and parastatals: - Gobabeb Training and Research Centre (GRTC) - Desert Research Foundation of Namibia (DRFN) - Namibia Nature Foundation - Ibis - Renewable Energy and Energy Efficiency Institute (REEE) - Namibia Wildlife Resorts - NamWater - Telecom Namibia - Habitat Research and Development Centre (HRDC) - Agribank - Electricity Control Board (ECB) - NamPower - Regional electricity distributors (REDs) - National Housing Enterprise (NHE) | Private sector and individuals: - Private housing developers - RE suppliers (e.g., Solar Age, Soltec, NEC, Terrasol) - RE technicians (a list of technicians is available from NAMREP) - Namibian breweries - Consultants (CSA, EmCon, Craddle) - Users (households, building owners, communal farmers, commercial farmers) |
| --- | --- | --- |
| Donor agencies: - DANIDA (REEECAP) - UNDP - Other agencies (GTZ, EU) | Capacity building organizations: - Polytechnic of Namibia - University of Namibia (UNAM) - Windhoek Vocational Training Centre (WVTC) | Financial institutions: - NedBank - Bank of Windhoek |

- Project strategy

- This chapter describes the rationale, goal, objective, outcomes and outputs of NAMREP Phase II. It describes per output the activities that were implemented in Phase I and those that are proposed under Phase II.

- 2.1	Project rationale and conformity

GEF alternative scenario and project implementation strategy

- In the alternative scenario, GEF resources will result in leveraging financial and human resources from government, private sector, financial institutions, NGOs and end-users that will be used to implement activities, aiming at lowering the technical, capacity, financial and institutional-policy barriers. This will allow the expanded use of solar and other sustainable energy services and in the longer run to a noticeable market transformation.

- The original USD 5,2 million, 5-year NAMREP project was split into 2 phases of 2,5 years duration each. The project document and budget for the first phase (USD 2,6m) was endorsed by the GEF CEO in 2003. Subsequently, implementation of phase I activities started in 2004 and will go up to the end of 2006. An independent evaluation of the progress in Phase I was carried out in February 2006 (NAMREP mid-term evaluation). The report recommends that, given the satisfactorily performance of Phase I, NAMREP should be extended into a second phase.  This current submission to the workprogramme of the June 2006 council is for phase II of the NAMREP project, requesting another USD 2,6 million to remove the remaining market barriers. The proposed Phase II will start by the end of 2006 and continue for another 2.5 years.

- In line with UNDP’s adaptive management approach and GEF’s learning culture adjustments to the implementation strategy and monitoring framework (including indicators) have been made at 2 critical stages during implementation of phase I. Firstly, at the beginning of phase I the logframe was revised and SMART indicators were designed based on the originally proposed indicators. The new set of indicators allows quantitative measurements of progress and forms the basis of regular data collection during project implementation. After the finalization of the indicators a baseline market survey was commissioned to collect data that is relevant with regard to the selected indicators. The second adjustment to NAMREP was made after the independent evaluation came up with a number of recommendations. These recommendations have been carefully considered and shape the design of the phase II strategy as presented in this proposal. For example: The independent evaluation recommends that Phase II of NAMREP should focus more on the implementation of financing modalities and developing the product supply chain (SET supplier/importer – rural-based solar business end-user) with targeted capacity strengthening activities and financial support mechanisms (supply side). More attention should also be given to development of the rural market for energy services, especially productive uses of energy (demand side).  The project strategy for phase II is build around those recommendations.

- Key achievements of phase I as documented in the evaluation report are as follows: Phase I has prepared the ground by building technical, institutional, policy-making and entrepreneurial capacities and awareness raising.  Quote from the evaluation report: “Regarding NAMREP’s performance our conclusion is that the project has performed highly satisfactorily in capacity building and awareness creation as well as in financial barrier removal, but marginally satisfactorily in the policy-institutional barrier removal activities (although due to factors outside the scope of direct influence of NAMREPs’ PMU, such as the delay in establishing the REEE Institute)…. If this dynamism continues in 2006, the evaluation team believes strongly that the Phase I of the project will have performed more than satisfactorily. Therefore, NAMREP should be continued in a follow-up Phase II with a clear focus on implementation of financing and technology delivery and maintenance modalities.” As also reported in the evaluation report NAMREP has been very successful in restructuring the Solar Revolving Fund (SRF) and setting up a financing scheme with a commercial Bank.

- Phase II will continue to address the capacity, awareness and policy-institutional barriers, but will focus on supporting innovative loan and grant mechanisms that will be extended through the Solar Revolving Fund (SRF) of the Ministry of Mines and Energy (MME), the Namibian banking sector (such as Bank Windhoek) and parastatal institutions (such as the development bank Agribank and the housing delivery agent Namibian Housing Enterprise).  The SRF provides soft loans for solar energy technologies (SETs). Loans awarded by the SRF have risen to 345 annually (in 2005) compared to 52 annually in average over the last 3 years after the restructuring of the SRF. In Phase I of NAMREP, an MoU was signed between MME and Bank Windhoek in which the bank provides a credit line for small solar energy entrepreneurs as well as personal loans for PVP, SHS and SWH at attractive interest rates, made possibly by the partial guarantee provided by MME to the bank. The SRF and Bank Windhoek credit schemes are described briefly in Annex D. In Phase II these credit schemes will be scaled up with GEF support and replicated to other financial institutions.

- NAMREP aims at expanding the use of SET's in three principal markets, namely:

- SETs that substitute an existing conventional energy service, such SWH for the provision of hot water, replacing electric geysers, and PVP in commercial farming, replacing diesel pumps;

- SETs for the off-grid rural markets, such as SHS and PVP in farming households to provide a new modern energy service for social uses (lighting, radio/TV) and productive uses (farming, small rural businesses, cold beverage shops);

- PV applications (SWH, PVP and SHS) in public institutions (e.g. schools, clinics, and police posts) for lighting, radio/TV, refrigeration and telecommunications.

- Regarding the first market, Phase II will continue to raise awareness on the benefits of using solar water heaters (in public institutions and electrified households) and PVP for commercial farming vis-à-vis conventional solutions and electric geysers). Here, the issue is substitution of an already existing energy services (electric geysers and diesel-powered water pumps) with sustainable energy options (solar water heaters and solar PV pumps). The public or private building owner and commercial farmers need to be convinced that SWHs and PVPs are cost-effective technologies and, where the initial investment cost is a barrier, need to be helped with a commercial loan facility, such as by the SRF or Bank Windhoek schemes.

- Special attention will be given in Phase II in developing the rural market for solar energy technologies. In the past some demonstration projects were implemented with very limited impact. The bulk of the market for SETs will have to build around commercial activities with the private sector engaging in sales and after-sales. First, it is important to strengthen the supply chain from SET supplier (mainly based in Windhoek) to locally based technicians and small solar energy entrepreneurs down to the end user. This implies providing technical and entrepreneurial training to rural-based technician to expand their services into small solar energy businesses that sell SETs to a local market they now well and by providing a maintenance service of sufficient quality. This supply chain needs to be backed up with appropriate credit facilities for supplier and rural solar entrepreneur and by facilitating interactions between SET supplier and the rural-based solar entrepreneurs.  Second, it is important not only to remove barriers to the penetration of solar technology (supply side) but of barriers to the development of the market for social and productive uses of renewable energy (demand side) as well. Here the first cost barrier is of particular importance. Most rural people cannot easily afford any of the modern energy technologies (neither cash nor conventional loan schemes), but social acceptability will be higher if SETs generate income, by linking up with productive activities (such as the use of PV in agriculture, e.g. productivity increases by solar-powered irrigation or small rural enterprises, e.g., cottage industries, small shops, shebeens).

- The third market is formed by the public sector that has to optimise its recurrent and capital expenditures over full life-cycle cost with full considerations for SET options, such as SWH in urban and rural public buildings (e.g., in school hostels and clinics) and PV application in rural services (education, clinics, police stations, communications).

- It is important that potential users of these SETs, whether government, community, wealthy or poor individuals see financial benefits from the use of the technologies from day one and be able to access finance so that they can feel first cost reduction benefits from day one of the installation of their solar system. Similarly it is important for suppliers, financiers and technicians to see improved sales and increased financial benefits as a result of financial barriers being removed to their enterprises.

Policy conformity

- The proposed project fits into the GEF Focal Area of Climate Change and addresses its Operational Programme 6, ‘Promoting the Adoption of Renewable Energy by Removing Barriers and Reducing Implementation Costs’.  Within the GEF framework of Strategic Priorities, the project fits well within CC-2, ‘Increased Access to Local Sources of Financing for Renewable Energy and Energy Efficiency’ and CC-4 ‘Productive Uses of Energy’.

- 2.2 	Project objective, outputs and activities

Project goal and objective

- The goal to which the project contributes is “to increase affordable access to sustainable energy services thus contributing to climate stabilization by reducing or avoiding CO2 emissions and improving livelihoods and income generation of rural people”.

- This project objective is “to promote the delivery of commercially, institutionally and technically sustainable energy services by solar energy, including solar electricity production (for off-grid lighting, radio, TV, water pumping, and refrigeration) and solar water heating to the household, institutional, commercial, and agricultural sectors.”

- The mid-term evaluation recommends rationalising the original list of 6 components (NamRep Phase I) into 4 components (1. capacity building, 2. policy-institutional, 3. awareness and social acceptability and 4. financing and product delivery schemes) plus adding a new component on learning, evaluation and adaptive management. Therefore, the proposed project for phase II has 5 main components each composed of 1 outcome, several outputs and associated activities that will contribute to the removal of the identified barriers. The outcomes of the NAMREP project phase II, and the associated outputs, are listed below:

- The link with activities implemented under the REEECAP project is explained in chapter 2 of Section D.

Outcome 1		Built capacity in the  public and private sectors and NGOs

- The capacity building component of the project is targeted at four groups, the private sector (PV industry and banks), national government staff and NGOs as well as local government staff and community leaders.  In the private sector, the overriding objective is to build national and local-level capacity of the solar energy sector to provide good-quality products and service to the markets by strengthening the SET supplier – local technician/small enterprise – end user chain. For governmental and non-governmental organisations (NGOs) the primary objective is to provide them with adequate and relevant information on SETs so as to enable them carry out advocacy, promotional and policy-making work and identify appropriate applications for the use of SETs.

Output 1.1	Training programmes for public and private sector and NGOs have been established and executed

- Activities – Phase I (completed):

- Technical and entrepreneurial training activities for solar technicians; publication of a training guide for technicians

- Formulation of a training guide for solar technicians

- Activities – Phase II:

- To provide business planning support and training on PV business best practice for solar technicians with (emerging) rural RE business. The training will done on-the-job and supplemented with workshop type of training, if necessary

- Continuing series of RET marketing and advocacy workshops (RE suppliers, government and parastatal staff, financiers, NGOs, training centres) to discuss SE product delivery modes and the role of various stakeholders in the provision of electricity services for rural areas

- Training activities for local government (municipalities), NGOs and community-based organisations, community leaders and parastatal staff on development of social and productive uses of renewable energy

Output 1.2		Decentralised RET companies are adequately supported

- Activities – Phase I (completed):

- SET entrepreneurs training workshops

- Activities – Phase II:

- Assist rural-based solar technicians and small RE entrepreneurs to develop stronger links with the RE suppliers in order to strengthen the supplier – local entrepreneur – end-user chain and with financial institutions

Output 1.3 	Capacity of vocational and training centres increased and centers are providing technical training on SETs

- Activities – Phase I (completed):

- Develop study materials and an appropriate curriculum for the Windhoek Vocational Training Centre and other vocational and training centres. A MoU was signed with the Windhoek Vocational Training Centre (WVTC) in December 2005.

- Activities – Phase II:

- Continuing support the development of study materials and courses at REEE Institute and vocational and training centres and support training of trainers

- Make a synopsis of donor-funded and/or RE-related courses and educational opportunities abroad

Outcome 2	New policies, laws, regulations and actions in support of renewable energy are in place

- The primary objective is to remove barriers to the appropriate use of SETs in the planning and budgeting processes at inter-sectoral levels and to prepare implementation plan to guide SET and off-grid development activities in collaboration with other relevant government agencies as well as in finding mechanisms to formulate standards and codes of practice. This component will provide valuable outputs that will justify the integration of SETs in electrification and rural development plans with the aim of securing political support and financial assistance in the longer term.

Output 2.1	Policy and regulatory frameworks for RE and off-grid electrification are formulated

- Activities – Phase I (completed):

- Development of a RE Strategic Action Plan, based on the clauses in the White Paper on Policy that affect SETs

- Consultancy on development of the Off-Grid Master Plan (that will supplement the 2005 Rural Electrification Master Plan)

- Discussions with ECB and RET suppliers on legal-regulatory issues (e.g., extending ECB’s mandate to the RET sector) and discussion on the development of Namibian standards and codes of practice

- Assessment of duties and taxes on RET suppliers and products

- Talks with six solar products manufacturers in Europe to look into the possibility of investing in local manufacturing of solar components. However, the visit concluded that the Namibian market is too small.

- Consultancy on the development of strategies to reduce first cost

- Activities – Phase II:

- Engage MME policy-makers and Government decision-makers in a policy dialogue, based on the results of the Off-Grid Master Plan and RE Strategic Action Plan (elaborated in Phase 1)

- Assist in the development of Namibian of a regulatory framework (e.g., quality of service, standards and warranty requirements, codes of practice for installation and maintenance of SETs, licensing and service contracts), in close cooperation with RET suppliers, MME, ECB and REEE Institute

- Assessment and design of a long-term (sustainable) subsidy scheme, in which the Government make resources available for renewable energy-based off-grid electrification and make recommendations on how to integrate such a scheme into fiscal and national policy. One option is the encouragement of cash sales into the SRF or financing schemes by offering a 10-15% discount to the customer that pays cash.

Output 2.2	Government ministries and public institutions finance and implement solar energy technologies and projects

- Activities – Phase I (completed):

- Consultancy and workshop on RET coordination amongst ministries and public institutions

- Activities – Phase II:

- Assess life-cycle economic cost and benefits of RETs and identification of niche areas for the inclusion of renewable energy into the national policies

- Support and convince the Government and its relevant ministries and local government (regional councils) to adopt policies that promote the use of SETs and optimise their budget expenditures by incorporating full consideration of SET options) e.g. by (a) provision of access to electricity with RETs to schools, clinics and main government institutions in off-grid areas, (b) making SWH compulsory for new public building that consume hot water, (c) setting RET and/or off-grid targets in national power supply, (d) definition of incentives for off-grid RETs, (e) setting up of ‘energy desks’ in the relevant ministries, (f) integrating PVP in MAWRD’s agricultural development programmes.

- Promote effective cooperation between line ministries and with grid suppliers (REDs), regional councils and other RET sector players on bundling of rural services (water, communications, financial services, productive uses of energy), e.g. by setting up of ‘energy desks’ in the relevant ministries or setting up a inter-ministerial coordination structure on the integration of socials and productive use of renewable energy in the development planning process

Output 2.3	The REEE Institute is established and functioning well

- Activities – Phase I (completed):

- Consultation with Polytechnic of Namibia (the chosen implementing agency of the Danida-funded REEECAP project) and MME on collaboration on REEECAP and REEE Institute

Outcome 3	Public awareness and social acceptability

- The objective of the SET awareness building and social acceptability component is to raise awareness throughout Namibia of SETs, addressing the particular development needs of and demand of energy services by the stakeholders. Knowledge, awareness and perceptions are important themes in the process to the successful penetration of SETs in rural and urban markets.

Output 3.1	Comparative information on demand for SET energy services and cost and benefits of SETs is collected and developed

- Activities – Phase I (completed):

- Establish and compare financial cost and benefits of using SETs and conventional energy

  - Cost-benefit study on SWH in comparison with electric geysers

  - Cost-benefit study on solar water pumps (PVP) in comparison with diesel pumps

- Survey on the market for SHS and other SETs in rural areas, looking into issues such as (a) opinion of rural persons regarding SETs (distinguishing between early adopters and people that do not SETs), e.g. awareness, willingness/ability to pay, maintenance service and reliability, (b) identifying uses of energy (individual, social infrastructure and productive uses), (c) costs and benefits of SHS and PV, in particular their potential for income generation, (d) local entrepreneurial capacity and (e) costs and benefits of SETs for social and productive applications in rural areas.

- Activities – Phase II:

- Update comparative information on costs and benefits of SETs to reflect changes in costs of SETs, power tariffs and fuel prices

Output 3.2	Increased knowledge of SETs among national and local decision-makers and potential end-users

- Activities – Phase I (completed):

- Cross-sectoral regional awareness workshops in all 13 regions of Namibia and giving follow-up to queries from participants

- Awareness campaigns through radio, TV, printed media (translating brochures in local languages) and presentations at trade fairs and business meetings

- Consultancies and workshop to develop SWH, PVP and PV refrigeration promotion campaigns

- Exhibition of RET equipment at trade fairs and assistance to MME in acquiring solar demonstration equipment for regional office

- Publication of NAMREP Quarterly Review

- Activities – Phase II:

- Targeted awareness and information packages for decision-makers in ministries, parastatals and regional councils about SE systems  (SHS, PVP, SWH) and their application in individual, social infrastructure and productive uses to offer rural development benefits as well as their application in urban areas (SWH in public and private buildings)

- Preparation and dissemination of an outreach and awareness campaign on the usefulness of SETs (SHS, PVP, SHS, solar refrigeration) in rural areas by dissemination and further preparation of printed materials (in English and in local languages); mobile demonstration of SETs and meetings at events, trade fairs, events, schools, regional government offices and community centres; exhibitions in the media (radio/TV); meetings with community-based organisations, community and religious leaders and agricultural extension workers:

  - Targeting rural households and rural-based civil servants (and their more wealthy relatives in urban areas) on the cost/benefits of SHS, availability of 12 DC and low-power AC appliances in the market (radios, lamps, TV, cell phone chargers), technical limitations and maintenance of PV systems, availability of financing opportunities and to raise awareness on the potential;

  - Targeting rural farming households and small rural businesses (farms, bars, restaurants, telephone shops, cottage and artisan workshops) to raise awareness on income-generating activities made possible as a result of off-grid solar-based power services by powering small tool and appliances (e.g., drills, blenders), lighting, radio/TV and cell-phone services

- Organisation of general awareness campaigns on PVP, targeting commercial farmers (through workshops, farmers’ associations meetings, media/radio/TV, brochures) on the costs and benefits and credit availability

- Organisation of general awareness campaigns of SWH, targeting private and commercial building owners (through seminars, training workshops; architects, engineering and plumbers associations networks; brochures, radio/TV and newspapers advertisements) as well as public building owners (through demonstration/installation in public buildings, workshops, radio/TV) on the costs and benefits and credit availability

Output 3.3	Active networks or associations of stakeholders are in place

- Activities – Phase I (completed):

- NAMREP Quarterly Review

- Support to establishment of a Namibian solar energy society or association

- Activities – Phase II:

- Support the functioning of the Sustainable Energy Namibian Society (SENS) and its networking with local, regional and international organisations

- Regularly informing stakeholders on progress in MME and the RE sector by means of the NAMREP Quarterly Review newsletter

Outcome 4	Appropriate financing and product delivery schemes set up and expanded

- The primary objective of this component is to reduce/overcome the financial barriers to the supply, installation, purchase and maintenance of SETs including reduction of the price and ready availability of finance for the purchase and maintenance of systems. The most appropriate delivery modalities in Namibia seem to be individually (or communally) owned RE technology, delivered by suppliers and serviced by local small RE entrepreneurs and (a) paid by cash right away or (b) over time with some dealer/supplier credit, (c) with personal consumer loans, (d) micro-finance loans or (e) loans through cooperative membership organisations. Other possible delivery modality could be (1) SET systems owned by the regional electricity distributors (REDs) and/or RESCO that sell units of energy (fee-for-services) or lease (hire-purchase) equipment or (2) mini-grid systems. However, due to Namibia’s low population and low population density the fee-for-services approach is deemed not feasible and pilot projects (such as in Ovitoto) have not been successful. Namibia has some experience with mini-grids, such as in Tsumkwe. However, the implementation of a possible government or RED-owned mini-grid system has not been budgeted for within NAMREP, which focuses on market development with the private sector as ‘driver’. Hence financial resources would have to come from non-GEF resources.

- The activities in this component of the project will remove/reduce financial barriers to SETs, by using different project instruments designed specifically to target each of a variety of solar technologies and their users (PVP and SHS for rural households and farmers; SWH for urban households and buildings). A desired outcome will be for private and public sector financiers to make affordable loans to SE users and providers (aiming at strengthening the supplier – rural technician – end-user chain). The goal of this component is to accelerate market transformation and to tangibly/visibly raise the profile of SETs through affirming demonstration of appropriate financing schemes throughout Namibia. For this purpose GEF is making available US$ 1,250,000 in the Phases I and II to support the capitalisation of existing and new credit and guarantee scheme and for providing technical assistance in setting up and operating these schemes. It should be stressed that GEF funds will not be used to procure equipment because this is the task of the suppliers and it would destroy the market.

Output 4.1	The Solar Revolving Fund (SRF) has been scaled up and expanded

- Activities – Phase I (completed):

- Assessment of bottlenecks and shortfalls of the SRF

- Advice on restructuring the SRF

- Technical assistance to the SRF. Activities included the assessment with MME of the contract conditions of Konga of problems experienced in the timely processing of loan application and repayments. In the SRF scheme, customers can apply for a loan for SETs at 5% interest rate, at a payback period of 5 years.

- Activities – Phase II:

- Technical advice on operating the SRF

- Provision of financial resources so that the demand for loans can be met. If the trend of increasing demand for loans continues, the amount of loans approved ($ 700,000) will exceed MME’s annual contribution of US$ 250,000 and annual loan repayments. The success of the SRF would result in a capital depletion because loan repayment is stretched over a period of 5 years. To avoid such situation GEF will strengthen the fund with a US$ 300,000 contribution to meet the customer demand.

Output 4.2	Financing schemes through (semi)-commercial financing institutions for customers and solar entrepreneurs have been set up and/or scaled up

- Activities – Phase I (completed):

- Study of international experiences with the financing and technology delivery models (in particular in the southern and eastern African region and of outcomes in other GEF-supported projects) and analysis of what modalities could work in Namibia for developing the market in rural areas for SETs and for strengthening the supplier – local technician/small entrepreneur – end user chain.

- Under agreement with MME and Bank Windhoek, the Bank provides short-to-medium term financing of between N$ 20,000-250,000 to SMEs that are awarded contracts under the MME/NAMREP programme and personal loans with a maximum amount of N$ 20,000 for SHS or SWH and up to N$ 40,000 for PVP at attractive interest rates that are of 3%, for SMEs, and 5%, for personal loans, below the prime interest rate. This is made possible, because MME provides the Bank with guarantee of 70-80% of the total loan capital. The scheme was capitalised in 2006 with US$ 300,000 of GEF micro-credit grant.

- Activities – Phase II:

- Technical support to and, if necessary, capitalisation with another US$ 100,000 of the two credit lines under agreement with Bank Windhoek and MME.

- Conclusion of similar agreements and capitalisation of SE credit schemes with other interested banks (possibly NedBank and First National) for SETs or with building societies (e.g., National Housing Enterprise) for adding an increment to house loan limits if SWH is used

- Conclusion of an agreements and capitalisation of SE credit schemes with development banks (e.g. AgriBank) to make loans available for rural small and micro-enterprises for RETs and productive applications

Outcome 5		Learning, evaluation and adaptive management

- As an extension at arms’ length of MME, the capacity of a Project Management Unit to take on the day-to-day tasks of managing the project and specified tasks was built in Phase I and the RE Resource Centre was set up.  At the end of Phase II, the PMU staff and RE Resource Centre would be absorbed by either MME or the new REEE Institute (see component 2). Another objective of this component is to improve the understanding about the practicalities of SET application and off-grid electrification, followed by dissemination of experience and lessons learned.

Output 5.1	Adaptive management, monitoring and evaluation

- Activities – Phase I (completed):

- Office administration and reporting by PMU

  - Hiring and contracting of PMU staff and establishing the PMU office

  - Regular project reporting (financial and progress reports)

  - Organisation of project inception workshop and drafting of the inception report

  - PMU staff participating in (inter)-national events (workshops, seminars, NAMREP events, trade fairs, etc.); PMU staff regularly meeting stakeholders and visiting project areas; observation trips to regions

- Establishment of RET Resource Centre at MME

- Baseline study for NAMREP, done by Consulting Services Africa (CSA, 2005)

- Mid-term evaluation

- Activities – Phase II:

- Office administration and reporting by PMU

- Design and implementation of a monitoring and evaluation plan for Phase II NAMREP. This will include doing a study the end of Phase II similar to the CSA (2005) baseline study to review the data and issues of the baseline study and to quantify the performance and impact indicators as well as defining a methodology to evaluate and measure the impacts of SETs on livelihoods and income generation

Output 5.2	Lessons learned from NAMREP have been documented and disseminated

- Activities – Phase I (completed):

- Publication of NAMREP Quarterly

- Activities – Phase II:

- Closely follow the activities in respect with the financial mechanisms and strengthening the supplier – local technician – end user chain and collect relevant data that can be used for decision-making in Namibia.

- Dissemination of lessons learned and results of NAMREP in the NAMREP Quarterly and in other publications within Namibia as well as to other countries and GEF-supported RE project in the region

- 2.3 	Project indicators, assumptions and risks

- Key indicators of success for the project include those listed below. NAMREP’s Logical Framework has been revised at the beginning of phase I and then again during the design of phase II with updated indicators for project performance and impacts, reflecting the experiences gained in Phase I. As much as possible indicators used in phase I will also be used in phase II thus assuring consistent tracking of impacts over a longer time span.

Environmental:

- Avoided emissions of greenhouse gases due to the application of SETs and reduced dependence on imported electricity and fossil fuels from South Africa. Direct reduction in CO2 emissions is an estimated 233,700 tCO2

Economic and social:

- Enhanced livelihood and income generating opportunities in rural communities

- Energy and cost savings for public institutions, urban households and commercial farmers

- Empowerment of local solar technicians and enabling them to set up small solar businesses

Capacity building, awareness creation and knowledge dissemination:

- Strengthened capacity in the operation, maintenance and after-sales services on solar technologies

- Strengthened capacities of stakeholders from government, private sector and NGOs in identifying, promoting, marketing and investing in solar energy technologies

- Strengthened capacity of training institute to provide courses on solar energy technologies

- Increased awareness and acceptance by the end-users of SETs for social and productive uses

Policy-institutional:

- An enabling policy and regulatory framework with consolidated plans for the promotion of renewable energy and off-grid electrification

- Adoption of ‘rules of the game’ (codes of practice, norms and standards) by the private sector and the Government

- Willingness of decision-makers to base decisions on SETs on the knowledge acquired

Financial:

- Strengthening and capitalisation of affordable credit schemes for small solar entrepreneurs and for customers in public and private financial institutions

- A strategy to reduce the first cost barrier of SETs has been formulated

- Important project assumptions are:

- Fuel and power prices will slowly go up

- Long-term financial and political support of the Government and its institutions, in particular MME

- Active interest of end-users in acquiring SETs

- Pro-active participation of the private sector (suppliers, financiers and rural technicians)

- During the project design stage, project risks have been closely analyzed and mitigation strategies have been incorporated. However, while the project is designed to minimize these risks, some issues are not entirely within the project’s control but may affect project implementation. These risks are listed below.

Policy-institutional:

- Despite the looming power shortage, renewable energy fails to become a Government priority

- While co-financing from MME for the direct interventions of NAMREP is assured, the sustained long-term contribution and larger-scale expansion of the Government’s financial resources for renewable energy and off-grid electrification fails to materialize

Social, market and financial:

- Due to the remote location and low population density, SETs may be difficult to supply and maintain in Namibia’s rural areas, access to financing for remote communities may be difficult, while the markets for products and services of the productive uses of energy may be too small or situated too far away from other markets

- The interest of PV suppliers and financial institutions to develop the rural PV market by cooperating with local agents (technicians, small solar entrepreneurs) may shift to other markets

- 2.4		Expected global, national and local benefits

- The increased sales of solar energy technologies (SETs) due to NAMREP’s intervention will result in the avoided greenhouse gas emissions of approximately 233,700 tons of CO2-equivalent over the lifetime of the SET installations (15 years). An estimate of the indirect impact of this project, resulting from replication (continuously growing sales of SETs after the project’s end) is in the order of 2.1 million tonnes of CO2.

- Removal of barriers to the more widespread use of SETs will also provide the private sector with the incentive to improve their services and rural-based solar technicians to extend or set up new small and medium-sized enterprises (SMEs) for the sale of SETs. This will benefit rural people in that they will have access to environmentally clean electricity services without the long wait for the arrival of grid-connected power and that it helps them to set up small RE SMEs that will contribute to ‘black empowerment’. Urban customers will have access to solar water heaters that will help them to save on their electricity consumption.

- In addition to bringing these global and local benefits, the project is consistent with Namibia’s development priorities. It will increase the use of the indigenously available solar energy resource and decrease dependency in imported power (or imported fuels to generate that power) required to meet current and future additional power demand.

- 2.5		Country ownership: country eligibility and country drivenness

- Namibia ratified the UN Framework Convention on Climate Change (UNFCCC) in 1995. One effort to address UNFCCC priorities was the launch of Namibia’s First National Communication to the UNFCCC in 2002, which established a GHG inventory and identified and vulnerability issues and policy measures. In Namibia, the Ministry of Environment and Tourism (MET) coordinates the formulation, implementation, and follow up of the national environmental policies and programs. MET acts as both the UNFCCC focal point and the GEF Operational and Political Focal Point. The proposed project is relevant to the on-going MET climate change programme, in particular to its efforts to develop a national mitigation plan and support the development of technologies that reduce GHG emissions, including renewable energy technologies (RETs).

- In the White Paper on Energy Policy (1998) the Government of Namibia recognises the importance of renewable energy in improving access to energy in rural areas (rural households, businesses, public services and water supply) as well as in generating electricity for the grid and the more rational use of electricity in buildings and for water heating, as is explained in more detail in paragraph 1.2.

- Both the Country Programme Plan (CP) and Country Action Plan (CPAP) 2006-2010 of the Government of Namibia and UNDP identify key challenges in meeting Vision 2030 and the Millenium Development Goals (MDGs) and is based on UNDP’s Multi-Year Funding Framework (MYFF) 2004-2007, while the outcomes are linked with the UN Development Assistance Framework (UNDAF) for Namibia 2006-2010. The CP has a component on ‘energy and environment for sustainable development’ and one its outcomes is ‘promoting biodiversity, renewable energy technologies and environmental education’ with ‘barriers to the delivery of solar and biomass energy systems removed’ as an output. The CPAP refers to MYFF outcome 10, ‘clean energy technologies promoted through energy efficiency, renewable energy and technology demonstrations’.

- 2.6		Sustainability and replicability

- Institutional Sustainability: To ensure sustainability of the project results upon completion of the project, MME, the new REEE Institute and also the new Sustainable Energy Association (SENS) will continue to play the role of prime movers in policy formulation and planning as well as promotion and implementation of renewable energy activities in Namibia. By attaching middle-level managers and technicians to the PMU and seconding MME staff to the PMU the project shall have trained a pool of experts whom the MME, REEE Institute and the private sector may re-deploy for their own long-term renewable energy activities. There are various options for the continuation of the PMU at the end of this project, for example, the unit may continue in MME, it may be taken over by the REEE Institute or staff will go to private and non-governmental organisations. Appropriate decisions would be made before the end of the project.

- Institutional mechanisms for this continuity are provided through the steady flow of funds into capacity building, awareness raising and other barrier removal activities that creates an enabling environment in which the market for solar energy services can thrive, driven by the demand in the urban areas (solar water heaters) and rural areas (solar home systems and solar water pumping).

- Financial Sustainability: The foundation for financial sustainability has been laid in phase I through the restructuring of the SRF and the signing of a MoU with a commercial bank (Bank of Windhoek) putting in place a credit guarantee scheme. During NAMREP phase I the SRF has been completely restructured which resulted in an increase of loans for the purchase of SHSs, PVPs and SWHs of approximately 700%. This is considered a key achievement in order to overcome the high first cost barrier. The restructured SRF needs to be further supported during phase II to ensure long-term financial sustainability of the fund. The success of the SRF is resulting in rapid “decapitalization”. The demand for loans cannot be met. Sufficient capital is provided to meet the rapidly increasing demand for loans Provide technical advice and contribute to capitalization so that these have sufficient working capital. Activities under outcomes 4 of the phase II proposal suggest to continue strengthen the SRF technically and financially. After the end of phase II the SRF would continue to operate as a revolving fund using funds from the recovered loans to award new loans to customers. Annex D describes in some more detail the success story of the SRF.

- In addition to the restructured SRF another financing scheme has been set up during phase I to address the financing barrier and ensure long-term financial sustainability. A MoU was signed in February 2006 between MME and the Bank of Windhoek in which the bank provides a credit line for small entrepreneurs as well as personal loans for PVP, SHS and SWH at attractive interest rates, made possible by the partial guarantee provided by MME to the bank. In Phase II these credit schemes will be scaled up with GEF support and replicated to other financial institutions such as the development bank Agribank and the housing delivery agent Namibian Housing Enterprise. Activities under outcome 4 of the phase II proposal and annex D describe this in more detail.

- SET Market Sustainability: NAMREP will provide business support services for the private sector, especially the development of rural-based solar technicians into small entrepreneurs (RE SMEs). These RE SMEs are an essential link in the supplier/RE SME/end-user chain, by providing products and services in the rural market that they know well.  Thus sustainability essentially lies in the stimulation of market mechanisms that allow the penetration of SWH and PVP as a least-cost alternative for electric geysers and diesel pumps and of PV as an off-grid electrification option.

- In addition to strengthening credit schemes and making these more affordable for (rural) low-income groups, NAMREP will focus on productive uses of energy in rural areas. Additional income generated at the local level will allow end users to pay more easily for the energy services provided by SETs, while development of the productive use itself will improve the livelihoods of rural households.

Replicability

- The replicability of the project hinges on the project’s ability to clearly demonstrate the financial and social benefits of solar energy. While Phase I focused on removing barriers through capacity building, institutional strengthening, policy planning, public awareness and information dissemination, the strategy of Phase II will shift to transforming the market by creating a favourable enabling environment (including an appropriate policy and regulatory framework for RET and off-grid energy and) and promotion of affordable financial guarantee and loan schemes for SETs. Private entrepreneurs can then seize the opportunity of a transforming market and take over the investment process to develop win-win models in which end users have willingness to pay for the initial investment and cost of maintenance of the SETs. Thus, NAMREP project focuses on developing and facilitating market-oriented financing and product delivery modality that will allow stakeholders to invest in renewable energy. It is expected that not only PV suppliers (based in Windhoek), but especially their agents, the small RE entrepreneurs based in the rural areas, will expand their business and that more rural-based technicians will develop their services into a viable solar energy business.

- Finally, the replication of the project’s results will be promoted through active dissemination and lessons learned. NAMREP actively works on information dissemination and public awareness enhancement activities, in the form of public exhibitions, multi-media presentations, dissemination of public information, and conduct of training courses, seminars and workshops. This means also that the project will engage in an active dialogue with similar GEF and non-GEF projects, particularly in Southern Africa, to both share the Namibian experience and learn from others.

- Management Arrangements

  - Links with other initiatives

- The proposed Phase II will build on efforts carried out through the NAMREP Phase I project and other initiatives in Namibia, incorporating their lessons learned and experiences.  The activities carried out under NAMREP – Phase I are described in the previous chapter 2. Two other initiatives, such as the GTZ and DANIDA-supported RE programmes, are described below.

- The Gesellschaft für Technische Zusammenarbeit (GTZ) has supported a capacity building programme in Ministry of Mines and Energy programme on the “Promotion of the Use of Renewable Sources of Energy in Namibia”, launched in 1993. The MME/GTZ Renewable Energy Programme (RE Programme) organised four training programmes for solar technicians and training manuals were made available. In a number of studies, jointly financed by MME and GTZ, the technical and economic exploitability of wind and solar resources were assessed, the economics of some RET’s and the socio-economic impact of rural electrification were analyzed, and some RET dissemination strategies developed. The project also provided valuable inputs to the Energy White Paper

- The Danish government has been supporting two projects in Namibia that have been included as collaborating partner projects and sources of co-financing in the NAMREP project:

- “Gobabeb REEE Training and Research Centre Support” project (supported by Danida with DKK 6 million)

- “Renewable Energy and Energy Efficiency Capacity Building (REEECAP)” project (supported by DANIDA with DKK 9.45 million).

- Implementation of the Gobabab project commenced in 2002 and was completed recently. REEECAP has met considerable obstacles, however. REEECAP was supposed to support and build capacity of the new R3E Bureau, an independent institute established in April 2002 as a means of outsourcing none-core activities of the Ministry of Mines and Energy (MME) with a view to coordinating and promoting RE and EE development and disseminating relevant information on these topics.

- Implementation of REEECAP started in May 2004. However, the MME informed the Bureau and the Royal Danish Embassy (RDE, in Pretoria) that in fact the establishment of the Bureau had not been legal. Consequently, the Bureau was closed and the RDE froze further disbursement of funds to REEECAP in October 2004. The project document was redrafted in August 2005 in order for REEECAP to resume activities with the REEE Institute as implementing agency, newly established by the Polytechnic of Namibia (PoN) under its Centre for Applied Research and Technology (CART).

- In the development and implementation of NAMREP, experiences are drawn from in the region, such as the GEF-supported projects Botswana, Lesotho, Malawi, South Africa and Tanzania. Particular attention in these regional examples of PV projects is paid to critiques of: financial mechanisms (to end-users and the PV industry); project institutional arrangements; institutional arrangements and delivery modes; credit ratings of PV purchasers; performance standards and codes of practice; training and accreditation of technicians trainees. Lessons learned from these projects will facilitate the Namibian project’s contribution to the momentum of PV electrification in Africa.

- Some lessons learned from the above-mentioned projects can be summarized as follows:

- Decentralized energy projects should be based on local energy needs and enhance end-user involvement at the planning and design stage. Local conditions, potential energy uses and social context should determine the choice of technological options. Local participation, including financial participation to, at minimum, cover operational and maintenance costs, is essential to the success of technology promotion;

- Projects need to go beyond technology demonstration towards building an enabling environment at local, national and regional levels, which is essential to increase private sector participation. This also includes infrastructure and capacity building for distribution, installation, maintenance and operation of renewable energy technologies (RETs);

- New funding and financing approaches, involving the private sector, need to be developed to ensure that projects influence the development of sustainable markets for RE technologies. This is essential both to ensure the sustainability of individual projects and to leverage private sector finance capital for new initiatives that replicate project benefits;

- The design of renewable energy projects that promote productive activities need to have a clear understanding of the productive use potential in the beneficiary community, to ensure adequate energy supply and financial viability;

- Increased attention should be paid to social issues during project site selection to ensure that project benefits reach all segments of rural society, alleviate poverty and decrease economic and social disparities;

- Off-grid power projects must be integrated in a broader and well-conceived rural development and national electrification strategies.

- NAMREP Phase II will build upon these initial experiences and achievements, especially in its components on financing and implementation mechanisms, to make best use of the knowledge and expertise already available. The envisaged NAMREP activities will put in place conditions for replication of a variety of pilot activities, by promoting a policy, regulatory and market context favourable for the continued development of solar energy services.

  - Project management

- Phase II will be implemented by UNDP and executed by the Ministry of Mines and Energy on behalf of the Government of Namibia under the same arrangements as for Phase I. The MME and UNDP will channel the contributions of the Government and GEF respectively to the PMU for implementation of Phase II.

- The structure and composition of project management in Phase II is the same as for Phase I. The Project Management Unit (PMU), created in MME in 2004, is responsible for running the day-to-day operations of the project. The PMU is chaired by the MME Director of Energy acting as National Project Director (NPD) and its activities are coordinated by the Chief Technical Advisor (CTA)/Project Coordinator and Deputy Chief Technical Advisor/National Project Manager (DCTA), assisted by one project associate, two project assistants and one office assistant. The NPD and project associate are MME energy professionals, while the other posts are paid by the project. In addition, the PMU appoints consultants and support staff on short-term contracts.

- A Project Steering Committee (PSC) is chaired by the MME Permanent Secretary and further consists of MME officials (Director and Deputy Director of Energy), PMU management (CTA and DCTA), representatives from UNDP and the Ministry of Environment and Tourism (the GEF focal point) and any other person, nominated by the PSC Chairperson.

- The Phase I Project Procedures Manual describes in detail the management of NAMREP and the operations of the PSC and PMU. The PPM describes also how project funds are managed.

- NAMREP and REEECAP will liaise closely and harmonise execution:

- The Project Directors and/or project managers of REEECAP and NAMREP sit in each other’s Project Steering Committee

- An Advisory Committee is established for both projects with participation of key stakeholders (including other relevant line ministries, such as MAWRD, education and health, and the National Planning Commission, as well as representatives from private sector and NGOs). This not only ensures cooperation between the two projects but also stakeholder engagement in the projects’ execution.

- MOnitoring and evaluation plan

- Project monitoring and evaluation (M&E) will be conducted in accordance with established GEF procedures as well as following new UNDP procedures in the ATLAS system.  Project M&E provided by the project team, supported by UNDP, i.e., the UNDP Country Office (CO) and the UNDP-GEF Regional Coordinating Unit (RCU). The Logical Framework Matrix in Section B provides performance and impact indicators for project implementation along with their corresponding means of verification. These will form the basis on which the project's Monitoring and Evaluation system will be built throughout the 5-year implementation period.

- The principle components of the Monitoring and Evaluation Plan will include: (1) establishing monitoring responsibilities and events, (2) project reporting and (3) independent evaluations. The project's Monitoring and Evaluation Plan will be presented and finalized at the Project's Inception Report following a collective fine-tuning of indicators, means of verification, and the full definition of project staff M&E responsibilities.

- Monitoring responsibilities and events

- A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for Steering and Advisory Committee Meetings and (ii) project related Monitoring and Evaluation (M&E) activities.

- Day-to-day monitoring of implementation progress will be the responsibility of the CTA and DCTA, based on the project's Annual Work plan (Strategic Planning Matrix) and its indicators. The PMU will inform the UNDP CO and MME of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion.

- Periodic monitoring of implementation progress will be undertaken by the Project Steering Committee (PSC) through quarterly meetings with MME and UNDP (or more or less frequently as deemed necessary). This will allow parties to take stock and to troubleshoot any problems pertaining to the project in a timely fashion to ensure smooth implementation of project activities.

- UNDP Country Office and UNDP-GEF Regional Coordination Unit are responsible for monitoring the project on a continuous basis and can conduct, as appropriate, visits to the project and field sites to assess first hand project progress. Any other member of the Project Steering Committee can also accompany, as decided by the Committee. A Field Visit Report will be prepared by the CO and circulated no less than one month after the visit to the project team, all PSC members and UNDP-GEF.

- Annual Monitoring will occur through the APR-PIR process.  The APR-PIR will highlight policy issues and recommendations for the decision of the PSC participants.  The CTA also informs the project participants of any agreement reached by stakeholders during the APR preparation on how to resolve operational issues. Separate reviews of each project component may also be conducted if necessary.

- Project reporting; learning and knowledge sharing

- The CTA will be responsible for the preparation and submission of the following reports that form part of the monitoring process. Items (a) through (f) are mandatory and strictly related to monitoring, while (g) through (h) have a broader function and the frequency and nature is project specific to be defined throughout implementation.

- a) Work Planning.  A first Project Inception Report was made in August 2004, containing a detailed work plan, a monitoring plan and details on coordination arrangements with key stakeholders involved in co-financing or project implementation. An update of the work plan, referred to as Strategic Planning Matrix, was made early 2005 and again in 2006, including a detailed list of outputs, activities and progress indicators that will guide implementation during the first year of the project as well as a detailed project budget. Also, in Phase II, the Strategic Planning Matrix will be updated on a yearly basis and in the first year of Phase II, 2006, this will include a reviewed logic framework of activities and precise and measurable performance indicators in a manner consistent with the expected outcomes for the project. Targets and indicators for subsequent years would be defined annually as part of the internal evaluation and planning processes undertaken by the PMU.

Indicative M&E work plan and budget for the Phases I and II

| Type of M&E activity | Responsible Parties | Budget US$ | Time frame |
| --- | --- | --- | --- |
| Strategic Planning Matrix (annual work plan) | - Project Team - UNDP CO | 0 | Annually, first SPM immediately following approval of Phase II |
| Baseline and End-of Project Study of Project Indicators | - PMU - Hired consultant | 150,000 | Start and end of project. |
| Measurement of Means of Verification for Project Progress and Performance (measured annually) | - Oversight by UNDP-GEF RCU and CTA - Counterpart organizations in the field or hired consultants on an as-needed basis | Part of the SPM’s preparation. | Annually prior to APR/PIR and to the definition of annual work plans |
| APR-PIR | - PMU - UNDP-CO - UNDP-GEF | 0 | Annually |
| Steering Committee Meetings | - CTA - UNDP CO | 0 | Following Project IW and held regularly |
| Technical reports | - PMU - Hired consultants | As part of project activities | To be determined by Project Team and UNDP-CO |
| Mid-Term Evaluation | - PMU - Hired consultants | 23,000 | Half a year before end of Phase I |
| Phase II Project Document | - PMU - Hired consultants | 24,500 | Half a year before end of Phase I |
| Final External Evaluation | - PMU - UNDP-CO - UNDP-GEF RCU - External Consultants (i.e. evaluation team) | 25,000 | At the end of project implementation |
| Terminal Report | - PMU - UNDP-CO | 0 | At least one month before the project’s end |
| Lessons learned | - PMU - UNDP-GEF RCU (suggested formats for documenting best practices, etc) | 10,000 | Yearly |
| Audit | - UNDP-CO - PMU | 4,000 | Yearly |
| Visits to field sites (UNDP staff travel costs to be charged to IA fees) | - UNDP CO - UNDP-GEF RCU (as appropriate) - Government representatives | 40,000 | Yearly |
| TOTAL indicative COST Excluding project team staff time and UNDP staff and travel expenses. |  | US$ 276,500 |  |

- b) Annual Project Report (APR) - Project Implementation Review (PIR). The APR-PIR is a UNDP and GEF requirement to facilitate central oversight, monitoring and project management. It is a self-assessment report by project management to the CO, providing inputs to the CO reporting process, as well as forming a key input to the UNDP/GEF M&E Unit, which analyzes the APR-PIRs by focal area, theme and region for common issues/results and lessons.

- c) Quarterly Progress and Financial Reports.  Short reports outlining main updates in project progress will be provided quarterly to the local UNDP Country Office (and forwarded to the UNDP-GEF RCU) by the Project Coordinator

d) Baseline and end-of-project reports.  A baseline market study was completed in 2005, which sets baseline data and values against which progress will be measured till the end of phase II. The first update of the baseline study was done in early 2006 to monitor the development of the market and collect data for key indictors.  Values for each indicator will be collected each year in the Strategic Planning Matrix and also as input in the APR-PIR. This should enable the quantitative evaluation of outputs and impacts of NAMREP intervention and on the progress in installation and loan servicing in RETs in general.

- e) Project Terminal Report. During the last three months of the project the project team will prepare the Project Terminal Report.  This comprehensive report will summarize all activities, achievements and outputs, objectives met (or not achieved!) of the Project, as well as lessons learnt and structures and systems implemented. It will also lay out recommendations for any further steps that need to be taken to ensure sustainability and replicability of the Project’s activities.

- f) Project reports and publications. Technical Reports are detailed documents covering specific areas of analysis, usually done in consultancy assignment in selected activities.  The PMU revises and regularly updates a Reports List that is included in subsequent APR-PIRs.  NAMREP Quarterly Review is the project publication is the key method for disseminating the results and achievements of the Project.

- Results from the project will be disseminated through a number of existing information sharing networks and forums.  The project will participate, as relevant and appropriate, in UNDP and GEF sponsored knowledge networks, organized for staff working on activities that share common characteristics. The project will identify, analyze, and share lessons learned that might be beneficial in the design and implementation of similar future projects. UNDP/GEF shall provide a format and assist the project team in categorizing, documenting and reporting on lessons learned.

Independent evaluation

- The project will be subjected to at least two independent external evaluations as follows:

Mid-term Evaluation

- An independent Mid-Term Evaluation was undertaken in January 2006. The Mid-Term Evaluation determined the progress made in Phase I towards the achievement of outcomes and suggested recommendations for Phase II. The evaluation focused on the effectiveness, efficiency and timeliness of project implementation, highlighted issues and presented some lessons learned about project design, implementation and management.

Final Evaluation

- An independent Final Evaluation will take place three months prior to the project’s termination date and will focus on the same issues as the mid-term evaluation and, in addition, will also look at impact and sustainability of results, including the contribution to capacity development and the achievement of global environmental goals. The Final Evaluation should also provide recommendations for follow-up activities. The Terms of Reference for this Final Evaluation will be prepared by the UNDP CO, based on guidance from the UNDP-GEF RCU.

Audit Clause

- The Government will provide the Resident Representative with certified periodic financial statements, and with an annual audit of the financial statements relating to the status of UNDP (including GEF) funds according to the procedures set out in Section 30503 of the UNDP Policies and Procedures Manual (PPM) and Section 10404 of the UNDP Finance Manual.  The Audit will be conducted by the legally recognized auditor of the Government, or by a commercial auditor engaged by the Government.

- Legal context and other agreements

- This project document shall be the instrument referred to as such in Article 1 of the Standard Basic Assistance Agreement (SBAA) between the Government of Namibia and the UNDP, signed by the parties on July 15, 1977. The host-country implementing agency shall, for the purpose of the SBAA, refer to the Government co-operating agency described in that Agreement. The following types of revisions may be made to this project document with the signature of the UNDP Resident Representative only, provided he or she is assured that the other signatories of the project document have no objections to the proposed changes:

- Revisions in, or addition of, any of the annexes of the project document (with the exception of the Standard Legal Text for non-SBAA countries which may not be altered and the agreement to which is a pre-condition for UNDP assistance);

- Revisions to the project will be permitted through agreement with the MME are allowed which; i) do not involve significant changes in the immediate objectives, outputs or activities of a project, but are caused by rearrangement of inputs agreed to or by cost increases due to inflation; and, ii) mandatory annual revisions, which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or which take into account agency expenditure flexibility.

- Section B. STrategic Results Framework

- 1.	Incremental cost analysis (Phase I and PHASE II)

titutiona

- See Annex A of the Executive Summary.

- 2.	lOGICAL FRAMEWORK ANALYSIS

titutionatutiona

- See Annex B of the Executive Summary.

- Section C. Total Budget and workplan

Incremental costs

- The main objective of this initiative relates to putting mechanisms in place that will create a favourable environment for private entrepreneurs (suppliers, financiers and rural-based technicians) to seize the opportunity of a transformed market and take over the investment process ensuring sustainability and replicability in the longer term. The implementation of the project will not only improve the commercial attractiveness of solar energy technologies. It will also transform the market through capacity building, institutional strengthening, public awareness and information dissemination, provision of financial incentives, technical standardization and the implementation of successful SET delivery, maintenance, ownership and financing models. The project incremental costs (to GEF) include these barrier removal activities as well as funding the incremental costs associated with management, and engineering service provision for emerging sustainable energy ventures. Six main groups of activities have been designed to remove the identified barriers to increased and sustained development of small-scale solar energy applications. The incremental costs related to the removing the barriers identified and summarized in the Incremental Cost matrix, given in Annex A of the Executive Summary.

Project financing

The total budget for Phase II is US$ 10,200,000 with US$ 2,6 million from GEF and US$ 7,6 co-financing contributions, as indicated in the following table:

- Section D.  ADDITIONAL INFORMATION

- I.  STAKEHOLDER INVOLVEMENT PLAN

- NAMREP tries to establish effective partnership arrangements for implementation of PV, SWS and PVP technologies with the relevant stakeholders as listed in paragraph 1.4 of Section A, such as the RE entrepreneurs and technicians, financial institutions, stakeholders from the national and local government and, last but not least, the end-users of the technologies. A detailed list of stakeholders is given in paragraph 1.4 of section A.

- NAMREP Phase I has established effective partnership arrangements for implementation of PV, SWS and PVP technologies with RE entrepreneurs and technicians, financial institutions and stakeholders from the national and local government.  NAMREP encourages the establishment of RE associations, e.g., a Sustainable Energy Namibian Society was formed early 2006 with NAMREP support.  NAMREP works with financial institutions, such as the Bank of Windhoek and MME’s Solar Revolving Fund, on financial mechanisms and with entrepreneurs to look at reduction of investment cost in RET equipment. The National Housing Enterprise (public) and private housing developers have expressed interest in including solar water heating in the houses they develop. Particularly the solar water heater component of the demonstration project will be undertaken in collaboration with these developers and will require inputs from the commercial and development banks to provide financial instruments as part of mortgages or as dedicated loans.

- NAMREP will cooperate with the REEE Institute, which is a newly established networking organisation on renewable energy and energy efficiency (REEE) at the Polytechnic of Namibia, aiming at coordination and promotion of activities in the area of renewable energy and energy efficiency. DANIDA will provide co-financing support through the REEECAP project that is complementing NAMREP. REEECAP itself will work closely with two NGOs, namely the Desert Research Foundation and the Habitat Research Centre.

- The Ministries dealing with water supply, health, education, public works, police, and agriculture, all have infrastructural development programmes that provide energy services such as lighting, refrigeration, water-pumping, warm water supply, which could be undertaken using SETs. As such the involvement of the ministries is essential if the project is to successfully integrate the use of solar energy technologies throughout the public sector. The regional electricity distributors (REDs) are involved in the provision of rural electricity and the breadth of their extension of technical and administrative infrastructure throughout Namibia will also contribute to a successful outcome of the project.

- An Advisory Committee is established for both projects with participation of key stakeholders (including other relevant line ministries, such as MAWRD, education and health, and the National Planning Commision, as well as representatives from private sector and NGOs). This not only ensures cooperation between the two projects but also stakeholder engagement in the projects’ execution.

- II.    CORRESPONDENCE OF NAMREP WITH REEECAP ACTIVITIES

| - OUTPUT - NAMREP | - Correspondence with REEECAP output |
| --- | --- |
| - Outcome 1: Built capacity in public and private sectors and in NGOs |  |
| - 1.1 Training programmes for NGOs, public and private sector have been established and executed | Output 2.4: Architects, engineers contractors and others are informed about RE&EE designs Output 2.5: Local politicians are informed about RE&EE designs (through workshops, conferences, publications, etc.) - Output 3.5: Training manual on awareness-raising |
| - 1.2 Decentralized RET companies are established |  |
| - 1.3 Vocational and training centres are capacitated and ready to provide technical training on SETs | - Output 3.2: Standard energy audit methologies for rural areas are developed - Output 3.3: Training-of-trainers course manual and training of DFRN facilitators |
| - Outcome 2: New policies, laws, regulations and actions in support of RETs are in place |  |
| - 2.1 Policy and regulatory framework for renewable energy and off-grid electrification are formulated |  |
| - 2.2 Government ministries and public institutions finance and implement solar energy technologies and projects | Output 3.1: Guidelines on RE&EE measures and mechanisms to integrate these measures in community development planning (with DRFN) - Output 3.6: RE&EE measures incorporated in a number of existing rural development programmes |
| - 2.3 The REEE Institute is established at the Polytechnic of Namibia and functioning well | - Output 1.1: Business and organisational development of REEE Institute |
| - Outcome 3: Increased public awareness and social acceptability amongst stakeholders |  |
| - 3.1 Comparative info on demand for energy services and cost and benefits of SETs is collected | - Output 2.2: Documentation of institutional, financial-economic and technical aspects and disssemination |
| 3.2 Increased knowledge of SETs among potential end-users and national and regional decision-makers | Output 1.6: RE&EE fact sheets and statistics published Output 2.1: Construction and demonstration of cost-effective RE&EE designs at HRDC Output 3.4: Rural RE&EE unit/kit to demonstrate RE&EE technologies to rural dwellers (with info on financial aspects and installation) Output 3.7: Document component experience through reports, workshops, videos, etc. |
| - 3.3 Active networks or associations of stakeholders are in place |  |
| - Outcome 4: Increased accessibility to RETs as result of more affordable financing schemes |  |
| - 4.1 New strategies/policies to reduce the barrier of high first cost |  |
| - 4.2 Financing schemes for customers and solar entrepreneurs have been set up and/or scaled up |  |
| Outcome 5: Learning, evaluation and adaptive management |  |
| - 6.1 Adaptive management, monitoring and evaluation | Outputs 1.2: REECAP project management Output 1.5: Resource Centre at REEE Institute - Output 2.3: RE&EE reference centre established at HRDC |
| - 6.2 Lessons learned have been documented and disseminated | - Output 1.4: Monitoring and lessons learned |

- SIGNATURE PAGE

Country: Namibia

UNDAF Outcome(s)/Indicator(s):

By 2010, livelihoods and food security amongst vulnerable groups are improved in highly affected locations (UNDAF, outcome 2)

Expected Outcome(s)/Indicator (s):

Promoting buiodiversity conservation, renewable energy (Country Programme 2006-2010), outcome 3.2). The project is linked to the MYFF 2004-2007 goal ‘Energy and environment for sustainable development’ and service lines 3.3 ‘Access to sustainable energy services’

Indicator (s):

Installation of renewable energy technologies

Expected Output(s)/Indicator(s):

Barriers to the delivery of solar energy systems and biomass energy technologies removed (Country Programme, output 3.2.2)

Implementing partner:				Ministry of Mines and Energy

Other Partners:						_________________________

_________________________

Total budget:		 ____________

Allocated resources:	 ____________

- Government	 ____________

- Regular 		 ____________

- Other:

  - Donor	_________

  - Donor	_________

  - Donor	_________

- In kind contributions _________

Programme Period: CP 2006-2010

Programme Component: Clean technologies promoted through energy efficiency, renewable energy and technology demonstrations (MYFF outcome 10, Country Programme Action Plan)

Project Title: Barrier Removal to Namibian Renewable Energy Programme

Project ID: PIMS 3062

Project Duration: 2006-2009

Management Arrangement: ______

Agreed by (Government): ___________________________________________________

Agreed by (Implementing partner/Executing agency):____________________________

Agreed by (UNDP):_________________________________________________________

Costing USD 65-90 for box cookers and USD 70-100 for parabolic cookers.

In Namibia DC systems are available at USD 860 (50 Wp, including the panels and the stand, a battery, controller, plugs and wiring and 4 lights), USD USD 1,380 (100 Wp, now including panels, two batteries and 8 lights), while AC systems come at USD 2,400 (150 Wp, three panels, three batteries, a AC/SC inverter, charge controller, 8 lights, plugs and wiring) and USD 3,330 (350 Wp, 5 panels, three batteries, 8 lights). Installation cost for the above systems varies from USD 65-210. A 105 A/h solar battery costs USD 95 (lasting 3-4 years), a 9 W fluorescent light costs USD 30.

In 2004, costs of dual-cycle SWH varied from USD 890 (100 litres), USD 1,270 (150 litres), USD 1,400 (180 litres) to USD 1,780 (300 litres), according to CSA (2005), to which USD 250 of installation is added.

The cost of a PVP installed pumping at 50 m depth is USD 3050 (water delivery of 7,000 litres), USD 7000 (15,000 litres) and USD 14,000 (50,000 litres) respectively, including installation cost. The 2004 price data are taken from CSA (2005)

A Solar Revolving Fund (SRF) was established by MME in 1996, but has was not able to gain expected reach and turnover, until 2005, when the SRF got boosted under new management and with technical support by the NAMREP staff in Phase I. Please refer to annex D of the Executive Summary for more details.

Being modular in nature, PV systems can be expanded incrementally and purchased over time, although quality of the systems may suffer

(R)ESCO: (rural) energy supply company, could be formed by a regional electricity distributor (RED), community or local authority, NGO, or private sector entity. Due to economics-of-scale  needed such schemes are sometimes implemented as a concession granting exclusive rights to a region for the RESCO.

Average number of loans awarded by the SRF per annum between 2001 and 2004 was 52; since April 2005 372 loans have been awarded.