## 2016
Social Cohesion and Democratic Participation Programme
Result Tracker 2016
[16 empty] | Not on track | On Track | Achieved
S.N | UNDAF/ CPD outcome | [8 empty] | Included in IWP? |  | Up to 5 Key Results for Year | Quarterly Targets and Progress Year ….. | [7 empty] | Final Progress against Annual Target | OBSERVATIONS/ comments
[12 empty] | AWP Targets and Indicators | Q1 |  | Q2 |  | Q3 |  | Q4
| 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Yes | No |  | Targets | Progress | Targets | Progress | Targets | Progress | Targets | Progress
[12 empty] | Result statement 1: Effective risk identification systems in place through capacity building, improved participation and networking Indicator 1: # of effective and functional risk identification mechanisms in place. Target 1: At least 12 risk identification mechanisms are functional in programme area with improved capacity | Selection of clusters and communities for social cohesion programme | Achieved: 14 clusters are selected | Mapping and assessment of risk identification mechanisms and entry points | Achieved: Assessment in 14 cluster completed,
GENDER RESULTS
[12 empty] | Result statement 2:Risk mitigation improved through Early Response Initiative, Quick Impact Support to Inter-Community Cohesion, and Local Participation and Accountability Initiative Indicator 1:# of actions taken for mitigating conflict related risks at local level Target 1: Risk Mitigation and community security is integrated in regular institutional plan of government and non government agencies of programme area Target 2: At least 8 EQ affected district development actors trained on Conflict Sensitive approaches | Organize 5 Conflict Sensitivity trainings in EQ affected districts | Achieved: Conflict Sensitivity trainings were organized in 6 districts by LDTA | Partner selection and capacity building for supporting them to develop risk mitigating strategies | Achieved: 12 partner organizations were selected for risk mitigation through micro grants
[12 empty] | Result statement 3: Policy makers (male and females) feel confident and committed to implement gender-responsive land reform policy Indicator 1: # of gender sensitive land policies in place Target 1: Gender sensitive land position paper of three major political parties and madeshi based parties are developed | Workshop with 3 major political parties | Achieved | gender sensitive position paper of major political parties | Nepali congress and CPN Maoist(Centre) developed the position paper, other are in process
[12 empty] | Result statement 4: d) Increased capacities of women members of IPWA, local leaders and existing conflict affected people’s district level networks, to influence local planning and budgeting and demand better services in project sites Indicator 1: Gender responsive Planning documents Target 1:Women leaders and local government work together to make gender responsive planning at DDCs of Bara and parsa Districts | 2 consultation meetings with stakeholders on gender responsive planning | Achieved: meetings organized in Bara and parsa district | 4 capacity Building events for women leaders and stakeholders | 3 completed one, one is planned in 3rd quarter
[12 empty] | Result statement 5: Increased knowledge, skills and confidence of key women leaders to mobilize people and resources for collective advocacy for women's inclusion in all aspects of peace and security processes Indicator 1: # of women led collective advocacy events Target 1: At lest 5 advocacy campaigns are organized through grant | 5 organizations will develop plan for women led advocacy campaign | Achieved: 5 organizations made plans and got support from N-PEACE grant | organize 5 advocacy campaign | Achieved: all five organizations completed planned activities
Note on B7: UNDAF/CPD Outcome 2: Vulnerable groups have improved access to economic opportunities and adequate social protection. Indicators: Gini coefficient (UNDAF I # No 2.1) % of employed people living below USD 1 (PPP) per day (UNDAF I # 2.2)
Note on C7: UNDAF/ CPD Outcome 3: Vulnerable groups experience greater self- confidence, respect and dignity Indicators: % of Dalits in selected Mid- and Far Western districts who perceive that caste discrimination has decreased in the last five years (UNDAF I # 3.2) Gender Empowerment Measure (GEM) in Mid- and Far Western Development Regions (UNDAF I # 3.4)
Note on D7: UNDAF/ CPD Outcome 4: Vulnerable groups benefit from strengthened legal and policy framework and have improved access to security and rule-of-law institutions Indicators: % of Universal Periodic Review (UPR), and treaty body and UN special procedures recommendations implemented by GoN (UNDAF I # 4.1) % of population satisfied with the services of courts/police and prosecutors (UNDAF I # 4.2) % of women who following sexual violence, would feel confident to (a) approach a prosecutor (b) seek legal aid (UNDAF I # 4.3)
Note on E7: UNDAF/CPD Outcome 5: Institutions, systems and processes of democratic governance are more accountable, effective, efficient and inclusive. Indicators: % of women and minority candidates in national and local election (UNDAF I # 5.1) % of eligible voters who turn out on national and local elections (UNDAF I # 5.2)
Note on F7: UNDAF Outcome 6: Tiers of government established and function to meet the provision of the new federal constitution. Indicators: % of Women, Dalits, Janajatis, Muslims and other minorities who perceive that they are represented at all levels of government (UNDAF I # 6.1) Elections to three tiers of government held (UNDAF I # 6.2)
Note on G7: UNDAF/CPD Outcome 7: People living in areas vulnerable to climate change and disasters benefit from improved risk management and capacity for climate change adaptation and mitigation of risk management and are more resilient to hazard-related shocks Indicators: # of districts covered by government-owned emergency operation networks for communicating relief needs (UNDAF I # 7.2) Number of VDCs meeting minimum criteria for disaster-resilient communities as defined by Nepal Risk Reduction Consortium(NRRC) Flagship Four on integrated community-based disaster risk reduction/ disaster risk management (UNDAF I # 7.3)
Note on H7: UNDAF Outcome 8: National institutions have addressed conflict- related violations of human rights and international humanitarian law and the post- conflict needs of victims. Indicators: % of recommendations of the National Human Rights Commission and the Universal Periodic Review (UPR) regarding transitional justice, or in relation to conflict-related violations, implemented (UNDAF I # 8.1) % of people who perceive that people affected by conflict-related issues regarding truth and reconciliation/ disappearances/ property rights have been adequately addressed (UNDAF I # 8.2) % of people who perceive that people affected by conflict have had their post-conflict needs met (UNDAF I # 8.3)
Note on I7: UNDAF Outcome 9: National actors and institutions have managed conflict risk and are progressively consolidating the peace. Indicators: % of people who perceive that there is a high or medium likelihood of national level armed conflict in the next five years (UNDAF I # 9.1 a) % of people who perceive that there is a high or medium likelihood of communal violence happening multiple times within five years in their district (UNDAF I # 9.1 b) % of people who are aware of selected peace-supporting commitments, policies and mechanisms (UNDAF I # 9.2)
Note on J7: UNDAF Outcome 10: Nepal's institutions are strengthened for more effective integration of policy and economy into inter governmental economic and normative processes, and international policy and legal regimes. Indicators: Trade deficit (UNDAF I # 10.1) Amount of climate financing receiving by government from international funding sources (UNDAF I # 10.2) # of bilateral or multilateral agreements that the government is party to that regulate high-value-added exports

## 2017
Social Cohesion and Democratic Participation program
Result Tracker 2017
[8 empty] | Not on track | On Track | Achieved
S.N | Up to 5 Key Results for Year | Quarterly Targets and Progress Year ….. | [7 empty] | Final Progress against Annual Target | OBSERVATIONS/ comments
| AWP Targets and Indicators | Q1 |  | Q2 |  | Q3 |  | Q4
|  | Targets | Progress | Targets | Progress | Targets | Progress | Targets | Progress
Result statement 1: Risk identification systems contribute to shape local responses to potential or actual issues that may affect social cohesion Indicator 1: # local risk identification mechanisms that report to have discussed potential or actual issues that may affect social cohesion Target 1: At least 12 risk identification mechanisms
Result statement 2: Risk mitigation improved through Early Response Initiative, Quick Impact Support to Inter-Community Cohesion Indicator 1:# of initiatives taken for mitigating conflict related risks at local level Target 1: 60 initiatives
Result statement 3: Community leaders (male and female), CBOs, youth organizations, marginalized groups lead actions and/or processes to make public institutions accountable Indicator 1: Increase in % of women, youth and marginalized groups participate in local level decision-making processes Indicator 2: # of initiatives taken by CBOs, women, youth and marginalized groups to enhance accountability Indicator 3: # initiatives taken by local stakeholders for strengthening community security Target 1: 20% Target 2: 30 initiatives Target 3: 12