## Overall Progress
Project ID
Quarter (1st, 2nd..)
Prepared by | Mahwish Bukhari
Reviewed by (Project Manager) | Usman Manzoor
Approved by (Program Officer) | Usman Manzoor
Project Quality Rating
Project Output Statements | Quarter Progress Status On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Progress Assessment/Remarks | Challenges | Follow-up Actions & Due-by | Responsibility | Lesson Learnt
1.1.1 Undertake Vulnerability Mapping and Assessment in the Tibetan Eco-region of Pakistan | Completed | The consultant has submitted the final report | Weather has been the main challenge for this study | Awaiting final payment | UNDP
1.2 Support Pakistan’s SE4ALL (Sustainable Energy for All) initiative | Ongoing | Initial meetings with all the relevant ministries have been held and TORs have been developed. IC notice has been developed and sent to procurement for recruitment of consultant. | Slow progress at the government level has been the cause of delay | Follow up with the Planning Commission on regular basis | UNDP
1.3 Scoping the potential for mainstreaming environment and climate change into the development agenda of Khyber-Pakhtunkhwa (KP). Technical support will be provided to develop a KP specific framework for action to manage climate change in the province. | Ongoing | Final Input from government awaited to finalize specific activities and start work accordingly | Government's non-responsiveness is taking considerable time. | Meetings have to be scheduled with the relevant government departments and concerned officials to be held in the 3rd Quarter. | UNDP
|  |  |  | Follow up with Chief foreign aid for the issuance of miuntes | UNDP
1.4 Developing and Launching Minimum energy performance standards (MEPS) for EE products including Refrigirator / AC etc, moreover, the market survey of EE products | Ongoing | Coordination with ENERCON is underway; ENERCON is finalizing list of technical activities to be executed by consultants to develop the TORs | Delayed response from ENERCON | List of activities and focal point from ENERCON to be finalized; space allocation for the consultant; coordination with industry and launching the workshop | UNDP
1.5 Promoting green energy to mitigate climate change and energy crisis | Ongoing | Finalizing agreements with local NGO to carry out the project | NA | NA | UNDP
1.6 Manage “New World: Inclusive Sustainable Human Development Initiatives” project (UNDP’s global programme funded by Coca-Cola) | Ongoing | Three projects initiated in GB, Punjab and Sindh | The activities are on track | Continue with the monitoring of the ongoing projects; inception workshops for the 2nd and 3rd Project to be held | UNDP
1.7 Support the process for strengthening the governance of Climate Change finance | Ongoing | CPEIR Report has been launched in the month of May; workplan has been finalized; TOR's have been developed and shared with the government to which GoKP and Federal Government have agreed | Delay in the receipt of funds from the regional office | Follow up with the regional office for the funds; hiring of consultants and mission from Bangkok is expected in end of July | UNDP
1.8 These funds will be used to create partnerships at the federal, provincial and regional level related to climate change management. The partnerships are envisioned to mobilize resources & foster UNDP’s relations and visibility. The fostering of relations will be with government entities with a role in climate management and research & acadimic entities as well. | Ongoing | TOR's being finalized for providing training to over 100 women journalists | The activity is on track. | Follow up with KE and local NGO | UNDP
1.9.1 Support continuation of the CFU in the GOP’s Climate Change Division as a means to leverage various funds | Ongoing | The activities are undergoing as per the workplan | The activity is on track. | Follow up with CFU on regular basis | UNDP
1.10 Assessing Climate Change impacts on national security by developing a study and engagement of stakeholders through dialogue | Ongoing | Initial meetings have been held with NDU and after inputs from their side, TORs have been developed and IC Notice generated and sent to procurement for advertising. | The activity is on track. | Follow up with NDU/Hiring of consultant | UNDP
1.11 Undertake Water Sector Climate Vulnerability Assessment of Pakistan | Ongoing | National Consultative meeting held; signing of the agreement with IISD and COMSATS underprocess with CFU | The activity is on track. | Expert Panel to be finalized | UNDP
1.12 midterm evaluation of climate change adaptation and mitigation project | Not yet started
1.13 Activity 1.13 Review and finalization of National Sustainable Development Strategy (NSDC). 1.14 Management and Administration | Not yet started
1.14 Management and Administration | Ongoing
Overall Project Progress
Project Financial Review
Fund Source | Budget ($) | Expenditure ($) | Delivery (%)
Core/TRAC 1 | 0 | 0 | 0%
Core/TRAC 2/3 (BCPR) | 490000 | 221916 | 45%
Donor ______________ | 622000 | 0 | 0%
Donor ______________ | 212000 | 0 | 0%
Total | 0 | 0 | 0%
[1] Rate each output’s and the overall project’s progress as Satisfactory, Partially Satisfactory or Inadequate based on the latest QPR and own assessment based on meetings with the project staff and stakeholders.

## QPR 1 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | RESULTS QUARTER 1 | [6 empty] | RESOURCES QUARTER 1
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q2 | AWP Budget ($) | Expenditure ($) | % Delivery
Completed, Ongoing, Delayed, Cancelled
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity
1.1.2. Activity
1.1.3. Activity
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL

## Quarter Progress Tracking Table
EXPECTED OUTPUTS | Quarter Progress - On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Status Explanation (Please be specific and concise) | PLANNED ACTIVITIES (as per AWP)
|  |  |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter | Preceding Quarter Follow-up
[9 empty] | Action(s) | Status Explanation
Project Output 1: Climate change adaptation and mitigation strategies and action plans developed and implemented.
Indicator 1.1:# of new programmes/action plans developed Baseline 1.1: Zero programmes/ action plans developed Target 1.1:06 programmes/studies will be developed | Completed | On 22nd April, a workshop was held in Gilgit and the report has been finalized and submitted. | Activity Result 1.1: The Tibetan eco-region in GB has the potential to be declared as Bio-Sphere reserve and that is being done in collaboration with MoST and UNESCO. Once the management plan is developed and approved, chances for further resource mobilization will be opened.
|  |  | Activity 1.1 UNDP Pakistan’s Climate Change Programme designed and operationalized Activity 1.1.1 : Undertake Vulnerability Mapping and Assessment in the Tibetan Eco-region of Pakistan | Weather has been the main challenge for this study | Follow up with MOST and MAB Network | UNDP |  |  | 0
|  |  | Activity 1.1.2 Organize national dissemination workshop of the report | Weather has been the main challenge for this study | Follow up with MOST and MAB Network | UNDP |  |  | 0
|  |  | Activity 1.1.3 Support the process to develop Management Plan for the Tibetan Eco- region and declare it as a Biosphere Reserve | Weather has been the main challenge for this study | Follow up with MOST and MAB Network | UNDP |  |  | 0
Indicator 1.2:# of projects and action plans implemented Baseline 1.2: Zero projects and action plans implemented Target 1.2: 05 projects shall be implemented | Ongoing | Initial meetings with all the relevant ministrues have been held and TORs have been developed, the IC notice has been advertised in order to develop the country action plan | Activity Result 1.2: The RA/GA report has been finalized and now the action plan and investment plan has to be developed. The investment plan will be shared to open partnerships and bring in resources
|  |  | Activity 1.2: Support Pakistan’s SE4ALL (Sustainable Energy for All) initiative: Activity: 1.2.1 Develop action plan & investment plan | Slow progress at the government level has been the cause of delay | Follow up with the Planning Commission on regular basis | UNDP
Activity 1.2.2 Stakeholders dialogue to promote SE4ALL at various levels through workshops, events/seminars
Indicator 1.3:% of resources mobilized required to implement newly designed programmes/projects Baseline 1.3: 0% resources mobilized for implementation of various programmes/ projects under development Target 1.3: 50% resources shall be mobilized to support various programmes/projects that will be developed. | Not yet started | Initial meeting have been held between CD UNDP and ACS KP and now baseed on the minutes of meeting that will be received in few days, we shall extract specific activities and shall start working accordingly | Activity Result 1.3: Based on the National Climate Change Policy, the institutional capacity in the province has to be enhanced through technical support in order to streamline CC into KP’s development initiatives
|  |  | Activity 1.3: Scoping the potential for mainstreaming environment and climate change into the development agenda of Khyber-Pakhtunkhwa (KP). Technical support will be provided to develop a KP specific framework for action to manage climate change in the province. | The scope of work has been revised with the govt of KP and meetings have to be scheduled with the relevant govt departments that has taken considerable time. Otherwise the activity is on track | Follow up with Chief foreign aid for the issuance of miuntes | UNDP
| Ongoing | Consultant hired, meeting held with relevant stakeholders; we shall continue with our commitments with the MOWP | Activity Result 1.4: The BRESL project left over activities (development & launching of MEPs for EE products) of 2014 that require technical support has been catered for under this activity and moreover, smooth transition of activities from BRESL to ENERCON has to be ensured to enable the manufacturers and retailers of EE products
|  |  | Activity 1.4 Developing and Launching Minimum energy performance standards (MEPS) for EE products including Refrigirator / AC etc, moreover, the market survey of EE products | The activity is on track. | Follow up with the consultants and activities with MOWP | UNDP
| Ongoing | Request for issuance of contracts submitted to procurement unit. MCG agreement with DTCE is in process. | Activity Result 1.5: To increase the access to sustainable energy in rural areas of Pakistan, while contributing to environment and social benefits through promoting clean energy production.
|  |  | 1.5 Promoting Green Energy to Mitigate Climate Change and Energy Crisis | The activity is on track. | Follow up with procurement and SMU. | UNDP
| Ongoing | Three projects initiated in GB, Punjab and Sindh | Activity Result 1.6:
|  |  | Activity 1.6: Manage “New World: Inclusive Sustainable Human Development Initiatives” project (UNDP’s global programme funded by Coca-Cola) | The activity is on track. | Continue with the monitoring of the ongoing projects; inception workshops for the 2nd and 3rd Project to be held | UNDP
| Ongoing | CPEIR Report has been launched in the month of May; workplan has been finalized; TOR's have been developed and shared with the government to which GoKP and Federal Government have agreed | Activity Result 1.7: DFID is supporting UNDP Pakistan for two and half years with a project on climate responsive budgeting and APRC is involved to support implementation of the activities with possibility of accessing more resources under this initiative
|  |  | 1.7 Support the process for strengthening the governance of Climate Change finance | Delay in the receipt of funds from the regional office | Follow up with the regional office. | UNDP
| Ongoing | TOR's being finalized for providing training to over 100 women journalists | Activity Result 1.8: These funds will be used to create partnerships at the federal, provincial and regional level related to climate change management. The partnerships are envisioned to mobilize resources & foster UNDP’s relations and visibility. The fostering of relations will be with government entities with a role in climate management and research & acadimic entities as well.
|  |  | Activity 1.8 Developing & Strengthening Partnerships and to help Pakistan meet its international obligations in Climate Change | The activity is on track. | Follow up with KE and local NGO | UNDP
| Ongoing | the activities are undergoing as per the workplan | Activity Result 1.9: The GEF Cell has now been upgraded to Climate Finance Unit (CFU) in CCD where the CFU team will ensure more resources and opportunities for CC related projects and increased involvement of UNDP in implementation.
|  |  | Activity 1.9 Strengthening of Climate Finance Unit (CFU) in the Climate Change Division Activity 1.9.1 Support continuation of the CFU in the GOP’s Climate Change Division as a means to leverage various funds | The activity is on track. | Follow up with CFU on regular basis | UNDP
| Ongoing | Initial meetings have been held with NDU and after inputs from their side, TORs have been developed and IC Notice generated and sent to procurement for advertising. | Activity Result 1.10 An emerging issue that needs to be addressed with National Defence University including other stakeholders to better address CC impacts on national security; increased chances for developing new partnerships and more resources. This is an important aspect of Climate Change
|  |  | Activity 1.10 Assessing Climate Change impacts on national security by developing a study and engagement of stakeholders through dialogue | The activity is on track. | Follow up with NDU | UNDP |  |  | 0
Indicator 2.2: Baseline 2.2: Target 2.2: |  |  | 2.2.3. Activity | [5 empty] | 0
|  |  | 3.1.1. Activity | [5 empty] | 0
Project Output 3 |  |  | 3.1.2. Activity | [5 empty] | 0
Indicator 3.1: Baseline 3.1: Target 3.1: |  |  | 3.1.3. Activity | [5 empty] | 0
|  |  | 3.2.1. Activity | [5 empty] | 0
|  |  | 3.2.2. Activity | [5 empty] | 0
Indicator 3.2: Baseline 3.2: Target 3.2: |  |  | 3.2.3. Activity | [5 empty] | 0
|  |  | 4.1.1. Activity | [5 empty] | 0
Project Output 4 |  |  | 4.1.2. Activity | [5 empty] | 0
Indicator 4.1: Baseline 4.1: Target 4.1: |  |  | 4.1.3. Activity | [5 empty] | 0
|  |  | 4.2.1. Activity | [5 empty] | 0
|  |  | 4.2.2. Activity | [5 empty] | 0
Indicator 4.2: Baseline 4.2: Target 4.3: |  |  | 4.2.3. Activity | [5 empty] | 0
| Ongoing | National Consultative meeting held; signing of the agreement with IISD and COMSATS underprocess with CFU | Activity Result 1.11 The study to assess CC impacts on Pakistan’s water sector shall open new avenues of study and attracting multiple donors for the implementation on the recommendations of the study
|  |  | Activity 1.11 Undertake Water Sector Climate Vulnerability Assessment of Pakistan | the funds have been received two weeks back and the activity is on track | expert panel to be finalized | UNDP |  |  | 0
| Not yet started |  | Activity Result 1.12
|  |  | Activity 1.12 Mid-Term evaluation of Climate Change Adaptation & Mitigation Project. |  |  | UNDP |  |  | 0
| Not yet started |  | Activity Result 1.13
|  |  | Activity 1.13 Review and finalization of National Sustainable Development Strategy (NSDC). |  |  | UNDP |  |  | 0
| Ongoing |  | Activity Result 1.13
|  |  | 1.14 Management and Administration |  |  | UNDP |  |  | 0

## field monitoring (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | QUARTERLY RESULTS
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Preceding Quarter Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter
|  |  | On Track/Achieved (0-49%), Require Monitoring/Not Achieved, Require Urgent Management Attention |  | Action(s) | Status Explanation
Indicator 1.1: Baseline 1.1: Target 1.1: Quarter 1 Target (%): | Project Output 1
Activity Result 1.1.1
| Activity 1.1.1 a |  |  |  | 0
| Activity 1.1.1 b |  |  |  | 0
| Activity 1.1.1 c |  |  |  | 0
Activity Result 1.1.2
| Activity 1.1.2 a |  |  |  | 0
| Activity 1.1.2 b |  |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: Quarter 1 Target (%): | Activity Result 1.2.1
Activity 1.2.1 a
Activity 1.2.1 b
Activity 1.2.1 c
Indicator 2.1: Baseline 2.1: Target 2.1: Quarter 1 Target (%): | Project Output 2
Activity Result 2.1.1
Activity 2.1.1 a
Activity 2.1.1 b
Activity 2.1.1 c
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  |  | 0
| 2.2.2. Activity |  |  |  | 0
| 2.2.3. Activity |  |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  |  | 0
| 3.1.2. Activity |  |  |  | 0
| 3.1.3. Activity |  |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  |  | 0
| 3.2.2. Activity |  |  |  | 0
| 3.2.3. Activity |  |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  |  | 0
| 4.1.2. Activity |  |  |  | 0
| 4.1.3. Activity |  |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  |  | 0
| 4.2.2. Activity |  |  |  | 0
| 4.2.3. Activity |  |  |  | 0

## QPR 3 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | RESULTS QUARTER 3 | [8 empty] | RESOURCES QUARTER 3
|  | Activity Status | Brief Status Explanation (Please be specific and concise) | Q2 Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q4 | AWP Budget ($) | Expenditure ($) | % Delivery
|  | Completed, Ongoing, Delayed, Cancelled |  | Action(s) | Status Explanation
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity |  |  | 0
| 1.1.2. Activity |  |  | 0
| 1.1.3. Activity |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity |  |  | 0
Baseline 1.2: | 1.2.2. Activity |  |  | 0
Target 1.2: | 1.2.3. Activity |  |  | 0
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity |  |  | 0
| 2.1.2. Activity |  |  | 0
| 2.1.3. Activity |  |  | 0
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  | 0
| 2.2.2. Activity |  |  | 0
| 2.2.3. Activity |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  | 0
| 3.1.2. Activity |  |  | 0
| 3.1.3. Activity |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  | 0
| 3.2.2. Activity |  |  | 0
| 3.2.3. Activity |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  | 0
| 4.1.2. Activity |  |  | 0
| 4.1.3. Activity |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  | 0
| 4.2.2. Activity |  |  | 0
| 4.2.3. Activity |  |  | 0
TOTAL

## Risks
Types of Risks
Environmental | Financial | Organizational | Political | Operational | Regulatory | Strategic | Other
|  | Institutional Arrangements | Government Commitment | Process Efficiency
Institutional/ Execution Capacity
Implementation arrangements

## Monthly Progress (hidden)
On Track/Achieved | 76-100%
Require Monitoring/Not Achieved | 50-75%
Require Urgent Management Attention | 0-49%
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) |  |  |  | RESULTS QUARTER 1
Activity Status Month 1/2/3
[5 empty] | Progress (Completed/OnTrack (76%-100%), Require Monitoring/Delayed/off track (50-75%), Cancelled (0-49%) | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise)
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | Activity Result 1.1.1
| Quarter 1: 20% | Quarter 2: 50% | Quarter 3: 80% | Quarter 4: 100%
| Activity: 1.1.1 a Activity: 1.1.1 b | Activity: 1.1.1 a Activity: 1.1.1 c | Activity: 1.1.1 c Activity: 1.1.1 d | Activity: 1.1.1 c Activity: 1.1.1 d Activity: 1.1.1 e
Activity Result 1.1.2
| Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 c | Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 d
Activity Result 1.1.3
| Activity: 1.1.3 a Activity: 1.1.3 b | Activity: 1.1.3 c Activity: 1.1.3 d | Activity: 1.1.3 e Activity: 1.1.3 f | Activity: 1.1.3 e Activity: 1.1.3 f
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL