## Overall Progress
Project ID | 79343
Quarter (1st, 2nd..) | Jan-June 2015
Prepared by (Project M&E Assistant) | Ms Mehtab Shaikh
Reviewed by (Acting Prog Assistant) | Mr Chatro Khatri
Approved by (National Program Manager) | Mr Masood Ahmed Lohar
Project Quality Rating
Project Output Statements | Quarter Progress Status On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Progress Assessment/Remarks | Challenges | Follow-up Actions & Due-by | Responsibility | Lesson Learnt
Improved sustainability of protected areas (PA) and biodiversity mainstreamed in landscapes and seascapes of Pakistan’s Indus Delta | Quarter Progress Status On Track/Achieved | Two meetings with Balochistan Govt officials are held and Consultanct contract also issued. Secondaly 5 NGOs issued contract for affrestation on 500acres of land |  | 2015-09-01 | SGP
Demonstration, deployment, and transfer of renewable energy and energy efficient technologies and approaches, and promote conservation and enhancement of carbon stocks | Quarter Progress Status On Track/Achieved | Consultancy contracts issued for trainings on EE products and meeting with 3 international university also done. Secondaly Resource center is also established at jamshoro |  | 2015-10-01 | SGP
Cross Cutting Capacity Development and Knowledge Management | Quarter Progress Status On Track/Achieved | Publication process is in progress for guidelines on EE products and 03 workshops already completed |  | 2015-09-01 | SGP
Overall Project Progress
Project Financial Review
Fund Source | Budget ($) | Expenditure ($) | Delivery (%)
UNOPS/TRAC | 693694 | 448270 | 64.62%
[1] Rate each output’s and the overall project’s progress as Satisfactory, Partially Satisfactory or Inadequate based on the latest QPR and own assessment based on meetings with the project staff and stakeholders.

## QPR 1 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | RESULTS QUARTER 1 | [6 empty] | RESOURCES QUARTER 1
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q2 | AWP Budget ($) | Expenditure ($) | % Delivery
Completed, Ongoing, Delayed, Cancelled
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity
1.1.2. Activity
1.1.3. Activity
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL

## Quarter Progress Tracking Table
EXPECTED OUTPUTS | Quarter Progress - On Track/Achieved, Require Monitoring/Not Achieved, Require Urgent Management Attention | Brief Status Explanation (Please be specific and concise) | PLANNED ACTIVITIES (as per AWP)
|  |  |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter | Preceding Quarter Follow-up
[9 empty] | Action(s) | Status Explanation
Project Output 1
Outcome 1 Improved sustainability of protected areas (PA) and biodiversity mainstreamed in landscapes and seascapes of Pakistan’s Indus Delta | Quarter Progress - On | Two meetings held with Baluchistan Govt and One Consultancy contract being issued | Activity Result 1.1
Indicators:
1. % METT Score improvement in four PA provides increased protection of globally significant species and habitats in Indus Delta, Baluchistan & Himalayan region. |  |  | Awareness Raising and capacity building of wildlife officials Baluchistan and Civil Society including Journalists of District of Habitat of Black Bear | 1.Lack of stakeholders engagement | 2015-09-15 | SGP |  | Organizational/ Implementation arrangements | Prepartion of Training Modules and Seesion Plans | Contract is being issued
2. # of guidelines and mechanisms for civil society engagement in community-managed PA. |  |  | Awareness Raising and capacity building of wildlife officials Hazar Ganji National Park (Kashmir) and Civil Society including Journalists of District of Habitat of Chiltan Markhor | 1.Lack of stakeholders engagement | 2015-09-15 | SGP |  | Organizational/ Implementation arrangements | Prepartion of Training Modules and Seesion Plans | Contract is being issued
3. # Of community-based initiatives for species conservation within PA. | Quarter Progress - On | Five Contracts issued to five NGOs. 100acres of afforestation is in progress | Activity Result 1.2
Baseline: ZERO |  |  | Replication of sustainable forestry/ reforestation for increasing the livelihood in 05 Riverine sites. | 1.Rehabilitation issues 2. Improper Risk Management | 2015-09-30 | SGP |  | Environmental / Natural Disasters/ Storm/Flooding | Activities are in Process (6 Months contact issued) | Project will complete in Septmber
Targets:
METT scores increase by 30%, indicating improved management of 4 Pas.
. At least 10 sets of guidelines and 10 sets of mechanisams for civil society engagement in community managed Pas.
. At least 4 by the end of project.
. 15000 ha forest and 3 rural landscapes
. Improved management for biodiversity conservation of 15000 ha of mangroves systems.
Project Output 2
Outcome 2. Demonstration, deployment, and transfer of renewable energy and energy efficient technologies and approaches, and promote conservation and enhancement of carbon stocks. | Quarter Progress - On | Consultancy contract issued for training | Activity Result 2.1
Indicators: |  |  | Training of 100 CBOs/NGOs from Pujab, KPK, Gilgit Baltistan, Sindh and Baluchistan trained to design and build low-carbon housing and use EE material | 1.Communications 2. Lack of coordination between partners | Sept/October | SGP |  | Operational/ Delivery | Preparation of training manuals are in process with the consultancy of NPM | In Progress
No of CBOs and NGOs completing training to design and build low carbon Housing using EE Materials. | Quarter Progress - On | Meeting with three international universities already done | Activity Result 2.2
No of knowledge platforms on EE Tec adoption established to share lessons learned among CBOs and CSOs. |  |  | Holding an international “ Living with Climate Change” Conference showcasing Pakistan innovations | 1. Lack of commitments form leaders | October/Nove | SGP |  | Operational/ Delivery | NPM is organizing | In Progress
No of public private NGOs able to identify properly benefits of EE products and Technologies. | Completed | Resource Center Established | Activity Result 2.3
No of homes using solar energy products as a result of grantees effort. |  |  | Establishment of “Living with Climate Change” resource center for sharing knowledge with CBOs and CSOs | 1. Lack of coordination | Completed | SGP | 1. vendor support outstanding |  | Resource Center Estabished | Completed
Baseline: ZERO | Quarter Progress - On | Consultancy contract to consultant | Activity Result 2.4
Targets: |  |  | Publications of Flyers “ How to Make” guideline book for low carbon EE Housing and Cooking | Publication delay | August | SGP |  | Operational/ Delivery | Designing of flyer is in process (Work order already issued) | In Progress
. At least 100 by the end of project with at least 20% of these to be led by women. | Quarter Progress - On | Contract issued, Work under process at Mohenjo daro site(Larkana) | Activity Result 2.5
. At least 1 knowledge platform on EE technology adoption establish to share lessons learned among SBOs and CSOs |  |  | 100,000 people in three urban areas with the reduced municipal waste from increased bio compositing | 1.Improper risk management. 2. Natural Calamities | Sept/October | SGP |  | Operational/ Delivery | Contruction work already in progress (Contract issued) | In Progress
. At least 50 by the end of project 20% of this target no of NGOs to be led by women
. At least 7000 solar products by the end of project
At least 2500 EE Stoves by the end of project.
. 138000 tC over 10 years or 506460 tCO 2 a
Project Output 3
Outcome 3. Cross Cutting Capacity Development and Knowledge Management. | Quarter Progress On | Publication is process | Activity Result 3.1
Indicators: Sub output 1:No of new grants that replicate consolidated approaches (BD/CC) by the year 4. |  |  | Guidelines and best practice notes and business models developed and demonstrated | 1. Lack of technical support | August | SGP |  | Operational/ Delivery | Guidelines are being prepared based on SGP findings | In Progress
Percent increase an amount of co-funding for Pakistan SGP by year 3.
No of Governors who launch community based partnership SGP by year 4.
Sub output 2. No of SGP grantees participating in Monitoring and Evaluation Training, Percent increase in knowledge before and after training. | Quarter Progress On | Contract issued | Activity Result 3.2
Baseline: ZERO |  |  | Common Marketing and branding mechanism for SGP supported initiatives in Pakistan | 1. Communication 2. Lack of proper marketing | August | SGP |  | Operational/ Delivery | Contract issued to Consultant | In Progress
Targets:
Consolidated approaches (BD/CC) replicated in at least 30 new grants by end of yr. .
50% increase in amount of co-funding for Pakistan SGP by year 3
At least 2 governors launch community based partnership SGP initiatives yr 4. | Quarter Progress On/Completed | 3 Tarining Workshops already completed | Activity Result 3.3
Improvement of 30% in level of knowledge on fundamentals of monitoring and evaluatin |  |  | Training on Identification and tracking of indicators and participatory monitoring | 1. Lack of commitments from partners | Completed | SGP | Consultants hired for trainings |  |  | Completed
At least 80 Community groups/grantees participating in the training.

## field monitoring (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | Identify SP/IRRF Output Indicator(s) | QUARTERLY RESULTS
|  |  | Activity Status | Brief Status Explanation (Please be specific and concise) | Preceding Quarter Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Next Quarter
|  |  | On Track/Achieved (0-49%), Require Monitoring/Not Achieved, Require Urgent Management Attention |  | Action(s) | Status Explanation
Indicator 1.1: Baseline 1.1: Target 1.1: Quarter 1 Target (%): | Project Output 1
Activity Result 1.1.1
| Activity 1.1.1 a |  |  |  | 0
| Activity 1.1.1 b |  |  |  | 0
| Activity 1.1.1 c |  |  |  | 0
Activity Result 1.1.2
| Activity 1.1.2 a |  |  |  | 0
| Activity 1.1.2 b |  |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: Quarter 1 Target (%): | Activity Result 1.2.1
Activity 1.2.1 a
Activity 1.2.1 b
Activity 1.2.1 c
Indicator 2.1: Baseline 2.1: Target 2.1: Quarter 1 Target (%): | Project Output 2
Activity Result 2.1.1
Activity 2.1.1 a
Activity 2.1.1 b
Activity 2.1.1 c
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  |  | 0
| 2.2.2. Activity |  |  |  | 0
| 2.2.3. Activity |  |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  |  | 0
| 3.1.2. Activity |  |  |  | 0
| 3.1.3. Activity |  |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  |  | 0
| 3.2.2. Activity |  |  |  | 0
| 3.2.3. Activity |  |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  |  | 0
| 4.1.2. Activity |  |  |  | 0
| 4.1.3. Activity |  |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  |  | 0
| 4.2.2. Activity |  |  |  | 0
| 4.2.3. Activity |  |  |  | 0

## QPR 3 (hidden)
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) | RESULTS QUARTER 3 | [8 empty] | RESOURCES QUARTER 3
|  | Activity Status | Brief Status Explanation (Please be specific and concise) | Q2 Follow-up |  | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise) | Anticipated Risks for Q4 | AWP Budget ($) | Expenditure ($) | % Delivery
|  | Completed, Ongoing, Delayed, Cancelled |  | Action(s) | Status Explanation
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | 1.1.1. Activity |  |  | 0
| 1.1.2. Activity |  |  | 0
| 1.1.3. Activity |  |  | 0
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity |  |  | 0
Baseline 1.2: | 1.2.2. Activity |  |  | 0
Target 1.2: | 1.2.3. Activity |  |  | 0
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity |  |  | 0
| 2.1.2. Activity |  |  | 0
| 2.1.3. Activity |  |  | 0
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity |  |  | 0
| 2.2.2. Activity |  |  | 0
| 2.2.3. Activity |  |  | 0
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity |  |  | 0
| 3.1.2. Activity |  |  | 0
| 3.1.3. Activity |  |  | 0
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity |  |  | 0
| 3.2.2. Activity |  |  | 0
| 3.2.3. Activity |  |  | 0
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity |  |  | 0
| 4.1.2. Activity |  |  | 0
| 4.1.3. Activity |  |  | 0
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity |  |  | 0
| 4.2.2. Activity |  |  | 0
| 4.2.3. Activity |  |  | 0
TOTAL

## Risks
Types of Risks
Environmental | Financial | Organizational | Political | Operational | Regulatory | Strategic | Other
Natural Disasters: storms, flooding, earthquakes | EXTERNAL economic factors: interest rates, exchange rate fluctuation, inflation | Institutional Arrangements | Corruption | Complex Design (size: larger/multi-country project; technical complexity; innovativeness, multiple funding sources) | New unexpected regulations, policies | Partnerships failing to deliver | Other risks that do not fit in an of the other categories
Pollution incidents | INTERNAL: | Institutional/ Execution Capacity | Government Commitment | Project Management | Critical policies or legislation fails to pass or progress in the legislative process | Strategic Vision, Planning and Communication | Might refer to socioeconomic factors such as: population pressures; encroachment – illegal invasions; poaching/illegal hunting or fishing
Social and Cultural | Co-financing difficulties | Implementation arrangements | Political Will | Human Error/Incompetence |  | Leadership and Management
Security/Safety | Use of financing mechanisms | Country Office Capacity (specific elements limiting CO capacity) | Political Instability | Infrastructure Failure |  | Programme Alignment
Economic | Funding (Financial Resources) | Governance | Change in Government | Safety being compromised |  | Competition
| Reserve Adequacy | Culture, Code of Conduct and Ethics | Armed Conflict and Instability | Poor monitoring and evaluation |  | Stakeholder Relations
| Currency | Accountability and Compensation | Adverse Public opinion/media intervention | Delivery |  | Reputation
| Receivables | Succession Planning and Talent Management |  | Programme Management |  | UN Coordination
| Accounting/Financial Reporting | Human resources Processes and Procedures |  | Process Efficiency |  | UN Reform
| Budget Allocation and Management |  |  | Internal Controls
| Cash Management/Reconciliation |  |  | Internal and External Fraud
| Pricing/Cost Recovery |  |  | Compliance and Legal
Procurement
Technology
Physical Assets

## Monthly Progress (hidden)
On Track/Achieved | 76-100%
Require Monitoring/Not Achieved | 50-75%
Require Urgent Management Attention | 0-49%
EXPECTED OUTPUTS | PLANNED ACTIVITIES (as per AWP) |  |  |  | RESULTS QUARTER 1
Activity Status Month 1/2/3
[5 empty] | Progress (Completed/OnTrack (76%-100%), Require Monitoring/Delayed/off track (50-75%), Cancelled (0-49%) | Brief Status Explanation (Please be specific and concise) | Challenges (Please be specific and concise) | Follow-up Action(s) & Due Date | Responsibility | Lesson(s) Learnt (Please be specific and concise)
Project Output 1
Indicator 1.1: Baseline 1.1: Target 1.1: | Activity Result 1.1.1
| Quarter 1: 20% | Quarter 2: 50% | Quarter 3: 80% | Quarter 4: 100%
| Activity: 1.1.1 a Activity: 1.1.1 b | Activity: 1.1.1 a Activity: 1.1.1 c | Activity: 1.1.1 c Activity: 1.1.1 d | Activity: 1.1.1 c Activity: 1.1.1 d Activity: 1.1.1 e
Activity Result 1.1.2
| Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 c | Activity: 1.1.2 a Activity: 1.1.2 b | Activity: 1.1.2 a Activity: 1.1.2 b Activity: 1.1.2 d
Activity Result 1.1.3
| Activity: 1.1.3 a Activity: 1.1.3 b | Activity: 1.1.3 c Activity: 1.1.3 d | Activity: 1.1.3 e Activity: 1.1.3 f | Activity: 1.1.3 e Activity: 1.1.3 f
Indicator 1.2: Baseline 1.2: Target 1.2: | 1.2.1. Activity
Baseline 1.2: | 1.2.2. Activity
Target 1.2: | 1.2.3. Activity
Project Output 2
Indicator 2.1: Baseline 2.1: Target 2.1: | 2.1.1. Activity
2.1.2. Activity
2.1.3. Activity
Indicator 2.2: Baseline 2.2: Target 2.2: | 2.2.1. Activity
2.2.2. Activity
2.2.3. Activity
Project Output 3
Indicator 3.1: Baseline 3.1: Target 3.1: | 3.1.1. Activity
3.1.2. Activity
3.1.3. Activity
Indicator 3.2: Baseline 3.2: Target 3.2: | 3.2.1. Activity
3.2.2. Activity
3.2.3. Activity
Project Output 4
Indicator 4.1: Baseline 4.1: Target 4.1: | 4.1.1. Activity
4.1.2. Activity
4.1.3. Activity
Indicator 4.2: Baseline 4.2: Target 4.3: | 4.2.1. Activity
4.2.2. Activity
4.2.3. Activity
TOTAL