##### Annual Work Plan 2014 as part of the CCPAP

United Nations Development Programme

Pakistan

| Project Title: Policy Support Programme |  |
| --- | --- |
| OP/Country Programme Outcome: Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships |  |
| Expected Output(s): 2.1.1) : Planning and finance institutions and women’s departments at federal and provincial levels are enabled to develop comprehensive development strategies, with a focus on MDGs acceleration, inclusive growth, gender equality and women’s empowerment |  |
| Implementing Partner: UNDP |  |
| Responsible Parties: UNDP, Planning and Development Departments, Planning Commission, |  |

Brief Description

Policy Support Programme (PSP) operationlizes UNDP’s support to evidence based public policy formulation  and advocacy as detailed in UNDP Common Country Programme Action Plan 2013-17. PSP is an implementation arm of the newly established Development Policy Unit at UNDP Pakistan. PSP has four main outputs: 1) Exchange of learning and solutions on selected themes promoted: Under this output, PSP will facilitate the exchange of knowledge and experiences on key development issues. This will include the establishment of at least two communities of practice on selected themes. 2) Research undertaken and knowledge generated: The project will support research on selected themes and produce knowledge products including policy papers on inequality, report on Multi-dimensional Poverty Indices etc. 3) Cross practice project development support: This would include support for the preparation of a long term project with the Planning Commission of Pakistan in support for the implementation of Vision 2025 and implementation of MDG Acceleration Framework. 4) Supporting advocacy around MDGs and poverty: PSP will advocate for policy reforms for improved results based monitoring, evaluation and policy discourse through workshops, dialogues and roundtable discussions. PSP will be implemented through the Direct Implementation (DIM) modality of UNDP.

Programme Period: 2013-2017

Atlas Award ID:  00074907

Atlas Project ID:  00087069

Start date:	01 September 2013

End Date	31 December 2017

PAC Meeting Date:

Project Board Meeting Date:

2014 AWP budget:		USD 950,000

Total resources required           	_________

Total allocated resources:		_________

- Regular			$ 750,000

- Other:

  - Donor		_________

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		$ 200,000

In-kind Contributions

Agreed by [Implementing Partner - NPD]:

Agreed by UNDP (CD / DCD-P):

# Annual Work Plan 2014

Project ID:_00087069_________	Project Title: _Policy Support Programme___

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Exchange of learning and solutions on selected themes promoted Indicator: - Number of Communities of Practice (CoP)on selected themes established and extent to which CoPs have been made effective - Extent to which best practices related to human development effectively informed policies / interventions in Pakistan Baseline: - No significant existence of online community of practice in Pakistan - No systematic and focused initiatives for south-south learning influencing national policies Targets: - 2 on line communities of practice revived/established - At least two policy papers - At least one international / regional best practice on poverty reduction or social protection or MDGs shared with partners in Pakistan - At least on national workshop / social good summit - One regional workshop on evaluation Related CP outcome: Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships | Activity Result 1: Establishing communities of practice on selected themes - Establishing online platforms for communities of practice - Training facilitators for communities of practice - Arranging online and face to face dialogues / consultations on selected themes Activity Result 2: South –South exchange of learning - Online exchange of international best practices / learning on innovative development models - Exposure visits, national and regional / international to best practices - Organizing a social good summit on MDGs at the national level |  | X | X | X | UNDP | UNDP | Consultancies, travel, and, staff salaries, Misc | 50,000 |
| Output 2: Research undertaken and knowledge generated /disseminated on selected development theme Indicator: - Number of policy papers on MDGs based on research / evidence based analysis - National Human Development Report (NHDR) - Number of district level MDG localization plans - Number of workshops? Baseline: - Lack of reporting on assessments and robust research undertaken specially on MDGs.. The latest National Human Development Report was compiled and published in 2002. - Limited knowledge and information on localization of MDGs at District level Target: - At least four research studies (including one study on horizontal inequality in Pakistan) designed and conducted resulting in four (or more?) Policy papers (including one on the issues and constraints affecting institutional effectiveness) on selected MDGs. - Updated and regionally comparable multi-dimensional poverty figures available - At least four district level localization plans available - Online dashboard on MDGs refined and expanded Related CP outcome: Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships | Activity Result 1: Undertaking research on selected themes - Developing partnerships with academic institutions - Establishing roster of experts - Floating requests for proposals - Organizing discussion forums / dialogues - Papers finalization, printing and dissemination Activity Result 2: Initiating the process of preparing National Human Development Report on youth - Selection of lead consultant - Initial consultations to finalize different sub-themes / the content for the NHDR - Hiring team / establishing infrastructure for the preparation of NHDR - Establishing an advisory committee for the NHDR - Primary research on selected sub-themes Activity Result 3: Refining online dashboard on MDGs - Exploring options to use Dev info for the online dashboard - Data cleaning and updating Activity Result 4: MDGs localization at the district level - Identification of districts - Developing partnership protocols - Undertaking desk review and consultations to develop district specific targets for MDGs - Developing and rolling out of district MDG plans Activity Result 5: Conducting study on the horizontal inequalities in Pakistan and discussion paper on institutional effectiveness - Data gathering and analysis - Report preparation - Printing and dissemination of the report - Policy dialogues on the study Activity Result 6: Working paper prepared on the institutional constraints with regard to the availability, accessibility and reliability of data on social issues in Pakistan - Discussion paper, Dialogues / roundtables on the issues related to social sector data availability, accessibility and reliability and seek recommendations for improvement |  | X | X |  | UNDP | UNDP | Micro-capital Grant, Travel, Personnel & Professional services | 100,000 |
|  |  | X | X | X | X | UNDP UNDP | UNDP TBC |  | 200,000 150,000 |
| Output 3: Cross practice project development support provided to other units of UNDP Indicators: - Mechanism established to facilitate cross-practice project development - Extent to which the cross-units project(s) support have been effective Baseline: - No institutional mechanism for cross practice project development support available Target: - Support to the governance unit through an established mechanism for developing project with the planning commission of Pakistan - Preparation of MDG Acceleration Framework Related CP outcome: Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships | Activity Result 1: Preparation of multi-donor project with the Planning Commission of Pakistan in support to the roll out of Vision 2025 and 11th Five Year Plan - Interim support, human resources to the Ministry of Planning, Development and Reforms with regard to Vision 2025/ Institutional reforms - TOR preparation for the project formulation mission - Mobilizing experts from the UNDP regional centre - Organizing consultations - Supporting the drafting of the project strategy document | X | X | X |  | UNDP | TBC | Travel, Personnel & Professional services | 50,000 |
|  | Activity Result 2: MDG Acceleration Frameworks (MAF) launched and advocacy support provided - Provincial stakeholders workshops - Background papers / reviews - Donors / stakeholders’ consultations - Roll out, dissemination and advocacy - Develop project to support MDG Acceleration Framework (MAF) | X | X | X |  | UNDP | UNDP | Travel, Personnel & Professional services | 50,000 |
| Output 4: Advocacy undertaken to influence government resource allocation policies and poverty measurement methodologies Indicator: - Establishing Multi-dimensional Poverty Indexes (MPIs) at the district level - Extent to which Development Advocate Pakistan / Multi-dimensional Poverty Index (or any other magazine) effectively influence government resource allocation policies Baseline: Limited information / analysis on key social indicators available at the sub-national level to inform policy formulation Target: - A comprehensive research undertaken and findings in the form, of report on MPIs in Pakistan prepared - At least three issues of the Development Advocate Magazine - An indication / progress towards government policies being impacted by MPIs / any other policy paper Related CP outcome: Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships | Activity Result 1: Preparing a report on MPI in Pakistan - Data gathering, analysis and compilation - Training for technical staff on calculating MPI - Report launch and dissemination Activity Result 2: Preparation and launching of Development Advocate Pakistan magazine - Selecting theme for each issue of the magazine - Writing articles - Preparing, printing and launching the magazine | X | X | X | X | UNDP | UNDP | Travel, Personnel & Professional services | 100,000 |
| Staff cost |  |  |  |  |  |  |  | Personnel Cost | 140,000 |
| Direct Project Costing (DPC) |  |  |  |  |  |  |  | Personnel Cost | 110,000 |

| TOTAL |  |  |  |  |  |  |  |  | 950,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# II. Monitoring Plan 2014

(Include all monitoring and evaluation activities/events

Project ID: _00087069_________	Project Title: _Policy Support Programme___

| Expected Results (Outcomes & Outputs) | Indicators | Baseline | Targets | Data Collection Plan |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source/Method of Collection | Schedule/ Frequency | Responsible Staff | Resources ($) | Risks and Assumptions |
| Obtained from the CPAP and project Results Frameworks) | Obtained from the CPAP and project Results Frameworks) | At the project start date | At the project end date | Specific publication, evaluation, survey, field observation, interviews, etc | Monthly, quarterly, annually, etc | Staff member responsible for collecting and reporting data | Estimated cost of collecting and reporting data | Any risks or assumptions concerning data collection |
| CPAP Outcome: 2.1) Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships | Number of evidence-based policy reforms that promote exclusive economic growth |  |  |  |  |  |  |  |
| CPAP Output: 2.1.1) : Planning and finance institutions and women’s departments at federal and provincial levels are enabled to develop comprehensive development strategies, with a focus on MDGs acceleration, inclusive growth, gender equality and women’s empowerment | Number of evidence-based policies and strategies formulated and implementation supported with federal and provincial governments; | Government’s Economic Growth Framework highlights policy and capacity gaps that limit the achievement of inclusive growth and MDGs; | Provincial growth strategies developed for each province; result-based management introduced in the Planning Commission and other line departments |  |  |  |  |  |
| Project Output 1: Exchange of learning and solutions on selected themes promoted | - Number of communities of practice on selected themes established and functional - Number of policy papers based on the feedback gathered through such communities of practice - Number of best practices related to human development informing policies / interventions in Pakistan - Number of national workshops on MDGs / related themes | - No online community of practice exists in Pakistan - No systematic and focused initiatives for south-south learning | 1.1.communities of practice established 1.2. At least two policy papers 1.3. At least one international / regional best practice on poverty reduction or social protection or MDGs shared with partners in Pakistan 1.4. At least on national workshop / social good summit - One regional workshop on evaluation | Project reports, Proceedings of the meetings, Publications, Workshop observation notes, documentation on best practices | Bi-annually | Project Manager | 100,000 | - Unavailability of data on thematic best practices. - Availability of required expertise |
| Project Output 2: Research undertaken and knowledge generated on selected development themes | - Number of policy papers on MDGs - Progress on the preparation of National Human Development Report (NHDR) - Number of district level MDG localization plans | 2013 MDGs Report 2002 National Human Development Report No robust research / policy papers on MDGs exist Limited knowledge and information on localization of MDGs - Prototype of online dashboard on MDGs Study on horizontal inequality in Pakistan | - At least four policy papers on selected MDGs - At least four district level localization plans available - Updated and regionally comparable multi-dimensional poverty figures available - Online dashboard on MDGs refined and expanded - One study on horizontal inequality in Pakistan - One discussion paper on the issues and constraints affecting institutional effectiveness | - Proceedings of virtual communities of practice. - Minutes of the meetings from the forum for preparation of NHDR. - Notes from the proceeding of consultation with the stakeholders for developing district level MDG localize plans | Bi-annually | Project Manager |  | - Buy-in of the government officials. - Availability of required expertise and sufficient time allocation required to map the international knowledge with the localized context. - Availability of the baseline data |
| Project Output 3: Cross practice project development support provided to other units of UNDP | - Number of strategy documents / project documents | No institutional mechanism for cross practice project development support available | - Support to the governance unit for developing projects with the planning commission of Pakistan - Preparation of MDG Acceleration Framework | Cross-functional team meeting notes, Technical Working Group meeting notes and discussions, Consultative workshop report, observation notes | Bi-annually | Project Manager |  | - Resources mobilization for the new project developed |
| Project Output 4: Advocacy undertaken to influence government resource allocation policies and poverty measurement methodologies | -Establishing Multi-dimensional Poverty Indexes (MPIs) at the district level - Preparation and launch of the Development Advocate Pakistan magazine | Limited information / analysis on key social indicators available at the sub-national level to inform policy formulation | - A comprehensive report on MPIs in Pakistan prepared - At least three issues of the Development Advocate Magazine | Surveys, Data from Bureau of Statistics, Development Advocate Magazine | Bi-annually | Project Manager |  | - Availability of district / UC level baseline data - Capacity to influence government resource allocation policies |

# II. Recruitment Plan Year (YYYY)

Project Name: Policy Support Programme						Recruitment Plan No:

Project Number: 									Recruitment Plan Revision N:

| NO | Post Title | Contractual Modality | Duty Station | Number of Posts | Category (National/ International) | Level of Post | Recruitment Process | Duration |  | Total budget availability based on Proforma Cost ( USD ) | Responsible party (UNDP/IP/ EAD/PMU, etc) | Focal point |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | TA/FTA/SC/NIM/Govt |  |  |  |  |  | Start date | End date |  |  |  |
| 1 | Project Manager | SC | Islamabad | 01 | National | SB 5/2 |  | March2014 | Feb. 2015 |  | UNDP | Shakeel Ahmad |
| 2 | Editor / content Analyst | SC | Islamabad | 01 | National | SB 3/2 |  | March2014 | Feb. 2015 |  | UNDP | Shakeel Ahmad |
| 3 | Admin and Finance Assistant | SC | Islamabad | 01 | National | SB 3/1 |  | March2014 | Feb. 2015 |  | UNDP | Shakeel Ahmad |
| 4 | Driver | SC | Islamabad | 01 | National | SB 1 |  | March2014 | Feb. 2015 |  | UNDP | Shakeel Ahmad |
| 5 | Graphic Designer | SC | Islamabad | 01 | National | SB3/2 |  | March2014 | Feb. 2015 |  | UNDP | Shakeel Ahmad |
| 6 | Provincial Human Development Officer | SC | KP, Punjab, Balochistan, Sindh | 04 | National | SB4/2 |  | 15 Feb 14 | 15 Jan 15 |  |  |  |

# II. Procurement Plan Year (2014)

Project Name: Policy Support Programme						Procurement Plan No:

Project Number: 87069								Procurement Plan Revision N:

| S.No | Description | Type of Supply (Goods, Services, Works) | Est. Contract Amount (USD) | Responsible party | Focal point | Issue of Expression of Interest (EOI) /Notification |  |  |  |  |  | Evaluation of Proposals |  |  | Committee Review/Approval |  |  |  | Contract Issuance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Date | Notice Period (days) | UNDP Web | IAPSO* | Local Paper | IP website | Single Stage | Two stage | Two stage with Combined Weights | CAP Members receive submission | CAP Meeting Date | Submission to ACP | ACP`s /CPO s approval | Start date | End date | Remarks |
| 1 | LOAs with National Universities | Services |  | UNDP | Shakeel Ahmad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | LOA with government institutions | Services |  | UNDP | Shakeel Ahmad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Micro capital grants agreements with Think-Tanks | Services |  | UNDP | Shakeel Ahmad |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

*Inter agency procurement support office

# IV. Management Arrangements

Explain the roles and responsibilities of the parties involved in managing the project.

Please refer to the Project Document – Deliverable Description to complete this component of the template.

Use the diagram below for the composition of the Project Board.

Project Manager

Project Board

Planning Commission / Planning Departments (Senior Beneficiary)

Planning Commission (Executive)

UNDP (Senior Supplier)

Policy Analyst (Project Assurance)

(by Board members or delegated to other individuals)

Admin and Finance Assistant

Project Organisation Structure

Human Development Officers (4 – one in each province)

Assistant Country Director

Young Professional Officer

01 Driver

Graphic Designer (1)

Editor (1)

Harmonised Approach to Cash Transfers

All cash transfers to an Implementing Partner are based on the Annual Work Plans agreed between the Implementing Partner and UNDP. Cash transfers for activities detailed in AWPs can be made by UNDP using the following modalities:

- Cash transferred directly to the Implementing Partner:

  - Prior to the start of activities (direct cash transfer), or

  - After activities have been completed (reimbursement);

- Direct payment to vendors or third parties for obligations incurred by the Implementing Partners on the basis of requests signed by the designated official of the Implementing Partner;

- Direct payments to vendors or third parties for obligations incurred by UNDP in support of activities agreed with Implementing Partners.

Direct cash transfers shall be requested and released for programme implementation periods not exceeding three months. Reimbursements of previously authorized expenditures shall be requested and released quarterly or after the completion of activities. The UNDP shall not be obligated to reimburse expenditure made by the Implementing Partner over and above the authorized amounts.

Following the completion of any activity, the Implementing Partner shall refund any balance of funds to UNDP, unless agreed otherwise by mutual agreement between the Implementing Partner and UNDP.

Cash transfer modalities, the size of disbursements, and the scope and frequency of assurance activities may depend on the findings of a review of the public financial management capacity in the case of a Government Implementing Partner, and of an assessment of the financial management capacity of the non-UN Implementing Partner. A qualified consultant, such as a public accounting firm, selected by UNDP may conduct such an assessment, in which the Implementing Partner shall participate.

Cash transfer modalities, the size of disbursements, and the scope and frequency of assurance activities may be revised in the course of programme implementation based on the findings of programme monitoring, expenditure monitoring and reporting, and audits.

Audit and Oversight

Implementing partners agree to cooperate with UNDP for monitoring all activities supported by cash transfers and will facilitate access to relevant financial records and personnel responsible for the administration of cash provided by the UNDP. To that effect, Implementing partners agree to the following:

- Periodic on-site reviews and spot checks of their financial records by UNDP or its representatives,

- Programmatic monitoring of activities following UNDP’s standards and guidance for site visits and field monitoring,

- Special or scheduled audits. UNDP, in collaboration with other UN agencies (where so desired: and in consultation with the [coordinating Ministry]) will establish an annual audit plan, giving priority to audits of Implementing Partners with large amounts of cash assistance provided by UNDP, and those whose financial management capacity needs strengthening.

The audits will be commissioned by UNDP and undertaken by private audit services. Assessments and audits of non-government Implementing Partners will be conducted in accordance with the policies and procedures of UNDP.

# V. Monitoring Framework And Evaluation

Please refer to the Project Document – Deliverable Description to complete this component of the template.

Suggested text to be adapted to project context

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted (see annex 1), a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- a project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project

- a Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

Annually

- Annual Review Report. An Annual Review Report shall be prepared by the Project Manager and shared with the Project Board and the Outcome Board. As minimum requirement, the Annual Review Report shall consist of the Atlas standard format for the QPR covering the whole year with updated information for each above element of the QPR as well as a summary of results achieved against pre-defined annual targets at the output level.

- Annual Project Review. Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Quality Management for Project Activity Results

| OUTPUT 1: : Exchange of learning and solutions on selected themes promoted |  |  |  |
| --- | --- | --- | --- |
| Activity Result 1 (Atlas Activity ID) Short title to be used for Atlas Activity ID | Knowledge management and outreach |  | Start Date: Jan 2014 End Date: Dec 2014 |
| Purpose What is the purpose of the activity? | To facilitate south-south learning and exchange of knowledge |  |  |
| Description Planned actions to produce the activity result. | Two main actions are planned under this activity. One, online communities of practice will be established on development themes to be decided in consultation with the government counterparts. Two, different events and if needed, visits to innovative regional / international best practices on different development issues will be organized. |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Number of persons involved in the exchange of ideas / knowledge |  | Project reports | End of the year |
| OUTPUT 2: Research undertaken and knowledge generated on selected development themes |  |  |  |
| Activity Result 2 (Atlas Activity ID) | Policy research and advocacy |  | Start Date: Jan. 2014 End Date: Dec 2014 |
| Purpose | Undertake research on selected themes and produced knowledge products including policy papers |  |  |
| Description | This activity will help produce different research studies and reports on poverty, MDGs and related themes. This will be done through partnership with different academic institutions and think-tanks in addition to some of reports / policy papers to be produced in-house. The main actions include partnership building with different partners, creating roster of experts and arranging different debates and dissemination events |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Policy debates and discussions triggered and informed by the various reports / studies produced under this output |  | Study reports, project progress reports, newspapers articles | End of the year |
| Output 3: : Cross practice project development support provided to other units of UNDP |  |  |  |
| Activity Result 3 (Atlas Activity ID) |  | Support to MDGs | Start Date: Jan 2014 End Date: Dec 2014 |
| Purpose |  | Providing support to the other units of UNDP in developing projects on selected themes / issues |  |
| Description |  | Support for the development of two projects will be provided. 1) Preparing a multi-donor project with the Planning Commission of Pakistan 2) Developing MDG Acceleration Framework Action Plans at the provincial level |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| The development of project strategy documents which agreed by the government counterparts |  | Meeting minutes, availability of project strategy documents | End of the year |
| Output 4: : Advocacy undertaken to influence government resource allocation policies and poverty measurement methodologies |  |  |  |
| Activity Result 4 (Atlas Activity ID) |  | Policy advocacy | Start Date: Jan 2014 End Date: Dec 2014 |
| Purpose |  | To inform and influence public policy discourse in favour of MDGs and human development |  |
| Description |  | To address inequalities in terms of government resource allocations, national and sub-national level Multi-dimensional Poverty Indexes will be prepared. This will be followed by advocacy with the federal and provincial governments to use these indexes for allocation of funds to different provinces and districts. |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| The use of MPIs, as reference point, for policy formulation and resource distribution |  | Availability of MPI report | End of the year |

# vi. Legal Context

UNDP as the Implementing Partner shall comply with the policies, procedures and practices of the United Nations safety and security management system.

UNDP agrees to undertake all reasonable efforts to ensure that none of the project funds/ [UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

ANNEXES

Risk Analysis: An assessment of risks that may affect the project should be conducted during the formulation. Please refer to the section “Defining a Project”.

Use the standard Risk Log template

Please refer to the Deliverable Description of the Risk Log for instructions

Agreements: Any additional agreements, such as cost sharing agreements, project cooperation agreements signed with NGOs (where the NGO is designated as the “executing entity”) should be attached.

Terms of Reference: TOR for key project personnel attached.

OFFLINE RISK LOG

(see Deliverable Description for the Risk Log regarding its purpose and use)

| Project Title: Policy Support Programme |  |  |  |  |  | Award ID: |  |  | Date: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response |  | Owner | Submitted, updated by |  | Last Update | Status |
| 1 | GoP’s focus on development issues continues, no significant crisis hits the country – which could divert GoP’s focus from development to humanitarian / recovery efforts | No specific date, | Natural / external | P = 3 I = 4 | The project work plan will be revised to accommodate a few key policy interventions related to crisis on need basis |  | Project Manager |  |  |  | no change |
| 2 | Availability of resources/project budget – especially for long term support beyond 2014 | Sep 2013 | Financial-X | P = 2 I = 5 | Rigorous and strategic resource mobilization campaign and relationship building. |  |  |  |  |  | No change |
| 3 | Publication of contentious data related to gender equality, poverty etc. | Sep 2013 | Political-X Strategic-X | Ownership of Government for reports such as NMDG, and NHDR is critical. If the GoP doesn’t own the statistics produced by the consultants, publication of such reports is delayed and jeopardized. P = 2 I = 4 | Close coordination and consultation with the GoP officials at each step of the process. |  |  |  |  |  | Resolved. The 2013 MDG report included poverty figures and information on district inequalities |
| 4 | Timely availability of key staff / experts for different assignments | August 2013 | Staffing | P=3 I=4 | Partnerships with academia / think-tanks to fill in any capacity gaps |  | Project Manager |  |  | 22 August 2013 | No change |

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner.

For GEF projects, the agreement with any NGO pre-selected to be the main contractor should include the rationale for having pre-selected that NGO.