##### Annual Work Plan 2015

United Nations Development Programme

Pakistan

| Project Title: Policy Support Programme |  |
| --- | --- |
| UNDP Strategic Plan Outcome 7: Development debates and actions at all levels prioritizes poverty, inequality and exclusion, consistence with our engagement principal OP/Country Programme Outcome: Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships |  |
| CPAP Expected Output(s): 2.1.1) : Planning and finance institutions and women’s departments at federal and provincial levels are enabled to develop comprehensive development strategies, with a focus on MDGs acceleration, inclusive growth, gender equality and women’s empowerment |  |
| Implementing Partner: UNDP |  |
| Responsible Parties: UNDP, Planning & Development Departments, Planning Commission, District Governments |  |

Brief Description

Policy Support Programme (PSP) operationalizes UNDP’s support to evidence based public policy formulation and advocacy as detailed in UNDP Common Country Programme Action Plan 2013-17. PSP is an implementation arm of the Development Policy Unit at UNDP Pakistan. The programme aims to influence Public Policy to address the vertical and horizontal forms of inequalities. It has four main outputs: Output 1: Effective support provided for development planning and monitoring of results for enhanced accountability; Output 2: Advocacy and innovation through knowledge generation and sharing on the key development issues; Output 3: Cross practice support across other thematic areas; Output 4:  Support to the globally agreed development agenda. PSP will advocate for policy reforms for improved results based monitoring, evaluation and policy discourse through workshops, dialogues and roundtable discussions. Through this programme UNDP will continue to coordination and provision of technical support for the preparation of MDG country monitoring reports and collaboration with partners on policy advocacy, while promoting a strong response to national MDG priorities; it will also target to
foster ownership for effective roll out and implementation of SDGs.

Programme Period: 2013-2017

Atlas Award ID:  00074907

Atlas Project ID:  00087069

Start date:	01 September 2013

End Date	31 December 2017

PAC Meeting Date: 18 September 2013

Project Board Meeting Date:

2015 AWP budget:		$1,000,000/-

Total resources required           	$1,000,000/-

Total allocated resources:	_________

- Regular			$400,000/-

- Other:

  - DRT-F		$600,000/-

  - Donor		_________

  - Donor		_________

  - Government	_________

Unfunded budget:		$ _0______

In-kind Contributions

Agreed by UNDP (CD / DCD-P):

# Annual Work Plan 2015

Project ID: _00087069_________	Project Title: _Policy Support Programme___

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Effective support provided for development planning and monitoring of results for enhanced accountability. Indicator: 1.1 Extent to which effective mechanisms are put in place for planning and monitoring of development results in selected government institutions 1.2.Extent to which Multi-dimensional Poverty Index effectively influence government resource allocation policies 1.3. Study/ report prepared. Baseline: 1.1.No concrete systems for institutional performance and progress monitoring in the public sector 1.2. Limited information / analysis on key social indicators available at the sub-national level to inform policy formulation 1.3. Lack of consistent and reliable data Targets: 1.1. KPI developed at least for one district and technical capacity developed 1.2. An indication / progress towards government policies being impacted by MPIs / any other policy paper 1.2.3. study/ report compiled with recommendation for he issues related to data | Activity Result 1.1: KPIs developed for performance management and results monitoring in one district piloted. - Scoping undertaken to identify sources of data and information on development indicators in the selected district for pilot demonstration - identify the key/priority MDG / development targets - based on above, KPIs developed - Study on devolution focusing role of Planning Commission in the context of 18 Amendment - Partnership with the UNDP global centre for excellence in public administration for a regional study on public administration | x | x | x | x | District Government (Narowal) | UNDP | Travel, Professional services, Individual Consultancy | 30,000 |
|  | Activity Result 1.2: Report on MPI finalized and disseminated. - Calculation and analysis of sub-national Multidimensional Poverty estimates - Research studies conducted - Support participatory budgetary process for public finance including PFCs, NFCs using MPI - Discussion paper, Dialogues / roundtables on the issues related to social sector data availability, accessibility and reliability and seek recommendations for improvement |  |  |  |  | UNDP | UNDP | Travel, Professional services/ consultancy | 30,000 |
| Output 2: Enhanced advocacy and innovation through knowledge generation and sharing on key development issues Indicator: 2.1. Extent to which Development Advocate Pakistan inform and influence debates on selected development issues 2.2. Extent to which national and sub-national youth policies / programmes are informed and benefited by UNDP’s led analysis and recommendations on youth issues 2.3. Extent to which evidence based analysis and best practices on human development inform public policies / UNDP programming in Pakistan Baseline: 2.1. Limited information / analysis on key social indicators available at the sub-national level to inform policy formulation 2.2. Last National Human Development Report published in 2003 2.3. Limited space / platforms for policy debates among diverse experts and stakeholders Target: 2.1. At least three issues of the Development Advocate Magazine developed and disseminated 2.2. National Human Development Report 2015 finalized 2.3. Advisory committee on Inclusive Human development established and functional | Activity Result 2.1: Preparation and launching of Development Advocate Pakistan magazine - Selecting theme for each issue of the magazine and identifying key contributors/ experts - Writing articles/ opinion pieces - Preparing, printing and launching the magazine - Partnerships established/ strengthened for development solutions | X | X | X | X | UNDP | UNDP | Travel, Professional services/ consultancy | 60,000 |
|  | Activity Result 2.2: National Human Development Report on “Youth” prepared. - Completion of series of consultation events in Baluchistan and Sindh - Development of 3 videos of consultation activities and audio-visual (including jingle) products developed to highlight youth issues - Youth ‘Hopes and Fears’ Survey launched, completed and analysed - Development of YDI (Youth Development Index) - Development of info-motion of survey data and key findings - Second and third stages of youth competitions launched - Final drafts of ten background papers on youth topics delivered - Finalization of the draft State of Youth background report with input/ feedback from the key stakeholders | x | x | x | x | UNDP | DRT-F | Travel, Professional services/ consultancy | 330,000 |
|  | Activity Result 2.3: Communities of Practice on Inclusive Human Development - Setting up an Advisory Committee (AC) on “inclusive human development - Finalizing the TORs and composition of the AC |  | X | X |  | UNDP | UNDP | Micro-capital Grant, Travel, Personnel & Professional services | 20,000 |
| Output 3: Cross practice support across other thematic areas Indicators: - Extent to which the cross-units project(s) support have been effective - Extent to which progress toward targeted MDG accelerated. accelerated Baseline: - No institutional mechanism for cross practice project development support available - MAF Action plan endorsed Target: - At least one new programme developed - Coordination and oversight secretariat for MDG Acceleration Framework developed and functional | Activity Result 3.1: MAF Secretariat established for coordination, follow up and support MAF Action plan - Develop the structure / mechanism for the secretariat - Partnerships developed with national and global initiatives for resource mobilization (The Gordon Brown (GB) initiative; MGD Achievement fund) - Study to understand key enablers and gaps impacting governance of education in a high performing district of Punjab |  |  |  |  |  |  |  | Subject to availability of funds |
|  |  | x | x | x | x | UNDP | UNDP | Travel, Personnel & Professional services |  |
| Output 4: Support to the globally agreed development agenda Indicators: - Extent to which SDGs aligned with national/ sub-national plans Baseline: - UNDP’s support to the Planning Commission of Pakistan for MDG Reports 2006 - UNDP’s mandate as to monitor MDGs Target: 4.1 Two round of national consultations on post 2015 agenda / SDGs and implementation framework developed | Activity Result 4.1: Dialogues to foster ownership, improved planning structures and multi-stakeholder partnerships to support its delivery. - Inclusive consultation on SDGs undertaken for adoption at national and sub-national level | X | X | X |  | UNDP | UNDP | Travel, Personnel & Professional services | 10,000 |
| Output 5: Project Management | Staff cost- Communication and Advocacy Manager Editor / content Analyst Research Analyst (03) Admin and Finance Assistant Graphic Designer Provincial Human Development Officer (01) YPO (01) | x | x | x | x |  | UNDP DRT-F | Personnel Cost | 90,000 135,000 |
|  | Direct Project Costing (DPC) |  |  |  |  |  | UNDP DRT-F | Personnel Cost | 110,000 70,000 |
|  | Rent |  |  |  |  | UNDP | UNDP DRT-F | Office rent (premises) | 35,000 45,000 |

| TOTAL |  |  |  |  |  |  |  |  | 1,000,000 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1% Fund Management Fee on DRT-F |  |  |  |  |  |  |  |  | 6,000 |
| ISS DRT-F |  |  |  |  |  |  |  |  | 14,000 |
| ISS TRAC |  |  |  |  |  |  |  |  | 15,000 |
| TOTAL |  |  |  |  |  |  |  |  | 1,000,000 |

# II. Monitoring Plan 2015

(Include all monitoring and evaluation activities/events

Project ID: _00087069_________	Project Title: _Policy Support Programme___

| Expected Results (Outcomes & Outputs) | Indicators | Baseline | Targets | Data Collection Plan |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source/Method of Collection | Schedule/ Frequency | Responsible Staff | Resources ($) | Risks and Assumptions |
| Obtained from the CPAP and project Results Frameworks) | Obtained from the CPAP and project Results Frameworks) | At the project start date | At the project end date | Specific publication, evaluation, survey, field observation, interviews, etc. | Monthly, quarterly, annually, etc. | Staff member responsible for collecting and reporting data | Estimated cost of collecting and reporting data | Any risks or assumptions concerning data collection |
| CPAP Outcome: CPAP Outcome: 2.1) Creation of employment opportunities and decent work through industry, construction, services, vocational/skills training, agricultural and cultural development, as well as promoting youth employment and public-private partnerships | Number of evidence-based policy reforms that promote exclusive economic growth |  |  |  |  |  |  |  |
| CPAP Output: CPAP Output: 2.1.1) : Planning and finance institutions and women’s departments at federal and provincial levels are enabled to develop comprehensive development strategies, with a focus on MDGs acceleration, inclusive growth, gender equality and women’s empowerment | Number of evidence-based policies and strategies formulated and implementation supported with federal and provincial governments; |  |  |  |  |  |  |  |
| Project Output 1: Effective support provided for development planning and monitoring of results for enhanced accountability. | 1.1 Extent to which effective mechanisms are put in place for planning and monitoring of development results in selected government institutions | 1.1.No concrete systems for institutional performance and progress monitoring in the public sector | 1.1. KPI and online dashboard developed at least for one district and technical capacity developed |  |  |  |  |  |
|  | 1.2.Extent to which Multi-dimensional Poverty Index effectively influence government resource allocation policies |  | 1.2. An indication / progress towards government policies being impacted by MPIs / any other policy paper |  |  |  |  |  |
|  | 1.3. Study/ report prepared. | 1.2. Limited information / analysis on key social indicators available at the sub-national level to inform policy formulation | 1.3. study/ report compiled with recommendation for he issues related to data |  |  |  |  |  |
| Project Output 2: Enhanced advocacy and innovation through knowledge generation and sharing on key development issues | 2.1. Extent to which Development Advocate Pakistan inform and influence debates on selected development issues | 2.1. Limited information / analysis on key social indicators available at the sub-national level to inform policy formulation | 2.1. At least three issues of the Development Advocate Magazine developed and disseminated |  |  |  |  |  |
|  | 2.2. Extent to which national and sub-national youth policies / programmes are informed and benefited by UNDP’s led analysis and recommendations on youth issues | 2.2. Last National Human Development Report published in 2003 | 2.2. National Human Development Report 2015 finalized |  |  |  |  |  |
|  | 2.3. Extent to which evidence based analysis and best practices on human development inform public policies / UNDP programming in Pakistan | 2.3. Limited space / platforms for policy debates among diverse experts and stakeholders | 2.3. Advisory committee on Inclusive Human development established and functional |  |  |  |  |  |
| Project Output 3: Cross practice support across other thematic areas | - Extent to which the cross-units project(s) support have been effective | - No institutional mechanism for cross practice project development support available | - At least one new programme developed |  |  |  |  |  |
|  | - Extent to which progress toward targeted MDG accelerated. accelerated | - MAF Action plan endorsed | - Coordination and oversight secretariat for MDG Acceleration Framework developed and functional |  |  |  |  |  |
| Project Output 4: Support to the globally agreed development agenda | - MDG country reports are one of the best instruments for obtaining nationally generated MDG based evidence and extracting main challenges and opportunities. | - UNDP’s support to the Planning Commission of Pakistan for MDG Reports 2006 | 4.1. 2015 (final) National MDG Report launched |  |  |  |  |  |
|  | 4.2. Extent to which SDGs aligned with national/ sub-national plans | - UNDP’s mandate as to monitor MDGs | 4.2 Two round of national consultations on post 2015 agenda / SDGs and implementation framework developed |  |  |  |  |  |

# II. Recruitment Plan Year (2015)

Project Name: Policy Support Programme						Recruitment Plan No:

Project Number: 00087069								Recruitment Plan Revision N:

| NO | Post Title | Contractual Modality | Duty Station | Number of Posts | Category (National/ International) | Level of Post | Recruitment Process | Duration |  | Total budget availability based on Proforma Cost ( USD ) | Responsible party (UNDP/IP/ EAD/PMU, etc) | Focal point |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | TA/FTA/SC/NIM/Govt. |  |  |  |  |  | Start date | End date |  |  |  |
| 1 | Research Analyst | SC | Islamabad | 02 | National | SB-4/1 | DIM | 01 January 2015 | 31 December 2015 |  |  |  |
| 2 | Communications and Advocacy Manager | SC | Islamabad | 01 | National | SB-5/1 | DIM | 01 January 2015 | 31 December 2015 |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |

# II. Procurement Plan Year (2015)

Project Name: Policy Support Programme						Procurement Plan No:

Project Number: 87069								Procurement Plan Revision N:

| S.No | Description | Type of Supply (Goods, Services, Works) | Est. Contract Amount (USD) | Responsible party | Focal point | Issue of Expression of Interest (EOI) /Notification |  |  |  |  |  | Evaluation of Proposals |  |  | Committee Review/Approval |  |  |  | Contract Issuance |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Date | Notice Period (days) | UNDP Web | IAPSO* | Local Paper | IP website | Single Stage | Two stage | Two stage with Combined Weights | CAP Members receive submission | CAP Meeting Date | Submission to ACP | ACP`s /CPO s approval | Start date | End date | Remarks |
| 1 | IC for study on Devolution | Services | 20,000 | UNDP | Policy Specialist | 15 January 2015 | 02 weeks | Yes | No | No | No | No | Yes | No | No | Not required | Not required | No | 01 April 2015 | 01 July 2015 |  |
| 2 | IC Results-based Management | Services | 15,000 | UNDP | Policy Specialist | 15 February 2015 | 02 weeks | Yes | No | No | No | No | Yes | No | No | Not required | Not required | No | 01 April 2015 | 01 July 2015 |  |
| 3 | Contract for Professional Services for DAP | Services | 10,000 | UNDP | Policy Specialist | 01 March 2015 | 02 weeks | Yes | No | Yes | No | No | Yes | No | No | Not required | Not required | No | 01 April 2015 | 01 June 2015 |  |
| 4 | IC Advisory Committee on Inclusive Human Development (Pro bono) | Services | 0 | UNDP | Policy Specialist | 01 February 2015 |  |  | No | No | No | No | No | No | No | Not required | Not required | No | 01 February 2015 | 31 December 2015 |  |
| 5 | IC Coordinator MAF Secretariat | Services | 20,000 | UNDP | Policy Specialist | 01 February 2015 | 02 weeks | Yes | No | No | No | No | Yes | No | No | Not required | Not required | No |  |  |  |
| 6 | Contract for professional services for Post 2015 advocacy | Services | 5000 | UNDP | Policy Specialist | 01 March 2015 | 02 weeks | Yes | No | No | No | No | Yes | No | No | Not required | Not required | No |  |  |  |
| 7 | IC for study on public sector performance management | Services | 15,000/- |  |  |  |  |  |  | No |  |  |  |  |  |  |  |  |  |  |  |

*Inter agency procurement support office

# IV. Management Arrangements

Explain the roles and responsibilities of the parties involved in managing the project.

Please refer to the Project Document – Deliverable Description to complete this component of the template.

Use the diagram below for the composition of the Project Board.

Harmonised Approach to Cash Transfers

All cash transfers to an Implementing Partner are based on the Annual Work Plans agreed between the Implementing Partner and UNDP. Cash transfers for activities detailed in AWPs can be made by UNDP using the following modalities:

- Cash transferred directly to the Implementing Partner:

  - Prior to the start of activities (direct cash transfer), or

  - After activities have been completed (reimbursement);

- Direct payment to vendors or third parties for obligations incurred by the Implementing Partners on the basis of requests signed by the designated official of the Implementing Partner;

- Direct payments to vendors or third parties for obligations incurred by UNDP in support of activities agreed with Implementing Partners.

Direct cash transfers shall be requested and released for programme implementation periods not exceeding three months. Reimbursements of previously authorized expenditures shall be requested and released quarterly or after the completion of activities. The UNDP shall not be obligated to reimburse expenditure made by the Implementing Partner over and above the authorized amounts.

Following the completion of any activity, the Implementing Partner shall refund any balance of funds to UNDP, unless agreed otherwise by mutual agreement between the Implementing Partner and UNDP.

Cash transfer modalities, the size of disbursements, and the scope and frequency of assurance activities may depend on the findings of a review of the public financial management capacity in the case of a Government Implementing Partner, and of an assessment of the financial management capacity of the non-UN Implementing Partner. A qualified consultant, such as a public accounting firm, selected by UNDP may conduct such an assessment, in which the Implementing Partner shall participate.

Cash transfer modalities, the size of disbursements, and the scope and frequency of assurance activities may be revised in the course of programme implementation based on the findings of programme monitoring, expenditure monitoring and reporting, and audits.

Audit and Oversight

Implementing partners agree to cooperate with UNDP for monitoring all activities supported by cash transfers and will facilitate access to relevant financial records and personnel responsible for the administration of cash provided by the UNDP. To that effect, Implementing partners agree to the following:

- Periodic on-site reviews and spot checks of their financial records by UNDP or its representatives,

- Programmatic monitoring of activities following UNDP’s standards and guidance for site visits and field monitoring,

- Special or scheduled audits. UNDP, in collaboration with other UN agencies (where so desired: and in consultation with the [coordinating Ministry]) will establish an annual audit plan, giving priority to audits of Implementing Partners with large amounts of cash assistance provided by UNDP, and those whose financial management capacity needs strengthening.

The audits will be commissioned by UNDP and undertaken by private audit services. Assessments and audits of non-government Implementing Partners will be conducted in accordance with the policies and procedures of UNDP.

# V. Monitoring Framework And Evaluation

Please refer to the Project Document – Deliverable Description to complete this component of the template.

Suggested text to be adapted to project context

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted (see annex 1), a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- a project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project

- a Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

Annually

- Annual Review Report. An Annual Review Report shall be prepared by the Project Manager and shared with the Project Board and the Outcome Board. As minimum requirement, the Annual Review Report shall consist of the Atlas standard format for the QPR covering the whole year with updated information for each above element of the QPR as well as a summary of results achieved against pre-defined annual targets at the output level.

- Annual Project Review. Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Quality Management for Project Activity Results

| Output 1: Effective support provided for development planning and monitoring of results for enhanced accountability. |  |  |  |
| --- | --- | --- | --- |
| Activity Result 1 (Atlas Activity ID) Short title to be used for Atlas Activity ID | Online dashboard on performance management and results monitoring in one district piloted. |  | Start Date: 01 January 2015 End Date: 31 December 2015 |
| Purpose What is the purpose of the activity? | Mechanisms put in place for planning and monitoring of development results for public sector service delivery. |  |  |
| Description Planned actions to produce the activity result. | - Scoping undertaken to identify sources of data and information on development indicators in the selected district for pilot demonstration - identify the key/priority MDG / development targets - based on above, KPIs developed and online dashboard operational - Study on devolution focusing role of Planning Commission in the context of 18 Amendment Partnership with the UNDP global centre for excellence in public administration for a regional study on public administration |  |  |
| Quality Criteria How/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Online dashboard used efficiently for delivery and monitoring of results. |  | Project reports | End of the year |
| OUTPUT 2: Enhanced advocacy and innovation through knowledge generation and sharing on key development issues |  |  |  |
| Activity Result 2 (Atlas Activity ID) | Report on MPI finalized and disseminated. |  | Start Date: 01 January 2015 End Date: 31 December 2015 |
| Purpose |  |  |  |
| Description | - Calculation and analysis of sub-national Multidimensional Poverty estimates - Research studies conducted Support participatory budgetary process for public finance including PFCs, NFCs using MPI |  |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Policy debates and discussions triggered and informed by the various reports / studies produced under this output |  | Study reports, project progress reports, newspapers articles | End of the year |
| Output 3: : Cross practice support across other thematic areas |  |  |  |
| Activity Result 4 (Atlas Activity ID) |  | Policy advocacy | Start Date: 01 January 2015 End Date: 31 December 2015 |
| Purpose |  | To inform and influence public policy discourse in favour of MDGs and human development |  |
| Description |  | To address inequalities in terms of government resource allocations, national and sub-national level Multi-dimensional Poverty Indexes will be prepared. This will be followed by advocacy with the federal and provincial governments to use these indexes for allocation of funds to different provinces and districts. |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| Output 4: : Support to the globally agreed development agenda |  | Availability of MPI report | End of the year |
| Activity Result 3 (Atlas Activity ID) |  | Support to MDGs | Start Date: 01 January 2015 End Date: 31 December 2015 |
| Purpose |  | Providing support to the other units of UNDP in developing projects on selected themes / issues |  |
| Description |  | Support for the development of two projects will be provided. 1) Preparing a multi-donor project with the Planning Commission of Pakistan 2) Developing MDG Acceleration Framework Action Plans at the provincial level |  |
| Quality Criteria how/with what indicators the quality of the activity result will be measured? |  | Quality Method Means of verification. What method will be used to determine if quality criteria has been met? | Date of Assessment When will the assessment of quality be performed? |
| The development of project strategy documents which agreed by the government counterparts |  | Meeting minutes, availability of project strategy documents | End of the year |

# vi. Legal Context

UNDP as the Implementing Partner shall comply with the policies, procedures and practices of the United Nations safety and security management system.

UNDP agrees to undertake all reasonable efforts to ensure that none of the project funds/ [UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/sc/committees/1267/aq_sanctions_list.shtml.  This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document.

ANNEXES

Risk Analysis: An assessment of risks that may affect the project should be conducted during the formulation. Please refer to the section “Defining a Project”.

Use the standard Risk Log template

Please refer to the Deliverable Description of the Risk Log for instructions

Agreements: Any additional agreements, such as cost sharing agreements, project cooperation agreements signed with NGOs (where the NGO is designated as the “executing entity”) should be attached.

Terms of Reference: TOR for key project personnel attached.

OFFLINE RISK LOG

(see Deliverable Description for the Risk Log regarding its purpose and use)

| Project Title: Policy Support Programme |  |  |  |  |  | Award ID: |  |  | Date: |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response |  | Owner | Submitted, updated by |  | Last Update | Status |
| 1 | GoP’s focus on development issues continues, no significant crisis hits the country – which could divert GoP’s focus from development to humanitarian / recovery efforts | No specific date, | Natural / external | P = 3 I = 4 | The project work plan will be revised to accommodate a few key policy interventions related to crisis on need basis |  | Project Manager |  |  |  | no change |
| 2 | Availability of resources/project budget – especially for long term support beyond 2014 | Sep 2013 | Financial-X | P = 2 I = 5 | Rigorous and strategic resource mobilization campaign and relationship building. |  |  |  |  |  | No change |
| 3 | Publication of contentious data related to gender equality, poverty etc. | Sep 2013 | Political-X Strategic-X | Ownership of Government for reports such as NMDG, and NHDR is critical. If the GoP doesn’t own the statistics produced by the consultants, publication of such reports is delayed and jeopardized. P = 2 I = 4 | Close coordination and consultation with the GoP officials at each step of the process. |  |  |  |  |  | Resolved. The 2013 MDG report included poverty figures and information on district inequalities |
| 4 | Timely availability of key staff / experts for different assignments | August 2013 | Staffing | P=3 I=4 | Partnerships with academia / think-tanks to fill in any capacity gaps |  | Project Manager |  |  | 22 August 2013 | No change |

To be used where UNDP is the Implementing Partner

To be used where the UN, a UN fund/programme or a specialized agency is the Implementing Partner.

For GEF projects, the agreement with any NGO pre-selected to be the main contractor should include the rationale for having pre-selected that NGO.