## Procurement Plan
FCPF PROCUREMENT PLAN FOR THE YEAR 2019
Procurement Activity No | Requisition Docs Ready | Description Activities | Project No./Award No. | Focal Point (Program Manager) | Type of Supply (Goods, Services, Works) | Est. Contract Amount (USD) | Solicitation Method | [5 empty] | Solicitation Document | [5 empty] | Evaluation of Proposals |  | Committee Review/Approval |  |  | Contract Issuance | [7 empty] | Remarks
| Date | [5 empty] | UNDP PNG Website | PSO (Procurement) Website | LTA | Local Paper | Pratice Network/ Roster/ E-mail sent directly to vendors | Others | Issue Date | Deadline for Receipt | Duration | RFQ | RFP / Procurement Notice | ITB | Lowest Price | Cummulative | CAP Approval Required | RR Aproval / Procurement Officer | ACP/CPO Approval | Date of Issue | PO | Inst. Contr. | Civil Works | Profes. Serv. | IC / RLA | Other | Status
FCPF REDD+ Readiness Project (Phase II)
| 2019-02-13 | Planning Retreat for Climate Change and Development Authority (CCDA) | 106398 | Mirzo Isoev | Services | 15000 | X | X |  |  |  |  | 2019-02-13 | 2019-02-27 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-02-22 | Amendment to Consultancy Services to Support the Review of Papua New Guinea’s (PNG’s) Forestry Act | 106398 | Mirzo Isoev | Services | 75000 | X | X |  |  | X |  | 2019-02-08 | 2019-02-22 | 14 |  | X |  |  | X | X |  |  | 2017-02-13 | X |  |  |  | X |  | Initiated
| 2019-02-22 | International Team Leader to develop Papua New Guinea’s National REDD+ Finance & Investment Plan and REDD+ Funding Proposal | 106398 | Mirzo Isoev | Services | 68400 | X | X |  |  |  |  | 2018-11-22 | 2018-12-06 | 14 |  | X |  |  | X | X | [9 empty] | completed
| 2019-02-22 | National Environmental Finance Expert to develop Papua New Guinea’s National REDD+ Finance & Investment Plan and REDD+ Funding Proposal | 106398 | Mirzo Isoev | Services | 25000 | X | X |  |  |  |  | 2018-11-22 | 2018-12-06 | 14 |  | X |  |  | X | [10 empty] | ongoing
| 2019-02-25 | Contracting International Consultant to support REDD+ Communications | 106398 | Mirzo Isoev | Services | 55000 | X | X |  |  |  |  | 2019-02-08 | 2019-02-22 | 14 |  | X |  |  | X | [10 empty] | Initiated
| 2019-02-25 | Amendment to consultancy services to support the review of PNG's National Sustainable Land Use Policy | 106398 | Mirzo Isoev | Services | 40000 | X | X |  |  |  |  | 2019-02-08 | 2019-02-22 | 14 |  | X |  |  | X | [10 empty] | Initiated
| 2019-02-27 | Stakeholders Consultation Workshop on the review of Climate Change (Management) Act | 106398 | Mirzo Isoev | Services | 5000 | X | X |  |  |  |  | 2019-02-27 | 2019-03-13 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-03-29 | Development and Support of PNG Palm Oil Platform | 106398 | Mirzo Isoev | Services | 60000 | X | X |  |  |  |  | 2019-04-03 | 2019-04-17 | 14 |  | X |  |  | X | [10 empty] | planned
| 2019-04-25 | Development of Safeguards Informaton System in PNG | 106398 | Mirzo Isoev | Services | 70000 | X | X |  |  |  |  | 2019-05-08 | 2019-05-22 | 14 |  | X |  |  | X | [10 empty] | planned
| 2019-04-25 | Stakeholders Consultation Workshop on the development of RFIP | 106398 | Mirzo Isoev | Services | 5000 | X | X |  |  |  |  | 2019-04-25 | 2019-05-09 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-04-18 | Regional Consultation on the review of Forestry Act (Region 1) | 106398 | Mirzo Isoev | Services | 15000 | X | X |  |  |  |  | 2019-04-18 | 2019-05-02 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-05-23 | Regional Consultation on the review of Climate Change Management Act | 106398 | Mirzo Isoev | Services | 15000 | X | X |  |  |  |  | 2019-05-23 | 2019-06-06 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-05-23 | Regional Consultation on the review of Forestry Act (Region 2) | 106398 | Mirzo Isoev | Services | 15000 | X | X |  |  |  |  | 2019-05-23 | 2019-06-06 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-06-20 | Stakeholders' Capacity Building Workshop on Safeguards | 106398 | Mirzo Isoev | Services | 5000 | X | X |  |  |  |  | 2019-06-20 | 2019-07-04 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-07-03 | National Validation Workshop on the Climate Change Management Act | 106398 | Mirzo Isoev | Services | 5000 | X | X |  |  |  |  | 2019-07-03 | 2019-07-17 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-09-12 | REDD+ Expert Capacity Building Training | 106398 | Mirzo Isoev | Services | 15000 | X | X |  |  |  |  | 2019-09-12 | 2019-09-26 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-10-02 | Regional Consultation on the review of National Sustainable Land Use Policy (All 4 Regions) | 106398 | Mirzo Isoev | Services | 40000 | X | X |  |  |  |  | 2019-10-02 | 2019-10-16 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-11-06 | National Validation Workshop on the Forestry Act | 106398 | Mirzo Isoev | Services | 5000 | X | X |  |  |  |  | 2019-11-06 | 2019-11-20 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-11-06 | National Validation Workshop on the National Sustainable Land Use Policy | 106398 | Mirzo Isoev | Services | 5000 | X | X |  |  |  |  | 2019-11-06 | 2019-11-20 | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-04-24 | FCPF PMU Partition at CCDA Office, Savannah Heights | 106398 | Mirzo Isoev | Services | 10000 | [8 empty] | 14 | X |  |  |  | X | [10 empty] | planned
| 2019-04-24 | Cost Extension of CLP contract | 106398 | Mirzo Isoev | Services | 65000 | [8 empty] | 14 |  |  |  |  | x | [10 empty] | planned
| 2019-04-24 | Production of a Climate Change Documentary | 106398 | Mirzo Isoev | Services | 30000 | [8 empty] | 14 |  |  |  |  | x | [10 empty] | planned
| 2019-04-24 | Development of Provincial Forest Plans in East New Britain and Madang Provinces | 106398 | Mirzo Isoev | Services | 30000 | [8 empty] | 14 |  |  |  |  | x | [10 empty] | planned
| 2019-04-24 | Cost Extension of IC for Phil Cowling | 106398 | Mirzo Isoev | Services | 12000 | [8 empty] | 14 |  |  |  |  | x | [10 empty] | planned
|  |  |  | Total Value |  | 670400

## Break up
Description of Activity | Flights | Venue Hire | Accom | Vehicle hire | DSA | Est. Contract Amount (USD) | Int. I/C | Nat. I/C
Planning Retreat for Climate Change and Development Authority (CCDA) |  | 1000 | 10000 | 1000 | 3000 | 15000
Amendment to Consultancy Services to Support the Review of Papua New Guinea’s (PNG’s) Forestry Act | [5 empty] | 75000 | 75000
International Team Leader to develop Papua New Guinea’s National REDD+ Finance & Investment Plan and REDD+ Funding Proposal | [5 empty] | 68400 | 68400
National Environmental Finance Expert to develop Papua New Guinea’s National REDD+ Finance & Investment Plan and REDD+ Funding Proposal | [5 empty] | 25000 |  | 25000
Contracting International Consultant to support REDD+ Communications | [5 empty] | 55000 | 55000
Amendment to consultancy services to support the review of PNG's National Sustainable Land Use Policy | [5 empty] | 40000 | 40000
Stakeholders Consultation Workshop on the review of Climate Change (Management) Act | 1000 | 2000 | 1000 |  | 1000 | 5000
Development and Support of PNG Palm Oil Platform | 13000 | 20000 | 10000 | 2000 | 15000 | 60000
Development of Safeguards Informaton System in PNG | [5 empty] | 70000 | 70000
Stakeholders Consultation Workshop on the development of RFIP | 1000 | 2000 | 1000 |  | 1000 | 5000
Regional Consultation on the review of Forestry Act (Region 1) | 5000 | 3000 | 4000 |  | 3000 | 15000
Regional Consultation on the review of Climate Change Management Act | 5000 | 3000 | 4000 |  | 3000 | 15000
Regional Consultation on the review of Forestry Act (Region 2) | 5000 | 3000 | 4000 |  | 3000 | 15000
Stakeholders' Capacity Building Workshop on Safeguards | 1000 | 2000 | 1000 |  | 1000 | 5000
National Validation Workshop on the Climate Change Management Act | 1000 | 2000 | 1000 |  | 1000 | 5000
REDD+ Expert Capacity Building Training | 3000 | 3000 | 4000 | 2000 | 3000 | 15000
Regional Consultation on the review of National Sustainable Land Use Policy (All 4 Regions) | 10000 | 10000 | 10000 |  | 10000 | 40000
National Validation Workshop on the Forestry Act | 1000 | 2000 | 1000 |  | 1000 | 5000
National Validation Workshop on the National Sustainable Land Use Policy | 1000 | 2000 | 1000 |  | 1000 | 5000
| 47000 | 55000 | 52000 | 5000 | 46000 | 538400 | 308400 | 25000
Summary | Activity1 | Activity 2
Travels | 44000 | 3000
Workshops, venue hire, accommodation, DSA | 129000 | 24000
Vehicle hire | 2000 | 3000
International IC | 55000 | 253400
National IC | 25000