DPR Korea

Terminal Tripartite Review Report

Project ID & Title: #00050817, award #00043495; SRED – Sustainable Rural Energy Development in DPRK Duration: July 2010 to October 2014 Total Initial Project Budget: US$ 5,650,000 Spent prior to resumption: US$ 768,294.15 Source of Funds: UNDP/TRAC Budget after resumption: US$ 5,035,596 Source of Funds: UNDP/TRAC Government cost-sharing: None Government (in-kind): None Other donors cost-sharing: None Expenditures in 2011: US$ 836,825.95 Expenditures in 2012: US$ 1,544,772.83 Expenditures in 2013: US$ 1,183,251.03 Budget in 2014: US$ 1,001,050.00 Implementing Partners/Responsible parties: UNDP Direct Implementation Country Programme Outcome: Strengthened enabling environment for use of conventional energy, and accessibility of alternative energy sources, and strategies in adaptation and mitigation to climate change

TABLE OF CONTENT

A.	OVERALL REMARKS	3

B.	PROJECT IMPLEMENTATION, PROJECT MANAGEMENT, MONITORING AND EVALUATION	3

C.	EVALUATION OF PROJECT ACTIVITIES	9

D.	LESSONS LEARNED	10

E.	BUDGET INFORMATION	10

F.	OVERALL CONCLUSION AND RECOMMENDATIONS	11

G.	ANNEXES	13

Annex 1. SRED Monitoring and Evaluation Framework	13

Annex 2. Study Tours and International Trainings under SRED Programme	14

Annex 3. In-Country Trainings under SRED Project	16

Annex 4. Impact of RE and EE Technologies on human life	19

Annex 5. Assets List	20

Annex 6. Annual Work Plan	25

Annex 7. Expected Delivery until end of October 2014	30

# OVERALL REMARKS

UNDP’s efforts in energy for sustainable development support the Millennium Summit objective of reducing by half the proportion of people living in poverty by 2015. None of the agreed-upon Millennium Development Goals (MDGs) can be achieved without major increases in energy services in developing countries.

The Sustainable Rural Energy Development Programme in DPRK, a UNDP Direct Implementation project (DIM), has contributed to the living standard of grassroots communities, under the close cooperation of National Coordination Committee (NCC) and several DPRK government organization such as Ministry of Electric Power Industry (MEPI), the State Academy of Sciences (SAOS), and State Commission for Science and Technology (SCST).

The work from January 2011 until October 2014 was done under close coordination with Ms. Hong Jong Hui, SRED National Project Director. The Project Manager kept the UNDP CO informed about project status and progress through regular information sharing with the assigned Programme Specialist and through periodic briefings to the Senior Management. The project was monitored by Mr. Martin Krause, Team Leader Environment and Energy, UNDP Asia-Pacific Regional Centre, Bangkok on 4 May 2011. The Project Manager consulted with Mr. Mathias Hölzer, International Expert for Technical Backstopping of the SRED Project Implementation and worked closely with Remi Rijs, International Consultant on SRED. The Inception workshop, PSC and TTPR meetings and some site visits were attended by key national partners and NCC. On 18-19 October 2014, one of the project sites of SRED – Mopung CoF was visited by Mr. Haoliang Xu, UNDP Regional Director together with Mr. Rim Yong Chol, Chief of Division of NCC and Mr. Pak Kyong Chol, NCC Coordinator for UNDP.

# PROJECT IMPLEMENTATION, PROJECT MANAGEMENT, MONITORING AND EVALUATION

OUTPUT 1: IDENTIFICATION OF PROVINCES AND COOPERATIVE FARMS FOR PILOT DEMONSTRATION OF RURAL ENERGY PROJECTS

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Compilation of rural energy consumption & supply, socio-economic, environmental data and assessment (for civil and engineering works and equipment specifications) reports for four counties completed by Month 2 of the first year. | In 2010 during the project inception phase, the SRED Programme has conducted preliminary pilot rural energy consumption surveys, assessment and planning studies in three counties representing three different types of rural energy situations that can be found in the DPRK (in terms of the dominant energy source being used, particularly by the household sector): Yaksu CoF of Kangso County in South Pyongan Province, Myongchon CoF in Jangyon County in South Hwanghae Province, Pobdong County in Kangwon Province. Later a separate preliminary rural energy survey was also done by the DPRK State Academy of Science in Ryudong Cooperative Farm of Unsan County in South Pyongan Province. Therefore, Pobdong County in Kangwon Province was replaced by Mopung CoF of Anbyon County in the same Kangwon Province. An energy survey and assessment was conducted in this new site between February-May 2011. The target was achieved in 2011 (see also Stocktaking report, page 11) |

OUTPUT 2: IMPLEMENTATION OF RURAL ENERGY DEMONSTRATION PROJECTS.

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Feasibility studies (applicability and adaptability of specific technology choices for SRED and potential follow-ups) of each technology application for rural energy services demonstration projects conducted by Month 6 of the first year. | In 2011, the Full Advantage Ltd Consultancy Company was selected to conduct the Feasibility Study and three missions (1st mission from 23 - 28 May 2011, 2nd mission from 19-24 June 2011 and 3rd mission from 10-13 July 2011) were executed to assess the feasibility of the original portfolio including evaluation of the engineering design, assessing the technical feasibility and financial viability of the renewable technology application demonstration projects such as small hydropower plants, gasifier systems, solar thermal systems, PV systems, biogas systems, biomass direct combustion systems and high-efficient coal combustion. All projects were carefully assessed for prioritization and selection based on the following criteria: (i) technical merits (quality, efficiency); (ii) environmental merits, (iii) operation and maintenance feasibility and (iv) replicability. In addition budget availability, project timeframe, technology mix, financial sustainability and ownership arrangements have been considered and taken into account for the final selection of demonstration projects. The Feasibility Study was completed by 10 February 2012. All bidding documents, technical and final reports were provided. The first 12 Priority Renewable Energy Technologies (RETs) demonstration projects out of 20 selected according to the above criteria with a total cost of $1,371,046 in addition to $310,130 for (Kangso Mine) were implemented in 2012 (See also Stocktaking report, page 11). |
| Optimal energy and technology mix for the target counties and farm cooperatives identified and appraised by Month 3 of second year. | Approximate projects list and budget breakdown allocation by sites was more carefully calculated and reported after consultation with UNDP CO, NPD and NTC and it was finalized on 17 June 2011 after consultation with Mr. Martin Krause, APRC Energy and Environment Practice Leader. The technical specifications of the equipment, instrumentation and other components that will be used in each demonstration project were submitted by Mr. Baba Mustafa Marong, Senior UNDP M&E Advisor to Mr. Selva Ramachandran and Mr. Tanni Mukhopadhyay on 26 September 2011 for further submission to BDP to ensure the CO involves BDP in reviewing and commenting on the report and allow the CO to proceed with initiating the procurement process. All information was copied to Mr. Martin Krause, APRC. The Draft reports on Basic Design and Equipment Technical Specifications were reviewed by APRC. All reports were accepted and the Feasibility Study Team submitted the Final Reports on Basic Design and Equipment Technical Specifications during the period from 4 November 2011 to 2 December 2012. The target was achieved in 2012 (See also Stocktaking report, page 11). |
| Demonstration projects consisting of different mix of technologies implemented in the four target counties by the end of Project. | All designed technologies such as the small hydropower plant, solar hot water systems, PV systems, pig-farm and household biogas systems, energy efficient biomass direct combustion systems, high-efficiency coal combustion systems and energy efficient measures in social buildings and households, except the gasifier system, have been implemented by October 2014. According to the decision by Project Steering Committee held on 27th of May 2014, PO 1353 with SPM COGEN on Rice Husk Gasification System was closed and the remaining amount of 386,000 USD was used for purchasing new Solar PV and additional SHW Systems. The target was achieved in October 2014. |

OUTPUT 3: RELEVANT OFFICIALS TRAINED & THEIR CAPACITIES ENHANCED THROUGH THE CONDUCT OF STUDY TOURS FOR:

A) POLICY AND TECHNOLOGY ASPECTS OF SUSTAINABLE RURAL ENERGY SYSTEMS;

B) PROJECT DEVELOPMENT, IMPLEMENTATION & INVESTMENTS IN SUSTAINABLE ENERGY SYSTEMS.

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Study tours for relevant officials organized in Asia (China, Philippines and Vietnam) by Month 8 of the first year. | 6 national experts participated in the study tour in Asia (China, the Philippines and Vietnam) from 6-22 April 2011. See details in Annex 1. The target was achieved in 2011. (See also Stocktaking report, page 12). |
| Training and short courses for different technological solutions and aspects of sustainable rural energy organized and conducted within and outside DPRK for relevant participants by end of the first year. | International training on solar energy resource mapping and solar energy system technology was conducted from 4 – 26 December 2010 in Guangzhou Institute of Energy Conversion, Guangzhou of China for 6 experts (USD 63,821). Six local experts who participated in this training have organized follow up in- country training on Solar Thermal and Photovoltaic System Technology in Pyongyang for 45 participants representing mostly experts and engineers from the relevant research & development institutes and centers. International training on Biomass Resource Mapping and Biogas System Technology was conducted from 4 – 26 December 2010 in Guangzhou Institute of Energy Conversion, Guangzhou of China for 6 experts (USD 63,716). Six local experts who participated in this training have conducted follow up in-country training on Biomass Energy Technology from 25-27 July 2011 in Pyongyang for 45 local experts representing mostly experts and engineers from the relevant R & D institutes and centers. In-country training on Energy Efficiency Technology was conducted by Mr. Frank Pool, international consultant from New Zealand for 18 trainees including experts from ministries/agencies and technicians from academic institutions in Pyongyang from 27-29 September 2011. In-country training on Biogas Technology was conducted by Mr. Alexey Vedenev and Ms. Tatiana Vedeneva from Public Foundation “Fluid”, Kyrgyz for 18 trainees, including experts from ministries/agencies and technicians from academic institutions in Pyongyang from 27 October – 1 November 2011. In-country training on Carbon Financing, Nationally Appropriate Mitigation Actions (NAMA) and Clean Development Mechanism (CDM) Issues was conducted by Mr. Dmitry Halubouski, CDM Consultant from Belorussia for 17 trainees, including experts from ministries/agencies and technicians from academic institutions in Pyongyang on 2-3 November 2011. See details in Annex 1 and 2. The Target was reached in 2012. |
| In-country training on integration of sustainable rural energy in education curricula conducted by end of Project | Due to the new requirements of UNDP Management, several activities under Output 3 “Capacity Development Needs at Different Levels Identified and Appropriate Training Programmes Organized and Implemented” were reviewed and cancelled. For example, International Training on the Integration of Sustainable Rural Energy in Education Curricula in Germany for staff of Ministry of Education was canceled in August 2012. The target was not achieved. (See Stocktaking report, page 12). |
| Participation in 3-5 international training workshops by end of Year 2. | Eight DPRK experts took part in the International Training on Small Hydropower Systems in International Center on Small Hydro Power (IC-SHP), Hangzhou City, Zhejiang Province in China from 24 November – 23 December 2011. ToRs for DPRK participants were prepared in advance with agreed follow up after completion of trainings. 7 experts from relevant DPRK institutes took part in the International Training on Planning and Management of Sustainable Rural Energy Systems in Renewables Academy (RENAC) in Berlin, Germany from 11 - 30 November 2012. ToRs for DPRK participants were prepared in advance with agreed follow up after completion of trainings. See details in Annex 1. The target was achieved in 2012. |
| Study tours for relevant officials organized in Asia (China, Philippines) and Europe (Denmark, Germany and Sweden) by Month 15 of the second year. | 6 local experts took part in the study tour on Sustainable Rural Energy Development in Kyrgyzstan and Tajikistan from 30 July – 16 August 2011. ToRs for DPRK participants were prepared in advance with agreed follow up after completion of the study tour. 6 local experts and officers took part in the study tour in Germany and Mongolia organized by Germany ProfEC from 27 October until 19 November 2012. ToRs for DPRK participants were prepared in advance with agreed follow up after completion of the study tour. See details in Annex 1. Although the target was reached in 2012 there were many delays in organizing the international trainings and study tours due to long internal national processes for selection of DPRK participants and providing nomination forms in the required time. In total 465 experts benefitted from improved capacity and knowledge in RET and EE through: 15 in-country trainings on Biomass Energy Technology, on Solar Thermal and Photovoltaic System technology, Energy Efficiency Measures, CDM and Climate Change negotiations. 6 of these trainings were conducted by international consultants and 9 by trained trainers. The target was achieved in 2012. |

OUTPUT 4: POLICIES AND MECHANISMS PUT IN PLACE TO REMOVE BARRIERS TO IDENTIFICATION AND IMPLEMENTATION OF ENERGY DEMONSTRATION PROJECTS.

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Barriers, opportunities and constraints related to the development and implementation of demonstration projects identified and measures to overcome them initiated by the first year. | Barrier removal activities were more difficult than anticipated. The approach proposed by SRED was subject to external factors and risks that may not have been acknowledged as such at the design stage. The PSC members on 14 September 2012 highlighted that although policy, regulatory or institutional improvement is important to address structural and systemic barriers to energy access but the project has not been able to do much in this area. PSC meeting concluded to revisit and address the above issues through a series of discussion. Output 4 can be implemented if a number of conditions are in place, including: (i) sufficient implementation capacity within UNDP CO; (ii) detailed propositions in terms of policies and support mechanisms for rural energy development; (iii) identified counterparts with a mandate to review and formalize new regulation and policy instruments; and (iv) effective high-level policy support to national project partners. Policy development (Output 4) was not actively pursued due to limited opportunity for policy engagement (see also Stocktaking report, page 12-13). |
| Detailed feasibility studies of different types of technologies (with specific reference to local products and products can be improved to international standards) for rural applications by Month 6 of the first year. | PM has reported to PTC and PSC that energy efficiency component has to be included and substantially increased in the SRED current work and it has to be properly planned for future activities. To help with this Mr. Frank Pool, consultant on Improvement of Energy Efficiency in Rural Buildings was contracted. His first mission was conducted from 8th to 15th July 2011. Energy Efficiency consultant’s main task was collecting information about selected project for demonstration. The second mission of Frank Pool took place from 26 September to 1 October 2011. The overarching purpose of the second mission was to follow up on the preliminary findings of the first mission, obtain additional information on the key rural building energy efficiency aspects that were not able to be fully ascertained during the first mission or in subsequent email exchanges, provide suitable training sessions in Pyongyang and finalize costs of energy efficiency options for UNDP and donor funding demonstrations and subsequent replication efforts in rural DPRK buildings. Two and half days training was provided in Pyongyang based on information related to the proposed demonstration project implementation in all 4 sites once necessary site specific data was obtained. |
| Baseline & methodological study, CER calculation, PIN production and investigation of potential international carbon buyers for bundled SHP by Month 10 of the first year. | The overall objective of the CDM consultancy was to develop in-country capacities for identification and implementation of CDM projects, including (i) technical assistance for CDM project pipeline development; (ii) identification of potential marketing opportunities for CDM projects from DPRK, and (iii) trainings to improve the understanding of carbon finance and carbon markets among the key stakeholders in DPRK. The first mission under this contract was fielded in DPRK by Mr. Dmitry Holubouski, CDM International Consultant from June 26 till July 5, 2011 with the purpose of meeting the key stakeholders to be engaged in CDM project development and/or implementation, gathering on-the-ground information on potential CDM projects, and providing trainings on (i) CDM procedures, requirements, project cycle, and (ii) financial assessment of CDM projects and Emission Reduction Purchase Agreement (ERPA). Mission 2 was undertaken from October 31 until November 4,including 2 trainings on Climate Change Negotiation process after Cancun and before Durban, updates on availability and emerging financial opportunities for DPRK, recommendations and decisions: 1.UNDP Senior Management will consult with NCC on considering NAMA approach as possible mechanism and methodology for 3d SRED Programmes Scaling-up Phase: Sustainable Rural Energy Development Programme updated/re-formulated and designed for the implementation at the national-scale. 2. PM will continue to work with project national partners and NPD on developing technical paper for describing NAMA implementation under SRED and adding relevant elements of SWEDPRA towards implementation of the Scaling-up Phase. Participants of 3rd PSC meeting on 1 March 2012 had noted that they lack understanding of concepts and knowledge on NAMA at this stage and suggested to consider this mater as separate from activities under SRED. |
| Local design criteria and quality standards for RE & EE technologies established by Month 18 in the second year. | After consultation with UNDP DRR it was agreed in PTC meeting on 14 February 2013 that the budget line for development of local design criteria and standards for renewable energy and energy efficient technologies will be deleted as the work can be covered through reports prepared after installation of demonstration Renewable Energy and Energy Efficiency projects. |
| Testing facilities & quality standard testing procedures for RE & EE technologies established by Month 20 in the second year. | Process of ToR preparation and hiring of international consultant on development of local design criteria, establishment of testing facilities and quality standards for RE and EE technologies was cancelled due to advice of UNDP Senior Management. Process of ToR preparation and hiring of international consultant and local experts on establishment of testing facilities and quality standards for renewable energy and energy efficiency technologies also were cancelled. |
| Local experts/ facilities for maintenance and repair of RE & EE equipment & devices put in place by end of Project. | Process of hiring an international consultant for developing local capabilities for the operation and maintenance and repair of RE and EE Equipment was cancelled due to advice of UNDP Senior Management. |
| Detailed feasibility study on potential for applications of biofuels (how to reform relevant national policies and regulations; adopt international standards and practices) in the country by Month 22 in the second year. | This activity was already removed due to the decision of previous PSC meeting |

OUTPUT 5: LESSONS LEARNT COMPILED:

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Project Development and Implementation Guides for different technologies completed by Month 22 in the second year; | Guides and manuals for project implementation based on each technology was developed by international/local suppliers of RE&EE equipment and materials, and translated into Korean, printed and distributed to the local beneficiaries. The 4th SRED PSC meeting on 5 September 2012 correctly observed that: “Output 5 “Lessons learned” can be done only after installation of demonstration projects and based on the results of the monitoring and evaluation of the installed equipment (See also Stocktaking Report, page 12). Thus this target was partially achieved. |
| Compilation of “good practices” report consisting of Case Studies of implemented projects including integration of financing and CDM aspects completed & printed by Month 20 in the second year; | The technical reports of each technology demonstration were produced including “good practices” and lessons learnt by local experts who are responsible for the technical supervision after completion of the application of renewable energy and energy efficiency demonstrations. Given the context of DPRK, CDM aspects were not pursued. Refer to the activity reports for technical supervision and enhancement of rural people’s skills, related to the demonstration of each technology application such as small hydropower system, pig-farm biogas system, solar water pumping system, solar hot water system, energy efficiency, household biogas system, solar PV system. |
| Investment study and financing packages, including carbon financing for sustainable rural energy systems conducted by Month 18 in the second year | Given the context of DPRK, these activities were not pursued. |
| Monitoring continuously being done and evaluation conducted at Month 13 in the second year | The Inception Workshop was conducted on 10 May 2011, 50 Project Technical Committee (PTC) Meetings, 9 Project Steering Committee meetings and Terminal Tripartite Review Meeting on 15 October 2014 ), 69 site monitoring reports, 4 inventories check visits by UNDP Operation Unit in 2013,. The Projects’ issues, risks and monitoring information were reflected in Atlas by PM. Stock-Taking Assessment was done by IC from 6-19 October 2012 and Stock-taking Review was provided in November 2013 for UNDP approval. The Stock-taking assessment consisted of a two-week mission to DPRK (from 26 January – 9 February 2013) and desk work, including a review of SRED project documents provided by UNDP, presentations, and notes handed over by NCC to perform an assessment of the SRED programme. It included the following objectives: (i) to review the project’s activities; (ii) to collect lessons learnt from project implementation; and (iii) to recommend removing shortcomings under the SRED Programme. Given the limited time available for the assignment, the extensive project documentation was selectively reviewed. Consulted documents include annual workplans (AWP), annual progress reports (APR), quarterly and M&E reports, procurement lists, and minutes of the Meetings by the Project Steering Committee (PSC) and Project Technical Committee (PTC). |
| Project life-cycle analysis and GHG emission impact analysis conducted by Month 23 in the second year; | Given the context of DPRK, these activities were not pursued. |
| Information materials produced and information campaigns regularly conducted for the general public from Month 20 in the second year; | Publication of Guides and Manuals for Project Implementation Based on Each Technology that was Demonstrated and Reports of case studies consisting good practices based on the implementation projects. Printing publications for awareness - building campaigns (1,000 copies for each of the 8 technologies) |
| Seminars and other awareness-building campaigns for policy makers and national/local decision makers conducted from Month 20 in the second year | Given the context of DPRK, these activities were not actively pursued. |

OUTPUT 6: A SUCCESSOR RURAL ENERGY PROGRAMME DESIGNED

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Integrated energy-economy-environment planning exercises & sustainable energy scenarios using LEAP and adaptation of LEAP in Korean language by Month 10 in the first year. | Long Range Energy Alternatives Planning System (LEAP), is a widely-used software tool for energy policy analysis and climate change mitigation assessment developed at the Stockholm Environment Institute. Given the context of DPRK, these activities were not actively pursued. Therefore instead of using LEAP software, local experts initiated to develop integrated energy-economy-environment planning exercises by using HOMER software after being trained from International Training on Planning & Management of Sustainable Rural Energy Systems in RENAC, Germany. In the follow-up energy project, the integrated planning exercise could be continued and finalized. |
| Pilot projects evaluated vis-à-vis standards & experiences on “good practices” by Month 22 of the second year. | It was proposed that this work should be done with great detail and include an assessment of the maturity of the various energy solutions demonstrated under SRED. To enable these activities, it was proposed that the project horizon should be extended beyond October 2014. A differentiated approach can be followed, including ongoing support of promising (but not yet mature) technologies (Component 2) and only if sufficient institutional capacity is available. |
| IRED initiated and applied to SRED by Month 16 of the second year. | Application of the Integrated Energy & Rural Development (IRED) approach might be used for the future work on rural energy development. |
| Provinces/counties with the most potential for national-scale replication of demonstration projects identified and RE resources and energy demand for provincial and county level mapped out by Month 16 of the second year. | See below “Rural energy surveys and energy assessment of selected additional provinces/counties conducted by Month 18 of the second year”. |
| Rural energy surveys and energy assessment of selected additional provinces/counties conducted by Month 18 of the second year. | During 8th PSC meeting on 27 May 2014 UNDP DRR stressed the importance of the local energy survey not only for the purpose of new energy project formulation but also for the new Country Programme Document for the new cycle 2016-2020. This survey also contributed to the ongoing projects such as SED and SERCARB for supplying sufficient energy for the maximizing the development input by each project. The contract with Institute of Development Strategy for Science and Technology (IDS) was signed on by UNDP DPRK by June 3rd 2014. According to the activity schedule under the Contract, this survey should be finalized within 8 weeks. As part of the work implementation, an International Consultant (IC) was involved by UNDP to provide guidance to the national consultant (IDS) to review their work plan and methodology, provide orientation on UNDP’s objectives and key questions, as well as expertise on energy-related issues remotely and through intensive direct interaction during two missions of IC to DPRK. During IC’s last mission from 25 August to 8 September in addition to several meetings with IDS, one field visit was completed to Hoechang County for interviewing representatives from the Management of the County People’s Committee, who are in charge of the dispatch of coal and electricity; as well as the heads of Cooperative Farms. In addition to BTOR after the visit to Hoechang County on 1-2 September 2014 an additional observation was provided by IC in a separate Informative Note. The mission found that the work done by IDS is insufficiently systematic. Data collection and reporting are poor and incomplete, and analysis is virtually absent. This subject was discussed by PM and IC with Ms. Hong Jong Hui, SRED NPD and Mr. Pak Kyong Chol, Coordinator of NCC for UNDP on 4 and 6 September 2014 accordingly and during the Wrap-Up Meeting with Mr. Ghulam Isaczai, UNDP RR on 8 September 2014. It was recommended to stop IDS’ work, as it did not meet the required standards for professional research and analysis. |
| Project Document on the National-scale Sustainable Rural Energy Programme prepared by Month 22 of the second year. | The International Consultant (IC) on UNDP Rural Energy Intervention Formulation conducted 3 mission to DPRK from: 20-27 April 2014; June – 4 July 2014; and 28 August – 8 September 2014. IC provided the first draft of new Sustainable Energy Solutions for Rural Livelihoods in DPRK (SES) Project (2015-2018) with total budget US$ 6,117,572. The Target was achieved in 2014. |
| Policy recommendations, including development of institutional and organizational capacities, for sustainable rural energy development by Month 23 of the second year. | The implementation of the SRED programme required important adjustments from the original strategy and budget. This was due to several factors, including the DPRK specific political environment, which led to: (i) a long suspension of activities; (ii) changes in budget distribution; (iii) the suspension of certain activities; and (iv) the inability to leverage additional financial resources from other agencies and/or financiers. These adjustments implied an alteration of the project strategy away from achieving its ultimate objective (i.e. to prepare DPRK to implement a nation-wide rural energy programme). The national partners and local communities have little experience with renewable energy projects and lack the managerial and technical skills to implement them. Upscaling will not be possible without substantial executing capacity among national entities. Given the context of DPRK, some activities were not actively pursued. After consultation with UNDP DRR it was agreed in the PTC meeting on 14 February 2013 that Budget line for Local experts on programme design, formulation and development of Sustainable Development Programme for implementation at the National Scale and formulation of policies to support the national scale programme for SRED and development of rural markets for RE/EE technologies will be deleted as it is not feasible due to limitations on policy engagement. |
| Donor consultations conducted by Month 22 of the second year. | During the SRED implementation it was recognized that several donors, EUPS and international organizations and their national partners have gained some experience and lessons learned, which can be beneficial for the SRED implementation. As different organizations are coordinated by different governmental bodies, it will be important if NCC can help to coordinate and arrange exchange of information among relevant partners who have institutional memory on similar work done in DPRK. |

PROJECT MANAGEMENT

| Initial Project Targets in the signed SRED Prodoc | Implementation |
| --- | --- |
| Project management team in place 3 months after project approval | The SRED Project Document was signed on 16 March, 2006 (Pre-resumption) and on 17 July, 2010 (Resumption). The project duration was set at 24 months after resumption in July 2010; (12 out of 36 initial months were completed during pre-resumption period). The key staff- as Project Manager (PM), National Training Coordinator (NTC), Project Assistant (PA) - and support staff (Driver, Cleaning Lady) were hired within January-April 2011 and the Project Office establishment, including premises renovation, purchasing office car, furniture and equipment was completed within January-May 2011. The end of the project in July 2012 was unrealistic. The initial Programme’s time schedule was highly optimistic and too short to finalize all envisaged components. Consequently, project implementation was continually perceived as “delayed”, while the technology pilots are in fact valuable elements in a learning process for UNDP and its Government partners. Therefore in the 2nd PSC meeting on 12 October 2011 it was suggested to extend SRED project until April 2013. During the 4th PSC on 14 September 2012 additional no-cost extension until December 2013 was endorsed due to delays with procurement and transportation of purchased equipment due to overall political situation and finally project was extended until October 2014 during 8th PSC meeting on 27 May 2014. The 1st PSC meeting on 6 July 2011 2011 endorsed the new M&E Project Framework under close consultation with Senior Programme M&E Advisor (Annex 2) and it was approved by UNDP and NCC as well as PSC meeting. The Inception Workshop was conducted on 10 May 2011, 50 Project Technical Committee (PTC) Meetings, 9 Project Steering Committee meetings (1st PSC meeting on 6 July 2011, 2nd PSC meeting on 12 October 2011 (first No-Cost Extension of SRED until April 2013), 3rd PSC on 1 March, 4th Joint SRED/SWEDPRA PSC meeting on 5 September, 5th PSC on 30 April 2013, 6th Joint SRED/SWEDPRA PSC meeting on 12 December, 7th PSC meeting on 6 March 2014, 8th PSC meeting on 27 May 2014 and Terminal Tripartite Review Meeting on 15 October 2014 ), 68 site monitoring reports, 4 inventories check visits by UNDP Operation Unit 2013, Stock-Taking Assessment from 6-19 October 2012 were conducted. The Projects’ issues, risks and monitoring information were reflected in Atlas by PM. Due to the inadequate local managerial skills of local partners, the PM had to supervise all activities very closely and visit the local project sites frequently, simultaneously using his observations for progress monitoring. During first half of 2011 it was recognized that (i) M&E should not be process oriented, cumbersome and complicating work with many reporting requirements which delay and affect project management efficiency and (ii) Structure of M&E in the ProDoc did not reflect the reality of decision making process and environment of project implementation. It is necessary to achieve results with less procedural burdens. With the operational closure of SWEDPRA project in December 2013 and due to lack of options on custodian arrangements and continuation of managerial and administrative support, it was agreed to transfer assets (PPM test and other equipment) to the SRED project and hence SWEDPRA asset monitoring was continued under SRED. |

# EVALUATION OF PROJECT ACTIVITIES

The stocktaking assessment consisted of a two-week mission to DPRK (from 26 January – 9 February 2013) and desk work, including a review of SRED project documents provided by UNDP, presentations, and notes handed over by NCC to contribute to an assessment of the SRED programme. It included the following objectives: (i) to review the project’s activities; (ii) to collect lessons learnt from project implementation; and (iii) to recommend on removing shortcomings under the SRED Programme.

Given the limited time available for the assignment, the extensive project documentation was selectively reviewed. Consulted documents include annual workplans (AWP), annual progress reports (APR), quarterly M&E reports, procurement lists, and minutes of the Project Steering Committee (PSC) and Project Technical Committee (PTC) meetings.

It was recognized during stocktaking assessment that the RE/EE demonstration pilots imply complex and lengthy processes which are not reflected as such in the flow chart during SRED project design. Instead, it is assumed that the pilots can be delivered “on demand”, after which the programme can move on to the next step. However, many specific conditions need to be in place for swift project execution, which cannot just be assumed. These conditions may not have been recognized or understood due to insufficient preparation time and expert support during the design phase of the SRED Programme.

According to observation in the stocktaking report “… the removal of barriers under output 4 (policy and mechanisms) is presented as part of the scale-up phase, which seems not fully consistent with the barrier identification step before pilot implementation. It must also be noted that the activities proposed in the SRF are not supportive (or sufficient) to establish the envisaged output 4. Barrier identification and analysis (output 4.1) should at least partly be done during the design phase of SRED. With limited previous working experience in rural energy in DPRK, the linear approach followed by SRED is highly optimistic and subject to external factors and risks that may not be acknowledged as such. In practice, the project follows a learning-by-doing approach, which makes complete sense. In many occasions, the PM recalls earlier experiences to expedite subsequent demonstration pilots. The Programme’s tight time schedule however, is not well matched to this more practical approach. By consequence, project implementation is continually perceived as “delayed”, while a more positive perception could be that very useful lessons are being learnt within a relatively short period (since 2011)”.

# LESSONS LEARNED

In 2010, the international context for DPRK had changed compared to 2005, when the Project was initially designed. The implementation of the SRED programme was thus impacted by the international political issues related to DPRK. Meanwhile, equipment costs and transportation costs to and within DPRK drastically increased since 2005 in comparison with initially allocated budget.  The high cost and low availability of construction materials on the local market further affected the budget requirements.

International sanctions were in place and the opportunities to leverage additional sources of funding greatly reduced.

The geo-political environment led to the disruption of several international missions; renegotiation of the resumption of the missions when the geo-political situation stabilized was difficult as the international experts had already other planned commitments under other countries’ projects.

Several project activities had to be delayed and postponed due to problems with local payments. All previously advertised products and services and completed selection of local vendors had to be cancelled due to restrictions on local payments and had to re-advertised for international vendors. Availability of local payments in late September and October 2013 did not solve the situation as some seasonal activities such as concrete works would not be possible. The situation with local payment was repeated in March 2014 and lasted almost until end of SRED project in October 2014. Purchasing of goods was moved to the beginning of cold season and arrival of cement was possible in the time when concrete work would not be possible. Significant delays occurred due to the fact that  very few vendors were responding to calls for bidding; price of suggested equipment were sometimes extremely high; and transportation of procured equipment was not possible due to absence of offers from transportation companies.

Very few international transportation companies participated in biddings due to high associated risks in the absence of information about the country circumstances.

Lack of capacity of local institutions and experts to organize proper supervision, coordinate with end users and monitor Renewable Energy Technologies (RET) installation works created situations when the project had to take corrective actions and PM had to be involved in operational issues at very detailed level and to supervise all activities very closely, visit the places frequently, simultaneously using PM observations for progress monitoring. Due to severe winter conditions, installation of some equipment could not be done from December until end of February. International technical specialists from hired companies came for very short time. Moreover, installation of solar hot water systems, biogas and energy efficiency sub-projects, which depended on the availability of electricity were delayed due to electricity shortages, although SRED Project made additional efforts to coordinate with local administrations on using diesel generators or other sources of electricity during the installation time.   In general absence of direct communication with local experts and between local and international experts and unavailability partners in cooperative farms for some periods during agricultural seasons contributed to delays in the processes.

Serious consideration should be given to reference check and selecting the right vendor which is capable of providing the equipment as per technical specifications. The case in point is the SPM COGEN, whose contract was terminated on May 5th, 2014. By end of 2013 it was already clear that due to slow response from UNDP Legal Support Office (LSO) and from SPM COGEN the sum USD 386,000 cannot be quickly reallocated and timely delivered. Following the decision of an ad hoc Project Steering Committee (PSC) meeting (6 March 2014), the Project Team provided the justification for other activities instead of RHG project in March, which was based on the December 2013 and January 2014 agreements between Deputy Resident Representative (DRR) and National Coordination Committee (NCC). Project Manager (PM) and National Project Director (NPD) provided justification on the list of new technologies instead of Rice Husk Gasification project. It was agreed that the Solar PV has to be a priority in order to strengthen efficiency of Solar Hot Water Systems (SHWS) in all four cooperative farms including households and social buildings. Additional PV System will be provided for social buildings and households to demonstrate an ability of solar technology to provide electricity supply. On 28 May 2014, Procurement Plan was finalized in line with project extension to the end of October 2014. On 27 May, 2014, PSC approved AWP and Procurement Plan for this activity. Nevertheless the process of procurement was delayed and finalized only in September-October 2014. Close monitoring and follow-up of procurement processes is thus required for timely implementation of project activities.

# BUDGET INFORMATION

The total project budget after resumption in 2010 was US$ 5,035,596. During 5 years from 2005-2010 the project spent only 13.6% of the resources. In 2011 the delivery drastically increased to 14.8%, 27.3% in 2012, 20.9% in 2013. Cooperative Farms provided in-kind local labor and safety premises for storage of procured equipment and materials.  About 76.7% of total resources were spent as of end December 2013. After last project no cost extension in June 2013, project operational activities ended in October 2014.

Breakdown of budget by years from 2006-2014:

| Approved Total SRED Budget | Expenditure 2005-2010 | Expenditure 2011 | Expenditure 2012 | Expenditure 2013 | Remained funding 2014 | Estimated delivery 2014 |
| --- | --- | --- | --- | --- | --- | --- |
| (US$) | (US$) | (US$) | (US$) | (US$) | (US$) | (US$) |
| 5,650,000.00 | 768,294.15 | 836,825.95 | 1,544,772.83 | 1,183,251.03 | 1,316,856.04 | 1,001,050.00 |
| (100%) | (13.6%) | (14.8%) | (27.3%) | (20.9%) | (23.3%) | (17.7%) |

The UNDP CO certified in the last UNDP M&E report, based on the Q2 June 2014 physical count of the inventory carried out and the inventory reports and Office Supplies & Fuel reports submitted for the SRED project, that the value of inventory balances reported as above was accurate and complete, in accordance with the guidance note received from the UNDP HQ for the purpose. All the inventories are in the control of UNDP and have been included in the report. Their costs and valuation are calculated and reported correctly in accordance with the guidance note received.

# OVERALL CONCLUSUIONS AND RECOMMENDATIONS

The SRED Programme was highly ambitious in its objectives, planned implementation time frame was extremely short, roles of national counterparts were not always clear and need for strengthening their technical and managerial skills were not fully taken into consideration. These are valuable lessons learned that were not available in 2005.

Project strategy and scope must have a direct relation with the chosen beneficiaries. The main counterpart must have functional linkages with the beneficiaries. If the objective of a project is to deliver a service to end-users (such as energy to rural households), logical counterparts can be local businesses or public entities promoting delivery mechanisms. If the objective is more high-level, appropriate counterparts can be research institutes (to address a technology barrier), or governmental agencies (to address a policy barrier).

The implementation of the SRED demonstration pilots produced a wealth of knowledge and lessons about the implementation of new technologies in the rural areas. Many problems and issues emerged that were reported by the PM to UNDP and the national partners (see BTOR, PSC and PMC reports in the SRED Programme files).

The SRED PSC on 14 September 2012 highlighted that although policy, regulatory or institutional improvement is important to address structural and systemic barriers to energy access the project had not been able to do much in this area due to the political context. Therefore Policy Development (Output 4, see prodoc) was not actively pursued due to limited opportunities for policy engagement.

The removal of barriers under SRED Output 4 is presented as part of the scale-up phase, which seems not fully consistent with the barrier identification step before pilot implementation. Barrier identification and analysis (output 4.1, see prodoc) should have been done at least partly during the design phase of SRED.

In practice, the project rather followed a learning-by-doing approach. In many occasions, the PM recalls his earlier experiences to expedite subsequent demonstration pilots. The project’s tight time schedules was not consistent with this more practical approach. Consequently, project implementation was continually perceived as “delayed”, while a more positive perception could be that many useful lessons were being learnt since 2011. More information on lesson learned is provided in separate End-of-Assignment Report by PM.

Nevertheless SRED performance from 2011-2014 was satisfactory overall as the key results were mostly achieved. The SRED Programme Outputs were achieved as follows:

Programme Development Phase:

“Provinces and cooperative farms identified for pilot demonstration schemes in rural energy development” was completed in 2011.

Implementation Phase:

“Demonstration activities implemented and running successfully” was completed in 2014;

“Capacity development needs identified and training programmes implemented” was completed in 2012;

“Lessons learned and ‘good-practices’ compiled for sharing and knowledge management” was partially completed in 2014;

“New rural energy initiative designed” was completed in 2014.

SRED project was operationally closed according to the UNDP rules and regulations in October 2014.  However, SRED assets could not be transferred to the Government pending further guidance on the assets transfer and disposal from UNDP HQ. Meanwhile the assets are being monitored by the by UNDP M&E Specialist using SRED management budget as SRED. The Government will ensure access to the SRED project sites.

Zharas Takenov, SRED Project Manager

# ANNEXES

# Annex 1. SRED Monitoring and Evaluation Framework

| MONITORING AND EVALUATION PLANM&E Activities | Frequency /Timing | Aspects to be Monitored & Evaluated/ Description | In-charge of Activity | To review/endorse/adopt |
| --- | --- | --- | --- | --- |
| Monthly Delivery Plan | Every beginning of month | Planned activities, deliverables, human resource and financial inputs for the next month | PM | UNDP |
| Annual Workplan and budget | Beginning of each year | Detailed activities, budget, milestones, deliverables, human resource inputs for the next year | PM, | PSC |
| Quarterly Progress Report | Quarterly | Quarterly accomplishments, lessons learned/problems faced during the execution of the activities and the planned activities for the next quarter. Quarterly report to be prepared for 1, 2 and 3 quarters. Report for 4 quarter to be combined with annual progress report. | PM | PSC |
| Annual Progress Report | End of Year | Annual accomplishments and outputs, indicators and targets and the efficiency and effectiveness with which they are produced; budget and final report for the year completed; update of Project workplan; lessons learned, recommendations and suggestions for re-orientation of activities (if necessary) | PM, | PSC |
| Terminal Report | End of Project | Project accomplishments against outputs, targets and indicators; Project expenses and financial report; Records and evidences of all outputs; Lessons learned and recommendations for future actions | PM, | PSC |
| Mission reports | After each mission | mission findings and recommendations (according to defined template) | NTC, Individual experts | PM, NPD, UNDP |
| Other reports and deliverables | After each TA or subcontract | Reports and deliverables vis-à-vis the TOR of the TA. These reports will also include reports by CO programme staff field visits. | NTC, Individual experts | PM, NPD, UNDP |
| Monitoring of project sites and investments | After commissioning of the plants | environmental/social impacts of the projects; access to equipment installed through site visits; verify delivery of products and services to target beneficiaries and the location, proper upkeep, safety and security of equipment. | NTC, NPD, PM; External service providers, UNDP; SPA to provide in quarterly reports | PSC |
| PSC meetings and minutes | Every 6 months | Minutes of meetings which reflect the discussions and decisions according to the functions of the PSC outlined in this document | PM | PSC |
| PTC meetings and minutes | Every 3 months | Minutes of meetings which reflect the discussions and decisions according to the functions of the PTC outlined in this document | PM | PTC, PSC |
| Financial recording & reporting | Throughout the Project; continuous | Monitoring and control of project expenditures; financial management & reporting; Project resource data tracking inputted in and regularly accessed from, the Atlas system | PM | UNDP |

# Annex 2. Study Tours and International Trainings under SRED Programme

| No | Description | Place | Mission Period | Name of Participants |
| --- | --- | --- | --- | --- |
| 1 | International Training on solar energy resource mapping and solar energy system technology | Guangzhou Institute of Energy Conversion, Guangzhou, China | 4 Dec - 26 Dec 2010 | Kwon Dae Yon, Senior officer, Department of International Science Cooperation, State Academy of Sciences(SAOS) Choe In Su, Head, Section of Energy Planning, Pyongyang Power Design Centre, Ministry of Electrical Power Industry(MEPI) Kim Chang Il, Senior Researcher, Section of Energy Planning, Pyongyang Power Design Centre, MEPI Yun Ho Nam, Head, Department of Solar Energy, Institute of Thermal Engineering, SAOS Han Myong Su, Senior Researcher, Department of Solar Energy, Institute of Thermal Engineering, SAOS Pak Kwang Sop, Researcher, Department of Solar Energy, Energy Center, State Commission on Science and Technology (SCoST) |
| 2 | International Training on biomass resource mapping and biogas system technology | Guangzhou Institute of Energy Conversion, Guangzhou, China | 4 Dec - 26 Dec 2010 | Choe Kwang Hun, Head, Section of International Organizations, Bureau for International S & T Cooperation, SCoST Han Hung Myon, Senior Officer, Bureau of Power and Machinery, SAOS Kim Ul Song, Head, Department of Rural Energy, Institute of Thermal Engineering, SAOS Ri Kwang Chol, Senior Researcher, Department of Biomass Energy, Energy Center, SCoST Ri Hak Chol, Senior Researcher, Department for cooperation with International Organizations, SAOS Yu Thae Gol, Senior Researcher, Section of Energy Planning, Pyongyang Power Design Centre, MEPI |
| 3 | Study Tour in Vietnam, the Philippines and China | Vietnam, the Philippines and China | 6 Apr - 22 Apr 2011 | Jang Chun Sik, Coordinator of National Coordinating Committee for UNDP Hong Jong Hui, Senior Officer of Ministry of Electric Power Industry Jang Myong Ok, Officer of Ministry of Coal Industry Kim Ul Song, Officer of State Academy of Sciences Ro Song Chol, Officer of Ministry of Electric Power Industry Ri Hyong Chol, Programme Analyst of UNDP Country Office, DPRK |
| 4 | Study Tour on Sustainable Rural Energy Development in Kyrgyzstan and Tajikistan | Kyrgyzstan and Tajikistan | 30 July - 16 Aug 2011 | Kang Tae Yun, Director, Bureau of Power and Machinery, State Academy of Sciences Ryu Kwang Min, Deputy Director, Bureau of International Cooperation on Science, SAoS Hong Jong Hui, Senior Officer, Bureau of External Affairs, MEPI Hong Chol Jun, Officer, Bureau of Energy, SCoST Ho Hyang, Officer, Bureau of Coal production, Ministry of Coal Industry Ri Hak Chol, Senior Researcher, Korea Science Corporation, SAoS |
| 5 | International Training on Small Hydropower Plants | International Center on Small Hydro Power (IC-SHP), Hangzhou City, Zhejiang Province, China | 24 Nov - 23 Dec 2011 | O Jun Ho, Director of Scientific Research, Ministry of Electric Power Industry Ri Sung Yong, Engineer and Interpreter, Ministry of Electric Power Industry Choe Sun Hup, Senior Officer, Bureau of Power and Machinery, SAoS Jon Sin Song, Senior Researcher, Bureau of International Cooperation on Science, State Academy of Sciences (SAoS) Sin Hyon Son, Head, Department of Hydro turbine, Institute of Hydraulic Engineering, SAoS Kim Myong Chol, Designer, Department of Civil Engineering, Central Electric Power Design Institute, MEPI Paek Kyong Il, Designer, Department of Machinery, Central Electric Power Design Institute, MEPI Jon Sang Gum, Designer, Department of Hydrology, Central Electric Power Design Institute, MEPI |
| 6 | Study Tour for Germany and Mongolia | Germany and Mongolia | 27 Oct - 19 Nov 2012 | Hong Jong Hui, Senior Officer, Ministry of Electric Power Industry, National Project Director of SRED Project Hong Chol Jun, Senior Officer, State Commission on Science and Technology Kim Ul Song, Senior Officer, State Academy of Sciences Kang Hyon Ok, Civil engineer, Central Electric Power Design Institute Jon Sung Chol, Head, Laboratory of rural energy development, Institute of Thermal Engineering, SAoS Paek Kyong Chol, Administrative Assistant, SRED and SWEDPRA, UNDP DPRK CO |
| 7 | International Training on Planning & Management of Sustainable Rural Energy Systems | Renewables Academy (RENAC) in Berlin, Germany | 12 Nov - 30 Nov 2012 | Choe Kwang Hun, Head of Division of International Organization, Bureau of International Cooperation on Science and Technology, State Commission of Science & Technology Ri Hak Chol, National Training Coordinator of SRED Programme, Senior Researcher, Division for Cooperation with International Organizations, State Academy of Sciences Jang Chol Ung, Researcher, Korea Science & Technology Cooperation Agency, State Commission of Science & Technology Choe In Su, Senior Engineer, Pyongyang Power Design Center, Ministry of Electrical Power Industry Pak Chol Nam, Senior Engineer, Central Institute of Electric Power Design, Ministry of Electrical Power Industry Yun Ho Nam, Researcher, Solar Energy Laboratory, Institute of Thermal Engineering, State Academy of Sciences Kim Hong Sam, Researcher, Rural Energy Laboratory, Institute of Thermal Engineering, State Academy of Sciences |

# Annex 3. In-Country Trainings under SRED Project

| No | Description | Place | Period | Trainers | Participants |
| --- | --- | --- | --- | --- | --- |
| 1 | In- Country Training on Biomass Energy Technology | Grand People’s Study House, Pyongyang | 25-26 July, 2011 (2 days) | Six Local Experts who participated in the International Training on biomass resource mapping and biogas system technology | The In-country training was attended by 45 participants representing mostly experts and engineers from the Ministries such as SAOS, MEPI, SCoST, MoCI, MoLEP, CBS and etc. and the relevant R & D institutes and centers. And UNDP officials joined in the workshop |
| 2 | In- Country Training on Solar Thermal and Photovoltaic System Technology | Grand People’s Study House, Pyongyang | 28-29 July, 2011 (2 days) | Six Local Experts who participated in the International Training on solar energy resource mapping and solar energy system technology | The In-Country Training was attended by 45 participants representing mostly experts and engineers from the Ministries such as SAOS, MoLEP, SCoST, CBS, MEPI, and MoCI etc. and the relevant research & development institutes and centers |
| 3 | In-Country Training on Energy Efficiency Technology | Haebangsan Hotel, Pyongyang | 27-29 September, 2011 (3 days) | Mr. Frank Pool, international consultant from New Zealand | 18 trainees including experts from ministries/agencies and technicians from academic institutions had participated in the training on the energy efficiency technology |
| 4 | In-Country Training on Biogas Technology | Haebangsan Hotel, Pyongyang | 27and 31 October, and 1 November, 2011 (3 days) | Mr. Alexey Vedenev and Ms. Tatiana Vedeneva from Public Foundation “Fluid”, Kyrgyz | 18 trainees including experts from ministries/agencies and technicians from academic institutions had participated in the training on the biogas technology |
| 5 | In-Country Training on Carbon Financing, Nationally Appropriate Mitigation Actions (NAMA) and Clean Development Mechanism (CDM) Issues | Haebangsan Hotel, Pyongyang | 2-3 November 2011 (2 days) | Mr. Dmitry Halubouski, CDM Consultant from Belorussia | 17 trainees including experts from ministries/agencies and technicians from academic institutions had participated in the training on the CDM and NAMA technology |
| 6 | In-country Training on Dissemination of Small Hydropower Technology (First Session for Experts) | People’s Palace of Culture, Pyongyang | 1-2 March, 2013 (2 Days) | Eight Local Experts who participated in the International Training on Small Hydropower Plants | 25 trainees including experts from ministries/agencies and technicians from academic institutions had participated in the training on the SHP technology |
| 7 | In-country Training on Dissemination of Small Hydropower Technology (Second Session for End-Users) | Yaksu Cooperative Farm, Kangso County, South Pyongan Province | March 27, 2013 (1 Day) | Eight Local Experts who participated in the International Training on Small Hydropower Plants | 24 trainees including end-users from four demo cooperative farms and technicians from institutions had participated in the training on the SHP technology |
| 8 | In-Country Training on Planning & Management of Sustainable Rural Energy Systems (First Session for Experts) | People’s Palace of Culture, Pyongyang | February 25-26, 2013 (2 Days) | Seven Local Experts who participated in the International Training on Planning & Management of Sustainable Rural Energy Systems | 26 trainees including experts from ministries/agencies and technicians from academic institutions had participated in the training on the Planning & Management of Sustainable Rural Energy Systems |
| 9 | In-Country Training on Planning & Management of Sustainable Rural Energy Systems (Second Session for End-Users) | Yaksu Cooperative Farm, Kangso County, South Pyongan Province | March 28, 2013 (1 Day) | Seven Local Experts who participated in the International Training on Planning & Management of Sustainable Rural Energy Systems | 26 trainees including end-users from four demo cooperative farms and technicians from institutions had participated in the training on the Planning & Management of Sustainable Rural Energy Systems |
| 10 | In-Country Training for Debriefing on Sustainable Rural Energy Systems in Mongolia and Germany | People’s Palace of Culture, Pyongyang | February 27 – 28, 2013 (2 Days) | Six Local Experts who participated in the 3rd Study Tour for Germany and Mongolia | 25 trainees including experts from ministries/agencies and technicians from academic institutions had participated in the training for Debriefing on Sustainable Rural Energy Systems in Mongolia and Germany |
| 11 | In-Country Training on Installation, Operation and Maintenance of Solar Water Pumping System | Mopung Cooperative Farm, Anbyon County, Kangwon Province | November 27-28, 2012 (2 days) | Four Local Experts from Pyongyang Power Design Center who are contracted for technical supervision | 20 trainees including end-users from four demo cooperative farms had participated in the training on the Installation, Operation and Maintenance of Solar Water Pumping System |
| 12 | In-Country Training on Installation, Operation and Maintenance of Solar Hot Water System | Yaksu for installation, Myongchon, Ryudong and Mopung for operation and maintenance | March 26 at Yaksu, April 3 at Myongchon, April 7 at Ryudong, April 13 at Mopung | Five Local Experts from Institute of Thermal Engineering who are contracted for technical supervision | 85 trainees including end-users from four demo cooperative farms had participated in the training on the Installation, Operation and Maintenance of Solar Hot Water System |
| 13 | In-Country Training on Installation, Operation and Maintenance of Pig-Farm Biogas System | Mopung Cooperative Farm, Anbyon County, Kangwon Province | May 16-17, 2013 (2 days) | Three Local Experts from Institute of Thermal Engineering who are contracted for technical supervision | 31 trainees including end-users from four demo cooperative farms had participated in the training on the Installation, Operation and Maintenance of Pig-Farm Biogas System |
| 14 | In-Country Training on Installation, Operation and Maintenance of Small Hydro Power System | Myongchon Cooperative Farm, Jangyon County, South Hwanghae Province | July 24-25, 2013 (2 days) | Four Local Experts from Central Electric Power Design Institute who are contracted for technical supervision | 28 trainees including end-users from three demo cooperative farms had participated in the training on the Installation, Operation and Maintenance of Small Hydro Power System |
| 15 | In-Country Training on Installation, Operation and Maintenance of Energy Efficiency Technology Application | Ryudong Cooperative Farm, Unsan County, South Pyongan Province | August 22-23, 2013 (2 days) | Four Local Experts from Institute of Thermal Engineering who are contracted for technical supervision | 32 trainees including end-users from three demo cooperative farms had participated in the training on the Installation, Operation and Maintenance of Energy Efficiency Technology Application |

# Annex 4. Impact of RE and EE Technologies on human life

| RE&EE Technology | Beneficiaries |
| --- | --- |
|  | Mopung | Myongchon | Yaksu | Ryudong | Total |
|  | No of houses & Buildings | No of people | No of houses & Buildings | No of people | No of houses & Buildings | No of people | No of houses & Buildings | No of people | No of houses & Buildings | No of people |
| SHW systems | 10 houses & 5 social buildings | 212 | 10 houses & 5 social buildings | 224 | 10 houses & 5 social buildings | 355 | 10 houses & 5 social buildings | 262 | 40 houses & 20 social buildings | 1,053 |
| Energy Efficiency in Buildings | 20 houses & 5 social buildings | 252 | 20 houses & 5 social buildings | 272 | 20 houses & 5 social buildings | 401 | 20 houses & 5 social buildings | 304 | 80 houses & 20 social buildings | 1,229 |
| Energy Efficient Coal/Biomass Stoves | 20 houses (biomass) | 90 | 20 houses (biomass) | 90 | 100 houses (coal) | 450 | 60 houses (coal) | 270 | 200 houses (100-coal, 40-biomass) | 900 |
| Solar Water Pump | 1 workteam | 25 |  |  |  |  |  |  |  | 25 |
| Pig-farm Biogas System | 20 houses & 2 social buildings | 122 |  |  |  |  |  |  | 20 houses & 2 social buildings | 122 |
| Small Hydro Power Plant |  |  | 670 houses, 25 social buildings and 5 small businesses | 2,700 |  |  |  |  | 670 houses, 25 social buildings and 5 small businesses | 2,700 |
| Household Biogas | 4 houses & 1 social building | 135 | 5 houses | 26 | 5 houses | 23 | 4 houses & 1 social building | 125 | 18 houses & 2 social buildings | 309 |
| Solar PV | 110 houses & 8 social buildings | 1,260 | 20 houses & 12 social buildings | 1,180 | 200 houses & 7 social buildings | 2,600 | 90 houses & 13 social buildings | 1,420 | 420 houses & 40 social buildings | 6,460 |
| Total |  | 1,260 |  | 2,700 |  | 2,600 |  | 1,420 |  | 7,980 |

Grand total of benefitted people – 7,980.

# Annex 5. Assets List

| ASSETS IN UNDP PROJECT OFFICE |
| --- |
| Asset ID | Project | TAG # | Profile ID | Dscrp | Custodian | Location | SN | Cost | Fund | Date of Purchase | Note |
| 000000000308 | SRED | PRK508170001 | Laptop | "HP EliteBook 8740w" | ZT | PO 101 | CNU051087D | USD 1916.13 |  | 11-Jan-2011 | used by SRED PM from 2011 and due to CPU problems, no more used by PM from Nov 2013 |
| 000000000309 | SRED | PRK508170002 | Laptop | "HP EliteBook 8740w" | RHC | PO 102 | CNU051088G | USD 1916.13 |  | 11-Jan-2011 | used by SRED NTC from 2011 |
| 000000000310 | SRED | PRK508170003 | Laptop | "HP EliteBook 8740w" | PKC | PO 102 | CNU05108FT | USD 1916.13 |  | 11-Jan-2011 | used by SRED PA from 2011 |
| 000000000311 | SRED | PRK508170004 | Laptop | "HP EliteBook 8740w" | ZT | PO 102 | CNU051087Z | USD 1916.13 |  | 11-Jan-2011 | used by SRED PM from Nov 2013 and due to Hard Disk problem, changed with Office computer from Apr 2014 |
| 000000000312 | SRED | PRK508170005 | Laptop | "HP EliteBook 8740w" | PKC | PO 102 | CNU05108TK | USD 1916.13 |  | 11-Jan-2011 |  |
| 000000000297 | SRED | PRK508170006 | Vehicle UNDP-08 | car "Pokkugi" 4X4 SUV MODEL: POKKUGI SUV engine No |  | UNDP DPRK | PW244G0600058 | USD 16,666.67 |  | 00-00-2006 | transferred to Govt on Nov 14, 2013 |
| 000000000302 | SRED | PRK508170007 | Vehicle UNDP-09 | car "Pokkugi" 4X4 SUV MODEL: DD6470A engine No SHY0862 | Project Manager of SRED and SWEDPRA | UNDP PO | PW244G100267 | USD 16,969.70 |  | 1-Dec-2010 | transferred to Govt on Sep 4, 2014 |
| 000000000345 | SRED | PRK508170008 | Portable Projector | "LG DX-540" | Project Manager of SRED and SWEDPRA | PO 102 | 904SRVG7943 | RMB 14,570 |  | 23-Feb-2011 |  |
|  | SRED | PRK508170009 | Air conditioner | GREE | Project Manager of SRED and SWEDPRA | PO 101 | GWH09NA-K1NNB4A/I | KPW 85,000 |  | 15-May-2012 |  |
|  | SRED | PRK508170010 | Air conditioner | GREE | Project Manager of SRED and SWEDPRA | PO 102 | GWH09NA-K1NNB4A/I | KPW 85,000 |  | 15-May-2012 |  |

| UNDP Assets delivered from 2011 to 2013 under SRED Programme |
| --- |
| No | Description | Quantity | Price (USD) | PO and Date | Delivery Date | Total Price (USD) | Location and Custodian Transfering equipment |
| 1 | Kangso Coal Mine Equipment from Golden Pack | Drain pipe | 2000 m | 68,000.00 | PO 1084 Nov-03-2011 | Dec-16-2011 | 310,129.43 | Kangso Coal Mine, Kangso County, South Pyongan Province Transferred on March 23, 2012 |
|  |  | Air compressor | 1 pcs | 24,100.00 |  |  |  |  |
|  |  | Truck | 2 pcs | 58,000.00 |  |  |  |  |
|  |  | High speed rock drill | 10 pcs | 4,700.00 |  |  |  |  |
|  |  | Sets of spare parts | 10 pcs | 4,900.00 |  |  |  |  |
|  |  | Wheel shovel loader | 1 pcs | 52,290.00 |  |  |  |  |
|  | Kangso Coal Mine Equipment from SUPPLYQUIP | Pump | 1 pcs | 18,265.09 | PO 1080 Oct-24-2011 | Mar-19-2012 |  |  |
|  |  | Electric motor | 2 pcs | 49,874.34 |  |  |  |  |
|  |  | Compressed air pipe | 2000 m | 30,000.00 |  |  |  |  |
| 2 | Energy Efficiency Stoves | Biomass stoves from Institute of Thermal Engineering | 40 pcs | 2,899.11 | PO 1200 May-15-2012 | Jul-12-2012 | 9,129.11 | Myongchon Cooperative Farm, Jangyon County, South Hwanghae Province - 20 pcs of Biomass stoves Mopung Cooperative Farm, Anbyon County, Kangwon Province - 20 pcs of Biomass stoves Yaksu Cooperative Farm, Kangso County, South Pyongan Province - 100 pcs of Coal stoves Ryudong Cooperative Farm, Unsan County, South Pyangan Province - 60 pcs of Coal stoves Transferred on August 31, 2012 |
|  |  | Coal stoves from Pyongyang Power Design Centre | 160 pcs | 6,230.00 | PO 1199 May-10-2012 | Jul-13-2012 |  |  |
| 3 | Solar Water Pumping System from HelliosWatt | Set of SWPs PV Module, Water Pump, Water Pipe and fittings and Water Valves | one set | 18,100.00 | PO 1228 Jun-28-2012 | Oct-16-2012 | 18,100.00 | Mopung Cooperative Farm, Anbyon County, Kangwon Province Should be Transferred |
| 4 | Solar Hot Water System from TOP Source | 150 liter | 49 pcs | 35,525.00 | PO 1278 Oct-15-2012 | Dec-6-2012 | 67,389.00 | Yaksu Cooperative Farm, Kangso County, South Pyongan Province - 13pcs of 150, 1pcs of 300 and 1pcs of 500 liters Myongchon Cooperative Farm, Jangyon County, South Hwanghae Province - 13pcs of 150 and 2 pcs of 300 liters Mopung Cooperative Farm, Anbyon County, Kangwon Province - 10 pcs of 150, 4pcs of 300 and 1pcs of 500 liters Ryudong Cooperative Farm, Unsan County, South Pyangan Province - 13pcs of 150, 1pcs of 300 and 1pcs of 500 liters Should be Transferred |
|  |  | 300 liter | 8 pcs | 9,424.00 |  |  |  |  |
|  |  | 500 liter | 3 pcs | 5,424.00 |  |  |  |  |
|  |  | PVC set and pipe |  | 6,752.00 |  |  |  |  |
|  |  | Supervision and training |  | 10,264.00 |  | Apr-24-2013 |  |  |
| 5 | 50m3 Pigfarm Biogas System from Fluid | Set of PBs |  | 25,115.00 | PO 1226 Jun-26-2012 | Jan-23-2013 | 104,205.84 | Mopung Cooperative Farm, Anbyon County, Kangwon Province Should be Transferred |
|  |  | Installation of equip |  | 25,700.00 |  |  |  |  |
|  |  | Training and Operation |  | 15,200.00 |  |  |  |  |
|  |  | International Transportation |  | 37,675.83 | PO 1310 Nov-08-2012 | Dec-18-2012 |  |  |
|  |  | Addition boiler |  | 515.01 | RDP | Apr-22-2013 |  |  |
| 6 | 600kW Hydropower equip from Hangzhou Nannan | 6.6kV electrical equip | 1 pcs | 26,700.00 | PO 1236 Jul-25-2012 | Feb-7-2013 | 416,737.75 | Myongchon Cooperative Farm, Jangyon County, South Hwanghae Province Should be Transferred |
|  |  | control, measuring, protection | 1 pcs | 9,500.00 |  |  |  |  |
|  |  | power, control cable | 1 pcs | 24,500.00 |  |  |  |  |
|  |  | Hydro turbine | 2 pcs | 134,000.00 |  |  |  |  |
|  |  | Technical water supply system | 2 pcs | 6,000.00 |  |  |  |  |
|  |  | Electric generator | 2 pcs | 58,000.00 |  |  |  |  |
|  |  | Excitation system | 2 pcs | 10,200.00 |  |  |  |  |
|  |  | Transportation |  | 21,000.00 |  |  |  |  |
|  |  | Spare parts | 1 set | 9,500.00 |  |  |  |  |
|  |  | 400V switchgear | 1 pcs | 8,400.00 |  |  |  |  |
|  |  | Turbine inlet valves | 2 pcs | 39,000.00 |  |  |  |  |
|  |  | Governor system | 2 pcs | 23,000.00 |  |  |  |  |
|  |  | Supervision and installation |  | 28,961.59 |  | Sep-7-2013 |  |  |
|  |  | Testing and commissioning |  | 17,976.16 |  |  |  |  |
| 7 | Materials to provide biogas from Pigfarm to 20 houses in Mopung CoF | 1650m of Polyethylene pipes, 45pcs of Gas valves, 7pcs of T-connectors, 7pcs of 90-elbow, varying diameter connectors, 50pcs of pipe connectors, 3pcs of manometers, 55pcs of clamping band for gas pipe, 120pcs of sealing tape, 5pcs of gas flow meters, 20pcs of biogas stoves, 16pcs of biogas lamps |  |  |  |  | CNY 123,797.73 | Mopung Cooperative Farm, Anbyon County, Kangwon Province Should be Transferred |
| 8 | Household Biogas System |  | 20 pcs |  |  |  | € 70,376.20 | 5 pcs in each Cooperative Farm - Yaksu, Ryudong, Myongchon and Mopung CoF |
| 9 | Solar PV System |  | 500 pcs |  |  |  | € 230,200.00 | 218 pcs in Yaksu, 129 pcs in Ryudong, 33 pcs in Myongchon and 120 pcs in Mopung CoF |
| 10 | Solar Hot Water System |  | 40 pcs |  |  |  | € 35,340.00 | 10 pcs in each Cooperative Farm - Yaksu, Ryudong, Myongchon and Mopung CoF |

# Annex 6. Annual Work Plan

| ANNUAL WORK PLAN |
| --- |
|  | United Nations Development Programme |
|  | Year: | 2014 |
|  | Project Number: | 00050817, Award ID: 00043495 |
|  | Donor: | UNDP |
| DPRK | Project Title: | Sustainable Rural Energy Development (SRED) Programme |
| Expected Output | Key Activities | Targets | Timeframe | Resp. Partner | Planned Budget |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Code | Budget Description | 2014-2 | Increase/ Decrease | 2014-3 |
| Strengthened sustainable and efficient use of conventional energy and accessibility of alternative energy sources for local communities and households. | Output2. Rural energy demonstration projects implemented and running successfully. | Annual Target(2014): - Demonstration projects consisting of different mix of technologies implemented in the four target counties by the end of Project. |  |  |  |  | UNDP | 04000 | UNDP | 72300 | Internl Technical Supervision and installation of Solar Hot Water Systems in 4 project sites | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72400 | Equipment of Hydro Power Plants for Myongchon, spare parts, etc | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72200 | Equipment of Hydro Power Plants for Myongchon | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72400 | Internl Technical Supervision and installation of Myongchon HPP | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72200 | Internl Technical Supervision and installation of Biogas Systems for Mopung pigfarm and greenhouse | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72400 | Equipment and international technical supervision of Rice Husk Gasification Power system for Yaksu | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72400 | International Technical Supervision and installation of Rice Husk Gasification Power system in Yaksu | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72300 | Construction Materials of Rice Husk Gasification Power system for Yaksu | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Pre-Delivery Inspection of Rice Husk Gasification Power Generation Equipment | 0.00 | 0.00 | 0.00 |
|  |  |  |  | x | x | x | UNDP | 04000 | UNDP | 72400 | Solar Photovoltaic and Solar Hot Water System (instead of Rice Husk Gasification Power system), Energy Efficiency Stoves | 486,724.00 | -149,324 | 337,400.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local Technical Supervision on Solar Water Pumping | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local Technical Supervision on Myongchon Hydro Power Plant | 3,750.00 | 0.00 | 3,750.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local Technical Supervision on Renewable Energy Technologies (RET) | 39,598.00 | -39,598.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local Technical Supervision on Household Biogas System | 0.00 | 4,800.00 | 4,800.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local Technical Supervision on Solar PV and Solar Hot Water System | 0.00 | 2,500.00 | 2,500.00 |
|  |  |  | x | x | x |  | UNDP | 04000 | UNDP | 72100 | Local consultancy service for energy efficiency measures in 4 CoFs | 8,854.00 | -154.00 | 8,700.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72400 | Construction Materials to supply biogas from Pigfarm Biogas Plant to Households in Mopung CoF - total 20 houses | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Construction Materials for Pigfarm Biogas Systems and Greenhouse in 3 CoFs (Myongchon, Yaksu, Ryudong) | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x | x |  | UNDP | 04000 | UNDP | 72300 | Construction Materials for Household Biogas System with Greenhouse in 4 project sites - total 80 households | 120,000.00 | -27,000.00 | 93,000.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72200 | Energy Efficiency Biomass/Coal Stoves for 4 project sites | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local transportation of Rice Husk Gasification system | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72300 | Cement Foam for Energy Efficiency improvement in 4 project sites | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x |  |  | UNDP | 04000 | UNDP | 75700 | In-country Trainings for RE and EE end-users in 4 cooperatives | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local Technical Supervision on 3 Pigfarm Biogas System in 3 CoF | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72300 | Insulation materials for Pigfarm Biogas system in Mopung CoF | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 74700 | Transportation of Insulation materials of Pigfarm Biogas system to Mopung CoF | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x |  |  | UNDP | 04000 | UNDP | 74500 | Miscellaneous | 0.00 | 0.00 | 0.00 |
|  |  |  | Sub-Total |  |  |  |  |  | 658,926.00 |  | 450,150.00 |
|  | Output3. Capacity development needs at different levels identified and appropriate training programmes organized and implemented. |  |  |  |  |  | UNDP | 04000 | UNDP | 75700 | International Consultant on Integration of Sustainable Rural Energy in Education Curricular. | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 75700 | In-country Trainings Integration of Sustainable Rural Energy in Education Curricular | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 75700 | Debriefing Sessions for Knowledge Sharing and Dissemination by Participants in International Trainings | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local experts on development of local design criteria and standards for renewable energy and energy efficient technologies. | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | International Consultant on development of local capabilities in the Operation and Maintenance and Repair of RE and EE Equipments | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | International Consultant on development of local design criteria, establishment of testing facilities and quality standards for RE and EE technologies. | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local experts on establishment of testing facilities and quality standards for renewable energy and energy efficiency technologies. | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Feasibility Study and Redesigning of Ryudong Small Hydro Power | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 74500 | Miscellaneous | 0.00 | 0.00 | 0.00 |
|  |  |  | Sub-Total |  |  |  |  |  | 0.00 |  | 0.00 |
|  | Output4. Policies and mechanisms are put in place to address barriers and constraints to implement rural energy projects. |  |  |  |  |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  |  |  |  |  |  | 0.00 | 0.00 | 0.00 |
|  |  |  | Sub-Total |  |  |  |  |  | 0.00 |  | 0.00 |
|  | Output5. Compilation and dissemination of lessons learned and "Good Practices". | Annual Target(2014): - Project Development and Implementation Guides for different technologies completed by end of project; - Compilation of “good practices” report consisting of Case Studies of implemented projects completed and printed by end of project; - Monitoring continuously being done and evaluation conducted at end of project; - Information materials produced and information campaigns regularly conducted for the general public by end of project; - Seminars and other awareness-building campaigns for experts and end users conducted by end of project. | x | x | x |  | UNDP | 04000 | UNDP | 72100 | Publication of Guides and Manuals for Project Implementation Based on Each Technology That was Demonstrated and Publication of Report of case studies consisting good practices based on the implemented projects. | 25,000.00 | -25,000.00 | 0.00 |
|  |  |  | x | x | x |  | UNDP | 04000 | UNDP | 75700 | Consultations, Workshops, Roundtables and Trainings on Project development and implementation guides based on each technology that was demonstrated. | 25,000.00 | -25,000.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Publication of Report of case studies consisting good practices based on the implemented projects. | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x | x |  | UNDP | 04000 | UNDP | 74200 | Printing publications for awareness - building campaigns (1,000 copies in each technology). | 30,000.00 | -25,200.00 | 4,800.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 74200 | Preparation of publication for awareness | 0.00 | 8,700.00 | 8,700.00 |
|  |  |  | x | x |  |  | UNDP | 04000 | UNDP | 75700 | In-country seminars, workshops for public awareness. | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x |  |  | UNDP | 04000 | UNDP | 74500 | Miscellaneous | 0.00 | 0.00 | 0.00 |
|  |  |  | Sub-Total |  |  |  |  |  | 80,000.00 |  | 13,500.00 |
|  | Output6: New Successor Sustainable Rural Energy Development Programme formulated and designed | Annual Target(2014): - Pilot projects evaluated vis-à-vis standards and experiences on “good practices” by end of project; - Provinces/counties with the most potential for successor rural energy project identified by end of project; - Rural energy surveys and energy assessment of selected additional provinces/counties conducted by end of project; - Draft Project Document on the successor rural energy project prepared by end of project; - Institutional development context analyses for sustainable rural energy development by end of project. |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Research on Legal and Institutional Framework | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local experts on rural energy surveys and energy assessment for country wide household level & Identification of additional provinces/counties for follow up sustainable rural development programme. | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72100 | Local experts on rural energy surveys, energy assessment for rural area identification of additional provinces/counties and research on legal/institutional framework for new rural energy intervention development. | 70,000.00 | -8,000.00 | 62,000.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local consultants for Identification of additional provinces/counties for New Successor Sustainable Rural Energy Development Programme formulated and designed | 0.00 | 0.00 | 0.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 71200 | International Consultant for stocktaking on SRED activities and provision of New Successor Sustainable Rural Energy Development Programme formulated and designed | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 71200 | International Consultant on programme design, formulation and development of New Successor Sustainable Rural Energy Development Programme formulated and designed | 50,000.00 | -2,000.00 | 48,000.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 71600 | International consultant travel fee for mission |  | 15,000.00 | 15,000.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 71200 | International Consultant for backstopping of SRED programme | 0.00 | 4,8000.00 | 4,800.00 |
|  |  |  |  |  |  |  | UNDP | 04000 | UNDP | 72100 | Local experts on programme design, formulation and development of New Successor Sustainable Rural Energy Development Programme formulated and designed | 0.00 | 0.00 | 0.00 |
|  |  |  | x | x |  |  | UNDP | 04000 | UNDP | 75700 | Stakeholders' consultations on programme design, formulation and development of New Successor Sustainable Rural Energy Development Programme formulated and designed | 10,000.00 | -7,700.00 | 2,300.00 |
|  |  |  | x | x |  |  | UNDP | 04000 | UNDP | 75700 | SRED Project Steering Committee Meeting for TTPR | 1,000.00 | -800.00 | 200.00 |
|  |  |  | Sub-Total |  |  |  |  |  | 131,000.00 |  | 132,300.00 |
|  | Activity1: Project Management |  | x | x | x | x | UNDP | 04000 | UNDP | 71600 | International travel | 5,000.00 |  | 5,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 71300 | National Training Coordinator of SRED (salary) | 5,000.00 |  | 5,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 71400 | National staff (salaries) | 20,000.00 |  | 20,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 61300 | Salary & Post Adj Cst-PM | 229,000.00 |  | 229,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 62300 | Recurrent Payroll Costs-PM | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 63300 | Non-Recurrent Payroll - PM | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 61300 | Salary & Post Adj Cst-IP | 55,000.00 |  | 55,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 62300 | Recurrent Payroll Costs-IP | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 63300 | Non-Recurrent Payroll - IP | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 61300 | Salary & Post Adj Cst-M&E | 37,000.00 |  | 37,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 62300 | Recurrent Payroll Costs-M&E | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 63300 | Non-Recurrent Payroll - M&E | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 64300 | Reassignments - IP Staff | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 63500 | Insurance and Security Costs | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 65100 | After Service Insurance | 0.00 |  | 0.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 71600 | In-country travel | 20,000.00 | -14,000.00 | 6,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 73100 | Rental | 7,000.00 |  | 7,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72200 | Office equipments | 4,000.00 | -2,500.00 | 1,500.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72500 | Supplies | 3,000.00 | -1,000.00 | 2,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72300 | Fuel, Petrolium & other oils | 5,000.00 | -2,000.00 | 3,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72400 | Communication & Audio | 7,000.00 | -6,000.00 | 1,000.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72400 | UN Dispensary C/S | 0.00 | 31,500.00 | 31,500 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 72400 | I-Direct cost | 0.00 | 1,100.00 | 1,100 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 73400 | Maintenance of vehicle & other Equip | 3,000.00 | -2,500.00 | 500.00 |
|  |  |  | x | x | x | x | UNDP | 04000 | UNDP | 74500 | Miscellaneous | 6,322.00 | -5,822.00 | 500.00 |
|  |  |  | Sub-Total |  |  |  |  |  | 406,322.00 |  | 405,100.00 |
| GRAND TOTAL |  |  |  |  |  |  |  |  |  |  | 1,276,248.00 |  | 1,001,050.00 |

Annex 7.      Expected Delivery until end of October 2014 under SRED Programme

| Key Activities | Description of Activities | Budget (USD) | Remarks |
| --- | --- | --- | --- |
| Output2. Rural energy demonstration projects implemented and running successfully. | Solar Photovoltaic and Solar Hot Water System (instead of Rice Husk Gasification Power system), Energy Efficiency Stoves | 337,400 | Contract is signed. Expected delivery by end of October. |
|  | Local Technical Supervision on Household Biogas System | 4,800 | Contract is signed. Expected delivery by end of October. |
|  | Local Technical Supervision on Solar PV and Solar Hot Water System | 2,500 | Contract is signed. Expected delivery by end of October. |
| Sub-total | 344,700 |  |
| Output5. Compilation and dissemination of lessons learned and "Good Practices". | Printing publications for awareness - building campaigns (1,000 copies in each technology). | 4,800 | Contract is signed. Expected delivery by end of October. |
|  | Preparation of publication for awareness | 8,700 | Contract is signed. |
| Sub-total | 13,500 |  |
| Output6: New Successor Sustainable Rural Energy Development Programme formulated and designed | Local experts on rural energy surveys, energy assessment for rural area identification of additional provinces/counties and research on legal/institutional framework for new rural energy intervention development. | 62,000 | 1st Payment (10% of Contracted amount KPW 606,230) has been paid on August 2014. The contract is under terminating. The remained contracted amount is KPW 5,456,070 (90% of Contracted amount). After contract closer the budget on this line will reduce to USD 55,800 and become USD 6,200. In this case total delivery will be USD 496,900. |
|  | International Consultant on programme design, formulation and development of New Successor Sustainable Rural Energy Development Programme formulated and designed | 48,000 | Will work until December 2014. |
|  | International consultant (Remi) travel fee for mission | 15,000 | Will be paid by end of October. |
|  | SRED Project Steering Committee Meeting for TTPR | 200 | Will be done by 21 October 2014. |
| Sub-total | 125,200 |  |
| Activity1: Project Management | National staff (salaries) | 2,000 |  |
|  | International staff (salaries and others) | 32,100 |  |
|  | In-country travel | 2,000 | Will be paid by end of October. |
|  | UN Dispensary C/S | 31,500 |  |
|  | I-Direct cost | 1,100 |  |
|  | Rental for project office | 600 | Will be paid by end of October. |
| Sub-total | 69,300 |  |
| Grand Total | 552,700 |  |

# Footnotes

Ministry of Electric Power Industry

State Commission of Science and Technology

Ministry of Coal Industry

Ministry of Land and Environment Protection

Central Bureau for Statistics