## 1. Roles & Responsiblities
In Summary | Platform Management Unit | Country Office | GCP team | UNDP Regional / HQ
| Platform stakeholder engagement | Government liaison | Global stakeholder engagement | Global stakeholder engagement
| Fundraising | Fundraising | Fundraising | Technical advice
| Project management | Project strategy definition & implementation | Upfront guidance | Financial management
| Platform promotion | Coordinate project specific partnerships | Technical advice | Hiring & contracting
| M&E | Participate and budget for learning activities | Coordinate learning | IT systems
|  | Project promotion | Provide learning opporutnities | Due diligence
|  | Financial management | International promotion | M&E
|  | Leadership | M&E
Legal
Hiring & contracting
Due diligence
M&E
national commodity platforms | More detail per life cycle stage in guidance. | support | upfront guidance and training. | Financial transfers
|  | facilitate | technical advice | Partnership due diligence
| coordinate | smooth operations at political levels | annual visits | Technical advice.
national public private partnerships | Maintaining engagement in platform | Domestic private sector supply chain mapping | Providing upfront guidance and tools | Due diligence support
| Implement national commodity private sector engagement plan | Coordinating project specific partnerships | Connecting with global supply chains where influence needed
Due diligence
technical services | Same as, and in collaboration with, Country Office. | share needs with GCP | Upfront guidance on root cause analysis. | Webinar system
|  | Develop root cause analysis | Provide technical advice and connect with technical expertise.
Draft strategies, work plans, reports, terms of reference.
learning from action | provide updates | provide updates | Manage quality of online learning portal | Set up and maintain online learning portal contract
| use online portal | use online learning portal | Biannual learning survey
|  | Budget for participation in learning activities | Global facilitated webinars
|  | Budget and plan for study tours | Annual workshop (thematic and community of practice)
|  | Logistics for hosting study tours | Design & follow up of study tours
global engagement & dialogue | Project promotion | National promotion | Develop global ambassador group | Due diligence
|  | International conference presentations | International promotion
Private sector multinational partnerships
communications | Platform strategy definition & implementation | Project strategy definition & implementation | GCP strategy definition & implementation & guidance | Rules
Global partnerships
Upfront guidance
Training
resourcing | Timely reporting | Direct Fundraising locally | Upfront guidance | Donor liaison
| Private sector sponsorship | Networking to support global fundraising | Direct fundraising globally | Financial management
|  | Timely reporting | Progress reporting,
M&E | Platform indicator collection | Impact indicator definition per project | Agreement with CO per project on how outcome indicators will be collected
|  | Baseline collection | Outcome indicators measured on annual basis
Input to outcome indicators

## 2. Task Managers
Task Manager Role
1 | Project risk analysis in Atlas
2 | Coaching and ongoing training / support
3 | Project design quality review: Root cause analysis / ProDoc and budget review
4 | Project delivery according to plan
5 | Financial review
6 | Work plan review
7 | Providing / finding technical advice when requested
8 | Requesting Andrew’s help to remove blockages
9 | Support fundraising & reporting
10 | Identify partnerships / alliances that need global engagement
11 | Focus on GCP added value of the project (private sector partnerships, fundraising, communications)
NB. separate between this role and the Project Manager in country (and how it is different for GEF projects)

## 3. Working practices
The GCP team committed to the following collaborative practices:
Better to say no - feel safe to say no
Training and capacity building needs assessment of the GCP team (Tomo & Eliana made specific requests)
Regular team calls (bimonthly - twice a month on first and third Tuesday)
Team calendar online with donor reporting, team calls, webinars, missions, etc.
Keeping needs of external communications in mind all the time and sharing internally
Provides support & guidance in a consistent way with learning from action methodology.
More interaction between each other to address isolation
More regular 121s with line manager and with country offices
Biannual team meetings
Ad hoc teams for specific tasks - use these more formally with the team.
Group understanding and clear delegation of responsibility, roles and authority.
1 person for 1 country only - relationship management
Andrew will not be engaging in project planning / management, producing donor reporting, communications document preparation, travel, procurement, administration, platform trainings & process.
Andrew has to approve comms products, donor reports, tools/guidance, financing and travel.

## 4. 2015 milestones
2015 Milestones - Green Commodities Programme
|  |  | Q1 Review | Q2 Review | Q3 Review | End of year
National Commodity Platforms | Platform training program v1.0 launched delivering integration with DD, REDD, Gender and GEF teams | Lise
National Commodity Platforms | Teams and country office staff of active platforms have completed training program modules 1 & 2 | Lise
National Commodity Platforms | Portfolio National Commodity Platforms have a stakeholder engagement plan in place. | Lise
National Commodity Platforms | Platforms all have monitoring plans for collecting global indicators and any other project relevant success indicators. | Lise
National Public Private Partnerships | All guidance and tools from GCP to support national public private partnerships are finalised and available online. | Kate
National Public Private Partnerships | All platforms have a private sector engagement plan | Kate
National Public Private Partnerships | 2 public private partnership pilot projects developed as case studies (Indonesia smallholder training & Ghana Farmer project (not platform) | Tomo, Leif
Global engagement & dialogue | 2 exposures at global events (purpose fundraising) | Andrew
Global engagement & dialogue | List of 10 prioritised companies and 4 related engagement strategies completed (Cargill, ADM, Walmart, Mondelez) & under implementation | Andrew, Kate, Kifah
Global engagement & dialogue | 7 global organisation engagement strategies completed and under implementation. | Andrew, Kate, Leif
Technical Services | Cost recovery model for global technical services agreed with all project countries. CHANGED | Andrew
Technical Services | All category A project technical needs are identified and agreed with Country Office and project lead. | Task Managers
Technical Services | 1-2 global webinars take place on relevant topics | Lise
Technical Services | Root cause analysis completed and accessible for all projects | Andrew
Learning in action | Learning portal set up with more than 50 users | Kifah
Learning in action | Learning workshop & webinar calendar established and delivered to GCP CoP | Lise
Learning in action | Funding secured in line with plans for GCP study tours in 2016 & 2017 | Kifah
Learning in action | Run community of practice workshop around the National Commodity Platform training workshop in 2015. | Lise
Communications | All GCP materials adapted to fit GCP strategic plan and communications strategy. | Sam
Communications | Key GCP people trained on how to be GCP Ambassadors & GCP global are consistent in their messaging | Sam
Communications | 2 communication products on GCP partnering with GEF and with UN REDD programme. | Sam
Communications | All category A projects have communication strategies, approved by global comms officer | Sam
Resourcing | GCP global team capacity, time and responsibilities for fundraising strengthened | Andrew
Resourcing | Investment pitch finalised and tested on at least 3 donors | Sam
Resourcing | Fundraising strategies completed for each Category A country | Task Managers
Resourcing | At least 2 new donors committed at global level and 1 donor at a country level | Andrew
Resourcing | 100% of 2015 funds secured by Q2, and 100% of 2016 work plan funds secured by end of Q3 (either new donor or adjusted work plan) | Andrew
Management | 2015 Annual work plan and budget finalised | Andrew
Management | Training and capacity needs assessment of global team completed and financing options discussed. | Andrew
Management | 100% global team contracts are signed as per procurement plan. | Eliana
Management | Deputy Resident Representatives of Country Offices in the GCP portfolio demonstrate support for the projects and GCP globally | Task Managers
Management | Resident Representatives and/or Country Directors of GCP portfolio countries demonstrate political support for the projects and GCP globally | Andrew
Monitoring & Evaluation | Global M&E Framework finalised | Kifah

## 5.2015 Work Plan
Green Commodities Programme, 2015 Work Plan
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators | Notes / Changes
Management System | Financial management | Finalise 2015 work plan and prioritised budget | 2015-02-13 | Andrew | Lise, Eliana, Leif
Management System | GCP Planning | Standard mission objectives written and circulated | 2015-02-16 | Andrew | Lise
Monitoring & Evaluation | Reporting | Donor reporting for 2014 | 2015-02-20 | Tomo | Task Managers
Global engagement & dialogue | global ambassador group | Develop engagement strategy with UN-REDD to embed and codify the partnership for long term | 2015-03-01 | Andrew | Kifah, Lise
Global engagement & dialogue | international private sector | Finalise analysis of multi-national linkages and list of top 10 companies | 2015-03-01 | Andrew
Technical services | project design | review and consider current prortfolio and prirotise where to get root cause analysis done | 2015-03-01 | Andrew | Task Managers
Management System | Procurement | Officialise Taylor internship | 2015-03-01 | Eliana | Sam
Management System | GCP Planning | Contract renewal schedule and notification in advance to ensure no contract gaps | 2015-03-01 | Eliana | Andrew
Management System | GCP Planning | Procurement Plan for 2015 | 2015-03-01 | Eliana | Procurement Team
Resourcing | engagement strategies | Develop and share 1 page approach BIoFinn - pilot attempt in Costa Rica | 2015-03-01 | Kifah
Management System | GCP Planning | Finalise 2015-2017 GCP Strategic Plan | 2015-03-01 | Lise | Andrew
Communications | strategy | 2015 work plan | 42064 | Sam
Communications | team of ambassadors | Email signature - unify internally | 2015-03-01 | Sam
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Management System | GCP team operations | Set up and keep dropbox (GCP online information management) up to date | 2015-03-01 | Sam (Taylor) | Lise to get running
Monitoring & Evaluation | Reporting | Table of Contents for Annual Report (format) | 2015-03-01 | Tomo | Andrew to approve
Resourcing | engagement strategies | Develop and submit GEF IAP (deforestation free supply chain) project framework document | 2015-03-10 | JJ (1) | Andrew
Management System | Procurement | Elodie - part-time / full-time programme support | 2015-03-15 | Eliana | Andrew
Management System | Financial management | 3 year financial planning and monitoring | 2015-03-30 | Andrew | Leif
Communications | global recognition | identify stakeholder influencers and agree them | 2015-04-01 | Andrew
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Mondelez (make template with this one) | 2015-04-01 | Andrew | Leif, Sam
Resourcing | engagement strategies | Develop and share 1 page approach with UN REDD | 2015-04-01 | Andrew | Jyoti, Lise
Resourcing | engagement strategies | Develop and share 1 page approach IKI (Germans) | 2015-04-01 | Andrew | Jyoti & Leif
Resourcing | engagement strategies | Develop and share 1 page approach with SECO (update after March) | 2015-04-01 | Andrew | Leif
Resourcing | engagement strategies | Develop and share 1 page approach with DANIDA | 2015-04-01 | Andrew | Leif
Resourcing | engagement strategies | Develop and share 1 page approach UNDP Env Trust Fund long term | 2015-04-01 | Andrew
Resourcing | national strategies | provide guidance framework for national teams to fundraise at local level | 2015-04-01 | Andrew | Task Managers
Resourcing | process & pitch | Define process for submission of a fundraising proposal | 2015-04-01 | Andrew
Technical services | cost recovery model | Define GCP day rate for cost recovery of technical services | 2015-04-01 | Andrew
Technical services | cost recovery model | Write overview of GCP offer to country office - menu of services, integrating all delivery strategies and being very specific | 2015-04-01 | Andrew
Learning in Action | CoP | Financial arranagements | 2015-04-01 | Eliana | Andrew
Management System | Financial management | Prepare for an audit | 2015-04-01 | Eliana | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach CLUA - Global | 2015-04-01 | Jyoti | Tomo
Resourcing | engagement strategies | Develop and share 1 page approach Green Climate Fund | 2015-04-01 | Jyoti | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach with EU | 2015-04-01 | Jyoti | Andrew
Communications | products | Assist with revision of script and narration for CR video (land use) | 2015-04-01 | Kifah | Sam
Learning in Action | Facilitated learning | Planning & designing webinars | 2015-04-01 | Kifah | Eliana
Monitoring & Evaluation | Tool development | Finalising and writing GCP M&E framework | 2015-04-01 | Kifah | Tomo, JJ, Leif, Lise
Global engagement & dialogue | global ambassador group | Develop and share 1 page approach for engagement with World Cocoa Foundation - For Ghana only | 2015-04-01 | Leif | Andrew | This should coincide with my mission to Ghana, tentatively April. Also, depends heavily on what will happen in the platform
Global engagement & dialogue | global ambassador group | Develop engagement strategy with ICCO - For Ghana only. | 2015-04-01 | Leif | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Cambio 2 | 2015-04-01 | Leif (1) | Andrew
Learning in Action | CoP | Planning & logistics of workshop | 2015-04-01 | Lise | Intern/Elodie
Learning in Action | Facilitated learning | Calendar of L4A events | 2015-04-01 | Lise | Kifah, Andrew
National Commodity Platforms | guidance | write and finalise methodology guidance | 2015-04-01 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | sponsorship | guidance on how to get sponsorship for Category A only | 2015-04-01 | Lise | Kifah
Communications | global recognition | Article - guardian | 2015-04-01 | Sam | Andrew
Communications | products | finish fact sheets and put on line (CR, DR, INDO, Platforms, Ghana) | 2015-04-01 | Sam | Taylor
Communications | strategy | Final external communications strategy | 42095 | Sam
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Management System | GCP team operations | Internal communications tools to be set up | 2015-04-01 | Sam (Taylor)
Global engagement & dialogue | global ambassador group | Develop engagement strategy with Consumer Goods Forum (TFA) | 2015-05-01 | Andrew | Tomo, Kate, Jyoti
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with ADM | 2015-05-01 | Andrew | Tomo, Leif, Lise, JJ
Management System | Procurement | Eliana position - shift from staff to consultant | 2015-05-01 | Andrew
Resourcing | cost recovery model | All global workshop participation is funded from project / country budgets. | 2015-05-01 | Andrew
Technical services | project design | Integration of gender mainstreaming into our work - in platforms | 2015-05-01 | Andrew | Intern?
Management System | Procurement | IC contract for Kate signed | 2015-05-01 | Eliana | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Moore Foundation | 2015-05-01 | JJ | Andrew
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Walmart | 2015-05-01 | Kifah | Andrew, Kate, JJ, Lise
Learning in Action | Learning Portal | Set up / administration of learning portal | 2015-05-01 | Kifah | Lise
Monitoring & Evaluation | Tool development | Impact indicators proposal | 2015-05-01 | Kifah | Tomo
National Commodity Platforms | training | launch of v1.0 | 2015-05-01 | Lise | Sam
Resourcing | engagement strategies | Develop and share 1 page approach SIDA | 2015-05-01 | Lise | Andrew
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Japan UNDP Partnership Fund for global & Indonesia | 2015-05-01 | Tomo | Kifah
National Commodity Platforms | guidance | develop & finalise tools | 2015-05-15 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | guidance | develop& finalise templates | 2015-05-15 | Lise | Kifah, Leif, Andrew
Global engagement & dialogue | global ambassador group | World Economic Forum engagement strategy | 2015-05-20 | Andrew | Jyoti
Global engagement & dialogue | fundraising / promotion | ISEAL Annual conference > Donors | 2015-05-20 | Lise
Resourcing | cost recovery model | Draft model developed and being negotiated with GEF | 2015-06-01 | Andrew
National Commodity Platforms | training | global training workshop (procurement and logistics) | 2015-06-01 | Eliana | Intern/Elodie, Lise
Management System | GEF Programme Design | Designing Paraguay GEF project | 2015-06-01 | JJ | Kifah
Management System | GEF Programme Design | Ensuring Peru GEF project fits into larger GEF project | 2015-06-01 | JJ | Leif
Management System | GEF Programme Design | Designing indonesia GEF project | 2015-06-01 | JJ | Tomo
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with Cargill | 2015-06-01 | Kate | Tomo, Leif, Lise, JJ
National public private partnerships | engagement plan | provide guidance on how to write plan (template) | 2015-06-01 | Kate | Lise, JJ
National public private partnerships | prioritise national level | provide guidance on how to do analysis (engage team via call) | 2015-06-01 | Kate | JJ, Lise, Andrew
National Commodity Platforms | guidance | Translation of all guidance into Spanish | 2015-06-01 | Kifah | Lise
Communications | products | Position paper - UNDP & REDD with a guidance doc to UN REDD on REDD and commodities | 2015-06-01 | Leif | Sam | Responsibility and collaborator should probably be switched around. Sam will help polish, but this is heavy on contents, and I think I will have to write it.
Resourcing | engagement strategies | Write a study showing in theory how GCP contributes to eradicating poverty | 2015-06-01 | Leif | Intern
National Commodity Platforms | guidance | USBs designed with all guidance | 2015-06-01 | Lise | Eliana
National Commodity Platforms | guidance | Video introducing platforms | 2015-06-01 | Lise | Sam
National Commodity Platforms | sharing & promoting | set up learning history tracking | 2015-06-01 | Lise | Kifah
National Commodity Platforms | training | design v1.0 of training program | 2015-06-01 | Lise | Kifah, Sam
National Commodity Platforms | training | coordination with Demoractic Dialogue team | 2015-06-01 | Lise | Andrew
National Commodity Platforms | training | coordination with ISEAL | 2015-06-01 | Lise | Andrew
Communications | products | GCP Highlights/Fast Facts - including links to stories from the field (considering gender and other cross-cutting themes) | 2015-06-01 | Sam | Andrew, Tomo
Communications | team of ambassadors | 1 master power point slide deck to pick from to pitch GCP (including procurement of designer) | 2015-06-01 | Sam
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
National Commodity Platforms | training | training of trainers (Leif - Kifah) in person (pre global delivery) | 2015-06-15 | Lise | Kifah, Leif | Will we do this in Istanbul? Perhaps add on a few days for this in-person
Learning in Action | CoP | Design & facilitation of workshop day | 2015-06-20 | Lise | Kifah
Communications | platforms | provide training on effective communication skills and developing a communications strategy | 2015-06-20 | Sam | Lise
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Management System | Procurement | Finance & Admin Assistant | 2015-07-01 | Andrew | Eliana
Learning in Action | Learning Portal | annual learning survey to users or portal - design & set up (run onc ein 2015 through CoP workshop) | 2015-07-01 | Intern
Global engagement & dialogue | global ambassador group | Develop engagement strategy with IDH to get full support and recognition for what GCP does | 2015-07-01 | Kate | Kifah, Lise
Global engagement & dialogue | global ambassador group | Develop engagement strategy with RSPO | 2015-07-01 | Kate | Tomo, JJ, Sam
National public private partnerships | guidance | private sector pitch framework written and kept updated | 2015-07-01 | Kate | Andrew, JJ, Sam
Communications | products | Position paper - how GCP reduces deforestation | 2015-07-01 | Sam | JJ
National public private partnerships | guidance | private sector presentation template and tips to pitch (key principles to follow when talking to the private sector) | 2015-07-01 | Sam | Kate, Andrew, JJ
Management System | Procurement | ToR & Hiring process for Global Fisheries Platform Coordinator | 2015-07-30 | Andrew | Lise, Kifah
National Commodity Platforms | training | coordination with UNREDD | 2015-08-01 | Lise | Andrew
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Management System | Country Office engagement | Getting regional bureaus and Country Office Directors and Res Reps on board with GCP for Category A & B countries | 2015-09-01 | Andrew
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers | This should be done with an expert facilitator. Perhaps half a day in a workshop setting
National Commodity Platforms | training | coordination with gender mainstreaming and with GAIN-UNDP (integrity module) | 2015-09-01 | Lise | Kifah, Sam
Technical services | project design | provide advice to project designers on how to prepare root cause analysis | 2015-09-01 | Task Managers
Management System | UNDP engagement | Develop alliance with other SD clusters in UNDP - Green Economy and Jobs & Livelihoods | 2015-10-01 | Andrew
Global engagement & dialogue | fundraising / promotion | Consumer Goods Forum event - Steering Committee meeting linked with Mondelez | 2015-10-01 | Kate | Andrew, Tomo
National public private partnerships | guidance | provide support on how to develop and implement 5P projects | 2015-10-01 | Kate | Lise, JJ
Communications | products | GCP video - using photos/CGI/narration | 2015-10-01 | Sam | Lise
Global engagement & dialogue | fundraising / promotion | IDH conference - Amsterdam | 2015-11-01 | Kate | Kifah
Learning in Action | South-south coop. | Finalise study tour plan for 2016 & 2017 (funds having been secured at project level - GEF) | 2015-11-01 | Kifah | Andrew
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Global engagement & dialogue | fundraising / promotion | RSPO annual meeting (RT13) | 2015-11-01 | Tomo | Kate
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Management System | GCP Planning | Training and capacity needs assessment of global team completed and financing options discussed. | 2015-12-01 | Andrew | Lise
Learning in Action | South-south coop. | Planning & organising study tour between CR and Indonesia for 2016 on land use monitoring | 2015-12-01 | Kifah | Tomo
Learning in Action | South-south coop. | Neogtiating budgets / costs with CO for CR-Indonesia trip | 2015-12-01 | Kifah
National Commodity Platforms | training | 121 coaching (1 mission per category A country focussed on platforms) - Lise will do Indonesia. | 2015-12-01 | Lise | Kifah, Leif, Tomo, Kate
National Commodity Platforms | measuring success | annual report input on results of national platforms | 2015-12-20 | Lise | Sam
Management System | Task Management | Costa Rica – Platform – pineapple | A / High | Kifah
Management System | Task Management | Ethiopia – Platform - coffee | A / High | Leif
Management System | Task Management | Ghana – Platform - cocoa | A / High | Leif
Management System | Task Management | Dominican Republic – platform – cocoa | A / High | Leif
Management System | Task Management | Peru – platform – palm oil | A / High | Leif
Management System | Task Management | Indonesia – platform – palm oil | A / High | Tomo
Management System | Task Management | Brazil – Platform – soy/cattle | A / Low | JJ
Management System | Task Management | Paraguay – platform – soy & cattle | A / Medium | Kifah
Management System | Task Management | Ghana - ESP | A / Medium | Leif
Management System | Task Management | Honduras – platform – cattle | A / Medium | Leif
Management System | Task Management | Peru – platform – cocoa & coffee | A / Medium | Leif
Management System | Task Management | Indonesia – other stuff | A / Medium | Tomo
Technical services | project implementation | annual mission to project with specific and standard objectives (additional specific ones can be added) | annual | Task Managers
Management System | Task Management | Cote d’Ivoire – REDD - cocoa | B / Low | Kate
Management System | Task Management | Costa Rica – Platform - fisheries | B / Very low | Andrew (until global coordinator) | Kifah
Management System | Task Management | Ecuador – platform – fisheries | B / very low | Andrew (until global coordinator)
Management System | Task Management | Indonesia - fisheries | B / very low | Andrew (until global coordinator) | Tomo
Management System | Task Management | Philippines – Platform - fisheries | B / very low | Andrew (until global coordinator) | Tomo
Management System | Task Management | Guatemala – platform – coffee | B / very low | Leif
Monitoring & Evaluation | Tool development | Policy enforcement scorecard development | Delay to 2016 | Andrew | Leif
Management System | GCP team operations | Bimonthly team calls | every 2 weeks | Eliana for set up and coordination | Andrew for agenda
Management System | Financial management | Provide monthly Financial Atlas reports for GCP proejcts to task managers | monthly | Eliana
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Learning in Action | CoP | Oversight & leadership | ongoing | Andrew
Management System | GEF Programme Design | Steering Committee engagement | ongoing | Andrew | JJ
National Commodity Platforms | training | liaison with CO Heads for support | ongoing | Andrew | Lise
Resourcing | cost recovery model | All category B projects are supported based on strategic plan cost recovery rules. | ongoing | Andrew
National public private partnerships | engagement plan | write private sector engagement plan | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | develop specific engagement strategies / actor | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular informal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular formal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | prioritise national level | sector / supply chain analysis | ongoing | COUNTRY OFFICE / PMU | Task Managers
Management System | Procurement | Consultants for PPG stage of GEF | ongoing | JJ | (GEF support)
Resourcing | GEF coordination | IAP design activities, budget and team to maximise alignment | ongoing | JJ | Andrew, Tomo, Leif, Kifah
Monitoring & Evaluation | Tool development | Promotion to UN-REDD of land use monitoring tool in Costa Rica | ongoing | Kifah | Tomo
National Commodity Platforms | training | coordination | ongoing | Lise | Andrew
National Commodity Platforms | training | quality assurance | ongoing | Lise | Andrew
Learning in Action | Learning Portal | Developing material for learning portal | ongoing | Lise Platforms/ Sam Com
Communications | global recognition | establish effective webiste in line with strategy (review by 01-April) | ongoing | Sam
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | platforms | review platform communication strategies and provide advice | ongoing | Sam | Leif, Tomo, Kifah
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Communications | team of ambassadors | Local comms liaison - Ghana | ongoing | Sam | Leif
Communications | team of ambassadors | Local comms liaison - Indonesia | ongoing | Sam | Tomo
Communications | team of ambassadors | Local comms liaison - DR | ongoing | Sam | Leif
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
Management System | Country Office engagement | Weekly or Bi-weekly 121s with project contacts (depending on project needs) | ongoing | Task Managers
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National public private partnerships | risk management | risk management plans set up and managed for both platform and project engagement beyond due diligence process | ongoing | Task Managers |  | I'm not sure I understand this. Is this the risk management in Atlas? Also, often we have limited tools to control risks, which is a real weakness in GCP. Essentially we try to influence others, but we have little formal say in things.
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project implementation | review and provide comments that are taken on board for annual work plans | ongoing | Task Managers
Technical services | project implementation | review and steer for high quality strategies (tehcnical / engagment) | ongoing | Task Managers
Technical services | project implementation | review and provide comments that are taken on board for Terms of References | ongoing | Task Managers
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew
Communications | products | Media coverage of palm oil work in Indonesia | ongoing | Tomo
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
National Commodity Platforms | guidance | Provide needs and request based support to roll out of Indonesia Sustainable Palm Oil Platform | ongoing | Tomo | Lise
National Commodity Platforms | sharing & promoting | promotion of NCP concept by comms | ongoing from Aug | Sam | Lise
Communications | internal comms | Flickr account | Q1 & ongoing | Sam | Taylor
Learning in Action | Facilitated learning | learning focussed team calls | quarterly | Andrew | Eliana
Learning in Action | South-south coop. | reporting on study tours | within 1 week | Study tour manager
Communications | global recognition | Develop & publish communiques on partnership with GEF and separately with UNREDD |  | Sam
Communications | strategy | integrate communications into UNDP & UN ("One UN") |  | Sam
Communications | strategy | Enable global team to embody the communications strategy |  | Sam
Communications | strategy | Enable country offices and project teams to take their cue from the strategy |  | Sam
Communications | strategy | key messaging adopted for top 5 stakeholder groups - government, producers, buyers, civil society (NGOs), donors |  | Sam

## 5.1 Andrew
Andrew Bovarnick
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | Financial management | Finalise 2015 work plan and prioritised budget | 2015-02-13 | Andrew | Lise, Eliana, Leif
Management System | GCP Planning | Standard mission objectives written and circulated | 2015-02-16 | Andrew | Lise
Monitoring & Evaluation | Reporting | Donor reporting for 2014 | 2015-02-20 | Tomo | Task Managers
Global engagement & dialogue | global ambassador group | Develop engagement strategy with UN-REDD to embed and codify the partnership for long term | 2015-03-01 | Andrew | Kifah, Lise
Global engagement & dialogue | international private sector | Finalise analysis of multi-national linkages and list of top 10 companies | 2015-03-01 | Andrew
Technical services | project design | review and consider current prortfolio and prirotise where to get root cause analysis done | 2015-03-01 | Andrew | Task Managers
Technical services | project design | review and consider current prortfolio and prirotise where to get root cause analysis done | 2015-03-01 | Andrew | Task Managers
Management System | GCP Planning | Contract renewal schedule and notification in advance to ensure no contract gaps | 2015-03-01 | Eliana | Andrew
Management System | GCP Planning | Finalise 2015-2017 GCP Strategic Plan | 2015-03-01 | Lise | Andrew
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Monitoring & Evaluation | Reporting | Table of Contents for Annual Report (format) | 2015-03-01 | Tomo | Andrew to approve
Resourcing | engagement strategies | Develop and submit GEF IAP (deforestation free supply chain) project framework document | 2015-03-10 | JJ (1) | Andrew
Management System | Procurement | Elodie - part-time / full-time programme support | 2015-03-15 | Eliana | Andrew
Management System | Financial management | 3 year financial planning and monitoring | 2015-03-30 | Andrew | Leif
Communications | global recognition | identify stakeholder influencers and agree them | 2015-04-01 | Andrew
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Mondelez (make template with this one) | 2015-04-01 | Andrew | Leif, Sam
Resourcing | engagement strategies | Develop and share 1 page approach with UN REDD | 2015-04-01 | Andrew | Jyoti, Lise
Resourcing | engagement strategies | Develop and share 1 page approach IKI (Germans) | 2015-04-01 | Andrew | Jyoti & Leif
Resourcing | engagement strategies | Develop and share 1 page approach with SECO (update after March) | 2015-04-01 | Andrew | Leif
Resourcing | engagement strategies | Develop and share 1 page approach with DANIDA | 2015-04-01 | Andrew | Leif
Resourcing | engagement strategies | Develop and share 1 page approach UNDP Env Trust Fund long term | 2015-04-01 | Andrew
Resourcing | national strategies | provide guidance framework for national teams to fundraise at local level | 2015-04-01 | Andrew | Task Managers
Resourcing | national strategies | provide guidance framework for national teams to fundraise at local level | 2015-04-01 | Andrew | Task Managers
Resourcing | process & pitch | Define process for submission of a fundraising proposal | 2015-04-01 | Andrew
Technical services | cost recovery model | Define GCP day rate for cost recovery of technical services | 2015-04-01 | Andrew
Technical services | cost recovery model | Write overview of GCP offer to country office - menu of services, integrating all delivery strategies and being very specific | 2015-04-01 | Andrew
Learning in Action | CoP | Financial arranagements | 2015-04-01 | Eliana | Andrew
Management System | Financial management | Prepare for an audit | 2015-04-01 | Eliana | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Green Climate Fund | 2015-04-01 | Jyoti | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach with EU | 2015-04-01 | Jyoti | Andrew
Global engagement & dialogue | global ambassador group | Develop and share 1 page approach for engagement with World Cocoa Foundation - For Ghana only | 2015-04-01 | Leif | Andrew | This should coincide with my mission to Ghana, tentatively April. Also, depends heavily on what will happen in the platform
Global engagement & dialogue | global ambassador group | Develop engagement strategy with ICCO - For Ghana only. | 2015-04-01 | Leif | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Cambio 2 | 2015-04-01 | Leif (1) | Andrew
Learning in Action | Facilitated learning | Calendar of L4A events | 2015-04-01 | Lise | Kifah, Andrew
National Commodity Platforms | guidance | write and finalise methodology guidance | 2015-04-01 | Lise | Kifah, Leif, Andrew
Communications | global recognition | Article - guardian | 2015-04-01 | Sam | Andrew
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | global ambassador group | Develop engagement strategy with Consumer Goods Forum (TFA) | 2015-05-01 | Andrew | Tomo, Kate, Jyoti
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with ADM | 2015-05-01 | Andrew | Tomo, Leif, Lise, JJ
Management System | Procurement | Eliana position - shift from staff to consultant | 2015-05-01 | Andrew
Resourcing | cost recovery model | All global workshop participation is funded from project / country budgets. | 2015-05-01 | Andrew
Technical services | project design | Integration of gender mainstreaming into our work - in platforms | 2015-05-01 | Andrew | Intern?
Management System | Procurement | IC contract for Kate signed | 2015-05-01 | Eliana | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Moore Foundation | 2015-05-01 | JJ | Andrew
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Walmart | 2015-05-01 | Kifah | Andrew, Kate, JJ, Lise
Resourcing | engagement strategies | Develop and share 1 page approach SIDA | 2015-05-01 | Lise | Andrew
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
National Commodity Platforms | guidance | develop & finalise tools | 2015-05-15 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | guidance | develop& finalise templates | 2015-05-15 | Lise | Kifah, Leif, Andrew
Global engagement & dialogue | global ambassador group | World Economic Forum engagement strategy | 2015-05-20 | Andrew | Jyoti
Resourcing | cost recovery model | Draft model developed and being negotiated with GEF | 2015-06-01 | Andrew
National public private partnerships | prioritise national level | provide guidance on how to do analysis (engage team via call) | 2015-06-01 | Kate | JJ, Lise, Andrew
National Commodity Platforms | training | coordination with Demoractic Dialogue team | 2015-06-01 | Lise | Andrew
National Commodity Platforms | training | coordination with ISEAL | 2015-06-01 | Lise | Andrew
Communications | products | GCP Highlights/Fast Facts - including links to stories from the field (considering gender and other cross-cutting themes) | 2015-06-01 | Sam | Andrew, Tomo
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Management System | Procurement | Finance & Admin Assistant | 2015-07-01 | Andrew | Eliana
National public private partnerships | guidance | private sector pitch framework written and kept updated | 2015-07-01 | Kate | Andrew, JJ, Sam
National public private partnerships | guidance | private sector presentation template and tips to pitch (key principles to follow when talking to the private sector) | 2015-07-01 | Sam | Kate, Andrew, JJ
Management System | Procurement | ToR & Hiring process for Global Fisheries Platform Coordinator | 2015-07-30 | Andrew | Lise, Kifah
National Commodity Platforms | training | coordination with UNREDD | 2015-08-01 | Lise | Andrew
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Management System | Country Office engagement | Getting regional bureaus and Country Office Directors and Res Reps on board with GCP for Category A & B countries | 2015-09-01 | Andrew
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers | This should be done with an expert facilitator. Perhaps half a day in a workshop setting
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers | This should be done with an expert facilitator. Perhaps half a day in a workshop setting
Technical services | project design | provide advice to project designers on how to prepare root cause analysis | 2015-09-01 | Task Managers
Management System | UNDP engagement | Develop alliance with other SD clusters in UNDP - Green Economy and Jobs & Livelihoods | 2015-10-01 | Andrew
Global engagement & dialogue | fundraising / promotion | Consumer Goods Forum event - Steering Committee meeting linked with Mondelez | 2015-10-01 | Kate | Andrew, Tomo
Learning in Action | South-south coop. | Finalise study tour plan for 2016 & 2017 (funds having been secured at project level - GEF) | 2015-11-01 | Kifah | Andrew
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Management System | GCP Planning | Training and capacity needs assessment of global team completed and financing options discussed. | 2015-12-01 | Andrew | Lise
Technical services | project implementation | annual mission to project with specific and standard objectives (additional specific ones can be added) | annual | Task Managers
Management System | Task Management | Costa Rica – Platform - fisheries | B / Very low | Andrew (until global coordinator) | Kifah
Management System | Task Management | Ecuador – platform – fisheries | B / very low | Andrew (until global coordinator)
Management System | Task Management | Indonesia - fisheries | B / very low | Andrew (until global coordinator) | Tomo
Management System | Task Management | Philippines – Platform - fisheries | B / very low | Andrew (until global coordinator) | Tomo
Monitoring & Evaluation | Tool development | Policy enforcement scorecard development | Delay to 2016 | Andrew | Leif
Management System | GCP team operations | Bimonthly team calls | every 2 weeks | Eliana for set up and coordination | Andrew for agenda
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Learning in Action | CoP | Oversight & leadership | ongoing | Andrew
Management System | GEF Programme Design | Steering Committee engagement | ongoing | Andrew | JJ
National Commodity Platforms | training | liaison with CO Heads for support | ongoing | Andrew | Lise
Resourcing | cost recovery model | All category B projects are supported based on strategic plan cost recovery rules. | ongoing | Andrew
National public private partnerships | engagement plan | write private sector engagement plan | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | develop specific engagement strategies / actor | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular informal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular formal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | prioritise national level | sector / supply chain analysis | ongoing | COUNTRY OFFICE / PMU | Task Managers
Resourcing | GEF coordination | IAP design activities, budget and team to maximise alignment | ongoing | JJ | Andrew, Tomo, Leif, Kifah
National Commodity Platforms | training | coordination | ongoing | Lise | Andrew
National Commodity Platforms | training | quality assurance | ongoing | Lise | Andrew
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Samantha | Everyone
Management System | Country Office engagement | Weekly or Bi-weekly 121s with project contacts (depending on project needs) | ongoing | Task Managers
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National public private partnerships | risk management | risk management plans set up and managed for both platform and project engagement beyond due diligence process | ongoing | Task Managers |  | I'm not sure I understand this. Is this the risk management in Atlas? Also, often we have limited tools to control risks, which is a real weakness in GCP. Essentially we try to influence others, but we have little formal say in things.
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project implementation | review and provide comments that are taken on board for annual work plans | ongoing | Task Managers
Technical services | project implementation | review and steer for high quality strategies (tehcnical / engagment) | ongoing | Task Managers
Technical services | project implementation | review and provide comments that are taken on board for Terms of References | ongoing | Task Managers
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
Learning in Action | Facilitated learning | learning focussed team calls | quarterly | Andrew | Eliana

## 5.2 Eliana
Eliana Garlarza (100%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | Financial management | Finalise 2015 work plan and prioritised budget | 2015-02-13 | Andrew | Lise, Eliana, Leif
Management System | Procurement | Officialise Taylor internship | 2015-03-01 | Eliana | Sam
Management System | GCP Planning | Contract renewal schedule and notification in advance to ensure no contract gaps | 2015-03-01 | Eliana | Andrew
Management System | GCP Planning | Procurement Plan for 2015 | 2015-03-01 | Eliana | Procurement Team
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Management System | Procurement | Elodie - part-time / full-time programme support | 2015-03-15 | Eliana | Andrew
Learning in Action | CoP | Financial arranagements | 2015-04-01 | Eliana | Andrew
Management System | Financial management | Prepare for an audit | 2015-04-01 | Eliana | Andrew
Learning in Action | Facilitated learning | Planning & designing webinars | 2015-04-01 | Kifah | Eliana
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Management System | Procurement | IC contract for Kate signed | 2015-05-01 | Eliana | Andrew
National Commodity Platforms | training | global training workshop (procurement and logistics) | 2015-06-01 | Eliana | Intern/Elodie, Lise
National Commodity Platforms | guidance | USBs designed with all guidance | 2015-06-01 | Lise | Eliana
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Management System | Procurement | Finance & Admin Assistant | 2015-07-01 | Andrew | Eliana
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Management System | GCP team operations | Bimonthly team calls | every 2 weeks | Eliana for set up and coordination | Andrew for agenda
Management System | Financial management | Provide monthly Financial Atlas reports for GCP proejcts to task managers | monthly | Eliana
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Samantha | Everyone
Learning in Action | Facilitated learning | learning focussed team calls | quarterly | Andrew | Eliana

## 5.3 Leif
Leif Pederson (100%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | Financial management | Finalise 2015 work plan and prioritised budget | 2015-02-13 | Andrew | Lise, Eliana, Leif
Monitoring & Evaluation | Reporting | Donor reporting for 2014 | 2015-02-20 | Tomo | Task Managers
Technical services | project design | review and consider current prortfolio and prirotise where to get root cause analysis done | 2015-03-01 | Andrew | Task Managers
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Management System | Financial management | 3 year financial planning and monitoring | 2015-03-30 | Andrew | Leif
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Mondelez (make template with this one) | 2015-04-01 | Andrew | Leif, Sam
Resourcing | engagement strategies | Develop and share 1 page approach IKI (Germans) | 2015-04-01 | Andrew | Jyoti & Leif
Resourcing | engagement strategies | Develop and share 1 page approach with SECO (update after March) | 2015-04-01 | Andrew | Leif
Resourcing | engagement strategies | Develop and share 1 page approach with DANIDA | 2015-04-01 | Andrew | Leif
Resourcing | national strategies | provide guidance framework for national teams to fundraise at local level | 2015-04-01 | Andrew | Task Managers
Monitoring & Evaluation | Tool development | Finalising and writing GCP M&E framework | 2015-04-01 | Kifah | Tomo, JJ, Leif, Lise
Global engagement & dialogue | global ambassador group | Develop and share 1 page approach for engagement with World Cocoa Foundation - For Ghana only | 2015-04-01 | Leif | Andrew | This should coincide with my mission to Ghana, tentatively April. Also, depends heavily on what will happen in the platform
Global engagement & dialogue | global ambassador group | Develop engagement strategy with ICCO - For Ghana only. | 2015-04-01 | Leif | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Cambio 2 | 2015-04-01 | Leif (1) | Andrew
National Commodity Platforms | guidance | write and finalise methodology guidance | 2015-04-01 | Lise | Kifah, Leif, Andrew
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with ADM | 2015-05-01 | Andrew | Tomo, Leif, Lise, JJ
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
National Commodity Platforms | guidance | develop & finalise tools | 2015-05-15 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | guidance | develop& finalise templates | 2015-05-15 | Lise | Kifah, Leif, Andrew
Management System | GEF Programme Design | Ensuring Peru GEF project fits into larger GEF project | 2015-06-01 | JJ | Leif
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with Cargill | 2015-06-01 | Kate | Tomo, Leif, Lise, JJ
Communications | products | Position paper - UNDP & REDD with a guidance doc to UN REDD on REDD and commodities | 2015-06-01 | Leif | Sam | Responsibility and collaborator should probably be switched around. Sam will help polish, but this is heavy on contents, and I think I will have to write it.
Resourcing | engagement strategies | Write a study showing in theory how GCP contributes to eradicating poverty | 2015-06-01 | Leif | Intern
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
National Commodity Platforms | training | training of trainers (Leif - Kifah) in person (pre global delivery) | 2015-06-15 | Lise | Kifah, Leif | Will we do this in Istanbul? Perhaps add on a few days for this in-person
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers | This should be done with an expert facilitator. Perhaps half a day in a workshop setting
Technical services | project design | provide advice to project designers on how to prepare root cause analysis | 2015-09-01 | Task Managers
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
National Commodity Platforms | training | 121 coaching (1 mission per category A country focussed on platforms) - Lise will do Indonesia. | 2015-12-01 | Lise | Kifah, Leif, Tomo, Kate
Management System | Task Management | Ethiopia – Platform - coffee | A / High | Leif
Management System | Task Management | Ghana – Platform - cocoa | A / High | Leif
Management System | Task Management | Dominican Republic – platform – cocoa | A / High | Leif
Management System | Task Management | Peru – platform – palm oil | A / High | Leif
Management System | Task Management | Ghana - ESP | A / Medium | Leif
Management System | Task Management | Honduras – platform – cattle | A / Medium | Leif
Management System | Task Management | Peru – platform – cocoa & coffee | A / Medium | Leif
Technical services | project implementation | annual mission to project with specific and standard objectives (additional specific ones can be added) | annual | Task Managers
Management System | Task Management | Guatemala – platform – coffee | B / very low | Leif
Monitoring & Evaluation | Tool development | Policy enforcement scorecard development | Delay to 2016 | Andrew | Leif
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
National public private partnerships | engagement plan | write private sector engagement plan | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | develop specific engagement strategies / actor | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular informal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular formal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | prioritise national level | sector / supply chain analysis | ongoing | COUNTRY OFFICE / PMU | Task Managers
Resourcing | GEF coordination | IAP design activities, budget and team to maximise alignment | ongoing | JJ | Andrew, Tomo, Leif, Kifah
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | platforms | review platform communication strategies and provide advice | ongoing | Sam | Leif, Tomo, Kifah
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Communications | team of ambassadors | Local comms liaison - Ghana | ongoing | Sam | Leif
Communications | team of ambassadors | Local comms liaison - DR | ongoing | Sam | Leif
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Samantha | Everyone
Management System | Country Office engagement | Weekly or Bi-weekly 121s with project contacts (depending on project needs) | ongoing | Task Managers
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National public private partnerships | risk management | risk management plans set up and managed for both platform and project engagement beyond due diligence process | ongoing | Task Managers |  | I'm not sure I understand this. Is this the risk management in Atlas? Also, often we have limited tools to control risks, which is a real weakness in GCP. Essentially we try to influence others, but we have little formal say in things.
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project implementation | review and provide comments that are taken on board for annual work plans | ongoing | Task Managers
Technical services | project implementation | review and steer for high quality strategies (tehcnical / engagment) | ongoing | Task Managers
Technical services | project implementation | review and provide comments that are taken on board for Terms of References | ongoing | Task Managers
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
Learning in Action | South-south coop. | reporting on study tours | within 1 week | Study tour manager

## 5.4 Tomo
Tomo Uno (100%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Monitoring & Evaluation | Reporting | Donor reporting for 2014 | 2015-02-20 | Tomo | Task Managers
Technical services | project design | review and consider current prortfolio and prirotise where to get root cause analysis done | 2015-03-01 | Andrew | Task Managers
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Monitoring & Evaluation | Reporting | Table of Contents for Annual Report (format) | 2015-03-01 | Tomo | Andrew to approve
Resourcing | national strategies | provide guidance framework for national teams to fundraise at local level | 2015-04-01 | Andrew | Task Managers
Resourcing | engagement strategies | Develop and share 1 page approach CLUA - Global | 2015-04-01 | Jyoti | Tomo
Monitoring & Evaluation | Tool development | Finalising and writing GCP M&E framework | 2015-04-01 | Kifah | Tomo, JJ, Leif, Lise
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | global ambassador group | Develop engagement strategy with Consumer Goods Forum (TFA) | 2015-05-01 | Andrew | Tomo, Kate, Jyoti
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with ADM | 2015-05-01 | Andrew | Tomo, Leif, Lise, JJ
Monitoring & Evaluation | Tool development | Impact indicators proposal | 2015-05-01 | Kifah | Tomo
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach Japan UNDP Partnership Fund for global & Indonesia | 2015-05-01 | Tomo | Kifah
Management System | GEF Programme Design | Designing indonesia GEF project | 2015-06-01 | JJ | Tomo
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with Cargill | 2015-06-01 | Kate | Tomo, Leif, Lise, JJ
Communications | products | GCP Highlights/Fast Facts - including links to stories from the field (considering gender and other cross-cutting themes) | 2015-06-01 | Sam | Andrew, Tomo
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Global engagement & dialogue | global ambassador group | Develop engagement strategy with RSPO | 2015-07-01 | Kate | Tomo, JJ, Sam
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers
Technical services | project design | provide advice to project designers on how to prepare root cause analysis | 2015-09-01 | Task Managers
Global engagement & dialogue | fundraising / promotion | Consumer Goods Forum event - Steering Committee meeting linked with Mondelez | 2015-10-01 | Kate | Andrew, Tomo
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Global engagement & dialogue | fundraising / promotion | RSPO annual meeting (RT13) | 2015-11-01 | Tomo | Kate
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Learning in Action | South-south coop. | Planning & organising study tour between CR and Indonesia for 2016 on land use monitoring | 2015-12-01 | Kifah | Tomo
National Commodity Platforms | training | 121 coaching (1 mission per category A country focussed on platforms) - Lise will do Indonesia. | 2015-12-01 | Lise | Kifah, Leif, Tomo, Kate
Management System | Task Management | Indonesia – platform – palm oil | A / High | Tomo
Management System | Task Management | Indonesia – other stuff | A / Medium | Tomo
Technical services | project implementation | annual mission to project with specific and standard objectives (additional specific ones can be added) | annual | Task Managers
Management System | Task Management | Indonesia - fisheries | B / very low | Andrew (until global coordinator) | Tomo
Management System | Task Management | Philippines – Platform - fisheries | B / very low | Andrew (until global coordinator) | Tomo
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
National public private partnerships | engagement plan | write private sector engagement plan | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | develop specific engagement strategies / actor | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular informal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular formal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | prioritise national level | sector / supply chain analysis | ongoing | COUNTRY OFFICE / PMU | Task Managers
Resourcing | GEF coordination | IAP design activities, budget and team to maximise alignment | ongoing | JJ | Andrew, Tomo, Leif, Kifah
Monitoring & Evaluation | Tool development | Promotion to UN-REDD of land use monitoring tool in Costa Rica | ongoing | Kifah | Tomo
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | platforms | review platform communication strategies and provide advice | ongoing | Sam | Leif, Tomo, Kifah
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Communications | team of ambassadors | Local comms liaison - Indonesia | ongoing | Sam | Tomo
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Samantha | Everyone
Management System | Country Office engagement | Weekly or Bi-weekly 121s with project contacts (depending on project needs) | ongoing | Task Managers
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National public private partnerships | risk management | risk management plans set up and managed for both platform and project engagement beyond due diligence process | ongoing | Task Managers
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project implementation | review and provide comments that are taken on board for annual work plans | ongoing | Task Managers
Technical services | project implementation | review and steer for high quality strategies (tehcnical / engagment) | ongoing | Task Managers
Technical services | project implementation | review and provide comments that are taken on board for Terms of References | ongoing | Task Managers
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew
Communications | products | Media coverage of palm oil work in Indonesia | ongoing | Tomo
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
National Commodity Platforms | guidance | Provide needs and request based support to roll out of Indonesia Sustainable Palm Oil Platform | ongoing | Tomo | Lise
Learning in Action | South-south coop. | reporting on study tours | within 1 week | Study tour manager

## 5.5. Sam
Sam Newport (60%) |  | Subject to change following proritisation with Andrew in early March
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Communications | strategy | 2015 work plan | 2015-03-01 | Sam
Communications | team of ambassadors | Email signature - unify internally | 2015-03-01 | Sam
Management System | Procurement | Officialise Taylor internship | 2015-03-01 | Eliana | Sam
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Management System | GCP team operations | Set up and keep dropbox (GCP online information management) up to date | 2015-03-01 | Sam (Taylor) | Lise to get running
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Communications | global recognition | Article - guardian | 2015-04-01 | Sam | Andrew
Communications | products | finish fact sheets and put on line (CR, DR, INDO, Platforms, Ghana) | 2015-04-01 | Sam | Taylor
Communications | products | Assist with revision of script and narration for CR video (land use) | 2015-04-01 | Kifah | Sam
Communications | strategy | Final external communications strategy | 2015-04-01 | Sam
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Mondelez (make template with this one) | 2015-04-01 | Andrew | Leif, Sam
Management System | GCP team operations | Internal communications tools to be set up | 2015-04-01 | Sam (Taylor)
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
National Commodity Platforms | training | launch of v1.0 | 2015-05-01 | Lise | Sam
Communications | products | GCP Highlights/Fast Facts - including links to stories from the field (considering gender and other cross-cutting themes) | 2015-06-01 | Sam | Andrew, Tomo
Communications | products | Position paper - UNDP & REDD with a guidance doc to UN REDD on REDD and commodities | 2015-06-01 | Leif | Sam
Communications | team of ambassadors | 1 master power point slide deck to pick from to pitch GCP (including procurement of designer) | 2015-06-01 | Sam
National Commodity Platforms | guidance | Video introducing platforms | 2015-06-01 | Lise | Sam
National Commodity Platforms | training | design v1.0 of training program | 2015-06-01 | Lise | Kifah, Sam,
Communications | platforms | provide training on effective communication skills and developing a communications strategy | 2015-06-20 | Sam | Lise
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Communications | products | Position paper - how GCP reduces deforestation | 2015-07-01 | Sam | JJ
Global engagement & dialogue | global ambassador group | Develop engagement strategy with RSPO | 2015-07-01 | Kate | Tomo, JJ, Sam
National public private partnerships | guidance | private sector presentation template and tips to pitch (key principles to follow when talking to the private sector) | 2015-07-01 | Sam | Kate, Andrew, JJ
National public private partnerships | guidance | private sector pitch framework written and kept updated | 2015-07-01 | Kate | Andrew, JJ, Sam
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
National Commodity Platforms | training | coordination with gender mainstreaming and with GAIN-UNDP (integrity module) | 2015-09-01 | Lise | Kifah, Sam
Communications | products | GCP video - using photos/CGI/narration | 2015-10-01 | Sam | Lise
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
National Commodity Platforms | measuring success | annual report input on results of national platforms | 2015-12-20 | Lise | Sam
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | establish effective webiste in line with strategy (review by 01-April) | ongoing | Sam
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | platforms | review platform communication strategies and provide advice | ongoing | Sam | Leif, Tomo, Kifah
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Communications | team of ambassadors | Local comms liaison - Ghana | ongoing | Sam | Leif
Communications | team of ambassadors | Local comms liaison - Indonesia | ongoing | Sam | Tomo
Communications | team of ambassadors | Local comms liaison - DR | ongoing | Sam | Leif
Learning in Action | Learning Portal | Developing material for learning portal | ongoing | Lise Platforms/ Sam Com
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
National Commodity Platforms | sharing & promoting | promotion of NCP concept by comms | ongoing from Aug | Sam | Lise
Communications | internal comms | Flickr account | Q1 & ongoing | Sam | Taylor
Communications | global recognition | Develop & publish communiques on partnership with GEF and separately with UNREDD |  | Sam
Communications | strategy | integrate communications into UNDP & UN ("One UN") |  | Sam
Communications | strategy | Enable global team to embody the communications strategy |  | Sam
Communications | strategy | Enable country offices and project teams to take their cue from the strategy |  | Sam
Communications | strategy | key messaging adopted for top 5 stakeholder groups - government, producers, buyers, civil society (NGOs), donors |  | Sam

## 5.6 Kifah
Kifah Sasa (25%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Monitoring & Evaluation | Reporting | Donor reporting for 2014 | 2015-02-20 | Tomo | Task Managers
Global engagement & dialogue | global ambassador group | Develop engagement strategy with UN-REDD to embed and codify the partnership for long term | 2015-03-01 | Andrew | Kifah, Lise
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Resourcing | engagement strategies | Develop and share 1 page approach BIoFinn - pilot attempt in Costa Rica | 2015-03-01 | Kifah
Technical services | project design | review and consider current prortfolio and prirotise where to get root cause analysis done | 2015-03-01 | Andrew | Task Managers
Communications | products | Assist with revision of script and narration for CR video (land use) | 2015-04-01 | Kifah | Sam
Learning in Action | Facilitated learning | Planning & designing webinars | 2015-04-01 | Kifah | Eliana
Learning in Action | Facilitated learning | Calendar of L4A events | 2015-04-01 | Lise | Kifah, Andrew
Monitoring & Evaluation | Tool development | Finalising and writing GCP M&E framework | 2015-04-01 | Kifah | Tomo, JJ, Leif, Lise
National Commodity Platforms | guidance | write and finalise methodology guidance | 2015-04-01 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | sponsorship | guidance on how to get sponsorship for Category A only | 2015-04-01 | Lise | Kifah
Resourcing | national strategies | provide guidance framework for national teams to fundraise at local level | 2015-04-01 | Andrew | Task Managers
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Walmart | 2015-05-01 | Kifah | Andrew, Kate, JJ, Lise
Learning in Action | Learning Portal | Set up / administration of learning portal | 2015-05-01 | Kifah | Lise
Monitoring & Evaluation | Tool development | Impact indicators proposal | 2015-05-01 | Kifah | Tomo
Resourcing | engagement strategies | Develop and share 1 page approach Japan UNDP Partnership Fund for global & Indonesia | 2015-05-01 | Tomo | Kifah
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
National Commodity Platforms | guidance | develop & finalise tools | 2015-05-15 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | guidance | develop& finalise templates | 2015-05-15 | Lise | Kifah, Leif, Andrew
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
Management System | GEF Programme Design | Designing Paraguay GEF project | 2015-06-01 | JJ | Kifah
National Commodity Platforms | guidance | Translation of all guidance into Spanish | 2015-06-01 | Kifah | Lise
National Commodity Platforms | sharing & promoting | set up learning history tracking | 2015-06-01 | Lise | Kifah
National Commodity Platforms | training | design v1.0 of training program | 2015-06-01 | Lise | Kifah, Sam
National Commodity Platforms | training | training of trainers (Leif - Kifah) in person (pre global delivery) | 2015-06-15 | Lise | Kifah, Leif
Learning in Action | CoP | Design & facilitation of workshop day | 2015-06-20 | Lise | Kifah
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Global engagement & dialogue | global ambassador group | Develop engagement strategy with IDH to get full support and recognition for what GCP does | 2015-07-01 | Kate | Kifah, Lise
Management System | Procurement | ToR & Hiring process for Global Fisheries Platform Coordinator | 2015-07-30 | Andrew | Lise, Kifah
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
National Commodity Platforms | training | coordination with gender mainstreaming and with GAIN-UNDP (integrity module) | 2015-09-01 | Lise | Kifah, Sam
Technical services | project design | provide advice to project designers on how to prepare root cause analysis | 2015-09-01 | Task Managers
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Global engagement & dialogue | fundraising / promotion | IDH conference - Amsterdam | 2015-11-01 | Kate | Kifah
Learning in Action | South-south coop. | Finalise study tour plan for 2016 & 2017 (funds having been secured at project level - GEF) | 2015-11-01 | Kifah | Andrew
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Learning in Action | South-south coop. | Planning & organising study tour between CR and Indonesia for 2016 on land use monitoring | 2015-12-01 | Kifah | Tomo
Learning in Action | South-south coop. | Neogtiating budgets / costs with CO for CR-Indonesia trip | 2015-12-01 | Kifah
National Commodity Platforms | training | 121 coaching (1 mission per category A country focussed on platforms) - Lise will do Indonesia. | 2015-12-01 | Lise | Kifah, Leif, Tomo, Kate
Management System | Task Management | Costa Rica – Platform – pineapple | A / High | Kifah
Management System | Task Management | Paraguay – platform – soy & cattle | A / Medium | Kifah
Technical services | project implementation | annual mission to project with specific and standard objectives (additional specific ones can be added) | annual | Task Managers
Management System | Task Management | Costa Rica – Platform - fisheries | B / Very low | Andrew (until global coordinator) | Kifah
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | platforms | review platform communication strategies and provide advice | ongoing | Sam | Leif, Tomo, Kifah
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Management System | Country Office engagement | Weekly or Bi-weekly 121s with project contacts (depending on project needs) | ongoing | Task Managers
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
Monitoring & Evaluation | Tool development | Promotion to UN-REDD of land use monitoring tool in Costa Rica | ongoing | Kifah | Tomo
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National public private partnerships | engagement plan | write private sector engagement plan | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | develop specific engagement strategies / actor | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular informal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular formal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | prioritise national level | sector / supply chain analysis | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | risk management | risk management plans set up and managed for both platform and project engagement beyond due diligence process | ongoing | Task Managers
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
Resourcing | GEF coordination | IAP design activities, budget and team to maximise alignment | ongoing | JJ | Andrew, Tomo, Leif, Kifah
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project implementation | review and provide comments that are taken on board for annual work plans | ongoing | Task Managers
Technical services | project implementation | review and steer for high quality strategies (tehcnical / engagment) | ongoing | Task Managers
Technical services | project implementation | review and provide comments that are taken on board for Terms of References | ongoing | Task Managers
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew

## 5.7 JJ
Juan Jose Dada (?%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Monitoring & Evaluation | Tool development | Finalising and writing GCP M&E framework | 2015-04-01 | Kifah | Tomo, JJ, Leif, Lise
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with ADM | 2015-05-01 | Andrew | Tomo, Leif, Lise, JJ
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Walmart | 2015-05-01 | Kifah | Andrew, Kate, JJ, Lise
Resourcing | engagement strategies | Develop and share 1 page approach Moore Foundation | 2015-05-01 | JJ | Andrew
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with Cargill | 2015-06-01 | Kate | Tomo, Leif, Lise, JJ
Management System | GEF Programme Design | Designing Paraguay GEF project | 2015-06-01 | JJ | Kifah
Management System | GEF Programme Design | Ensuring Peru GEF project fits into larger GEF project | 2015-06-01 | JJ | Leif
Management System | GEF Programme Design | Designing indonesia GEF project | 2015-06-01 | JJ | Tomo
National public private partnerships | engagement plan | provide guidance on how to write plan (template) | 2015-06-01 | Kate | Lise, JJ
National public private partnerships | prioritise national level | provide guidance on how to do analysis (engage team via call) | 2015-06-01 | Kate | JJ, Lise, Andrew
Communications | products | Position paper - how GCP reduces deforestation | 2015-07-01 | Sam | JJ
Global engagement & dialogue | global ambassador group | Develop engagement strategy with RSPO | 2015-07-01 | Kate | Tomo, JJ, Sam
National public private partnerships | guidance | private sector pitch framework written and kept updated | 2015-07-01 | Kate | Andrew, JJ, Sam
National public private partnerships | guidance | private sector presentation template and tips to pitch (key principles to follow when talking to the private sector) | 2015-07-01 | Sam | Kate, Andrew, JJ
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
National public private partnerships | guidance | provide support on how to develop and implement 5P projects | 2015-10-01 | Kate | Lise, JJ
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Management System | Task Management | Brazil – Platform – soy/cattle | A / Low | JJ
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Management System | GEF Programme Design | Steering Committee engagement | ongoing | Andrew | JJ
Management System | Procurement | Consultants for PPG stage of GEF | ongoing | JJ | (GEF support)
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
Resourcing | GEF coordination | IAP design activities, budget and team to maximise alignment | ongoing | JJ | Andrew, Tomo, Leif, Kifah

## 5.8 Lise
Lise Melvin (50%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | Financial management | Finalise 2015 work plan and prioritised budget | 2015-02-13 | Andrew | Lise, Eliana, Leif
Management System | GCP Planning | Standard mission objectives written and circulated | 2015-02-16 | Andrew | Lise
Global engagement & dialogue | global ambassador group | Develop engagement strategy with UN-REDD to embed and codify the partnership for long term | 2015-03-01 | Andrew | Kifah, Lise
Management System | GCP Planning | Finalise 2015-2017 GCP Strategic Plan | 2015-03-01 | Lise | Andrew
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Management System | GCP team operations | Set up and keep dropbox (GCP online information management) up to date | 2015-03-01 | Sam (Taylor) | Lise to get running
Learning in Action | CoP | Planning & logistics of workshop | 2015-04-01 | Lise | Intern/Elodie
Learning in Action | Facilitated learning | Calendar of L4A events | 2015-04-01 | Lise | Kifah, Andrew
Monitoring & Evaluation | Tool development | Finalising and writing GCP M&E framework | 2015-04-01 | Kifah | Tomo, JJ, Leif, Lise
National Commodity Platforms | guidance | write and finalise methodology guidance | 2015-04-01 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | sponsorship | guidance on how to get sponsorship for Category A only | 2015-04-01 | Lise | Kifah
Resourcing | engagement strategies | Develop and share 1 page approach with UN REDD | 2015-04-01 | Andrew | Jyoti, Lise
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with ADM | 2015-05-01 | Andrew | Tomo, Leif, Lise, JJ
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Walmart | 2015-05-01 | Kifah | Andrew, Kate, JJ, Lise
Learning in Action | Learning Portal | Set up / administration of learning portal | 2015-05-01 | Kifah | Lise
National Commodity Platforms | training | launch of v1.0 | 2015-05-01 | Lise | Sam
Resourcing | engagement strategies | Develop and share 1 page approach SIDA | 2015-05-01 | Lise | Andrew
National Commodity Platforms | guidance | develop & finalise tools | 2015-05-15 | Lise | Kifah, Leif, Andrew
National Commodity Platforms | guidance | develop& finalise templates | 2015-05-15 | Lise | Kifah, Leif, Andrew
Global engagement & dialogue | fundraising / promotion | ISEAL Annual conference > Donors | 2015-05-20 | Lise
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with Cargill | 2015-06-01 | Kate | Tomo, Leif, Lise, JJ
National Commodity Platforms | guidance | USBs designed with all guidance | 2015-06-01 | Lise | Eliana
National Commodity Platforms | guidance | Video introducing platforms | 2015-06-01 | Lise | Sam
National Commodity Platforms | guidance | Translation of all guidance into Spanish | 2015-06-01 | Kifah | Lise
National Commodity Platforms | sharing & promoting | set up learning history tracking | 2015-06-01 | Lise | Kifah
National Commodity Platforms | training | design v1.0 of training program | 2015-06-01 | Lise | Kifah, Sam
National Commodity Platforms | training | coordination with Demoractic Dialogue team | 2015-06-01 | Lise | Andrew
National Commodity Platforms | training | coordination with ISEAL | 2015-06-01 | Lise | Andrew
National Commodity Platforms | training | global training workshop (procurement and logistics) | 2015-06-01 | Eliana | Intern/Elodie, Lise
National public private partnerships | engagement plan | provide guidance on how to write plan (template) | 2015-06-01 | Kate | Lise, JJ
National public private partnerships | prioritise national level | provide guidance on how to do analysis (engage team via call) | 2015-06-01 | Kate | JJ, Lise, Andrew
National Commodity Platforms | training | training of trainers (Leif - Kifah) in person (pre global delivery) | 2015-06-15 | Lise | Kifah, Leif
Communications | platforms | provide training on effective communication skills and developing a communications strategy | 2015-06-20 | Sam | Lise
Learning in Action | CoP | Design & facilitation of workshop day | 2015-06-20 | Lise | Kifah
National Commodity Platforms | training | global training workshop (design and facilitation) | 2015-06-29 | Lise | Leif, Sam, Kifah, Tomo, Eliana, Andrew
Global engagement & dialogue | global ambassador group | Develop engagement strategy with IDH to get full support and recognition for what GCP does | 2015-07-01 | Kate | Kifah, Lise
Management System | Procurement | ToR & Hiring process for Global Fisheries Platform Coordinator | 2015-07-30 | Andrew | Lise, Kifah
National Commodity Platforms | training | coordination with UNREDD | 2015-08-01 | Lise | Andrew
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
National Commodity Platforms | training | coordination with gender mainstreaming and with GAIN-UNDP (integrity module) | 2015-09-01 | Lise | Kifah, Sam
Communications | products | GCP video - using photos/CGI/narration | 2015-10-01 | Sam | Lise
National public private partnerships | guidance | provide support on how to develop and implement 5P projects | 2015-10-01 | Kate | Lise, JJ
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
Management System | GCP Planning | Training and capacity needs assessment of global team completed and financing options discussed. | 2015-12-01 | Andrew | Lise
National Commodity Platforms | training | 121 coaching (1 mission per category A country focussed on platforms) - Lise will do Indonesia. | 2015-12-01 | Lise | Kifah, Leif, Tomo, Kate
National Commodity Platforms | measuring success | annual report input on results of national platforms | 2015-12-20 | Lise | Sam
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Learning in Action | Learning Portal | Developing material for learning portal | ongoing | Lise Platforms/ Sam Com
National Commodity Platforms | guidance | Provide needs and request based support to roll out of Indonesia Sustainable Palm Oil Platform | ongoing | Tomo | Lise
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National Commodity Platforms | training | coordination | ongoing | Lise | Andrew
National Commodity Platforms | training | quality assurance | ongoing | Lise | Andrew
National Commodity Platforms | training | liaison with CO Heads for support | ongoing | Andrew | Lise
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
National Commodity Platforms | sharing & promoting | promotion of NCP concept by comms | ongoing from Aug | Sam | Lise

## 5.9 Jyoti
Jyoti Mathur-Filipp 30%
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Resourcing | engagement strategies | Develop and share 1 page approach CLUA - Global | 2015-04-01 | Jyoti | Tomo
Resourcing | engagement strategies | Develop and share 1 page approach Green Climate Fund | 2015-04-01 | Jyoti | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach with EU | 2015-04-01 | Jyoti | Andrew
Resourcing | engagement strategies | Develop and share 1 page approach with UN REDD | 2015-04-01 | Andrew | Jyoti, Lise
Resourcing | engagement strategies | Develop and share 1 page approach IKI (Germans) | 2015-04-01 | Andrew | Jyoti & Leif
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Global engagement & dialogue | global ambassador group | Develop engagement strategy with Consumer Goods Forum (TFA) | 2015-05-01 | Andrew | Tomo, Kate, Jyoti
Global engagement & dialogue | global ambassador group | World Economic Forum engagement strategy | 2015-05-20 | Andrew | Jyoti
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone

## 5.10 Kate
Kate Bottriell (50%)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Global engagement & dialogue | global ambassador group | Develop engagement strategy with Consumer Goods Forum (TFA) | 2015-05-01 | Andrew | Tomo, Kate, Jyoti
Global engagement & dialogue | international private sector | Develop engagement strategy , work plan and relationship with Walmart | 2015-05-01 | Kifah | Andrew, Kate, JJ, Lise
Resourcing | national strategies | advice on securing national funds with global components - kick off 01-May with target of 01 July to se fundraising targets collaboratively with country offices, and ongoing activity throughout year | 2015-05-01 | Task Managers | Andrew
Global engagement & dialogue | international private sector | Develop engagement strategy, work plan and relationship with Cargill | 2015-06-01 | Kate | Tomo, Leif, Lise, JJ
Management System | Country Office engagement | Develop relationships with the Deputy Res Reps | 2015-06-01 | Task Managers | Andrew
National public private partnerships | engagement plan | provide guidance on how to write plan (template) | 2015-06-01 | Kate | Lise, JJ
National public private partnerships | prioritise national level | provide guidance on how to do analysis (engage team via call) | 2015-06-01 | Kate | JJ, Lise, Andrew
Global engagement & dialogue | global ambassador group | Develop engagement strategy with IDH to get full support and recognition for what GCP does | 2015-07-01 | Kate | Kifah, Lise
Global engagement & dialogue | global ambassador group | Develop engagement strategy with RSPO | 2015-07-01 | Kate | Tomo, JJ, Sam
National public private partnerships | guidance | private sector presentation template and tips to pitch (key principles to follow when talking to the private sector) | 2015-07-01 | Sam | Kate, Andrew, JJ
National public private partnerships | guidance | private sector pitch framework written and kept updated | 2015-07-01 | Kate | Andrew, JJ, Sam
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Technical services | project design | Global advisors train to be experts in root cause analysis | 2015-09-01 | Andrew | Task Managers
Technical services | project design | provide advice to project designers on how to prepare root cause analysis | 2015-09-01 | Task Managers
Global engagement & dialogue | fundraising / promotion | Consumer Goods Forum event - Steering Committee meeting linked with Mondelez | 2015-10-01 | Kate | Andrew, Tomo
National public private partnerships | guidance | provide support on how to develop and implement 5P projects | 2015-10-01 | Kate | Lise, JJ
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Global engagement & dialogue | fundraising / promotion | RSPO annual meeting (RT13) | 2015-11-01 | Tomo | Kate
Global engagement & dialogue | fundraising / promotion | IDH conference - Amsterdam | 2015-11-01 | Kate | Kifah
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
National Commodity Platforms | training | 121 coaching (1 mission per category A country focussed on platforms) - Lise will do Indonesia. | 2015-12-01 | Lise | Kifah, Leif, Tomo, Kate
Technical services | project implementation | annual mission to project with specific and standard objectives (additional specific ones can be added) | annual | Task Managers
Management System | Task Management | Cote d’Ivoire – REDD - cocoa | B / Low | Kate
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Communications | products | Support country offices with layout of translated fact sheets and other products | ongoing | Sam | Task Managers
Communications | recognition | Press releases/Media coverage of national activities, eg palm oil work in Indonesia, finalization of action plan in CR, and draft NAP in DR | ongoing | Sam | Task Managers
Communications | team of ambassadors | all missions provide communications materials for global use (photo, 3 successes, new ideas) | ongoing | Sam | Task Managers, Andrew
Management System | Country Office engagement | Weekly or Bi-weekly 121s with project contacts (depending on project needs) | ongoing | Task Managers
Monitoring & Evaluation | Reporting | Donor reporting for 2015 (aggregation and relationship) | ongoing | Tomo | Task Managers, Sam (stories from field)
National Commodity Platforms | measuring success | collecting indicators of success | ongoing | Task Managers | Lise
National public private partnerships | engagement plan | write private sector engagement plan | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | develop specific engagement strategies / actor | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular informal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | engagement plan | regular formal interaction with private sector partners | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | prioritise national level | sector / supply chain analysis | ongoing | COUNTRY OFFICE / PMU | Task Managers
National public private partnerships | risk management | risk management plans set up and managed for both platform and project engagement beyond due diligence process | ongoing | Task Managers
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
Technical services | connecting needs with expertise | ensure connections are made with other programmes / UNDP technical services based on requests only | ongoing | Task Managers | Andrew
Technical services | project design | assign global advisors to project based on identified and agreed needs with CO | ongoing | Task Managers | Andrew
Technical services | project implementation | review and provide comments that are taken on board for annual work plans | ongoing | Task Managers
Technical services | project implementation | review and steer for high quality strategies (tehcnical / engagment) | ongoing | Task Managers
Technical services | project implementation | review and provide comments that are taken on board for Terms of References | ongoing | Task Managers
Technical services | project implementation | showcase successes and help to develop solutions to blockages / problems | ongoing | Task Managers | Andrew

## 5.11 Elodie-Taylor-Intern
Elodie / Taylor / Intern (to be separated later)
UPDATED | 2015-02-19 | If you update this work plan, please remember to talk to your collaborators and inform them as it effects their work too.
Delivery Area | Activity | Sub Activities | Target date | Lead responsible | Collaborators
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Management System | GCP team operations | Set up and keep dropbox (GCP online information management) up to date | 2015-03-01 | Sam (Taylor) | Lise to get running
Management System | GCP team operations | Set up and keep updated a GCP google calendar (team fills updates travel plans 3 months in advance) | 2015-03-01 | Sam (Taylor) | Everyone
Communications | products | finish fact sheets and put on line (CR, DR, INDO, Platforms, Ghana) | 2015-04-01 | Sam | Taylor
Learning in Action | CoP | Planning & logistics of workshop | 2015-04-01 | Lise | Intern/Elodie
Management System | GCP team operations | Internal communications tools to be set up | 2015-04-01 | Sam (Taylor)
Resourcing | process & pitch | develop GCP investment pitch | 2015-04-01 | Sam | Everyone
Technical services | project design | Integration of gender mainstreaming into our work - in platforms | 2015-05-01 | Andrew | Intern?
National Commodity Platforms | training | global training workshop (procurement and logistics) | 2015-06-01 | Eliana | Intern/Elodie, Lise
Resourcing | engagement strategies | Write a study showing in theory how GCP contributes to eradicating poverty | 2015-06-01 | Leif | Intern
Learning in Action | Learning Portal | annual learning survey to users or portal - design & set up (run onc ein 2015 through CoP workshop) | 2015-07-01 | Intern
National public private partnerships | guidance | proof of concept case studies that speak to private sector (can be non GCP e.g. collective impact) | 2015-08-01 | Sam | Everyone
Communications | team of ambassadors | training of GCP team in communications - presentations, public speaking, messaging etc. | 2015-11-01 | Sam | Everyone
Management System | GCP Planning | Define and complete 2016 planning process for work plan and budget | 2015-11-30 | Andrew | Everyone
National Commodity Platforms | training | webinars x 8 (split between Spanish & English) | monthly | Lise | Everyone
Communications | global recognition | Mainstreaming GCP into UNDP messaging, via reports, speeches, social media, position papers, website etc | ongoing | Sam | Everyone
Resourcing | engagement strategies | Provide existing donors with exposure and recognition | ongoing | Sam | Everyone
Communications | internal comms | Flickr account | Q1 & ongoing | Sam | Taylor