QUARTERLY PROGRESS REPORT

| Project Title | Caribbean Risk Management Initiative Phase II |
| --- | --- |
| Delivery date: | January 2013 |
| Prepared by: | Jacinda Fairholm |
| Award No: | 60722 |
| Project ID: | 76586, 76587,76588 |
| Regional Programme Expected Outcomes: | Focus Area 3: Crisis Prevention and Recovery Strengthened regional, national and local capacities to manage and mitigate the risks of disasters Focus Area 4: Environment and sustainable development Strengthened regional capacity to adapt to climate change |
| Project Expected outputs: | Output 1.0: Capacity for disaster risk reduction and adaptation to climate change developed within the Caribbean region is strengthened. Output 2.0: Improved management of knowledge on climate change adaptation and disaster risk reduction Output 3.0: Partnerships and Resource mobilization are enhanced |
| Executing entity : | UNDP- Regional Centre |
| Implementation entities: | UNDP RSC-LAC, CDEMA, UVW, CIMH, INSMET (Cuba) |
| Award ID start date: | October 25th, 2010 |
| Award ID end date: | December 31st, 2012 |
| Total Project Budget (Award ID): | USD 950.000 |
| Participating countries: | Cuba, Jamaica, DR, Haiti, Guyana, Trinidad and Tobago, Belize, Barbados and OECS |
| Period of the report: | Jan – March 2013 |
| Total expenditure for the reporting period: | 80,625.18 |

Brief Description

This project combines aspects of UNDP’s corporate strategic plan (2008-2011) from operations areas: Crisis prevention and recovery – disaster risk reduction and: environment and sustainable development – promoting adaptation to climate change. The project falls under focus areas three and four from the RBLAC regional plan and the RBLAC key results areas Strengthened regional, national and local capacities to manage and mitigate the risks of disasters; and strengthened regional capacity to adapt to climate change. Capacity in the Caribbean for managing climate-induced disaster risk is low despite gains made by the Caribbean Risk Management Initiative (CRMI) Phase one and other initiatives undertaken by regional governments, the United Nations, and other development partners. To develop such capacity, this project will establish throughout the region, disaster risk reduction centres which will map hazards, vulnerability and risk due to climate change and geological hazards and be part of the national early warning system at the local government and community level. The project will support collection and generation of data on climate and the development of accurate climate change scenarios for key economic sectors to inform effective adaptation to climate change within the highly vulnerable SIDS of the Caribbean. Capacity to manage risk and adapt to climate change will be developed by establishing and supporting a Community of Practice, and developing educational courses and increasing awareness among, inter alia, the media, policy-makers and stakeholders in communities, technical agencies and government. The project will also support development of financial mechanisms and promulgation of guidelines for reducing risk and integrating climate change adaptation into livelihoods, policy and practice.

- MAIN ACHIEVEMENTS OF THE PROJECT

Description of the main achievements of the Project in this quarter

In the first quarter of 2013 (Jan - March), the main achievements of the Project were: Output 1: Capacity for disaster risk reduction and adaptation to climate change within the Caribbean region is strengthened. RRMC technical support mission to British Virgin Islands and Trinidad and Tobago: meetings with UNDP-COs, national and local counterparts. Site visit to proposed RRMC locations (Anegada Island and Mayaro Claro) Three-day (Feb 26 -28) training on the Risk Reduction Management Centre model, targeted at decision-makers from the five pilot countries, held in Havana, Cuba. Work session in Cuba to develop program for technical training, discuss systematization efforts and putting together a RRMC tool kit and video All five pilot countries submitted an Implementation Plan, effective April – Nov 2013. Output 2: Improved management of knowledge on climate change adaptation and disaster risk reduction Pilot version of “Gender, Public Policy and Risk Management” online course, developed by CPR Practice Areas in RSC, and led by the UNDP Virtual School, completed on Feb 21st, 2013. Supporting CDEMA to strengthen approach to integrating gender into DRR through the commission of a discussion paper on the state, advances and challenges of integrating gender into disaster management in the region, co-financed by CRMI and CIDA. Support to CDEMA to coordinate a gender and disaster management training offered to all National Disaster Management authorities in CDEMA participating states, and building capacity of the CDEMA technical team. The training will take place at the 2013 CDEMA Technical Advisory Council (TAC) Meeting in April, 2013. Collaborated with CDEMA to create entry-point for national women’s ministry and partners to provide input in the CDM Strategy 2013+ through the session “Women and Girls – the (in)visible force of resilience” at the CDM conference. Sharing of experience, analysis and tools from Caribbean and Pacific on gender integration into DRM through the session “Women and Girls – the (in)visible force of resilience” at the CDM conference: 4 case studies. Gender Working Group providing input into CDM Strategy, developing questionnaires and providing feedback on Gender Discussion Paper direction Website coordinator working with Escuela Virtual to re-design CRMI website, with increased social-media focus. Content input provided. Agreed upon launch date: May 6th, 2013. Outcome 3: Partnerships and Resource mobilization are enhanced First 2013 Quarterly Newsletter disseminated Budget revised in preparation for the RRMC activities in five countries Input and contribution to the Caribbean-Pacific S-S Project Evaluation Coordinated efforts with UNDP-Cuba for implementation of RRMC South-south initiative

- PROJECT PERFORMANCE

Indicate the progress in the activities programmed for the quarter

| Result 1 | Baseline | Target | Indicator |
| --- | --- | --- | --- |
| Capacity for disaster risk reduction and adaptation to climate change enhanced within the Caribbean region is strengthened. | 56 RRMC established in Cuba but no others exist in the Caribbean | RRMCs Replicated in 6 countries in the region | South-south cooperation to increase institutional capacity to manage and reduce local risk through establishing local risk management centres in most vulnerable municipalities |
| Activity Result 1.1 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| RRMCs Replicated in 6 countries in the region | Establish 3 to 5 centres Identification of specific areas of technical assistance required per pilot Implementation of vulnerability and hazard studies, risk assessments, data collection, database management, GIS mapping of vulnerabilities, gender analysis, seismic risk and/or planning for recovery Guidelines for vulnerability and hazard mapping produced 4 -8 communities/ municipalities with improved DRM protocols and procedures, including data collection Review and improve 4 national databases, based on coordinated information provided by RRMC Replication Guidelines strengthened Documentation of best practices and lessons | Project Progress Report Copy of Guidelines Copy of Materials Workshop Evaluations MOUs with governments | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 25% |  |  |  |
| Comments | Technical support missions undertaken to RRMC pilot countries; all UNDP COs abreast of the RRMC initiative. Awareness workshop targeted at decision-makers held in Havana, Feb 2013. All countries submitted concept paper for review and Implementation Plan, expressing commitment to the RRMC South-South Initiative. |

| Result 2 | Baseline | Target | Indicator |
| --- | --- | --- | --- |
| Improved management of knowledge on climate change adaptation and disaster risk reduction | Each Activity has baseline | See below for each activity result | Each activity result has indicator |
| Actividad Result 2.1 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Improved integration of DRR and CCA in Caribbean actors | Target: Caribbean stakeholders have access to information on DRR and CCA Quality Criteria: Site up and running thru the life of the project; number of users monitored; quantity of information downloaded; Number of group meetings; Review of best practice models in DRR and CCA integration | A report on the utility, functioning and potential of the web portal will be compiled and sent to the Project Manager; Meeting Minutes or Outcome documents, Project Progress Report | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 20% |  |  |  |
| Comments | Web coordinator contracted to oversee and manage redesign of KM platform and EV team. Social media accounts established ie. twitter. |
| Activity Result 2.2 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Increased capacity building in emergent themes | Target: 2 workshops in emergent themes such as seismic risk or pre-planning for recovery; National pre-planning for recovery plans are developed in at least 2 Caribbean nations Quality Criteria: Number of participants; number of presenters | Workshop evaluations; project progress report; conference agenda | Timeline (as perAWP) |  | x | x |  |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 0% |  |  |  |
| Comments | Both PDNA and Seismic Risk Workshops are scheduled for the 2nd and 3rd Quarters. |
| Actividad Result 2.3 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Gender is integrated into national DRM and CCA structures, policies, plans and programs | Target: Support to roll-out of at least 1 distance teaching program with University in Caribbean; Gender Working Group supports 2013 action plan implementation; Gender checklist is disseminated to all NDMOs in the region; 1 training on gender integration in DRR is held with partners CDEMA Quality Criteria: Reviewed comments by GWG; # of participants providing feedback on online course; coordination of regional gender activities; checklist disseminated. | Emails; meeting minutes; written feedback; training agendas; outcome document; | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 20% |  |  |  |
| Comments | GWG is actively contributing to the CDM Strategy framework and discussion; Agreement with CDEMA to commission a discussion paper and conduct a Gender and DRR Training. Scheduled for 2nd Quarter. Online Gender Course completed in Feb 2013 and currently under review. |
| Activitity Result 2.4 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Improved knowledge sharing and management in climate change adaptation practices | Target: 2 best practices, studies and guidelines in CCA in tourism, agriculture and coastal zone management; 5 countries supported in processes of reporting risk reduction (HFA); Experiences and practices shared between Pacific-Caribbean SIDS in meetings, platforms and documents Quality Criteria: Consultant hired; quality of information generated; HFA reporting complete | Consultant and Project Reports; UNISDR HFA Report & Stats; Assessment by other stakeholders | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 5% |  |  |  |
| Comments | Barbados and Turks and Caicos completed HFA Reports in Jan 2013. Intern will undertake one of the best practices activities. Other activities require resource mobilization. |

| Result 3 | Baseline | Target | Indicator |
| --- | --- | --- | --- |
| Partnerships and Resource mobilization enhanced | CRMI II has commitment from UNDP for critical elements, but additional resources needed to realize the entirety of proposed project activities; Partnerships built or extended with key institutions including the INSMET in Cuba; CCCCC, CDEMA, UWI and others but CRMI still substantially a UNDP initiative | 2 Proposals developed and funded. Liaison with Governments and regional organizations Attendance at existing regional meetings for technical exchange Capacity & interest in project ownership evaluated Project transitioned to regional partner Project implemented on time and on budget with all outputs delivered Monitoring Administration and Execution | Resource Mobilization; Partnerships and Sustainability |
| Activity Result 3.1 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Resource mobilization plan developed and implemented | Target: 2 Proposals developed and funded. Liaison with Governments and regional organizations Quality Criteria: Management Committee meeting convened; Resource Mobilization Plan developed; CRMI activities resourced | Management Meeting Minutes; Existence of 2 plans; 2 proposals drafted; ATLAS and Project Manager reports; MOUs | Timeline (as perAWP) | x | x | x | x |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 10% |  |  |  |
| Comments | Proposal for 450,000 Euros submitted to DIPECHO in Jan 2013; not successfully funded. |
| Activity Result 3.2 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| Caribbean Participation in South-South Caribbean – Pacific Cooperation Sustained | Target: strengthen technical capacity in SIDS; Attendance at existing regional meetings for technical exchange Quality Criteria: Evidence of Exchange; networking | Joint Activities visible in Project reports | Timeline (as perAWP) | x | X | X | X |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 10% |  |  |  |
| Comments | Caribbean-Pacific South South project was completed in 2012. Have provided input into Project Evaluation, sitting on Project Board. Current discussion re. a 2nd phase. |
| Activity Result 3.3 | Target and quality criteria | Quality Method | Assessment of Progress | Period |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 |
| CRMI is managed | Target: Capacity & interest in project ownership evaluated Project transitioned to regional partner Project implemented on time and on budget with all outputs delivered Monitoring Administration & Execution Quality Criteria: Project is adequately administered; regional agency engaged in project activities; project resourced; final evaluation conducted. | Annual report emitted; ATLAS reports, minutes; funding resources; project documents developed; evaluation report | Timeline (as perAWP) | x | X | X | X |
|  |  |  | Indicator value |  |  |  |  |
|  |  |  | % of achievement | 25% |  |  |  |
| Comments | CRMI II is fully operational; intern selected to assist with project implementation; CDEMA is engaged in both Gender and RRMC implementation. |

| Total of Achievement of Results Programmed |
| --- |
| % total of results achieved | Período |
|  | Q1 | Q2 | Q3 | Q4 |
|  | 17/25% |  |  |  |

III. Risk Log

| Type of Risk | Date of Identification | Description | Comments/Response |
| --- | --- | --- | --- |
| Financial | Jan 2013 | Many activities are not under-resourced | Need to do more resource mobilization |
| Organizational | N/A |  |  |
| Strategic | March 2013 | Alignment with CDEMA for potential handover | Need to develop a plan and meetings to initiate this discussion |
| Political | N/A |  |  |
| Operational | N/A |  |  |

IV. Problem Log

| Type | Date of Identification | Description | Comments/Response | Date of Solution |
| --- | --- | --- | --- | --- |
| Budget Revision | March 2013 | Need to do a budget revision to account for 5 country implementation | Budget revision will take place in April | April 2013 |
| Communication | Feb 2013 | Communication strategy developed, which includes newsletter and website for broader stakeholder updating on CRMI. | 1st Q newsletter disseminated; website to be launched in May 2013 | current |