## Sheet1
Evidence-Based Information Management for Citizen Security in Central America
PROCUREMENT* ACTION PLAN - UNDP-USAID
| Requisition Docs Ready |  |  | Type of Supply (Goods, Services, Works) | Est. Contract Amount (USD) | Issue of Expression of Interest (EOI) /Notification |  |  |  |  | Solicitation Document | [5 empty] | Evaluation of Proposals |  |  |  | Committee Review/Approval |  |  |  | Contract Issuance
No | Date | By | Description |  |  | DATE | UNDP Web | IAPSO | Local Paper | Int.Paper /Media | Issue Date | Deadline for Receipt | Duration (days) | RFQ | RFP | ITB | Single Stage | Two stage | Two stage with Combined Weights | IC | Yes/No | CAP Meeting Date | Submission to ACP | ACP`s /CPO s approval | Date of Issue | PO | Inst. Contr. | Works | Profes. Serv. | Publ. Transl | Publication | Reprinting | Security | Travel | Other
1 |  |  | Team Leader | Services | 391114 |  | x | x |  | x | 4Q 2013 | 1Q 2014 | 25 day | [6 empty] | x | YES | 2005-03-12 | 2005-03-12 | 2005-03-12 | 1Q 2014 | [9 empty] | x
2 |  |  | Regional Project Coordinator | Services | 432928 |  | x | x |  | x | 4Q 2013 | 1Q 2014 | 25 day | [6 empty] | x | YES |  |  |  | 1Q 2014 | [9 empty] | x
3 |  |  | Regional Statistical/epidemiology | Services | 144000 |  | x | x |  | x | 4Q 2013 | 1Q 2014 | 25 day | [6 empty] | x | NO |  |  |  | 1Q 2014 | [9 empty] | x
4 |  |  | Regional Finance | Services | 180000 |  | x | x |  | x | 4Q 2013 | 1Q 2014 | 25 day | [6 empty] | x | NO |  |  |  | 1Q 2014 | [9 empty] | x
5 |  |  | National Coordinators of SUT Support Teams (El Salvador) | Services | 126000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 day | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
6 |  |  | National Coordinators of SUT Support Teams (Hondura) | Services | 126000 |  | x | x | x |  | 1Q 2014 | 1900-01-01 | 25 day | [6 empty] | x | NO |  |  |  | 1900-01-01 | [9 empty] | x
7 |  |  | National Coordinators of SUT Support Teams (Gutatemala) | Services | 126000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 day | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
8 |  |  | National Coordinators of SUT Support Teams (Panama) | Services | 126000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 day | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
9 |  |  | National statistical experts (El Salvador) | Services | 119000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
10 |  |  | National statistical experts (Guatemala) | Services | 119000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
11 |  |  | National statistical experts (Honduras) | Services | 119000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
12 |  |  | National statistical experts (Panama) | Services | 119000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
13 |  |  | National Administrative (El Salvador) | Services | 102000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
14 |  |  | National Administrative (Guatemala) | Services | 102000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
15 |  |  | National Administrative (Honduras) | Services | 119000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
16 |  |  | National Administrative (Panama) | Services | 119000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
17 |  |  | Monitoring and Evaluation | Services | 108000 |  | x | x | x |  | 4Q 2013 | 1Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 1Q 2014 | [9 empty] | x
18 |  |  | RBM Coordination and Communication | Services | 126000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
19 |  |  | OBSICA Consultant 1 El Salvador | Services | 105000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
20 |  |  | OBSICA Consultant 2 El Salvador | Services | 105000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
21 |  |  | Gender Expert El Salvador | Services | 42000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
22 |  |  | Technical Consultant for FactsSheets El Salvador | Services | 8000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
23 |  |  | Technical Consultant for FactsSheets Honduras | Services | 8000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
24 |  |  | Technical Consultant for FactsSheets Guatemala | Services | 9000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
25 |  |  | Consultant for Victimization Baseline El Salvador | Services | 18000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 2Q 2014 | [9 empty] | x
26 |  |  | Consultant for Victimization Baseline Honduras | Services | 18000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
27 |  |  | Consultant for Victimization Baseline Guatemala | Services | 21000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
28 |  |  | Technical experts for SUT support | Services | 315000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 25 days | [6 empty] | x | YES |  |  |  | 3Q 2014 | [9 empty] | x
29 |  |  | Consultant for National Enhancement Plan El Salvador | Services | 3000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
30 |  |  | Consultant for National Enhancement Plan Honduras | Services | 3000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
31 |  |  | Consultant for National Enhancement Plan Guatemala | Services | 3500 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
32 |  |  | Consultant to formulate a roadmap for strengthening the capacities El Salvador | Services | 3000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
33 |  |  | Consultant to formulate a roadmap for strengthening the capacities Honduras | Services | 3000 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
34 |  |  | Consultant to formulate a roadmap for strengthening the capacities Guatemala | Services | 3500 |  | x | x | x |  | 2Q 2014 | 3Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 3Q 2014 | [9 empty] | x
35 |  |  | Consultant to identify allies | Services | 5000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
36 |  |  | Consultant to identify pivot organizations for generating information El Salvador | Services | 9000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
37 |  |  | Consultant to identify pivot organizations for generating information Honduras | Services | 9000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
38 |  |  | Consultant to identify pivot organizations for generating information Guatemala | Services | 10500 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
39 |  |  | Consultant to identify pivot organizations for generating information Panama | Services | 6000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
40 |  |  | Consultant to identify pivot organizations for generating information Belize | Services | 6000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
41 |  |  | Consultant to identify pivot organizations for generating information Costa Rica | Services | 3000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
42 |  |  | Consultant to identify pivot organizations for generating information Dominican Republic | Services | 3000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
43 |  |  | Consultant to develop national enhancement plans El Salvador | Services | 3000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
44 |  |  | Consultant to develop national enhancement plans. Belize | Services | 3000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
45 |  |  | Consultant to develop national enhancement plans. Honduras. | Services | 3000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
46 |  |  | Consultant to develop national enhancement plans. Panama | Services | 3000 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
47 |  |  | Consultant to develop national enhancement plans. Guatemala | Services | 3500 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
48 |  |  | Consultant to develop national enhancement plans. Nicaragua | Services | 3500 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
49 |  |  | Consultant to develop national enhancement plans. Costa Rica | Services | 3500 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
50 |  |  | Consultant to develop national enhancement plans. Dominican Republic | Services | 3500 |  | x | x | x |  | 3Q 2014 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
51 |  |  | Evaluation expert for ex-post evaluation of the Project | Services | 21000 |  | x | x | x |  | 3Q 2016 | 4Q 2014 | 10 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
52 |  |  | Technical experts for ad-hoc consultancies on gender, youth, GIS, crime, etc. | Services | 108000 |  | x | x | x |  | 4Q 2014 | 4Q 2014 | 25 days | [6 empty] | x | NO |  |  |  | 4Q 2014 | [9 empty] | x
53 |  |  | Project Steering Committee Meetings in El Salvador | Services | 48000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
54 |  |  | National Technical Committee Meetings in El Salvador | Services | 48000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
55 |  |  | National Technical Committee Meetings in Guatemala | Services | 30000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
56 |  |  | National Technical Committee Meetings in Honduras | Services | 30000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
57 |  |  | Regional Technical Committee Meeting in El Salvador | Services | 36000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
58 |  |  | OBSICA Technical assistance meetings in El Salvador | Services | 14000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
59 |  |  | Workshops on identification of allies/partners in El Salvador | Services | 6400 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
60 |  |  | Workshops on identification of allies/partners in Guatemala | Services | 3840 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
61 |  |  | Workshops on identification of allies/partners in Honduras | Services | 3200 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
62 |  |  | Workshops on identification of allies/partners in Panama | Services | 8400 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
63 |  |  | Workshops on identification of allies/partners in Costa Rica | Services | 8400 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
64 |  |  | Workshops on identification of allies/partners in Dominican Republic | Services | 2100 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
65 |  |  | Workshops on identification of allies/partners in Belize | Services | 1500 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
66 |  |  | Workshops on identification of allies/partners in Nicaragua | Services | 1200 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
67 |  |  | National Pilot Encounters El Salvador | Services | 7200 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
68 |  |  | National Pilot Encounters El Salvador | Services | 4320 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
69 |  |  | National Pilot Encounters Honduras | Services | 3600 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
70 |  |  | Regional youth conference in El Salvador | Services | 25000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
71 |  |  | SUT Support Unit Workshops El Salvador | Services | 96000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
72 |  |  | SUT Support Unit Workshops Guatemala | Services | 60000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
73 |  |  | SUT Support Unit Workshops Honduras | Services | 60000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
74 |  |  | Annual coordination meetings with the CCSICA | Services | 7500 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
75 |  |  | Regional ROC Conference in El Salvador | Services | 12000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
76 |  |  | Regional Civil Society meeting in El Salvador | Services | 16000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
77 |  |  | National Civil Society meetings in Guatemala | Services | 6000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
78 |  |  | National Civil Society meetings in Honduras | Services | 6000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
79 |  |  | National Civil Society meetings in El Salvador | Services | 8000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
80 |  |  | Annual National Coordination workshops in El Salvador | Services | 24000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
81 |  |  | Annual National Coordination workshops in Costa Rica | Services | 24000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
82 |  |  | Annual National Coordination workshops in Dominican Republic | Services | 24000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
83 |  |  | Annual National Coordination workshops in Guatemala | Services | 15000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
84 |  |  | Annual National Coordination workshops in Honduras | Services | 15000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
85 |  |  | Annual National Coordination workshops in Nicaragua | Services | 15000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
86 |  |  | Annual National Coordination workshops in Panama | Services | 18000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
87 |  |  | Annual National Coordination workshops in Belize | Services | 18000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
88 |  |  | Monthly meetings “Citizens for Security” in El Salvador | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
89 |  |  | Monthly meetings “Citizens for Security” in Guatemala | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
90 |  |  | Monthly meetings “Citizens for Security” in Honduras | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
91 |  |  | Monthly meetings “Citizens for Security” in Belize | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
92 |  |  | Monthly meetings “Citizens for Security” in Costa Rica | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
93 |  |  | Monthly meetings “Citizens for Security” in Dominican Republic | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
94 |  |  | Monthly meetings “Citizens for Security” in Nicaragua | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
95 |  |  | Monthly meetings “Citizens for Security” in Panama | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
96 |  |  | ROC meetings for civil society in El Salvador | Services | 16000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
97 |  |  | ROC meetings for civil society in Honduras | Services | 10000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
98 |  |  | ROC meetings for civil society in Guatemala | Services | 10000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
99 |  |  | ROC meetings for civil society in Nicaragua | Services | 10000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
100 |  |  | ROC meetings for civil society in Belize | Services | 10000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
101 |  |  | ROC meetings for civil society in Costa Rica | Services | 14000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
102 |  |  | ROC meetings for civil society in Dominican Republic | Services | 14000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
103 |  |  | ROC meetings for civil society in Panama | Services | 12000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
104 |  |  | 6 Gender workshops for 30 persons in El Salvador | Services | 45000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
105 |  |  | 6 Gender workshops for 30 persons in Guatemala | Services | 45000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
106 |  |  | 6 Gender workshops for 30 persons in Honduras | Services | 45000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
107 |  |  | 6 1-day Information Management, RBM, Monitoring and Evaluation in El Salvador | Services | 27000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
108 |  |  | 6 1-day Information Management, RBM, Monitoring and Evaluation in Guatemala | Services | 27000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
109 |  |  | 6 1-day Information Management, RBM, Monitoring and Evaluation in Honduras | Services | 27000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
110 |  |  | 3 1-day Quality control workshops in El Salvador | Services | 40500 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
111 |  |  | 3 1-day Quality control workshops in Honduras | Services | 40500 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
112 |  |  | 1-day Youth and Crime workshops for 20 persons in El Salvador | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
113 |  |  | 1-day Youth and Crime workshops for 20 persons in Guatemala | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
114 |  |  | 1-day Youth and Crime workshops for 20 persons in Honduras | Services | 54000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
115 |  |  | Regional workshop on Como Vamos Methodology in El Salvador | Services | 33333 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
116 |  |  | Regional workshop on Como Vamos Methodology in Guatemala | Services | 33333 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
117 |  |  | Regional workshop on Como Vamos Methodology in Honduras | Services | 33333 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
118 |  |  | South-South Cooperation workshops in El Salvador, | Services | 24000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
119 |  |  | South-South Cooperation workshops in Guatemala | Services | 24000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
120 |  |  | South-South Cooperation workshops in Honduras | Services | 24000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
121 |  |  | Awareness workshops for the media in El Salvador | Services | 72000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
122 |  |  | Awareness workshops for the media in Guatemala | Services | 72000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
123 |  |  | Awareness workshops for the media in Honduras | Services | 72000 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | YES |  |  |  | 2Q 2014 |  |  |  | x
124 |  |  | Diploma courses on Citizen Security in El Salvador | Services | 43750 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
125 |  |  | diploma courses on Citizen Security in Panama | Services | 43750 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
126 |  |  | Diploma courses on Citizen Security in Guatemala | Services | 43750 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
127 |  |  | Diploma courses on Citizen Security in Honduras | Services | 43750 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 |  |  |  | x
128 |  |  | Miscellaneous Workshop costs | Services | 7932 |  | x | x | x |  | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
129 |  |  | IT Goods for all projects under LTA | Goods | 319200 | [5 empty] | 1Q 2014 | 2Q 2014 | 10 days | x | [6 empty] | NO |  |  |  | 2Q 2014 | x
Note on D34: Admin: 17.5 años?