UNDP Romania

PIMS 3458 Improving Energy Efficiency in Low Income Areas and Households of Romania;

ATLAS #77064

Oct-Dec 2013

____________________________________________________________________________

The national experts (in Fuel Poverty, Financing, Legal, local sustainable materials) have finalized their studies. The respective reports are in the process of consolidation into an integrated report, while the main findings are followed up with national institutions and local policy makers in order to be adopted and used for implementation of actual fuel poverty alleviation measures. The 4th session of the Inter-Organizational Working Group has taken place, allowing policy making institutions to receive and exchange information relevant to fuel poverty tackling. All trainings for the Regional Development Agencies were delivered and the new, low cost, sustainable insulation materials have been officially certified. The fuel-poverty awareness campaign was implemented and the official website is now online. The second round for showcase thermal rehabilitation works was launched (to be finalized in January 2014). The Mid-term Evaluation is still under preparation, while the main fund-intensive activity of the implementing partner (MDRAP) was extended also to January 2014.