Management Response template

UNDP Management Response Template

Mid-Term Evaluation Report Date: February 2014

| Prepared by: Monica Moldovan | Position: Head of Programme | Unit/Bureau: ROU/RBEC |
| --- | --- | --- |
| Input into and update in ERC: June 2014 |  |  |

| Evaluation Recommendation or Issue 1: UNDP should take full formal responsibility and direct control over project implementation (Direct Implementation Modality) |
| --- |
| Management Response: UNDP has initiated a dialogue with the implementing partner in order to secure the agreement and cooperation with regard to change of implementation modality from NIM (with advances) to DIM. On the same time, UNDP country office has taken the necessary steps for HQ DIM clearance and authorization. |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking* |
|  |  |  | Comments | Status |
| 1.1 Inter-institutional dialogue on NIM-DIM change initiated | February 2014 | UNDP Programme |  | Achieved |
| 1.2Official letter of agreement on NIM-DIM change secured | 22 May 2014 | UNDP Programme |  | Achieved |
| Evaluation Recommendation or Issue 2: The project should have one full-time project manager fully responsible for management and coordination of all project activities |
| Management Response: UNDP will hire a full time project manager/coordinator |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking |
|  |  |  | Comments | Status |
| 2.1.Recruitment of project coordinator | June 1st | UNDP Programme |  | Achieved |
| 2.2.Recruitment of additional Monitoring and Implementation specialist | June 1st | UNDP Programme |  | Achieved |
| 2.3 |  |  |  |  |
| Evaluation Recommendation or Issue 3: Address also the most vulnerable households with lowest income – provide information on cheap solutions for do-it-yourself installation, demonstrate suitable solutions through on-the-job trainings, disseminate practical how-to guides for the most vulnerable groups |
| Management Response: UNDP will develop information materials on cheap insulation and EE solutions, affordable materials and “do it yourself” guides |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking |
|  |  |  | Comments | Status |
| 3.1 Identification of the most appropriate cheap materials that will be promoted | July 2014 | Project team/UNDP Programme Unit |  | Initiated |
| 3.2 Development of information materials | By December 2014 | Project team |  | Not started |
| 3.3 Organization of a series of events targeting the poorest segment of the population in the poor regions of Romania | By June 2015 | Project team |  | Not started |
| Evaluation Recommendation or Issue 4: Strengthen the link of the project with national programs and activities supporting energy efficiency in buildings to maximize its impact and additional direct GHG savings |
| Management Response: UNDP will focus on the National Rehabilitation Programme and Regional Operational Programme for the development of necessary normative acts or methodologies that will promote EE in buildings esp. in poor areas |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking* |
|  |  |  | Comments | Status |
| 1.1 Identification of the type of additional support to Ministry of Regional Development | September 2014 | Project team/UNDP Programme unit |  | Initiated |
| 1.2 Hiring technical expertise needed | November 2014 | Project team/UNDP Programme unit |  | Not started |
| 1.3. Development of the normative acts/draft legislation | June 2015 | Project team/UNDP Programme unit |  | Not started |
| Evaluation Recommendation or Issue 5: Strengthen and expand trainings and information dissemination |
| Management Response: Noted. UNDP project team will expand the trainings in relation to Recommendation no. 3 and within the budget limits |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking |
|  |  |  | Comments | Status |
| Organization of at least 3 training/dissemination sessions in three different areas, marked as poorest areas on poverty map. Topic: cheap affordable insulation materials for EE measures | June 2015 | Project team/UNDP programme unit |  | initiated |
| Evaluation Recommendation or Issue 6: Develop back up/mitigation plan B for demonstration of alternative sustainable insulation solutions based on local raw materials |
| Management Response: The project will develop a back-up plan for recalibrating the demonstrative retrofits and development of a local market for new ecological rehabilitation/construction materials. |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking |
|  |  |  | Comments | Status |
| 3.1 Assessment of the quantity of rehabilitation ecological materials that the producer- identified within the project- can supply by end 2014 | Sept 2014 | Project team |  | Initiated |
| 3.2 Identification of the exact no of buildings that can be retrofitted with this quantity of materials | Sept2014 | Project team |  | Initiated |
| 3.3 Assessment of the feasibility of having a local market developed at the pilot site | Sept 2014 | Project team |  | Initiated |
| 3.4 Development of alternative scenarios | Sept 2014 | Project team |  | Not started |
| 3.5 Implementation of alternative scenarios | June 2015 | Project team |  | Not started |
| Evaluation Recommendation or Issue 7: Work also with associations of apartment owners in multi-apartment buildings in low-income households to disseminate experience in implementing and financing energy efficiency |
| Management Response: Noted. Working with apartment owners associations has proven difficult due to their inability to function coherently, as the private apartment owners most often than not have different opinions. The project will identify- with the support of local authorities representatives member in National Steering Committee- those association of apartment owners in low income areas that are willing to engage in EE activities. |
| Key Action(s) | Time Frame | Responsible Unit(s) | Tracking* |
|  |  |  | Comments | Status |
| 1.1 Initiation of dialogue with local municipalities members in the project board | June 2014 | Project team |  | Achieved |
| 1.2 Identification of apartment owners associations | October 2014 | Project team |  | Initiated |
| 1.3. Engaging the owners associations through meetings or roundtables with the help of local authorities | June 2015 | Project team |  | Not started |