Agreed by UNDP Resident Representative / UNDP Director:

| Name, position | Signature | Date: (Month, day, year) |
| --- | --- | --- |
| Mr. Sascha Graumann, Resident Representative a.i., UNDP Russia | _______________________ | ________________________ |

INITIATION   PLAN

for a GEF Project Preparation Grant (PPG)

Section I. Brief Description of Initiation Plan

(one paragraph narrative)

The objective of this Project Preparation Grant (PPG) is to develop a full project document for a UNDP/GEF project in Biodiversity focal area addressing barriers to effective mainstreaming of biodiversity conservation in three major energy sectors in the Russian Federation: oil and gas, coal and hydropower. PPG proposal approved by the GEF Secretariat is presented in the Section II. below.

UNDP Russia will lead the project development process and manage the PPG budget. The PPG Atlas budget is presented in the Section III. “Total Budget and Work Plan”. UNDP Russia will be responsible for the selection and recruitment of PPG consultants (local and international), developing TORs, arranging travel and meetings, maintaining project disbursements. A tentative list of local and international consultants to be financed by the PPG is attached to the PPG proposal.

Quality assurance and technical advice for the full project development will be provided by the UNDP/GEF Regional Unit (Bratislava).

PPG Steering Committees will be established to review and endorse PPG outcomes. The Ministry of Natural Resources of the Russian Federation will chair the Steering Committee. Regular consultations (working meetings) will be carried out among key PPG participants (the Ministry of Natural Resources, UNDP, UNDP/GEF and project consultants) to plan for the project preparation activities, to review the TORs for key experts/consultants and analyze information gaps.

GEF PPG approved grant document and TBWP (see Section II. and Section III.)

Section II. GEF PPG approved grant document

request for project preparation grant (PPG)

Project Type: Full Sized Project

the GEF Trust Fund

Submission date:  March 6, 2009

GEF Project ID:

GEF Agency Project ID: 4241

Country(ies): Russian Federation

Project Title: Mainstreaming biodiversity conservation into Russia’s energy sector policies and operations

GEF Agency(ies): UNDP

Other Executing partner(s): Ministry of Natural Resources and Environment

GEF Focal Area(s): Biodiversity

GEF-4 Strategic program(s): BD-SP4

name of parent/program/umbrella project (if applicable): NA

a.   Project preparation Timeframe

| Start date of PPG | April 2009 |
| --- | --- |
| Completion date of PPG | March 2010 |

- Past project preparation activities ($)  	NA

C.  proposed project preparation activities ($)

| The PPG is requested to finance three components critical for the preparation of the FSP: Component 1. Detailed assessment of the institutional and legal environment at the national/regional levels and across the three major energy sectors (oil-and-gas, coal, and hydropower), taking into account the international guidance and practices: Preparatory activities under this component will be directly contributing to the full design of the Component I of the expected FSP (“Enabling Policy, legislative and institutional environment”) and will result in the following outputs: (i) information gathered, analyzed and collated on institutional and legal aspects important for biodiversity mainstreaming in energy, at the federal and regional levels, as well as at the level of sector-specific regulations and laws (oil and gas, hydropower and coal sectors), taking into account international best practices; (ii) analysis of the strengths and opportunities for mainstreaming biodiversity in energy, in parallel to analysis of the potential conflicts between energy land uses and conservation objectives; mechanisms/recommendations developed to address the conflicts; (iii) risk assessment and recommendations for mitigation measures; At the national policy level the preparatory activities under this component will include an assessment of: The national environment protection policies and legislation on Environmental Impact Assessment, state ecological expertise, national regulations and standards on the design of investment projects and their environmental safety with the view of improving the coverage of BD mainstreaming aspects in these regulations; National policy and legislative context and existing or missing regulatory prerequisites for the introduction of the “avoid-reduce-remedy” principles in the energy sectors. Extract lessons from the UNDP/GEF South Africa Grasslands project on mapping of areas where (a) energy development is to be avoided altogether; (b) energy projects are allowed, but should have mitigation measures to reduce biodiversity impacts; and (c) restoration is needed. Develop a strategy for the project to implement a similar approach in the Russian context. The legal requirements and barriers for full economic assessment (valuation) of biodiversity degradation and loss; The legal basis for, existing policies and plans and any regulatory gaps regarding compensation for biodiversity loss from energy development projects/investments; regulations on post-project rehabilitation methods with a view to require maximum proximity of the restored ecosystem to its pre-project ecology; Policy, legal and regulatory provisions and barriers for introduction of environmental insurance and biodiversity off-sets programmes; National land tenure context for spatial planning; At the regional (provincial) level the PPG assessment will focus on regions with heavy energy industry development and help identify/confirm regions with potential to host demonstration sites, and will review: Regional policies and regulatory frameworks affecting the proposed project plans; special consideration will be given to policies on the territorial (spatial) planning at the regional level; Region-specific energy development plans and investment proposals; Past experience in the regions with heavy industry development on introduction and enforcement of environmental protection and specifically biodiversity mainstreaming legislation and regulations; take stock of the willingness of regional governments to cooperate on biodiversity mainstreaming solutions. Confirm availability/willingness of certain regions/sites to be demonstration areas for the project. At the sectoral level the PPG will support the assessment of: Energy development programmes and plans by sector (oil and gas, coal, hydropower) including spatial planning and priority investment plans; Sector-specific regulations, standards, norms, guidelines currently preventing mainstreaming of conservation goals into energy development projects. The PPG assessment will also look at: (i) International best practice and experience in policy development, legal and regulatory frameworks and enforcement systems for effective mainstreaming of biodiversity conservation objectives into energy sector; this will include taking stock of relevant experience from the UNDP/GEF projects in South Africa and Mauritania; (ii) The legal context for the federal and regional administrative reform processes affecting the proposed project plans; and (iii) The current shortcomings and gaps/risks in the planning, policy and legal framework and related risks that may affect the efficacy of project activities, and recommendations on how to mitigate these constraints/risks. Component 2. Baseline biodiversity and industry assessments and development of detailed work-plans for the project’s sectoral components (Components II – IV): The preparatory activities under this component are key for defining the detailed barrier-removal strategy and specifics of sector work in Components II-IV of the proposed FSP. The outputs will be: (i) baseline analysis of the state of technology, know-how and information barriers for BD mainstreaming, energy sectors affecting globally valuable biodiversity per each sector (oil and gas, coal, hydropower); (ii) biodiversity pressures per industry qualified and quantified; (iii) selection of demonstration sites, and biodiversity and technologies solutions data developed at each site; (iv) BD SP-2 Tracking Tool completed; (v) global biodiversity benefits of the proposed project documented. Specifically, the activities covered under this component will: Analyze and document, country-wide, threats to biodiversity from energy development plans and energy operations (oil and gas, coal and hydropower sectors) and their root causes; Analyze the macroeconomic and political context at the national level (key business sectors, socio-economic development, political environment), and its current and future impacts on the biodiversity mainstreaming plans; Identify/confirm the technical and knowledge barriers to effective mainstreaming of conservation objectives into energy development plans and operations, per each of the three sectors; [this material will be critical to define the project’s barrier-removal strategy]; Preparatory work on sector-specific compendiums of biodiversity mainstreaming: assessments of options for biodiversity solutions in each industry (i.e. first outputs expected under each Component II-IV). Extract lessons from leading international guidance and adapt it to Russia’s context. Develop a detailed action plan to finalize the compendiums at the FSP stage; Establishing working contacts with the team working on the Integrated Risk Assessment Scheme for Mining at Shelf Areas, and agree on the work plan to add a biodiversity module not only on shelf, but also on the continent. Finalize the selection of the project areas from the following preliminary list: Arctic (Nenetsk AO), Caucasus (Krasnodar Krai, Dagestan Republic), Eastern Siberian Taiga (South of Yakutia (Sakha Republic), Sayany (Khakassia, Kemerovo oblast). For each project site, the PPG will: Define the spatial extent of the proposed project areas, Determine the current spatial distribution of land uses and levels of transformation in the proposed project areas, existing and potential conflicts among land uses affecting conservation objectives, Conduct biodiversity study with particular focus on unique flora and IUCN Red List species, and document threats to biodiversity; Elaborate biodiversity solutions to be tested; Analyze the conservation and economic/energy development plans, projects, programs and initiatives affecting or impacting on the proposed project activities (this will be cross-referenced to the general outcomes of Activity 1) in the project areas and correct the proposed solutions as need be; Reach agreement with local governments and companies/investors on implementation of demonstration projects; Select biodiversity impact indicators (with baseline values) to measure the project progress; Develop monitoring plan for each site, taking into account that the key monitoring instrument for the whole project is going to be the SP-2 Biodiversity tracking tool. Component 3. Assessment of the capacity of different agencies to support implementation of project activities This component is designed to ensure that implementation arrangements, partnership strategies and capacities are in place and adequate for the successful project implementation and its sustainability. Funding support from the PPG will be used to conduct an assessment of the capacity of the national and regional governmental agencies and corporate sector in respect of: (i) roles, functions and/or responsibilities in the energy sector development with the focus of biodiversity conservation mainstreaming; (ii) capacity constraints in supporting or implementing mainstreaming biodiversity activities. The focus of this assessment will be on identifying potential incentives and the capacity development needs of the different stakeholder groups to ensure the sustainability of project investments beyond the term of the project. The following will be appraised under this overarching activity: The roles, functions and responsibilities of different institutions and organizations in the regulation, planning, operations, compliance and performance monitoring of energy projects in oil and gas, coal and hydropower sectors; The governance, cooperation and partnership arrangements between these institutions and organizations; Existing and potential incentives (and disincentives) for energy companies and energy investment projects to mainstream conservation considerations; the level of interest in, and influence on the proposed project activities; existing level of corporate environmental responsibility and quality of non-financial reporting; level of penetration/influence of companies’ environmental performance information in the market indices; The capacity of these institutions to implement and sustain the proposed project activities, including recommendations for the ongoing development of capacity in the project design to address any gaps; and The feasibility of different options for the implementation of project activities and project governance. This will include the selection and detailed description of the preferred implementation and governance arrangements for the project. Component 4. Feasibility analysis and budget PPG funding will be used to assess the feasibility and to develop the detailed budget for the proposed project strategy. Preparatory activities under this component will cover: assessment of the social, economic and financial sustainability of proposed project activities; assessment of the alternatives to the project strategy and establishing the cost effectiveness of the preferred strategy and suite of activities; development of a replication strategy for project activities; development of a monitoring and evaluation plan and budget; costing the expected project outcomes and outputs, identify co-financing sources and secure co-financing commitments |
| --- |
| PPG activities | Outputs of the PPG Activities | PPG amount (a) | Co-financing (b) | Total, c = a + b |
| Block 1. Detailed assessment of the institutional and legal environment at the national/regional levels and across the three major energy sectors (oil-and-gas, coal, and hydropower), taking into account the international guidance and practices: | (i) information gathered, analyzed and collated on institutional and legal aspects important for biodiversity mainstreaming in energy, at the federal and regional levels, as well as at the level of sector-specific regulations and laws (oil and gas, hydropower and coal sectors), taking into account international best practices; (ii) stock taken of strengths and opportunities for mainstreaming biodiversity in energy, in parallel to analysis of the potential conflicts between energy land uses and conservation objectives; mechanisms / recommendations developed to have these conflicts addressed within the scope of FSP Component I; (iii) enable elaboration of an adequate project risk matrix and mitigation measures | 31,200 | 30,000 | 61,200 |
| Block 2. Biodiversity and industry assessments and development of detailed work-plans for the project’s sectoral components (Components II – IV): | (i) stock taken of the baseline state of technology, know-how and information barriers for BD mainstreaming, energy sectors affecting globally valuable biodiversity per each sector (oil and gas, coal, hydropower); (ii) biodiversity pressures per industry qualified and quantified; (iii) choice of demonstration sites finalized, and biodiversity and technologies solutions data developed for at each site; (iv) BD SP-2 Tracking Tool completed, (v) global biodiversity benefits of the proposed project documented. | 76,600 | 110,000 | 186,600 |
| Block 3. Assessment of the capacity of different agencies to support implementation of project activities | (i) recommendations for capacity building and institutional mainstreaming actions; and (ii) a description of the project governance and implementation arrangements | 23,200 | 20,000 | 43,200 |
| Block 4. Feasibility study and budget | (i) cost-effectiveness strategy; (ii) assessment of the social, economic and financial sustainability of proposed project activities; (iii) development of a replication strategy for project activities; (iv) development of a monitoring and evaluation plan and budget; (v) costing the expected project outcomes and outputs, identify co-financing sources and secure co-financing commitments | 42,636 | 20,000 | 62,636 |
| Total Project Preparation Financing | 173,636 | 180,000 | 353,636 |

D.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| GEF financing | 173,636 | 17,364 |
| Co-financing | 180,000 |  |
| Total | 353,636 | 17,364 |

E.  PPG  requested by agency(ies), focal area(s) and country(ies) 1      N/A

F.   PPG Budget Request

| Cost Items | Total Estimated Person Weeks for GEF Grant (PW) | GEF ($) | Co-financing ($) | Total ($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 157 | 100,000 | 160,000 | 260,000 |
| International consultants* | 17 | 51,000 |  | 51,000 |
| Travel |  | 12,636 | 5,000 | 17,363 |
| Miscellaneous** |  | 10,000 | 15,000 | 25,000 |
| Total PPG Budget |  | 173,636 | 180,000 | 353,636 |

* Please see Annex A for Consultant cost details and TOR.

** Miscellaneous costs involve mainly translation and interpretation costs and minor costs for PPG inception workshop

G.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| Yannick Glemarec, UNDP/GEF Executive Coordinator |  | 3/6/09 | Adriana Dinu | +421 905 428 238 | Adriana.dinu@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Position / Titles | $/Person Week1 | Estimated PWs2 | Tasks to be performed |
| --- | --- | --- | --- |
| Local |  |  |  |
| Leading national BD expert | 650 | 30 | The leading BD mainstreaming and baseline assessment expert will be responsible for collecting information on globally valuable biodiversity affected or threatened with the energy development plans; analysis of threats to biodiversity from energy sector and their root causes; socio-economic context; analysis of barriers to mainstreaming biodiversity conservation into energy policies, planning and operations. The lead expert will define tasks in the biodiversity groups for the other expert, will have overall coordination role in collection and compiling baseline information by other national PPG experts and communicate with international consultants. The following information will have to be collated and developed at the national level by the two biodiversity experts jointly with the BD-friendly technology experts in each sector at the national level: Analyze and documents, country-wide, threats to biodiversity from energy development plans and energy operations (oil and gas, coal and hydropower sectors) and their root causes; The macroeconomic and political context at the national level (key business sectors, socio-economic development, political environment), and its current and future impacts on the conservation mainstreaming plans; Coordinate and contribute to the threat-barrier analysis, [most of which will be implemented by the bd-friendly technology experts], Coordinate and contribute to the preparation of sector compendiums Coordinate the 4 national site planning experts to obtain detailed data on project demonstration areas. Contribute to project site studies. |
| Law and policy experts | 650 | 24 | A group of 2 national legal and policy experts will collect baseline information on policy, legal and regulatory context, outline legislative and regulatory barriers and gaps for mainstreaming biodiversity objectives at the national and regional levels. Specific functions: At the national policy level, analysis of: The national environment protection policies and legislation on Environmental Impact Assessment, state ecological expertise, national regulations and standards on the design of investment projects and their environmental safety with the view of improving coverage of BD mainstreaming aspects in these regulations; National policy and legislative context and existing or missing regulatory prerequisites for the introduction of the “avoid-reduce-remedy” principles in the energy sectors. The legal requirements and barriers for full economic assessment (valuation) of biodiversity degradation and loss; The legal basis for, existing policies and plans and any regulatory gaps in support of adequate compensation for biodiversity loss from energy development projects/investments; regulations on post-project rehabilitation methods with a view to require maximum proximity of the restored ecosystem to its pre-project ecology; Policy, legal and regulatory provisions and barriers for introduction of environmental insurance and biodiversity off-sets programmes; National land tenure context for spatial planning; The legal context for the federal and regional administrative reform processes affecting the proposed project plans; The current shortcomings and gaps/risks in the planning, policy and legal framework and related risks that may affect the efficacy of project activities, and recommendations on how to mitigate these constraints/risks At the regional (provincial) level, review: Regional policies and regulatory frameworks affecting the proposed project plans; special consideration will be given to policies on the territorial (spatial) planning at the regional level; Region-specific energy development plans and investment proposals; Take stock of past experience in the regions with heavy industry development on introduction and enforcement of environmental protection and specifically biodiversity mainstreaming legislation and regulations; take stock of the willingness of regional governments to cooperate on biodiversity mainstreaming solutions. Confirm availability/willingness of certain regions/sites to be demonstration areas for the project. The experts will outline the current shortcomings and gaps in the planning, policy and legal framework and related risks that may affect the efficacy of project activities, and provide recommendations for FSP planning. |
| Energy sector policies and planning expert/s (hydropower, oil and gas, coal) | 650 | 24 | Describe national and regional energy development plans in oil and gas, coal and hydropower sectors, specifically: Energy development programmes and plans by sector (oil and gas, coal, hydropower) including spatial planning and priority investment plans; Major corporate players in the selected sectors and pilot regions and their development/investment plans; Sector-specific regulations, standards, norms, guidelines affecting or preventing mainstreaming of conservation goals into energy development projects. Existing and new technical regulations and project development software for oil, gas, coal and hydropower projects with the recommendations to incorporate biodiversity information/requirements. Outline gaps and barriers at the policy and planning level and provide recommendations for the full project planning. |
| BD-friendly technology expert/s (hydropower, oil and gas, coal) | 650 | 24 | The experts will: Contribute to the analysis and documentation of the threats to biodiversity emanating from energy development plans and energy operations. This analysis is led by the BD lead national expert, and is assisted by the expert on energy policies and plans. Specifically, the bd-friendly technology experts will describe energy sectors affecting globally valuable biodiversity (oil and gas, coal, hydropower) with the focus of the state of technology, operational practices, know-how and information barriers for BD mainstreaming. (oil and gas, coal and hydropower sectors) and their root causes; Identify/confirm the technical and knowledge barriers to effective mainstreaming of conservation objectives into energy development plans and operations, per each of the three sectors; [this material will be critical to define the project’s barrier-removal strategy]; Preparatory work on sector-specific compendiums of biodiversity mainstreaming: assessments of options for biodiversity solutions in each industry (i.e. first outputs expected under each Component II-IV). Review of sectoral risk assessment and risk mitigation schemes with the view of incorporating biodiversity elements. |
| Pilot sites planning experts (x 4) | 600 | 20 | Under the leadership of the lead national BD expert, describe characteristics of the four proposed project areas. [The preliminary list includes Arctic (Nenetsk AO), Caucasus (Krasnodar Krai, Dagestan Republic), Eastern Siberian Taiga (South of Yakutia (Sakha Republic), Sayany (Khakassia, Kemerovo oblast)] and identify demonstration sites and activities for the proposed project. Define the spatial extent of the proposed project areas, Determine the current spatial distribution of land uses and levels of transformation in the proposed project areas, existing and potential conflicts among land uses affecting conservation objectives, Conduct detailed biodiversity study (i.e. species, habitats and ecosystem processes, protected areas) with particular focus on unique flora and IUCN Red List species An analysis and documentation of the threats to biodiversity from energy development plans and energy operations (oil and gas, coal and hydropower sectors) and their root causes at project sites Elaborate biodiversity solutions to be tested, Analyze the conservation and economic/energy development plans, projects, programs and initiatives affecting or impacting on the proposed project activities (this will be cross-referenced to the general outcomes of Activity 1) in the project areas and correct the proposed solutions as need be, Reach agreement with local governments and companies/investors on implementation of demonstration projects, Elaboration of biodiversity indicators (with baseline values) to measure the project progress, Develop monitoring plan for each site, taking into account that the key monitoring instrument for the whole project is going to be the SP-2 Biodiversity tracking tool. The collation of baseline information for the four proposed project areas will primarily involve a desk review of existing data and reports. This will then be supplemented by focused interviews and consultations with key stakeholders. No new field research or surveys will be conducted with PPG funding support. The SP-2 Biodiversity Tracking Tool will be completed as a baseline for future project M&E at the implementation phase. |
| Institutional capacity expert | 650 | 18 | Describe: The roles, functions and/or responsibilities of various agencies in the energy sector development with the focus of biodiversity conservation mainstreaming; The roles, functions and responsibilities of different institutions and organizations in the regulation, planning, operations, compliance and performance monitoring of energy projects in oil and gas, coal and hydropower sectors; The governance, cooperation and partnership arrangements between these institutions and organizations; The capacity of these institutions to implement and sustain the proposed project activities, including recommendations for the ongoing development of capacity in the project design to address any gaps. The feasibility of different options for the implementation of project activities and project governance. Deliver: recommendations for capacity building and institutional mainstreaming actions; description of the project governance and implementation arrangements; |
| Private sector involvement and market instruments expert/s | 650 | 10 | Conduct a private sector assessment focusing on energy sector companies operating in Russia and in the project sites. Describe: Existing and potential incentives (and disincentives) for energy companies and energy investment projects to mainstream conservation considerations; The level of interest in, and influence on the proposed project activities; Existing level of corporate environmental responsibility and quality of non-financial reporting; Level of penetration/influence of companies’ environmental performance information in the market indices. Review existing practices for preparation of corporate and statistical plans and reports of energy companies and provide recommendations for incorporating biodiversity impact and information into the non-financial reporting of the energy companies. Recommend tools for presentation of biodiversity information at the stock markets. Coordinate the work with the PPG Institutional capacity expert. |
| Other | 500 | 7 | PPG might involve other technical expertise as needed in the course of the development of the full project. |
| International |  |  |  |
| BD mainstreaming policy development specialist | 3,000 | 10 | Compile and share with the national PPG team and stakeholders the international best experience in policy development, legal and regulatory frameworks and enforcement systems for effective mainstreaming of biodiversity conservation objectives into energy sector; including analysis of the UNDP/GEF projects in South Africa and Mauritania, Based on the inputs from national experts and in close cooperation with the lead national expert on BD mainstreaming and baseline assessment compile final baseline/situational analysis for the full project. Based on the international experience assist in reconfirming/specifying the project strategy, finalizing project sections on: (a) An assessment of the social, economic and financial sustainability of proposed project activities; (b) Assessment of alternatives to the project strategy and establishing the cost effectiveness of the preferred strategy and suite of activities; (c) A replication strategy for project activities; (d) Assessment of the risks to the proposed project activities and identifying measure to mitigate these risks; (e) incremental cost analysis; Assist in setting up a project monitoring and evaluation system for the full project including: A set of biodiversity indicators with baseline values and end-project targets; Logical framework for the project (SRF) M&E plan and budget. |
| Sectoral consultant/s on BD mainstreaming practices and mainstreaming tools in hydropower, oil and gas and coal sectors | 3,000 | 7 | Compile and share with the national PPG team and stakeholders the international best practice and experience in sector-specific practices, tools and technical solutions for effective mainstreaming of biodiversity conservation objectives into energy sector (oil and gas, coal and hydropower). Extract lessons from the UNDP/GEF South Africa Grasslands project on mapping of areas where (a) energy development is to be avoided altogether; (b) energy projects are allowed, but should have mitigation measures to reduce biodiversity impacts; and (c) restoration is needed. Develop a strategy for the project to implement a similar approach in the Russian context. Assistance in the feasibility study on the introduction of off-sets in mining sectors in Russia, based on international best practices. Help build international contacts and cooperation with international conservation agencies involved in biodiversity mainstreaming projects in the energy sector; with leading energy companies and other players that possess experience in biodiversity mainstreaming. |

1 Provide dollar amount per person week.

2 Provide person weeks  needed to carry out the task and corresponds to the dollar amount per person week in the previous column.

Section III. Total Budgets and Work Plans

| Award ID: | 00057111 |
| --- | --- |
| Award Title: | PIMS 4241 BD PPG: Mainstreaming biodiversity conservation into Russia’s energy sector policies and operations |
| Business Unit: | RUS 10 (UNDP Russia) |
| Project Title: | PIMS 4241 BD PPG: Mainstreaming biodiversity conservation into Russia’s energy sector policies and operations |
| Project ID: PIMS no.4051 | 00070439 |
| Implementing Partner (Executing Agency) | UNDP CO |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Total (USD) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Assessment of the institutional and legal environment | UNDP | 62000 | GEF | 71300 | Local Consultants | 31,200 | 31,200 |
|  |  |  |  |  | Total Outcome 1 | 31,200 | 31,200 |
| OUTCOME 2: Baseline assessments and pilot projects | UNDP | 62000 | GEF | 71300 | Local Consultants | 50,600 | 50,600 |
|  |  |  |  | 71200 | International Consultants | 21,000 | 21,000 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 |
|  |  |  |  |  | Total Outcome 2 | 76,600 | 76,600 |
| outcome 3: Institutional capacity and stakeholder assessment | UNDP | 62000 | GEF | 71300 | Local Consultants | 18,200 | 18,200 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 |
|  |  |  |  |  | Total Outcome 3 | 23,200 | 23,200 |
| OUTCOME 4: Feasibility study and budget | UNDP | 62000 | GEF | 71200 | International Consultants | 30,000 | 30,000 |
|  |  |  |  | 71600 | Travel | 2,636 | 2,636 |
|  |  |  |  | 74500 | Miscellaneous | 10,000 | 10,000 |
|  |  |  |  |  | Total Outcome 4 | 42,636 | 42,636 |
|  |  |  |  | PROJECT TOTAL | 173,636 | 173,636 |

| Summary of Funds: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | GEF |  | $ | $173,636 |
|  |  |  |  | Government of Russia (in-kind) |  | $ | $180,000 |
|  |  |  |  | TOTAL |  | $ | $353,636 |

# Footnotes

Project ID number will be assigned by GEFSEC.  If PIF has already been submitted, please use the same ID number as PIF.

Summary table should include all financing of all kinds: GEF financing, cofinancing, cash, in-kind, etc.  etc

# Text boxes

Total budget:		 	US$353,636

Allocated resources:

- GEF		 	US$173,636

- Regular

- Other:

- In kind contributions

Government of Russia	US$180,000

Programme Period: 2008-2010

Programme Component: Energy and environment

PPG Title: Mainstreaming biodiversity conservation into Russia’s energy sector policies and operations

ATLAS Award: 00057111

ATLAS Project ID: 00070439

PIMS Project ID: 4241

Duration:	April 2009 – March 2010

Management Arrangement: UNDP CO execution

Country:  Russia

UNDAF Outcome(s)/Indicator(s):

_____________________________________

(Link to UNDAF outcome., If no UNDAF, leave blank)

Expected Outcome(s)/Indicator (s):

Improved environmental sustainability of development processes /

Environmental dimension in development policy

(CP outcomes  linked t the SRF/MYFF goal and service line)

Expected Output(s)/Indicator(s):

Conserved ecosystems are considered as important resource for sustainable development

(CP outcomes  linked t the SRF/MYFF goal and service line)