Agreed by UNDP Resident Representative / UNDP Director:

| Name, position | Signature | Date: (Month, day, year) |
| --- | --- | --- |
| Mr. Frode Mauring, Resident Representative, UNDP Russia | _______________________ | ________________________ |

INITIATION   PLAN

for a GEF Project Preparation Grant (PPG)

Section I. Brief Description of Initiation Plan

(one paragraph narrative)

The objective of this Project Preparation Grant (PPG) is to develop a medium-sized project document for a UNDP/GEF project in Climate Change focal area promoting energy efficiency and low-carbon technologies in the Russian Federation by greening Sochi 2014 Olympic Games. PPG proposal approved by the GEF Secretariat is presented in the Section II. below.

UNDP Russia will lead the project development process and manage the PPG budget. The PPG Atlas budget is presented in the Section III. “Total Budget and Work Plan”. UNDP Russia will be responsible for the selection and recruitment of PPG consultants (local and international), developing TORs, arranging travel and meetings, maintaining project disbursements. A tentative list of local and international consultants to be financed by the PPG is attached to the PPG proposal.

Quality assurance and technical advice for the full project development will be provided by the UNDP/GEF Regional Unit (Bratislava).

PPG Steering Committee will be established to review and endorse PPG outcomes. The Ministry of natural resources and environment of the Russian Federation will chair the Steering Committee. Regular consultations (working meetings) will be carried out among key PPG participants (Ministry of natural resources and environment of the RF, State Corporation “Olympstroy”, National Organization Committee for the Sochi Olympics and others) to plan for the project preparation activities, to review the TORs for key experts/consultants and analyze information gaps.

GEF PPG approved grant document and TBWP (see Section II. and Section III.)

Section II. GEF PPG approved grant document

request for project preparation grant (PPG)

Project Type: Medium Sized Project

the GEF Trust Fund

Submission date:  21 July 2009

GEF Project ID: 4030

GEF Agency  Project ID: 4320

Country(ies): Russian Federation

Project Title: Greening 2014 Sochi Olympics: A Strategy and Action Plan for the Greening Legacy

GEF Agency(ies):

Other Executing partner(s): Ministry of natural resources and environment of the RF

GEF Focal Area(s):

GEF-4 Strategic program(s): CC-1, CC-3, CC-5(see preparation guidelines section on exactly what to write)

name of parent/program/umbrella project (if applicable):  n/a

a.   Project preparation Timeframe

| Start date of PPG | August 2009 |
| --- | --- |
| Completion date of PPG | December 2009 |

- Past project preparation activities ($)  	n/a

| List of Past Project Preparation Activities | Output of the Activities | Project Preparation Amount (a) | Co-financing (b) | Total c = a + b |
| --- | --- | --- | --- | --- |
| Total Project Preparation Financing |  |  |  |

C.  proposed project preparation activities ($)

| The PPG will finance the following activities aimed at the development of the MSP proposal: 1. Baseline analysis, stock-taking of infrastructure development plans and of the other national preparatory activities for the Olympic Games. 1.1. Review of infrastructure development plans, power planning and suggested technical solutions for the Sochi Olympics. 1.2. Assessment of current knowledge on and mainstreaming of climate change mitigation agenda into Olympics planning and investments. 1.3. Review and assessment of existing regulatory framework (national, regional, local, corporate) and regulatory gaps related to planning and implementation of project activities – building norms, energy efficiency incentives, environmental regulations, etc. 1.4. Stakeholder assessment and analysis, capacity building needs assessment, stakeholder involvement plan and capacity building plan. 1.5. Stock-taking of available national and international best practices on events greening. 1.6. Review and stock-taking of on-going and planned awareness, advocacy and public engagement programmes for Olympics. 1.7. Stock-taking and analysis of investment planning, financing framework and public-private partnerships for Olympics, co-financing consultations. 2. MSP project scoping, project strategy and costing. 2.1. Project strategy and project scoping. 2.2. Cost effectiveness analysis and incremental costs analysis. 2.3. Barrier and risks assessment and risk management strategy. 2.4. Project costing and budget; co-financing framework. 2.5. Assessment of GHG emission reduction potential; global environmental benefits, national and local benefits sought from the project. 2.6. M&E framework, a set of measurable indicators. 2.7. Project management, implementation and coordination arrangements, TORs for MSP consultants. |
| --- |
| List of Proposed Project Preparation Activities | Output of the PPG Activities | Project Preparation Amount (a) | Co-financing (b) | Total c = a + b |
| Baseline analysis; stock-taking of infrastructure development plans and of other preparatory activities for the Olympic Games | Baseline situation analysis; assessment of planning and regulatory framework; stakeholder assessment and involvement plan; capacity building plan. | 20,000 | 50,000 | 70,000 |
| MSP project scoping, project strategy and costing | MSP project document and CEO endorsement template incorporating a project strategy and M&E plan, cost effectiveness analysis, incremental costs assessment, GEF and co-financing budgets, barrier and risk analysis, GEB analysis, project implementation arrangements and TORs. | 35,000 | 20,000 | 55,000 |
| Total Project Preparation Financing | 55,000 | 70,000 | 125,000 |

D.  Financing plan summary for project preparation grant: ($)

|  | Project Preparation | Agency Fee |
| --- | --- | --- |
| GEF financing | 55,000 | 5,500 |
| Co-financing | 70,000 |  |
| Total | 125,000 | 5,500 |

E.  PPG  requested by agency(ies), focal area(s) and country(ies) 1      n/a

| GEF Agency | Focal Area | Country Name/ Global | (in $) |
| --- | --- | --- | --- |
|  |  |  | PPG (a) | Agency Fee (b) | Total c = a + b |
| Total PPG Requested |  |  |  |

1  No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

F.   PPG Budget Request

| Cost Items | Total Estimated Person Weeks for GEF Grant (PW) | GEF ($) | Co-financing ($) | Total ($) |
| --- | --- | --- | --- | --- |
| Local consultants * | 20 | 15,000 | 45,000 | 60,000 |
| International consultants* | 10 | 30,000 |  | 30,000 |
| Travel |  | 5,000 | 15,000 | 20,000 |
| Miscellaneous (translation) |  | 5,000 | 10,000 | 15,000 |
| Total PPG Budget |  | 55,000 | 70,000 | 125,000 |

*  Annex A for Consultant cost details should be prepared first before completing this table.  See notes on Annex A for the 
     required detailed information.  This table is the sum of all local and international consultants presented in Annex A.

G.   GEF Agency(ies) Certification

This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation.

| Agency Coordinator, Agency name | Signature | Date (Month, day, year) | Project Contact Person | Telephone | Email Address |
| --- | --- | --- | --- | --- | --- |
| John Hough UNDP/ GEF Officer-in-Charge |  | July 21, 2009 | Marcel Alers, Principal Technical Advisor Climate Change Mitigation UNDP-BDP/EEG | +1-212-906-6199 | marcel.alers@undp.org |

Annex A

Consultants Financed by the Project Preparation Grant (PPG)

| Position / Titles | $/ Person Week1 | Estimated PWs2 | Tasks to be performed |
| --- | --- | --- | --- |
| Local |  |  |  |
| Infrastructure planning expert | 750 | 7 | Review of the Sochi Olympic infrastructure development plans; Review and assess power supply planning; Analyze suggested and available technical and technological solutions for the Sochi Olympics. Assess current knowledge on and mainstreaming of climate change mitigation agenda into Olympics planning and investments. Assess existing regulatory framework (national, regional, local, corporate) and regulatory gaps: building norms, energy efficiency incentives, environmental regulations, tender procedures, etc; Analyze investment plans, financing framework and public-private partnerships for Olympics, conduct co-financing consultations; Compile PPG situation analysis; Provide recommendations and inputs for the MSP strategy and scoping, in particular for components on green standards, energy efficiency and power planning, renewable energy and transport, including costing of proposed outputs. Suggest MSP management, implementation and coordination arrangements; Provide inputs for the TORs for MSP technical consultants. |
| Advocacy, awareness and stakeholder analysis expert | 750 | 7 | Complete stakeholder assessment and stakeholder involvement plan; Complete capacity building needs assessment and capacity building plan; Compile information on available national and international best practices on events greening; Review and analyze on-going and planned awareness, advocacy and public engagement programmes for Olympics; Build partnerships with national NGOs and media; Provide recommendations and inputs for the MSP strategy and scoping, in particular for components on public awareness and advocacy strategy and on carbon offsets program, including costing of proposed outputs. Provide inputs for the TORs for MSP technical consultants. |
| GHG assessment expert | 750 | 4 | Review baseline analysis report and infrastructure planning completed by the Infrastructure Planning Expert; Complete GHG assessment for baseline and GEF alternative scenario (early mainstreaming of CC mitigation agenda into planning and investments); Assess global environment benefits sought from the project; propose and justify a proposed methodology for the GHG assessment based on the GEF guidelines; Provide recommendations for the carbon offsets programme for the MSP. |
| Other | 750 | 2 | Other experts might be engaged as needed during the PPG implementation |
| International |  |  |  |
| Green standards and energy efficiency consultant | 3,000 | 7 | Review and present international best practice on international events greening; Review and present international best practice on green standards, energy efficiency and renewable energy technologies applicable for Sochi Winter Olympics; Based on the baseline analysis report by national experts propose MSP project strategy and project activities; M&E framework, plan and budget; Complete cost effectiveness analysis and incremental costs analysis Complete barrier and risks assessment and suggest a risk management strategy for the MSP; Based on the inputs from the national team complete project costing, GEF and co-financing budgets; Based on the inputs from national GHG assessment expert verify the assessment of GHG emission reduction potential and global environmental benefits analysis. |
| Carbon offsets and business engagement consultant | 3,000 | 3 | Share international experience and best practice on carbon offsets programmes, provide recommendations for the MSP activities; Provide recommendations on event greening and a strategy and criteria for the “carbon neutral” Olympic games; Provide inputs to GHG assessment as necessary; Provide lessons and recommendations for the MSP public and business engagement strategy and activities. |

1  Provide dollar amount per person week.

2   Provide person weeks  needed to carry out the task and corresponds to the dollar amount per person week in the previous column.

Section III. Total Budgets and Work Plans

| Award ID: | 00058329 |
| --- | --- |
| Award Title: | PIMS 4320 CC PPG: Greening 2014 Sochi Olympics: A Strategy and an Action Plan for Greening Legacy |
| Business Unit: | RUS 10 (UNDP Russia) |
| Project Title: | PIMS 4320 CC PPG: Greening 2014 Sochi Olympics: A Strategy and an Action Plan for Greening Legacy |
| Project ID: PIMS no.4320 | 00072416 |
| Implementing Partner (Executing Agency) | UNDP CO |

| GEF Outcome/Atlas Activity | Responsible Party/ Implementing Agent | Fund ID | Donor Name | Atlas Budgetary Account Code | ATLAS Budget Description | Amount Year 1 (USD) | Total (USD) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OUTCOME 1: Baseline data collection and information gap analysis | UNDP | 62000 | GEF | 71300 | Local Consultants | 15,000 | 15,000 |
|  |  |  |  | 71600 | Travel | 5,000 | 5,000 |
|  |  |  |  |  | Total Outcome 1 | 20,000 | 20,000 |
| outcome 2: Project scoping and project strategy | UNDP | 62000 | GEF | 71200 | International consultants | 30,000 | 30,000 |
|  |  |  |  | 74500 | Miscellaneous | 5,000 | 5,000 |
|  |  |  |  |  | Total Outcome 4 | 35,000 | 35,000 |
|  |  |  |  | PROJECT TOTAL | 55,0000 | 55,000 |

| Summary of Funds: |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | GEF |  | $ | $55,000 |
|  |  |  |  | Government of Russia (in-kind) |  | $ | $70,000 |
|  |  |  |  | TOTAL |  | $ | $125,000 |

# Footnotes

Project ID number will be assigned by GEFSEC.  If PIF has already been submitted, please use the same ID number as PIF.

Summary table should include all financing of all kinds: GEF financing, cofinancing, cash, in-kind, etc.  etc

# Text boxes

Total budget:		 	US$125,000

Allocated resources:

- GEF		 	US$55,000

- Regular

- Other:

- In kind contributions

Government of Russia	US$70,000

Programme Period: 2008-2010

Programme Component: Energy and environment

PPG Title: Greening 2014 Sochi Olympics: A Strategy and an Action Plan for Greening Legacy

ATLAS Award: 00058329

ATLAS Project ID: 00072416

PIMS Project ID: 4320

Duration:	September 2009 – January 2010

Management Arrangement: UNDP CO execution

Country:  Russia

UNDAF Outcome(s)/Indicator(s):

_____________________________________

(Link to UNDAF outcome., If no UNDAF, leave blank)

Expected Outcome(s)/Indicator (s):

Improved environmental sustainability of development processes /

Environmental dimension in development policy

(CP outcomes  linked t the SRF/MYFF goal and service line)

Expected Output(s)/Indicator(s):

Energy efficiency measures are incorporated into local development strategies

(CP outcomes  linked t the SRF/MYFF goal and service line)