## Plan Jan to Mar 2020
Ministry in Charge of Emergency Management
Disaster Programme/ SPIU
QUARTER WORK PLAN - JANUARY TO MARCH 2020
Project " Strengthening National and Local Disaster Risk Management Capacity, Resilience and Enhancing Preparedness and Early Warning System in Rwanda"
Intended Outcome as stated in the UNDAF/Country Programme Results and Resource Framework: Outcome 2: By 2023 Rwandan institutions and communities are more equitably, productively and sustainably managing natural resources and addressing climate change Outcome 4: By 2023 people in Rwanda, particularly the most vulnerable have increased resilience to both natural and man-made shocks and enjoy a life free from all forms of violence and discrimination
Applicable Output(s) from the UNDP Strategic Plan: Output 3 :Build resilience to shocks and crises
Project outcome : Increasing resilience to climate and natural disaster through evidence-based disaster preparedness and effective early warning system.
Activities | Activity Planning Description | Indicators (cfr project) | Targets (Cfr annual plan) | TIMEFRAME (2020) |  |  | Quarter Budget |  |  | Annual budget as reference (USD)
|  |  |  | Jan | Feb | March | Source of Funds | TOTAL (RWF) | USD
Output1: 00114220 Institutions at national, district and community level have improved technical capacities to reduce risks, manage and respond to natural disasters and limit gender-differentiated impacts
1.3 Enhance the capacity of DRR/DRM organizations involved in disaster management: MINEMA, NPDM, METEO Rwanda and local staff including disaster management committees | conduct onel training programe on disaster risk assessment with line departments at the district level | Number of MINEMA and Meteo Rwanda staff, and members of DIDIMACs and SEDIMACs men and women trained that have improved technical skills in risks reduction, management and response to natural disasters and limit gender-differentiated impacts | Training on disaster management and preparedness at Sector and District level conducted |  |  | X | UNDP-TRAC | 1506984.64 | 1616 | 12465
1.6 Support to the effective operation of NPDM and to the development, update and dissemination of DM policies, strategies and plans. | conduct the NPDM consultation workshop/meeting for national strategy for DRR | Number of NPDM meetings held | 1 meeting |  |  | x | UNDP-TRAC | 3730160 | 4000 | 8000
1.7 Support to mainstream DRR/DRM into national and district Development Plans and Development Sectors | Monitoring of DRR mainstreaming status in Nyarugenge, Rulindo,Rwamagana, Gicumbi and Ngoma Distrcts; Monitoring of project implementation | Number of development sectors and districts in which DRR is updated and mainstreamed at national and local level | 1 District |  | X | X | UNDP-TRAC | 1865080 | 2000 | 8000
Sub total for output 1 | [7 empty] | 7102224.64 | 7616 | 28465
Output2: 00114221 Increased knowledge and skills
2.4.Conduct DRR awareness raising activities among population through TV/radio programmes and production targeting vulnerable population and including specific gender awareness activities | community based awareness raising activities on DRR through Radia, TV, printed materials, and community meetings; prepare for the ToR and procurment to hire a national consultatant to conduct the public awareness survey. | Percentage of Rwanda’s male, female and vulnerable population in selected 10 districts prone to disasters aware of disaster risk | 85% |  | X | X | UNDP | 5595240 | 6000 | 35000
2.6.Collect, document and cover disaster data, events and evidences through digitalized system for public awareness and communication | support communication team for disaster documentation | % of disaster program event and best practivce covered, documented, digitalised and published for awareness | Disaster communication team operationalised - All (100%) informative events and best practices covered , documented and published for awareness | X | X | X | UNDP | 2154167.4 | 2310 | 16170
Sub total for output 2 | [7 empty] | 7749407.4 | 8310 | 51170
Output 3 00114222: Enhanced multi hazard early warning systems to enable effective preparedness, response and recovery
3.3 Upgrade national disaster communication system and provide real-time early warnings | upgrade the communication system to disseminate warning from centre to local ; conduct trainings for local leaders at the community level | Percentage of disasters from extreme weathers warned 24 hours before occurring | 75% | x | x | x | UNDP | 4122759.34 | 4421 | 25393
Sub total | [7 empty] | 4122759.34 | 4421 | 25393
Output 4: 00114223 Strengthened Communication
4.4.Support the implementation of innovative mitigation and adaptation measures through community-based approach including specific measures implemented by local women’s groups’ | support communities in Musanze and Ngororero Districts to develop innovative mitigation and adaptation projects to prevent hydrometeorological disasters. | Number of households (gender-disaggregated, female-headed and male-headed) having benefitted from the implementation of disaster mitigation project | 300HHs Disaster mitigation projects Identified |  |  | x | UND | 932540 | 1000 | 33520
4.5.Support innovative socioeconomic initiatives of population vulnerable to disasters | support micro projects related to livestoock, agriculture, handcraft and Carpentry, Masonry and tailoring as identified by beneficiaries; conduct a kick off meeting and training for local people | Number of community members identified to be benefited from economic activities; Number. of trained groups | All beneficiaries selected and grouped in associations /groups - Train grouped members | x | x | x | UNDP | 1119048 | 1200 | 25000
Sub total output 4 | [7 empty] | 2051588 | 2200 | 58520
Project Management
MINEMA Programme management support | SPIU salsary support for SPIU Coordinator, Program Manager, Disaster Project Specialist, Disaster Technical Advisor, Accountant; Bank charges | % of project staff remunerated | 100% of project staff | X | X | X | UNDP-TRAC | 26076616.02 | 27963 | 111852
Sub total Project management | [7 empty] | 26076616.02 | 27963 | 111852
TOTAL | [7 empty] | 47102595.4 | 50510 | 275400
Date: 12/02/2020 | Date: /02/2020
Prepared by : | Approved by:
HODARI Jean | KAYUMBA Olivier |  |  | Stephen Rodriques
Ag. SPIU Coordinator | MINEMA Permanent Secretary |  |  | UNDP Resident Representative