United Nations Development Programme

PIMS No. 3592 - ENABLING ACTIVITIES FOR THE PREPARATION OF SUDAN‘S SECOND NATIONAL COMMUNCIATION TO THE UNFCCC

Project ID: 00046263

##### Brief Description

This project aims to assist Sudan with the enabling activities necessary to prepare and report the Second National Communication to the Conference of Parties in accordance with guidance of the UN Framework Convention on Climate Change (UNFCCC) and in the long tern, to strengthen Sudan’s capacity to fulfill its commitments to the UNFCCC on a continuing basis. The objectives of the project are based upon Sudan’s previous experience in developing the Initial National Communication and through a self-assessment exercise also carried out. There are several main goals of the project including; (a) preparation of an up-to-date national GHG inventory and the establishment of a national system for regular update of the GHG inventory; (b) elaborate a programme of measures to mitigate GHG emissions; (c) strengthening of national technical and institutional capacity and institutionalization of the National Communications process; (d) increased scientific understanding of vulnerability and adaptation to future climate change in Sudan; (e) preparation of the Second National Communication of Sudan and submission to the COP. Stakeholder consultations and public awareness activities are also proposed as elements of this project with the overall goal of enhancing general knowledge and awareness on climate change-related issues in The Republic of Sudan. The goal of these activities is to encourage and enable national planners and policy makers to take climate change-related issues into account in their work at the national level.

Table of Contents

|  | Page |
| --- | --- |
| Signature page | 3 |
| Part I: Elaboration of Narrative: 1.1 Situational Analysis | 5 5 |
| 1.2 Strategy | 7 |
| 1.3 Logical Results - Resource Framework | 7 |
| Part 2: 2.1: Budget | 12 |
| Table 1: Annual Workplan Budget Sheet: Year 2007 | 8 |
| Table 2: Annual Workplan Budget Sheet: Year 2008 | 16 |
| Table 3: Annual Workplan Budget Sheet: Year 2009 | 19 |
| Table 4: Government of Sudan in Kind contribution | 21 |
| Table 5: detailed workplan for implementation of Sudan’s SNC activities |  |
| 2.2 Management Arrangement | 22 |
| 2.3 Monitoring and Evaluation | 25 |
| 2.4. Legal Context | 26 |
| Part 3:Appendices | 27 |
| Appendix A: Summary report of the self-assessment exercise | 27 |
| A.1. Scope and Approach to Stocktaking Analysis | 27 |
| A.2. Summary of main findings of the self - assessment | 27 |
| A.2.1. Lessons and Good Practice | 28 |
| A.2.3. Identified gaps, priorities and methodologies –GHG Inventory | 28 |
| A.2.2. Difficulties and Barriers Associated with the INC | 29 |
| A.2.4. Identified gaps, priorities and methodologies – GHG Mitigation Analysis | 29 |
| A.2.5. Identified gaps, priorities and methodologies – vulnerability and Adaptation | 30 |
| A.2.6. new studies and Areas of Work | 30 |
| A.2.7. Difficulties and barriers Associated with INC | 31 |
| A.2.8. Priorities for Sudan’s SNC’s | 31 |
| A.2.9. Synergies | 31 |
| Appendix B: technical components of the project proposal |  |
| B.1. Background/Context | 33 |
| B.2 Project Objectives | 33 |
| B.3. Project Strategy | 34 |
| B.4. Project’s Activities | 35 |
| B.4.1 Preparing the National Circumstances chapter | 35 |
| B.4.2 Updating the national GHG Inventory | 35 |
| B.4.3. Assessing measures to facilitate Adequate Adaptation to Climate Change | 36 |
| B.4.4. Assessing programmes to mitigate GHG emissions | 37 |
| B.4.5. Assessing other information considered relevant to the achievement of the convention | 39 |
| B.4.6. Understanding Constraints, gaps and related financial, technical and capacity needs. | 39 |
| B.5. Institutional Framework for Project Implementation | 41 |
| B.6. Assessing project Impact | 41 |
| B.7. project Risks | 41 |
| B.8. detailed Workplan | 42 |
| Appendices (C.1-C.4); Terms of Reference (TORs) | 46 |
| Appendix D: Letters of Endorsement | 53 |
| Appendix E: stakeholders participated in the Stocktaking | 55 |

SIGNATURE PAGE

Country:     Sudan

UNDAF Outcome(s)/Indicator(s):

(Link to

NDAF outcome., If no UNDAF, leave blank)

Expected Outcome(s)/Indicator (s):	       Capacities in govt. and civil society to manage natural resources for sustainable  livelihoods, to promote equitable access to land ; and to meet global environmental commitments strengthened.

(CP outcomes  linked t the SRF/MYFF goal and service line)    National government capacities strengthened to meet the global environmental conventions and commitments.  Land commissions with capacity to perform its mandate as stipulated in the CPA.

Expected Output(s)/Indicator(s):		_Preparation of SNC report and submission to the SEC of UNFCCC

(CP outcomes  linked t the SRF/MYFF goal and service line)	_____________________________________

Implementing partner:	Higher Council for Environment and Natural Resources (HCENR)

(designated institution/Executing agency)

Other Partners: Ministry of International Cooperation (formerly implementing agencies )

Agreed By:

Government: Ministry of International Cooperation ____________________________________ Date:

Implementing Partner: Higher Council for Environment and Natural Resources ______________Date

The United Nations development programme, on behalf of John Hough, OIC, GEF DOA letter

dated 9th May 2007. _________________________________________________________Date

###### List of Acronyms

AIAAC		Assessment of Impact and Adaptation to Climate Change

APR		Annual Project Review

APC		Assistant Project Coordinator

CC		Climate Change

CCCU 		Climate Change Coordination Unit

CBD		Convention on Biodiversity

CDM		Clean Development Mechanism

CP		Conference of the Parties

CPA 		Comprehensive Peace Agreement

CSO		Civil Society Organization

DPC		Deputy Project Coordinator

EFDB 		Emission Factor Database

FAO		Food and Agriculture Organization

INC		Initial National Communication

GCM		Global Circulation Model

GEF		Global Environment Facility

GHG		Greenhouse Gas

GHGNI		Green House Gas National Inventory

GPG 		Good Practice Guidance

HCENR	Higher Council for Environment and Natural Resources

IPCC		Intergovernmental Panel on Climate Change

JAM		Joint Assessment Mission

LEAP		Long Term Energy Planning model

LEG		Least Developed Countries Expert Group

LUCF		Land Use Change and Forestry

MCA 		Multicriteria assessment

MDG		Millennium Development Goal

MEAs		Multilateral Environmental Agreements

MEM		Ministry of Energy and Mines

NAPA 		National Adaptation Programme of Action

NCCC 		National climate change committee

NCSP 		National Communications Support Programme

NGO		Nongovernmental Organization

NMVOC	Non Methane Volatile Organic Compounds

NPC		National Project Coordinator

PIR		Project Inception Report

POP 		Persistent Organic Pollutant

SBAA 		Standard Basic Assistance Agreement

SNC		Second National Communication

SEI-US 	Stockholm Environment Institute - US Center

TNA		Technology needs assessment

TOR		Terms of Reference

UNDP		United Nations Development Programme

UNFCCC	United Nations Framework Convention on Climate Change

V & A		Vulnerability and Adaptation

# Part 1: Elaboration of Narrative

## 1.1 Situation Analysis

The Republic of Sudan borders the Red Sea and is located between Egypt and Eritrea in Northern Africa. The nation covers an area of approximately 2,505,810 square kilometers (967,499 sq mi), making it the largest country on the continent of Africa. The land area is comprised primarily of flat plains, rising in the East and West to mountain ranges, with the Nile River and its tributaries comprising most of the hydrology of the region.  The climate varies from tropical in the south to arid, desert climate in the north. The country, comprised of particularly fragile ecosystems, is extremely vulnerable to the impacts of climate change. In particular, frequent droughts, soil erosion and desertification are environmental hazards already affecting the region.

The continuing fragility of the Sudan's ecosystems and, in turn livelihoods, has been particularly manifest in the wide fluctuations in precipitation patterns commonplace over the past several decades. Severe droughts have already lead to serious dry land degradation characterized by a significant disruption of rural economies and causing sharp decline in crop production and in rangeland vegetation, both for grazing and for browsing. For example, the results of the vulnerability and adaptation assessment conducted during the preparation of Sudan’s INC indicated that in the coming 30 years, Sorghum production is expected to declined by more than 50% in some of its current cultivated areas

Rain fed cultivation, in combination with sedentary animal husbandry, has progressively come to occupy large tracts of traditional grazing lands.  This continued expansion of rain fed farming onto marginal lands, together with a variable rainfall regime and continuing high level of firewood consumption, has contributed to a process of desertification that has engulfed vast regions of the country and is adversely affecting prospects for future food security.

This expansion of rain fed agriculture has forced many of Sudan's nomadic groups, who have traditionally adapted well to climate fluctuations through their high mobility over vast areas, to make use of even more marginal areas.  The result is an increasing cycle of overgrazing and over-browsing, leading to a loss of woody vegetation. These expansions and changes in farming practices have also triggered a number of resource based conflicts in several parts of the country especially in the Darfur Region.

Recognizing the importance of addressing climate change and the need to integrate its environmental and development objectives, Sudan ratified the UNFCCC on 19 November 1993 and submitted its Initial National Communications (INC) in 2003 with the assistance of the UNDP. In 2004, Sudan initiated a National campaign for human development and Millennium Development Goals (MDGs), to raise the public awareness about the MDGs and to advocate for including the eight global MDGs in national planning and strategies

The signing of the historic Comprehensive Peace Agreement (CPA) in January 2005 has opened an unprecedented window of opportunity to turn the devastation of years of war, displacement, and underdevelopment into a new era of peace and prosperity. The government of Sudan recognizes the need for sweeping reforms to governance, the creation of new institutions, and significant capacity building at all levels of government to allow for effective decentralization and equitable resource allocation in pursuing the CPA.

Sudan’s vast natural resource endowments and significant human capital offer enormous development potential. To achieve this, Sudan also launched the Joint Assessment Mission (JAM) in 2005 which led to the development of a Framework for Sustained Peace, Development and Poverty Eradication, which will be supported by domestic efforts and resources, as well as development partners, in addressing underlying structural causes of conflict and underdevelopment in the Sudan. The JAM process is now under implementation and is being financed from a special fund. Similarly, the signing of the Darfur Peace Agreement in May 2006 has resulted, among other things, in the initiation of the Darfur Joint Mission Assessment to gauge the post conflict needs of that region.

The preparation of this SNC proposal started by a self-assessment exercise which involved a stocktaking exercise and highly consultative and participatory process of needs assessment to identify critical priorities for UNFCCC implementation in Sudan as well as the SNC project proposal. This approach helps to ensuring that the SNC is build upon previous activities, studies, experiences, and institutional settings. The stocktaking exercise took about 15 weeks brought together about 100 participants representing technical, planning and policy making experts from different ministries, public institutions, NGOs, academia, and the private sector, as summarized in Annex A. The outcomes of the stocktaking exercise, including the main elements of this proposal for the SNC, were then presented to a wider group of stakeholders from all related institutions in a final consultative workshop. Discussions during this workshop covered critical areas of the National Communications process (e.g. existing data sources and their reliability, the gaps, the methodologies and the capacity building needs).

In order to develop effective climate change response strategies in which development priorities coincide with long-term local and environmental concerns, there is a need for considerable additional technical and institutional capacity throughout these institutions. There is also a need to replicate and scale-up the current project and build in key aspects which have been identified as gaps in the current project. It was clear, however, that each institution has been hampered by infrastructure weakness stemming from shortages in financial resources and specific areas of technical expertise.  To this point, there is a need to ensure increased technical and institutional capacities, ensure availability of policy related information to support integrate climate change issues and concerns into national development and availability of national GHG inventory for all possible source/sink categories, develop an up-to-date national GHG inventory for all possible source/sink categories, improve scientific knowledge and understanding of Sudan’s vulnerabilities and adaptation responses to current and future climate change;

- The proposed project will therefore build on findings from the Initial National Communications (INC), and other documents such as the NAPA and IAC in accordance with guidance of the UN Framework Convention on Climate Change (UNFCCC) and in the long term to strengthen Sudan’s capacity to fulfill its commitments to the UNFCCC on a continuing basis. The project will integrate its outcomes within the framework of continuing to implementing and expand international and national agreed best practice strategies in UN Framework Convention on Climate Change (UNFCCC). This relates directly to the achievement of MDG 7, target 9 which relates to integration of the principles of sustainable development into country policies and programmes to reverse the loss of environmental resources.

- In addition Southern Sudan has not been covered in the preparation of INC due the war situation at that time. However after the signature of the CPA, Climate Change activities have been extended to the south through the National Adaptation Programme of Action project (NAPA). A focal point has been designated within the Ministry of Agriculture of Central Equatoria State. Two workshops have been conducted in Juba town. In the first one, 50 experts representing local government and non-government institutions has been trained in climate change, impact, vulnerability and adaptation including technical issues to build their capacities to handle climate change related tasks. The second workshop was devoted to NAPA introduction and consultation with all relevant stakeholder communities. These was later followed by participatory vulnerability assessment of climate change impacts in the agriculture, water and human health sector in the state conducted by a group of local experts from these sectors. A number of urgent needs have been identified through this survey and discussed in the final NAPA workshop held in Khartoum (March 2007) with participation of representatives from the south and other four States that represent the Sudan’s ecological zones

The SNC project will build on such a link and benefit from the level of awareness and capacities created by the NAPA project.

1.2 Strategy

This project addresses a continuing policy objective of seeking to integrate environmental and development objectives. Within this broad framework, the project will enable Sudan to prepare its Second National Communication (SNC) in accordance with Article 12 of the UNFCCC. The project will help facilitate the implementation of response measures and also promote continued capacity strengthening to fulfill Sudan’s commitments to the Convention.  A more detailed strategy is included in appendix B, however it can summarized in the following points:

Preparation of the SNC will build on the capacities, expertise, and institutional infrastructure developed during the preparation of the INC. It will also aim to establish a permanent structure for regular and continued preparation of national communications, build the technical and institutional capacities, obtain agreements and legal support and commitment of intuitions involved.

The overall strategy of the SNC project aims to expand awareness and knowledge by government planners and civil society groups regarding climate change in order to enhance Sudan’s national capacity to fulfill its commitments to the Convention, as well as account for climatic change in its development planning. It will make use of a number of synergistic activities and networks related to vulnerability and adaptation that have already been initiated as a part of the Sudan NAPA process.

Capacity building will be another key aim of the SNC project, enabling sustained efforts to mobilize additional resources for projects related to the mitigation of greenhouse gases and adaptation to climate change. Such projects may also be eligible for funding or co-funding by GEF or other multilateral or bilateral organizations.

Sudan recognizes the need for global cooperation to achieve the ultimate goal of the climate change convention. Therefore the overall development objective of Sudan's national Climate Change implementation strategy is to promote sustainable development paths that improve Sudan's adaptive capacity and limit its growth in GHG emissions through integration of climate change issues and concerns into national policies, strategies and development plans.

1.3 Logical Results – Resource Framework:

The purpose of this project is to enable Sudan to prepare and submit its second national communication to the UNFCCC and to support the nation in meeting its Convention obligations by improving human and institutional capacity in the climate change field throughout the relevant sectors and at the national and regional levels. This linked to UNDP’s CCF bridging programme, outcome (8) which stipulates that Capacities in govt. and civil society to manage natural resources for sustainable livelihoods; and to meet global environmental commitments strengthened. The logical Results resource framework below highlights the project’s intended outcome, outputs, indicative activities and the required resources to achieve the project’s intended results. For detailed information on project’s objectives and activities reference is to be made to appendix B.

PROJECT RESULTS AND RESOURCE FRAMEWORK

| Intended outcome as stated in the country Result Framework: Outcome 8 Capacities in govt. and civil society to manage natural resources for sustainable livelihoods; and to meet global environmental commitments strengthened. |
| --- |
| Outcomes indicators as stated in the Country Programme Results and Resource Framework, including baseline and target: Outcome indicator: 1. No. of institutions integrating climate change issues in their policies and development plans 2nd NC prepared, approved and endorsed by the UN FCCC |
| Applicable MYFF Service Line: 3.1 |
| Partnership Strategy: UNDP will play the lead/coordinating role in providing the necessary financial and technical support. It will also increasingly focus outreach activities to keep current and potential partners |
| Project number: PIMS No.3592, ATLAS ID 00046263 |
| Intended Outputs | Output Targets for (years) | Indicative Activities | Responsible parties | Inputs |
|  | Y1 | Y2 | Y3 |  |  |  |
| 1. Implementation arrangements in place and project inception report prepared. | **** | **** | **** | Establish Project Coordination Unit including recruitment of NPC, 2 Assistant coordinators and support staff. Establish a Project Steering Committee and technical committee. Conduct Initiation workshop Avail project’s operational costs to facilitate implementation of the project’s plan. | PMU MIC UNDP PSC | Communications Miscellaneous Contractual services;individual Operating expenses supply USD 74,000 |
| 2. National circumstances report prepared. |  |  | **** | Update and assess gaps and need for information. Collect data needed for updating national circumstances. draft and review report on National Circumstances section Prepare the National Circumstances section under the SNC. | NPC APCs technical committee Steering committee | Communications Miscellaneous USD 10,000 |
| 3. GHG inventory updated. | **** |  |  | Develop inventory plan including specifications of methods and tool, base year and scope Train 30 national expert on GHG inventory methods Collect and assess data for GHG Identify estimates for possible GHG sources and sinks. Prepare and review inventory report Organizes a workshop to present findings of the GHG inventory. Prepare GHG inventory section in the SNC | NPC APCs National Team Steering committee | International consultant Communications Miscellaneous USD 75,000 |

| 4. Measures to mitigate GHG emissions assessed. | **** | ** |  | Identify options for GHG mitigation based on GHG Inventory report and INC. Train 30 experts on GHG mitigation. Identify scope, data needs, methods and tools Update baseline and mitigation scenarios. Analyze potential for GHG reduction and economy of mitigation options. Prepare and review mitigation report for the SNC document. organize a national workshop to present findings of the GHG mitigation . | NPC APCs National Team Steering committee | International consultant Communications Miscellaneous USD 40,000 |
| --- | --- | --- | --- | --- | --- | --- |
| 5. Measures to facilitate adaptation to climate change assessed. | ** | **** | ** | Develop Scoping by national team. Define approaches, methods and tools. Identify needs, collect and analyze data. Define and assess current vulnerability and priority area(s) Assess future climate risks and adaptation measures in the priority area. Prepare a paper on Adaptation Policy. Prepare and review Vulnerability and & Adaptation (V&A) report Organize a national workshop to present findings from the V&A . Finalize V&A report prepare V&A section in the SNC. Train 50 national experts on methods and tools of V&A assessment. | NPC APCs National Team Steering committee | International consultant Communications Miscellaneous USD 135,000 |
| 6. Other relevant information to the achievement of the objective of the convention assessed. |  | ** | ** | Collect and summarize overall information relevant to Article 6 of the UNFCCC convention. Collect and summarize information on steps taken to integrate climate change into national planning. Collect and summarize information on the research and systematic observation systems Assess and summarize findings of technology need assessment. Conduct synthesis of information on relevant ongoing projects. Prepare section on Other Relevant Information in SNC . | NPC APCs National Technical committee Steering committee | International consultant USD36,000 |
| 7. constraints, gaps and related needs identified and reported. |  |  | ** | Identify, assess and reports constraints, gaps and needs in all thematic areas. | NPC APCs National Technical committee Steering committee | International consultant USD 20,000 |
| 8. SNC produced, translated, submitted and disseminated |  |  | **** | Compile a draft of the Sudan’s Second National Communication. circulate the draft SNC for comments and review by stakeholders. Organize a national workshop organized for review and approval of the draft SNC by all stakeholders Finalize the draft SNC and submit for the Government endorsement. prepare e-copies of Sudan’s SNC in CD-ROMs and download in relevant websites. | NPC APCs National Technical committee Steering committee | International consultant USD 15,000 |

Part 2:

2.1: Budget

The proposed project budget is US $405,000 with an additional contribution from the Government of Sudan (in kind) of $75,000. The details of the budget covering UNDP-GEF contribution are given in tables 1,2 and 3. The Government of Sudan in-kind Contribution for Activities Implemented by the HCENR amounts to USD 75,000 as indicated in table 4, while table 5 reflects a detailed work plan for implementation of Sudan’s SNC activities by year and quarter.

Table 1: Annual Workplan Budget Sheet

### Year 2007

| Expected Output | Key Activities | Timeframe | Resp. Partner | Planned Budget |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Budget Description | Amount |
| National Circumstances | Research, data acquisition and synthesis | X | X | X | X | HCENR |  | GEF | 71300 Local personnel | 7,500 |
| Sub total |  |  |  |  |  |  |  |  | 7,500 |
| National Greenhouse Gas Inventory | Updating existing GHG inventory to account for new requirements | X | X | X | X | HCENR |  | GEF | 71300 Local personnel | 15,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 8,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72100 Contractual service companies | 5,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 7,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing & publication cost | 4,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
| Sub total |  |  |  |  |  |  |  |  | 45,000 |
| GHG Mitigation. | Development of updated analysis of costs/benefits of GHG mitigation options |  |  |  |  | HCENR |  | GEF | 71200 International consultants |  |
|  |  |  |  |  |  | HCENR |  | GEF | 71300 Local consultants |  |
|  |  |  |  |  |  | HCENR |  | GEF | 71600 Travel |  |
|  |  |  |  |  |  | HCENR |  | GEF | 72200 Equipment & furniture |  |
|  |  |  |  |  |  | HCENR |  | GEF | 72400 Communication and audiovisual equipment |  |
|  |  |  |  |  |  | HCENR |  | GEF | 74200 Printing/ publication cost |  |
|  |  |  |  |  |  | HCENR |  | GEF | 72500 Supply |  |
|  |  |  |  |  |  | HCENR |  | GEF | 74000 Miscellaneous |  |
| Sub total |  |
| Vulnerability & Adaptation | Assessment of impacts of climate change on vulnerable sectors and communities; development of adaptation strategies | X | X | X | X | HCENR |  | GEF | 71200 International consultants | 6,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 29,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing & publication costs | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 0 |
| Sub total |  |  |  |  |  |  |  |  | 44,000 |
| Gaps and constraints, related Financial, technical and capacity needs | Board-based internal capacity assessment | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 4,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 1,000 |
| Sub total | 5,000 |
| Other information | Collection and synthesis of additional information to be included in the SNC | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71400 Contractual; services/individuals | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
| Sub total | 8,000 |
| Project Management | Coordination of project activities | X | X | X | X | HCENR |  | GEF | 71400 Contractual; services/individuals | 21,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 2,000 |
| Sub total | 25,000 |
| Monitoring and Reporting (M&R) | Coordination of monitoring and evaluation activities | X | X | X | X | HCENR |  | GEF | 74100 Professional services | 5,000 |
| Sub total | 5,000 |
| Grand Total – Year 2007 | 139,500 |

Table 2: Annual Workplan Budget Sheet

Year 2008

| Expected Output | Key Activities | Timeframe | Resp. Partner | Planned Budget |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Budget Description | Amount |
| National Circumstances | Research, data acquisition and synthesis | X | X | X | X | HCENR |  | GEF | 71300 Local personnel | 2,500 |
| Sub total |  |  |  |  |  |  |  |  | 2,500 |
| National Greenhouse Gas Inventory | Updating existing GHG inventory to account for new requirements | X | X | X | X | HCENR |  | GEF | 71300 Local personnel | 10,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 4,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72100 Contractual service companies | 5,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing & publication cost | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 1,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 1,000 |
| Sub total |  |  |  |  |  |  |  |  | 23,000 |
| GHG Mitigation. | Development of updated analysis of costs/benefits of GHG mitigation options | X | X | X | X | HCENR |  | GEF | 71200 International consultants | 4,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 10,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 2,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication and audiovisual equipment | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing/ publication cost | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 4,000 |
| Sub total | 24,000 |
| Vulnerability & Adaptation | Assessment of impacts of climate change on vulnerable sectors and communities; development of adaptation strategies | X | X | X | X | HCENR |  | GEF | 71200 International consultants | 9,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 35,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 7,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 3,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing & publication costs | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
| Sub total |  |  |  |  |  |  |  |  | 64,500 |
| Gaps and constraints, related Financial, technical and capacity needs | Board-based internal capacity assessment | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 8,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
| Sub total | 10,000 |
| Other information | Collection and synthesis of additional information to be included in the SNC | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71400 Contractual; services/individuals | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 4,000 |
| Sub total | 10,000 |
| Project Management | Coordination of project activities | X | X | X | X | HCENR |  | GEF | 71400 Contractual; services/individuals | 21,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 2,000 |
| Sub total | 25,000 |
| Monitoring and Reporting (M&R) | Coordination of monitoring and evaluation activities | X | X | X | X | HCENR |  | GEF | 74100 Professional services | 5,000 |
| Sub total | 5,000 |
| Grand Total – Year 2008 | 164,000 |

Table 3: Annual Workplan Budget Sheet

Year 2009

| Expected Output | Key Activities | Timeframe | Resp. Partner | Planned Budget |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Fund | Donor | Budget Description | Amount |
| National Circumstances | Research, data acquisition and synthesis | X | X | X | X | HCENR |  | GEF | 71300 Local personnel | 0 |
| Sub total |  |  |  |  |  |  |  |  | 0 |
| National Greenhouse Gas Inventory | Updating existing GHG inventory to account for new requirements | X | X | X | X | HCENR |  | GEF | 71300 Local personnel | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 1,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72100 Contractual service companies | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing & publication cost | 1,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 0 |
| Sub total |  |  |  |  |  |  |  |  | 7,000 |
| GHG Mitigation. | Development of updated analysis of costs/benefits of GHG mitigation options | X | X | X | X | HCENR |  | GEF | 71200 International consultants | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 6,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication and audiovisual equipment | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing/ publication cost | 1,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 3,500 |
| Sub total | 16,000 |
| Vulnerability & Adaptation | Assessment of impacts of climate change on vulnerable sectors and communities; development of adaptation strategies | X | X | X | X | HCENR |  | GEF | 71200 International consultants | 2,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 15,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71600 Travel | 2,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 72200 Equipment & furniture | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 0 |
|  |  | X | X | X | X | HCENR |  | GEF | 74200 Printing & publication costs | 2,500 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
| Sub total |  |  |  |  |  |  |  |  | 26,500 |
| Gaps and constraints, related Financial, technical and capacity needs | Board-based internal capacity assessment | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 4,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 1,000 |
| Sub total | 5,000 |
| Other information | Collection and synthesis of additional information to be included in the SNC | X | X | X | X | HCENR |  | GEF | 71300 Local consultants | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 71400 Contractual; services/individuals | 2,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72400 Communication & audiovisual equipment | 12,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 2,000 |
| Sub total | 18,000 |
| Project Management | Coordination of project activities | X | X | X | X | HCENR |  | GEF | 71400 Contractual; services/individuals | 21,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 74000 Miscellaneous | 3,000 |
|  |  | X | X | X | X | HCENR |  | GEF | 72500 Supply | 0 |
| Sub total | 24,000 |
| Monitoring and Reporting (M&R) | Coordination of monitoring and evaluation activities | X | X | X | X | HCENR |  | GEF | 74100 Professional services | 5,000 |
| Sub total | 5,000 |
| Grand Total – 2009 | 101,500 |

Table 4: Government of Sudan in-kind Contribution

| Description of Inputs | Total US$ |
| --- | --- |
| Administration and support staff | 4000 |
| Office and related operations | 15000 |
| Stationery and other office supplies | 10000 |
| Furniture and office equipment | 33000 |
| Utilities and maintenance | 3000 |
| Media activities: leaflets, press calls, workshops | 10000 |
| Grand total | 75000 |

2.2.  Management Arrangements

The Higher Council for Environmental and Natural Resources (HCENR) will assume the role of the leading agency responsible for oversight, coordination, and implementation of activities for preparing Sudan‘s Second National Communication to the UNFCCC.  The CC focal units and the CC Unit at HCENR, having gained experience through the coordination of all activities for the INC, are uniquely positioned to undertake this task. The involvement of the relevant stakeholders, and their support and commitment to the implementation of the proposed activities, will ensure the achievement of the overall outcome of the project.

The activities of the Project coordination unit will focus on coordination of all technical activities. Initially, this will involve the convening of a workshop will be held at the beginning of the project activities to raise the awareness about the UNFCCC and the SNC at both the official and the public levels.  The workshop participants will include all relevant stakeholders including representatives of the Civil Society Organizations, and the media.  The workshop will discuss the project workplan, priorities and area coverage. An initial activity will be to finalize the project organization and coordination structure. A tentative structure is illustrated in Figure 1.

### Project Coordination Unit (PCU)

The Climate Change Unit of HCENR will host and guide the project coordination unit (PCU) which in turn will work closely with the National Climate Change Committee and the national Technical Committee (national teams of experts on V&A, Inventory and Mitigation) and UNDP-Khartoum to conduct the capacity building, the different studies and assessments and implement all project activities leading to the preparation of the Sudan’s second national communication.

The PCU will be responsible for carrying out all the activities specified in the project document and provide overall project management and supervision to ensure that the implementation of the project activities are in line with what was agreed/approved and stipulated in the project document. The specific responsibilities of the PCU and project management may include the following:

- Enhance the capacity and role of the climate change unit of HCENR.

- Prepare in consultation with the NCCC a detailed project work-plan as well as annual and quarter plans.

    - In consultation with NCCC, re-constitute the national Technical Committee on a permanent basis (on GHG inventory and GHG mitigation, and Vulnerability and Adaptation).Sectoral experts will be identified in each of the expert groups, responsible for coordination of the particular section of the SNC. The expert groups will be retained as local consultants. On the basis of past experience with the INC these individuals are well know to the Project Coordination.

- Prepare the agenda, organize the meetings of and serve as secretary for, the NCCC.

- Coordinate national training activities, seminars and workshops.

- Coordinate recruitment of consultants, project procurements, facilitation of studies, participation in international conferences and events relevant for the project.

- Approve the allocation of funds under the direction of the NCCC and in accordance with UNDP procedures.

- Prepare and submit technical reports, progress reports, evaluation reports, and other reports as requested.

- Undertake any related activities considered necessary to facilitate the implementation of the project.

Fig1. Organization structure for Sudan’s SNC

A Project Coordinator (PC) and two Assistant Project Coordinators (APCs) will be hired and appointed on part and/or full-time basis, resources allowed. The selection process will be carried out on the basis of a formal recruitment process and will consider the strategic need for institutionalizing the national communication process. They will be responsible for the coordination of project activities in close consultation with the National Climate Change Committee (NCCC) and the National Technical Committee (NTC) and UNDP-Khartoum. The tasks and responsibilities will be clearly defined and assigned to the members of the PCU based on their respective expertise e.g. one will be responsible for the coordination of the Inventory and mitigation and other for the V&A activities etc.

Where needed, technical backstopping will also be provided by SEI-US in order to enhance national capacities in areas where national expertise are not sufficient or lacking. Assistance provided by staff at SEI-US will take the form of technical support in the updating of the GHG inventory, GHG mitigation analysis and V&A methods and tools, as well as support in the review and finalization of the SNC.

### Project Steering Committee (National Climate Change Committee (NCCC))

Initiation of the project will include the establishment of a high level political oversight and coordination body that includes representatives of stakeholders from all relevant sectors including government research and academic, non-governmental institutions and UNDP/GEF representatives. This National Climate Change Committee (NCCC) will also serve as the Project Steering Committee (PSC) and will be chaired by the Secretary General of HCENR and the National Project Coordinator (NPC) will serve as its secretary.

Members of the NCCC may include, but are not necessary be limited to, Ministry of Energy and Mining, Ministry of Agriculture and Forestry, National Forest Corporation, Ministry of Industry, Ministry of Health, Ministry of Irrigation, Ministry of Foreign Affairs, Ministry of Science and Technology, Meteorological Authority, Institute of Environmental Studies (U of K), Sudanese Environmental Conservation Society,  Industrial Chamber, etc. A representative of UNDP-Khartoum will be invited as an ex-officio member of the Steering Committee.

Since the submission of the national communications has become regular now (according to the relevant COP decision), the NCCC will be established as a permanent body that deal with policy issues and assist HCENR to achieve the objectives of the national implementation strategies and in the integration of climate change into national development process. The overall responsibilities of the NCCC will be:

- Establish and prioritize overall policy directions.

- Ensure effective cooperation between government and non-government and all stakeholders on climate change issues and concerns.

- Review and approve periodic work plans (quarterly and annually) prepared by the project coordination unit.

- Review and approve the periodic reports (quarterly and annual evaluation) prepared by the project coordination and unit on progress, problems encountered and future strategies and plans.

- Periodically review the status of implementation and ensure the agreed upon activities are being properly executed.

- Participate in review meetings and mid-term and final project evaluation

- Provide technical advice to the PCU through the review of data, technical and reports, analysis and assessment and training needs.

- Periodically review the technical progress and recommendations as necessary

- Meet every three months.

### National Technical Committee (NTC)

It will be re-constituted on the basis of the previous national teams of experts from relevant sectors, government, non-government, research, academic and private sectors institutions. The NTC will consist of two experts groups on (a) GHG Inventory and Mitigation and (b) Vulnerability and Adaptation. The membership of the committee will be based on technical expertise of the individuals involved and the mandate of their respective institutions in areas relevant to the climate change.  The NTC will have a technical and consultative role to the project and will help the project to maintain contact with relevant institutions.

2.3. Monitoring and Evaluation

Monitoring responsibilities and events: A detailed schedule of project reviews meetings will be developed by the project management, in consultation with project implementation partners and stakeholder representatives and incorporated in the Project Inception Report. Such a schedule will include: (i) tentative time frames for National Committee Meetings, and (ii) project related Monitoring and Evaluation activities.

Through the project assurance function UNDP in coordination with the implementing partners will  monitor and evaluate a set of output and outcome indicators agreed upon through timely data from both routine and non-routine sources and continuous monitoring visits to the project areas. Standard UNDP procedures for monitoring and evaluating projects will be applied

Day to day monitoring of implementation progress will be the responsibility of the Project Coordinator, based on the project's Quarter and Annual Workplan and its indicators. The Project Team will inform the UNDP-CO of any delays or difficulties faced during implementation so that the appropriate support or corrective measures can be adopted in a timely and remedial fashion

## Periodic monitoring of implementation progress will be undertaken by the UNDP-CO together with MIc and HCENR through quarterly meetings with the project proponent, or more frequently as deemed necessary. This will allow parties to to compare performance against planned activities. These meetings will examine the status of planned activities in a quarter; identify implementation challenges and solutions including lessons learnt. The technical review meeting will create synergies within and between the project and UNDP programs. There will also be continues analysis of data to support project management and its fine-tuning to achieve set objectives

Project Monitoring Reporting the Project Coordinator in conjunction with the UNDP-GEF extended team will be responsible for the preparation and submission of the following reports that form part of the monitoring process.

### Project Inception Report

A Project Inception Report (will be prepared immediately following the Inception Workshop. It will include a detailed First Year Work Plan divided in quarterly timeframes detailing the activities and progress indicators that will guide implementation during the first year of the project. The Report will also include the detailed project budget for the first full year of implementation, prepared on the basis of the Annual Work Plan, and including any monitoring and evaluation requirements to effectively measure project performance during the targeted 12 months time-frame.

The Inception Report will include a more detailed narrative on the institutional roles, responsibilities, coordinating actions and feedback mechanisms of project related partners.  In addition, a section will be included on progress to date on project establishment and start-up activities and an update of any changed external conditions that may effect project implementation.

Finally, the Inception Report will provide a draft list of technical reports that will be expected on key areas of activity and tentative due dates.  The technical reports will represent emerging knowledge in Sudan about specific areas and topics, and will be used in local awareness raising activities and be available to the international climate change community.

When finalized the report will be circulated to project counterparts who will be given a period of one calendar month in which to respond with comments or queries.  Prior to this circulation of the IR, the UNDP Country Office and UNDP-GEF’s Regional Coordinating Unit will review the document.

Quarterly Progress Reports

Short reports outlining main updates in project progress will be provided quarterly to the UNDP Country Office in Khartoum and to the UNDP-GEF regional office in by the project team. In addition to these short reports, the technical reports list will be revised and updated as necessary and included in subsequent quarterly reports.

Technical Reports

Technical Reports are detailed documents covering specific areas of analysis or scientific specializations within the overall project.  Technical Reports will be prepared by Technical Committee members, and assisted as needed by external consultants. These reports should be comprehensive, specialized analyses of clearly defined areas of research within the framework of the project.

## Audit Clause

The Government will provide the UNDP Resident Representative with certified periodic financial statements, and with an annual audit of the financial statements relating to the status of UNDP/GEF funds according to the established procedures set out in the Programming and Finance manuals. The Audit will be conducted by the legally recognized auditor of the Government, or by a commercial auditor engaged by the Government.

## .2.4. Legal Context

This Project Document shall be the instrument referred to as such in Article I of the Standard Basic Assistance Agreement (SBAA) between the Government of Sudan and the United Nations Development Programme, signed by the parties on [24 October 1987]. The host country implementing agency shall, for the purpose of the Standard Basic Assistance Agreement, refer to the government co-operating agency described in that Agreement.

UNDP will act in this Project as an Implementing Agency of the Global Environment Facility (GEF), and all rights and privileges pertaining to UNDP as per the terms of the SBAA shall be extended mutatis mutandis to GEF.

The UNDP Resident Representative is authorized to effect in writing the following types of revision to this Project Document, provided that he/she has verified the agreement thereto by GEF Unit and is assured that the other signatories to the Project Document have no objection to the proposed changes:

- Revision of, or addition to, any of the annexes to the Project Document;

- Revisions which do not involve significant changes in the immediate objectives, outputs or activities of the project, but are caused by the rearrangement of the inputs already agreed to or by cost increases due to inflation;

- Revisions which do not conflict with UNFCCC guidelines and Sudan’s commitments under the UNFCCC.

- Mandatory annual revisions which re-phase the delivery of agreed project inputs or increased expert or other costs due to inflation or take into account agency expenditure flexibility; and

- Inclusion of additional annexes and attachments only as set out here in this Project Document.

# Part 3. Appendices

## Appendix A: Summary report of the self-assessment exercise

### A.1. Scope and Approach to Stocktaking Analysis

1The main objective of the self-assessment exercise is to carry out a highly consultative and participatory process of needs assessment to identify critical priorities for UNFCCC implementation in Sudan as well as the SNC project proposal. The self-assessment exercise was performed in accordance with GEF Operational Procedures for the Expedited Financing of National Communications from Non-Annex I Parties (GEF/C.22/Inf.16). This self-assessment exercise was the first and most critical step in preparing Sudan’s proposal for its SNC. The stocktaking exercise was focused on all thematic areas related to National Communication as indicated by COP Decision 17/CP8.

The approach used in the stocktaking exercise was based on pre-determined terms of reference and made use of some key tools for stocktaking including: (i) in-desk review of relevant documents; (ii) discussions among stakeholders; and (iii) consultative meetings and workshops. The information obtained provides an assessment of gaps, uncertainties, barriers and lessons learnt during previous and ongoing activities. This approach helps to ensuring that the SNC is build upon previous activities, studies, experiences, and institutional settings.

Stocktaking work began with a workshop to introduce the process of preparing the proposal for the SNC. Presentation and discussions covered climate change problem and its impacts, global response, commitments and challenges, the Initial National Communication and the guidelines for preparing the SNC. Following the initial workshop, the national team convened several meetings, the objective of which was to review and assess the INC process with respect to the GHG inventory, GHG mitigation and the V&A groups.

The stocktaking exercise took about 15 weeks brought together about 100 participants representing technical, planning and policy making experts from different ministries, public institutions, NGOs, academia, and the private sector, as summarized in Annex A. The identification of stakeholders for the stocktaking exercise was based on the following criteria; a) membership in the national climate change committee; membership of a INC national team; having relevant experts (research and academic institutions); interested member of a non-government al or civil society organization (NGOs, CSOs), and interested member of the private sector.

The outcomes of the stocktaking exercise, including the main elements of this proposal for the SNC, were then presented to a wider group of stakeholders from all related institutions in a final consultative workshop. Discussions during this workshop covered critical areas of the National Communications process (e.g. existing data sources and their reliability, the gaps, the methodologies and the capacity building needs).

### A.2. Summary of main findings of the self-assessment

The stocktaking team performed an assessment of each thematic area relevant to the preparation of SNC. The main focus of assessment was Sudan’s INC performed under the GEF funded enabling activity project, its top-up phase funded by GEF. In addition, other projects funded either by GEF (i.e, the NAPA) or other donors (i.e., AIACC) relevant to each thematic area were considered.

#### A.2.1 Lessons and Good Practice

In the course of the INC, a number of elements of good practice were gleaned from the experience, all of which will promote a positive environment in which to prepare the SNC of Sudan. Both technical practices and management structures were established during the INC including the following, identified in the course of the stocktaking process;

- Local expert involvement which resulted in the creation of adequate capacities within the different related sectors to handle climate change issues;

    - International technical assistance, which resulted in training (vulnerability, mitigation) and networking;

    - Trainings in inventories, mitigation analysis, and vulnerability assessment which resulted in increased capacity to undertake independent analyses

    - Other lessons were learned from participation in regional initiatives and participation in international climate change events

#### A.2.2 Difficulties and Barriers Associated with the INC

Each of the institutions involved in the stocktaking analysis has been involved in the pursuit of national development objectives and is in possession of knowledge pertinent to climate change issues.  It was clear, however, that each institution has been hampered by infrastructure weakness stemming from shortages in financial resources and specific areas of technical expertise.  Developing climate change response strategies in which development priorities coincide with long-term local and environmental concerns therefore requires considerable additional technical and institutional capacity throughout these institutions. General difficulties and barriers are outlined below.

- Data problems: availability, compatibility, accessibility and reliability of a wide range of data necessary for analysis. Many assumptions were made to overcome the data availability problems. Data gaps include incomplete historical records of climate, crop production, disease incidences, etc.

- Methodological problems: limitation in the definition of sources, sink categories, lack of methods to estimate and manage uncertainties, lack of local emission and other coefficient factors in GHG inventory. Limitations with regard to suitability and applicability of models used in generating the climate scenarios and impact models used for assessing the vulnerability of different sectors.

- Technical capacity problems: lack of adequate resources and institutional capacity including relevant expertise and technical capacity. For example, the limited expertise in modeling, long-term projections and computer model “know-how.”

- Others: Future socio-economic changes and their effects on the exposure are not well taken into account due to the lack of relevant expertise and methodological constraints. Adaptation measures are not well defined and assessed due to the lack of relevant expertise and due to methodological constraints.

#### A.2.3 Identified Gaps, Priorities and Methodologies – GHG Inventory

A number of specific gaps and uncertainties in the INC were identified in the course of the stocktaking exercises for the GHG inventory thematic area, as outlined.

Energy Sector: The Energy Sector portion of the GHG inventory process faced a number of gaps in the INC process, as identified in the course of the stocktaking exercise. The following elements of the Energy Sector GHG inventory were considered limitations;

- Data for lubricants are based on the assumptions offered by the Ministry of Energy and Mining (MEM).

- No data for bunker fuels are available by fuel type and/or mode of transport.

- There is uncertainty in the end use data of some fuels (e.g. diesel/gas oil is switched from the transport sector to the household).

- Uncertainties of some data sources that are based on estimates.

- The data for biomass fuel in the year 1995 is based on previous studies done by the MEM and the Forests National Corporation (INC).

- Mainly the default values (emissions and coefficient factors) supplied by the IPCC methodologies were used.

- Data for petroleum products is supplied by the MEM (one source).

However, some improvements have been recorded regarding:

- Improved data availability and reliability e.g. data on exports, supply, distribution and consumption of petroleum and;

- New data is also available form the recent energy survey (2005).

Agricultural Sector: In the agricultural sector, the primary gap in the analysis was the limited inventory carried out, as it did not cover the entire country of Sudan.

Industrial Sector: In the analysis of the industrial sector GHG inventory, a number of the IPCC industrial sources are not produced in Sudan including Nitric Acid, Adipic Acid, Calcium Carbide production, etc. In addition to this gap, there are no regularly updated surveys and reliable data in the sector with the exception of the last comprehensive industrial survey of 2001. There also remains limited expertise in GHG inventory in the industrial sector of Sudan.

LUCF Sector: Stocktaking in the LUCF sector identified a number of gaps in the analysis namely;

- The fraction of wood left to decompose was considered negligible;

- annual increment of woody biomass in plantation was estimated and not measured;

- The INC data was limited to the area between 10- 16◦ N., and did not include Southern Sudan;

- Default values do not reflect Sudan conditions and their use is associated with risks;

- Annual growth rates of urban trees were roughly estimated.

Waste sector: In the water sector, the stocktaking exercise also identified various gaps in the INC process. The shortage of data management systems within the relevant national and regional institutions was acknowledged, as was the lack of compiled data (with the exception of the industrial waste survey 2001-2004, which is only available for the state of Khartoum). Information about oil industry waste is also completely unknown except for some studies for certain private companies.

#### A.2.4 Identified Gaps, Priorities and Methodologies – GHG Mitigation Analysis

The GHG mitigation analysis aimed at identifying options that can serve both national development priorities and contribute to the fulfillment of the general commitments of the UNFCCC. Using the results of GHG inventory, the mitigation study focused mainly on the energy and the LUCF sectors as being the dominant areas where GHG emission reductions could be achieved. The stocktaking exercise also identified the following gaps encountered in the mitigation analysis carried out as part of the INC;

- Lack of detailed end-use data (energy sector).

- Lack of up to date land use data.

- Compatibility (land use and energy data found in different formats).

- Available data was not consistent across sectors.

- Problems of Reliability and accessibility.

#### A.2.5 Identified Gaps, Priorities and Methodologies –  Vulnerability and Adaptation

The main gaps and limitations encountered in the INC as regards the Vulnerability include the following:

- Limitations related to the suitability and applicability of the models used in generating the climate scenarios. A major disadvantage of using GCMs is that, although they may accurately represent global climate, their simulations of current regional climate are often inaccurate. The MAGICC/SCENGEN software does not produce output on geographic and temporal scales fine enough for impact assessment, making linear interpolation necessary.  There are also gaps in climate data as the only baseline available in MAGICC/SCENGEN software is 1961-1990.

- As regards the impacts, Vulnerability and Adaptation, limitations include the inadequacy of the impacts models used.  The methodologies used in the INC do not satisfy the whole requirements in the assessment. The adaptations options have not been assessed. The socioeconomic data was not integrated in the INC due to the lack of expertise and the models. In addition, the limitations included the limited expertise in modeling, long-term projections and computer models “know-how “and many data gaps.

#### A.2.6 New Studies and Areas of work

Various new areas of study and work were put forth in the course of the stocktaking exercise for focus in the SNC throughout the sectors as outlined in the following paragraphs.

Energy: In the energy sector, detailed studies and surveying of the sector is proposed in order to improve GHG emission inventories. In addition, new developments that occurred during 1995 to 2006 in the energy and petroleum sectors are to be covered in the SNC, including;

  - More discoveries of crude oil and hence venting of gases;

  - New infrastructure including pipelines with many booster stations;

  - New refineries were built and expanded;

  - Consumption of petroleum products increased;

  - New electricity plants were installed;

  - Refining the data concerning the marine and aviation bunker fuels.

In addition, the stocktaking exercise for energy also identified the need to focus on the following

    - The electricity self-generation in the commercial and household sectors;

    - New modes of mass passenger transport like the so-called "Rakshas";

    - Estimates of the local GHG conversion factors suitable for both biomass and petroleum products.

Agriculture: In the agricultural sector, the stocktaking exercise proposed the integration of new data sources based on recent surveys and data bases and the incorporation of socio-economic aspects, animal nutrition and data management into the study.

LUCF: The stocktaking exercise identified several areas of new study and focus in the LUCF sector. The Use of remote sensing images for acquiring national data by zones, the development of national conversion figures as better and accurate options than default figures and the incorporation of more data on trees outside forests needed by species were all proposed as areas of focus for the SNC.

Industrial: Several new industries were proposed as areas of additional study for the SNC including;

  - Ceramic production.

  - New cement factories.

  - Other industries.

In addition to the inclusion of these new industries, the partial phasing out of halocarbons in different sectors will be excluded.

Waste: Stocktaking with regard to the waste sector proposed the need for surveys in some of the states to estimate waste quality and quantity, particularly in southern and western Sudan

Vulnerability and Adaptation Training: The stocktaking exercise proposed additional areas of focus for the vulnerability and adaptation training team. The following additional elements of the training program were proposed.;

  - Climate scenarios.

  - Socioeconomic scenarios.

  - Impact models.

  - Integrated models.

  - Adaptation assessment methods.

  - Bottom-up methods and tools (rapid assessment, sustainable livelihoods, MCA and others).

#### A.2.7 Measures to Ensure the Sustainability of  Recommendations

It was considered important that INC recommendations were sustainable in the long term development climate of Sudan. Accordingly, the following measures have been taken to maintain the sustainability of climate change institutional processes in Sudan;

  - An overall goal and objectives have been defined to guide the implementation of the UNFCCC and the climate change process in Sudan

  - A permanent coordination unit was established within the HCENR to address climate change issues, and follow up with climate change issues and the government agencies.

  - Consultation mechanisms were established between government agencies and academic and research institutes involved with climate-related studies.

  - More participation of Sudanese experts in the UNFCCC, the IPCC and other climate change related processes and events is encouraged

  - Continued efforts on building capacities and awareness at all levels

#### A.2.8 Priorities for Sudan’s SNC

The SNC will place a focus particularly in those areas identified during the stocktaking exercise where new information is available and which were not addressed in the course of the INC including those areas outlined above in Sections A.2.3 through A.2.6.

With the goal of promoting the incorporation of climate-change related issues into National Policy, the project will also prioritize those areas of climate change-related study that might have the most immediate and lasting affect on National and Regional Policy. These are considered to be both the vulnerability of sectors and communities in Sudan to the climatic shocks and long-terms climate change trends, and the challenges associated with integrating adaptation activities into national development planning.

#### A.2.9 Synergies

A number of national and regional climate-change related projects and coordinated efforts were identified in the course of the stocktaking exercise including;

  - NAPA activities. There are strong synergies between the activities undertaken as part of the development of Sudan’s National Adaptation Programme of Action (NAPA) an the V &A activities that are expected to be undertaken as part of the SNC. The work of the NAPA team has served to identify priority areas of vulnerability that can serve as important starting point for analyses to be undertaken as part of the SNC.

  - AIACC activities. There are important synergies between the findings of Project AF-14, funded as part of the Assessment of Impacts and Adaptation to Climate Change (AIACC) project.   The methods tools that were used as part of the research can represent an important expertise that can be built upon as part of the SNC.

  - NCSA activities.  There are strong link between the activities undertaken by the national capacity self-assessment project and the sustainability of the climate change process in Sudan

  - MEAs. There are important link between SNC and the climate change process and activities undertaken under UNCBD, UNCCD and other MEAs at the national level

  - There are strong links between SNC, implementation of the UNFCCC and the national policies and development planning

## Appendix B: Technical components of the project proposal

### B.1. Background/Context

Sudan has submitted to the Secretariat of the United Nations Framework Convention on Climate Change (UNFCCC) its Initial National Communication in February, 2003 thanks to funding from the Global Environment Facility (GEF), funds and management of the UNDP, and execution by the HCENR.

In its INC, Sudan conducted a number of studies to assess its contribution to the global emissions of anthropogenic GHG, assess the vulnerability of water, agriculture and public health sectors to the impacts of climate change, identify options to mitigate GHG emissions, and assess capacity building needs to support successful implementation of the UNFCCC. To pursue the main objective of the enabling activities capacity building project, these studies were conducted by national teams consisting of representatives from relevant sectors, supported technically by international and national experts

The GHG inventory covered a number of sources and sink categories in five sectors namely energy, industrial processes, agriculture, land use change and forestry and waste management for the base year 1995.

The main objective of the V&A was to uncover the types of challenges that Sudan may likely be facing in the not too distant future with regard to food security, water resources and human health in order to discern the necessary national strategies and priority areas for intervention and adaptation.

The GHG mitigation analysis provided an assessment of the costs and emission reduction benefits associated with the integration of renewable energy resources in Sudan’s electricity expansion plans and industrial facilities. The analysis evaluated the role of energy efficiency (electricity and fuels) in the residential and commercial sectors, as well as the potential for carbon sequestration in the forestry and rangeland sectors.

This project is being pursued in order to provide assistance to Sudan through enabling activities for the process of undertaking an updated national GHG inventory and in preparing the SNC in accordance with UNFCCC guidelines. In addition, the project also aims to strengthen Sudan’s institutional structure toward other UNFCCC processes and for future, continued work in the National Communications program.

In keeping with Decision 17/CP.8 of the UNFCCC, the SNC will include development of the following elements:

- National circumstances;

- Updating of the GHG Gas National Inventory;

- Vulnerability and adaptation to climate change.

- Gaps and constraints, related financial, technical and capacity needs

- General description of steps taken to apply the convention; and,

- Other information

The project will build utilize and build upon the breadth of experience collected in the course of the INC.

## B.2 Project Objectives

Sudan recognizes the need for global cooperation to achieve the ultimate goal of the climate change convention. Therefore the overall development objective of Sudan's national implementation strategy is to promote sustainable development paths that improve Sudan's adaptive capacity and limit its growth in GHG emissions through integration of climate change issues and concerns into national policies, strategies and development plans.

While work being conducted in shorter term endeavors such as NAPA will provide invaluable information on the particularly vulnerable sectors of Sudanese society as well as prioritized and detailed information on potential adaptation initiatives, the nature of the effects of climate change require that the SNC focus on the promotion of long-term, sustainable development structures and courses of action.

Hence, the purpose of this project is to enable Sudan to prepare and submit its second national communication to the UNFCCC and to support the nation in meeting its Convention obligations by improving human and institutional capacity in the climate change field throughout the relevant sectors and at the national and regional levels.

Regarding immediate objectives, the project aims to;

- Strengthen national capacity (technical and institutional) and institutionalize the national communication process in Sudan.

- Prepare an up-to-date national GHG inventory for all possible source/sink categories and establish a national system for regular update.

- Improve scientific knowledge and understanding of Sudan’s vulnerabilities and adaptation responses to current and future climate change.

- Improve understanding of the public and private sectors and their access to technology and CDM opportunities.

- Raise public awareness and create an enabling environment to integrate climate change issues and concerns into national development.

## B.3. Project Strategy

The Higher Council for Environment and Natural Resources (HCENR) is the designated institutional focal point for the UNFCCC, IPCC and other multilateral environmental agreements (MEAs) such as the CBD, POPs, etc.

During the INC process, a Climate Change Coordination Unit (CCCU) was established within HCENR.  This unit is currently charged with the responsibility of supervising and coordinating the implementation of the national strategy and all climate change activities in Sudan.  The CCCU also coordinates regional and international participation of Sudan in various climate change events.

The institutionalization of the national communications process requires that a permanent National Climate Change Committee should be formed from representatives of all the relevant institutions. Climate change focal units are to be established and strengthened in the appropriate institutions within the related sectors such as energy, forestry, industry, etc.  Roles and responsibilities of these focal units need to be clearly defined and political commitment and governmental support for this structure need to be obtained.  The project strategy will emphasize effective coordination between the CCCU in the HCENR and other government ministries.

It will be important to develop targeted training programmes that can serve to deepen national capability in applying advanced methods and tools and conducting analyses, as well as equip Sudan to attract investments in climate change projects. A training strategy will be developed where training can help advance a national consensus for climate change in Sudan. Training courses, workshops, and seminars will be identified and designed to complement the other activities of the HCENR.

Another strategic dimension of the project will be to build a climate change information database. This will involve the identification of required data and sources. Subsequently, it will involve establishing mechanisms for data collection and reporting, training on methods and techniques of data collection, compiling and management, research to fill data gaps and the integration of climate change data needs into the normal reporting systems for the relevant institutions. The creation and maintenance of a well-designed web-based database will facilitate access to climate change data and the preparation of future national communications.

Finally, the sustainability of the project will be pursued by building technical and institutional capacities, establishing effective institutional structures and a dynamic climate change database will certainly contribute to the sustainability of the process of preparing future national communications and ensure effective preparation and implementation of the climate change strategies in Sudan.

## B.4. Project’s Activities

The key project activities and designated outputs are outlined in the following bullets and described in detail in the following subsections.

- Preparing the National Circumstances chapter

- Updating the national GHG Inventory

- Assessing programmes to mitigate national GHG emissions

- Assessing measures to facilitate adequate adaptation to climate change

- Assessing other information considered relevant to the achievement of the Convention

- Understanding constraints and gaps, and related financial, technical and capacity needs

#### B.4.1 Preparing the National Circumstances chapter

A number of important developments have occurred in Sudan since the preparation of the INC, resulting in gaps and important areas not addressed in the document. These will require a revision and update of the national circumstances in the SNC based on substantive and geographical dimensions.  The updating of this information will be carried out by relevant institutions. This process of developing the National Circumstances will focus on the following main activities;

- Special focus will be paid to the socioeconomic parameters as the Sudan is embarking on its 4th National Census which will avail a lot of data;

- There will also be wider geographical coverage as South Sudan was not accessible during the preparation of the INC, now it will be included following the prevalence of peace generated by the signature of the Comprehensive Peace Agreement in January 2005;

- The conflicts in Darfur region and the implications on people livelihoods will also have an impact on the outcome of the SNC;

- The sectors that have not been covered in the INC – e.g. coastal zone - will be included in the SNC;

- There are also the new investments and development projects particularly in the energy sector and the Sudanese economy that should be considered.

#### B.4.2 Updating the national GHG Inventory

An updated GHG inventory of enhanced accuracy will be a major contribution of this project. The main constraints experienced during the preparation of the GHG inventory in the INC were data problems (availability, computability and accessibility); methodological problems including limitation in the definition of sources, sink categories, lack of methods to estimate and manage uncertainties, lack of local emission and other coefficient factors; and technical capacity problems including lack of relevant expertise and institutional facilities.

Based on the experience gained in developing the first national greenhouse gas inventory, there are several efforts that should be carried out. These include the following;

- A reliable and dynamic greenhouse gas database is a prerequisite for regular improvement of the GHG inventory estimates; therefore, such a database will also be a focus of project work. The database will serve as an inventory management system.

- For the second national communication, an inventory plan will be developed by the national team. It will include specific objectives, methods, data management, training, etc. In addition, the plan will specify the base year(s), responsibilities for the institutions involved and will consider arrangements for future updates. The inventory plan will also outline the priorities identified in the course of the INC, and the stocktaking exercise.

- Ongoing capacity building efforts will be planned and implemented in the methods and tools to be used for ensuring that an inventory updating system is both sustainable and of high quality. Capacity building training initiatives will be incorporated in a number of forms including;

- Mainly the recent IPCC methods, data and tools will be used in the SNC.As regards waste, the raw data is available for Khartoum state only and each municipality has its own data which is available on monthly basis until March 2006.  For the industrial waste the data can be obtained from the Industrial Survey (2001-2004).  However, for waste water qualitative data is available only for the years 2004 and 2005.

- All possible GHG from available source sink categories will be covered.  However, special attention will be given to the key categories to improve the qualities of their estimates as has been recommended in the good practices guidance. Key categories to be considered will be those identified in the INC, as well as any key categories resulting from the initial

- In order to strengthen the institutional structure for carrying out future assessments, while a permanent climate change unit has been established within the HCENR and designated to coordinate future updates to the national inventory, it is recommended that a national system include all relevant institutions involved in the inventory development process to be established in order to develop protocols for GHG data collection, monitoring, reporting and verification.

- Where resources allow, local GHG emission factors that better represent Sudanese conditions should be developed and used in future updates to the inventory.

#### B.4.4 Assessing programmes to mitigate national GHG emissions

The GHG mitigation analysis in the INC focused on options that serve both national development priorities and the UNFCCC objectives. The mitigation analysis was carried out by the mitigation team which was composed of national experts from relevant sectors and institutions. The analysis covered options in both the energy and the non-energy sectors. The objectives were to build technical capacity of national experts and to define potential GHG mitigation options for Sudan to undertake a sustainable energy and natural resources development approach

The methodologies used in the INC included the Long-range Alternatives Planning System (LEAP model) in the energy sector to integrate demand and supply mitigation options and to calculate emission reductions.  While in the non-energy sector the COMAP was used to analyze options for carbon sequestration potential and for economic feasibility.

The gaps and constraints encountered in the mitigation analysis in the INC included a lack of detailed end-use data (energy sector) and the lack of up-to -date land use data.  This lack of data was compounded by the problem of data compatibility (land use and energy data found in different formats); available data was not consistent across sectors, reliable or easily accessible.

The outcomes of the analysis carried out during the INC were not sufficient to inform policies and development planning.  However, it gave clear indications about the potentials for Sudan to participate in the global efforts to cut emissions of GHG through the CDM and other available mechanisms. Therefore, the following activities will be carried out in the SNC:

- An in-depth analysis will be conducted for the potential GHG mitigation options focusing on both energy sector (transportation, industry, household, agriculture and commercial & services) and the non-energy sectors which cover forestry, rangeland and agriculture.

- There will be special focus on efficiency in the transport, end-use and on solar energy and the other options identified during the first mitigation study.

- Recent data and suitable methods and tools will be identified and used.

- Efforts will be exerted to collect and use the most reliable and new data in the mitigation analysis.

- National policies, strategies and plans will be considered in the analysis, particularly the accelerated development in the energy sector in order to identify constraints and opportunities and to facilitate integration into national planning.

- There is a clear need to build the capacities and increase the number of experts in GHG mitigation particularly in:

- Modeling and long-term projections and the use and application of the new models and methodologies.

- Financial and economic analysis of potential options including the implications for sustainable development.

- Data collection management.

#### B.4.3 Assessing measures to facilitate adequate adaptation to climate change

Sudan is particularly concerned with the impacts of the climate change processes as the majority of its land is quite sensitive to changes in temperature and precipitation, in addition to its fragile ecosystems and weak infrastructure. More than 70% of the Sudan population is directly dependant on climate-sensitive resources for their livelihood. As such, the changes in climate have triggered recurrent food shortages and famines, scarcity of the resources and conflicts in some regions of the country.

In the INC, the analysis of the impacts of climate change was focused on the Kordofan Region. This region is  located in central part of Sudan between latitudes 9˚ 30’ and 16 ˚ 24’ North and longitudes 27 ˚ to 32 ˚ East.  The exposure units covered certain crops in the rainfed agricultural sector (i.e., sorghum, millet and gum Arabic), water resources (i.e., surface water), and human health (i.e., malaria). The V & A study was conducted by a team that consisted of experts from national institutions involved in these sectors.

Following the submission of the INC, there were two major activities undertaken in Sudan related to adaptation. First, there were a number of case studies were carried out under the AIACC AF14 project to identify suitable adaptation options for the most vulnerable people using a bottom-up approach. Second, the National Adaptation Programme of Action (NAPA) process is being carried out concurrently, using an extensive consultation process based on the LEG guidelines, in five states representing the five ecological zones of the country.

Sudan national implementation strategy aims at improving scientific knowledge and gaining a better understanding of climate change and its physical and socioeconomic impacts in order to make informed policies, plans and practical adaptation actions. This aim sets the context for planned V&A work in Sudan, under which both adaptation planning (i.e., implementing initiatives generated by the NAPA process) and the V&A assessments conducted as part of the under SNC (as well as future V&A assessments) are complementary.

In other words, V&A assessments undertaken as part of the SNC will contribute towards improving scientific knowledge and understanding of Sudan vulnerability to the impacts climate change. This in turn will help to better revising and updating national adaptation plans and improve development planning and decision making process.

Another important aspect of the complementarity between the NAPA and V&A under the SNC, is the intention to apply both top-down and bottom-up approaches in the V&A assessment in the SNC which in itself is an important methodological development for Sudan. In this regards the outcomes of the participatory vulnerability assessment (identification of vulnerable areas and systems in the five ecological zones of Sudan) conducted during the NAPA process will provide a very useful input to this approach as well as the adaptation options identified by the NAPA consultations. These will enable the V&A to conduct scientific assessment and expand the outcomes to other parts of Sudan. Also the experience gained from AIACC AF14 project, in applying bottom-up methodology for identification and assessment of adaptation options, will be a very useful input.

The assessment of measures to facilitate adequate adaptation to climate change in the SNC will seek to build upon the above activities. For the SNC, priority vulnerability areas will be those that are affected by recurrent impacts of climate change (e.g. drought), severe food insecurity, poverty, resource-based conflicts and areas not fully covered in the INC or in subsequent assessments (e.g. coastal zones and South Sudan).

The V&A assessments to be undertaken as part of the SNC will build on the studies completed under the INC and NAPA efforts. However, these new V&A studies will be distinguished from both of the previous efforts by an emphasis on delving deeper into the issues previously only touched upon. The use of bottom-up and top-down methodologies will be a strategic approach in these new analyses. Specifically, the following are proposed activities of the V&A Assessment in the SNC;

- To undertake, for the first time, a comprehensive assessment and mapping of vulnerability to climate change for the whole country.

- To develop a new planning system to rank priorities on a region-specific basis according to the degree of vulnerability of sectors and communities to the impacts of climate change (temperature and rainfall).

- To identify the most suitable adaptation options with regards to the most vulnerable sectors and groups, relative to the outputs emerging from the new V&A studies.

- To identify the expected gaps, constraints, barriers and difficulties in the related fields.

- To establish a close coordination and integration among the relevant institutions.

- To facilitate integration of V&A outputs into national development planning and updates, as needed, of national adaptation plans.

The methodological approach used for the V&A assessment in the SNC will include the following elements;

- A combination of top-down and bottom-up approaches will be used.

- Advance versions of climate change scenario models and down scaling software will be used for impacts assessment.

- Livelihood framework for adaptation assessment will be adopted

- The NAPA regional consultations and AIACC case studies will provide basic information for the SNC.

Work carried out as part of the NAPA regional consultations and the AIACC case studies will provide information on the particularly vulnerable sectors in Sudan, as well as insight into the experiences with adaptation initiatives (particularly as part of the case studies). It is important to note here, however, that the goals of the SNC and the National Communications program in general are, at a broader level as outlined in Decision 17/CP8, to take steps towards “formulating, implementing, publishing, and regularly updating national and, where appropriate, regional programmes containing measures to facilitate” achievement of the Convention.

The NAPA and AIACC work will provide background in the area of particularly vulnerable sectors, priority areas of adaptation and priority projects, work on the SNC will aim at further developing these studies and placing this information in the larger, national and regional development context. As per the NC guidelines, this SNC should strive to make use of concurrent work in the area of vulnerability and adaptation in;

- Outline those sectors of Sudanese society particularly vulnerable to climate change;

- Identifying uncertainties inherent in methodologies used to assess vulnerability and adaptation capacity;

- Present key findings which allow for integrated analysis of climate change vulnerability; and

- Outline key strategies and measures for adapting to climate change in the Sudanese context.

#### B.4.5 Assessing other information considered relevant to the achievement of the Convention

Sudan’s INC included a chapter called Towards a National Implementation Strategy, in which specific objectives have been defined to elaborate and develop a national response to implement the objectives of the climate change convention in Sudan. Following the preparation of the INC, a number of activities guided by the objectives of the implementation strategy have been carried out including research and studies, awareness raising and capacity building, and integration of adaptation to climate change in national planning.

The SNC will build on these results by making a detailed assessment of the progress and development made towards achieving the objectives. Also, issues and needs to further elaborate and develop Sudan efforts to implement the UNFCCC will be defined and reported.

On research and systematic observation, SNC activities will include identification of organizations and institutions involved in climate related research and systematic observations, their activities and programmes, capacities, gaps, needs and priorities and links and participation in regional and international activities.

Some of the activities related to Article 6 of the UNFCCC envision during the SNC will include:

- Identification and description of existing activities and plans, if any, to incorporate climate change into education programmes.

- Identification and description of education, training and public awareness campaigns launched/planned, if any, and the role/involvement of stakeholders such as civil society, NGOs, the private sector and others, as well as the media.

- Identify in details the gaps, needs and priorities, including international assistance, in developing and implementing initiatives and programmes, including information exchange and dissemination, in climate change education, training and public awareness.

Sudan intends to conduct a technology needs assessment (TNA) during the preparation of its SNC.  The focus of the assessment will be on both mitigation and adaptation. The intention is to solicit additional resources from UNDP to conduct a TNA study during the preparation of the SNC, pending the availability of resources. The guidelines prepared by the UNDP in collaboration with the EGTT will be used in the technology need assessment. Conducting this activity in parallel to the SNC should offer strong synergies regarding the types of technologies for mitigation and adaptation. The main results and findings of the TNAs will be reported in the SNC

#### B.4.6 Understanding constraints and gaps, and related financial, technical and capacity needs

The detailed assessment of the constraints, gaps and capacity needs resulted from the stocktaking and the stakeholders’ consultations are presented in Appendix E.  Capacity building activities within the SNC will be focused on two components.

- The first one deals with enhancing the ability and effectiveness of the institutional structure responsible for regular preparation of national communications, which include the Climate Change Unit of HCENR and the Focal Units in the partner institutions.

- The second component will focus on enhancing the technical capacities of the assessment teams and other relevant experts from the institutions involved in the preparation of the National Communications and the implementation of the UNFCCC.

The training programme will be prepared based on the outcomes of the stocktaking exercise (appendix E) and the TNA study, will benefit from the outcomes of the National Capacity Self Assessment (NCSA) process (on-going now), will consider the actual needs for conducting studies, assessments and preparing the various technical components of the SNC and in addition to the need for institutionalizing the National Communication process. The capacity building activities for the SNC will cover the needs as discussed below:

Establishing Institutional arrangements for National Communications: activities that aim at establishing permanent institutional infrastructure for preparing GHG Inventory and National Communications, they may include:

- Identification of the relevant institutions that should be included.

- Defining role and responsibilities.

- Providing computers, software and methods and tools used in climate change studies and assessment.

- Building technical capacities and effective coordination mechanisms.

- Build awareness.

- Developing agreement for continuous support and commitment.

GHG Inventory: Ongoing capacity building efforts will be planned and implemented in the methods and tools to be used for ensuring that an inventory updating system is both sustainable and of high quality. For the SNC it will include training on the IPCC Good Practice Guidance GPG2000 and GPG LULUCF 2003, Emission Factor Database (EFDB) and data collection and management techniques.

GHG Mitigation: There is a clear need to build the capacities and increase the number of experts in GHG mitigation particularly in:

- Modeling and long term projections and the use and application of the new models and methodologies.

- Financial and economic analysis of potential options including the implications for sustainable development.

- Data collection management.

Vulnerability and Adaptation Assessment: To enhance the technical capacities of the national V&A team and to train new experts, in the use and application of the most recent methods and tools for impact vulnerability and adaptation assessment. Training programme may include:

- Climate scenarios and downscaling techniques

- Socioeconomic scenarios.

- Impact models.

- Integrated models.

- Adaptation assessment methods.

- Bottom-up methods and tools (rapid assessment, sustainable livelihoods, multicriteria assessment (MCA) and others).

Other areas of training may include: Technology Needs Assessment (TNA) and methods and tools for developing sound climate change-related projects (e.g., CDM, technology transfer, adaptation)

## B.5. Institutional Framework for Project Implementation

Preparation of the SNC will build on the capacities and expertise developed during the preparation of the INC and the assessment studies that have been conducted by national teams composed of experts from all relevant government and non-government institutions. Moreover, the SNC will continue to benefit from the technical advice and help of Stockholm Environment Institute- US Center (SEI-US). The present project will build on the institutional infrastructure identified during the INC and will aim at establishing a permanent structure for regular preparation of national communications, build the technical and institutional capacities, obtain agreements and legal support and commitment of intuitions involved.

HCENR will be the leading agency responsible for the oversight and implementation of the Enabling Activities for the Preparation of Sudan‘s Second National Communication to the UNFCCC.  The involvement of the relevant stakeholders, and their support and commitment to the implementation of the proposed activities, will ensure the achievement of the overall outcome of the project.

## B.6. Assessing Project Impact

Provision has been made to conduct an end-of-project evaluation a few months after the completion and submission of the SNC. A short-term consultant will be hired for this purpose. The UNDP country office may decide to utilize the UNDP Environmental Outcome Evaluation to determine the impact of the project.

At the beginning of the project, a practical framework to assess capacity development and the potential impacts of the national communication process will be developed. The framework may look into five strategic areas: 1) Capacity to conceptualize and formulate policies, legislation, strategies and programmes; 2) Capacity to implement policies, legislation, strategies and programmes; 3) Capacity to engage and build consensus among all stakeholders; 4) Capacity to mobilize information and knowledge; 5) Capacity to monitor, evaluate, report and learn will be included in the framework.

The framework will identify a few practical indicators to assess the impacts of the SNC in incorporation climate change concerns into development and sectoral planning, as appropriate. The National Communications Support Programme (NCSP) would provide guidance on developing an impact assessment framework, linked to the different components of the SNC, and the possible indicators that may used to assess impacts.

In developing this framework, capacity development impacts may be given special attention. Capacity building at the individual, organization, and systemic levels will be carried out to meet the objective of increasing the ability of Sudan to meet its commitments under the UNFCCC and increasing the ability of Sudan to respond to these commitments in terms of specific policies and decisions.

It is important to note that the development and adoption of such a framework would be a country-driven exercise that seeks to bring the SNC process closer to development priorities in the context on national policy-making. Under the guidance of the NCSP, Sudan would design an impact assessment framework that meets the country’s needs and priorities in terms of facilitating the linkage between the SNC and development issues.

## B.7. Project Risks

There are three classes of risks that could potentially jeopardize the implementation of activities for Sudan’s SNC. Difficulties could arise in a) recruitment of key experts, b) access to the required data from various ministries involved, and c) adequate degree of representation and involvement of NGOs and CBOs. Given the importance of the outputs of the work groups in the process of elaboration of the adaptation and mitigation measures, should any of the mentioned difficulties arises, rapid action will be taken so that activities are not adversely affected.

## B.6. Detailed Workplan

A detailed work plan of the SNC project distributed over the project duration of three years is shown in the following table. The major work in the first year is devoted to project initiation and preparation of GHG inventory. The second year will be devoted to activities pertaining to mitigation and vulnerability and adaptation. The third year will be provided to other information as well as project documentation and dissemination.

Detailed workplan for implementation of Sudan’s SNC activities

| Outputs/Activities | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Implementation arrangements and project inception: | Year 1 | Year 2 | Year 2 |
| 1. Contract the project office staff | X |  |  |  |  |  |  |  |  |  |  |  |
| 2. Establish technical teams | X |  |  |  |  |  |  |  |  |  |  |  |
| 3. Update the composition of the PCU | X |  |  |  |  |  |  |  |  |  |  |  |
| 4. Organize a project initiation workshop | X |  |  |  |  |  |  |  |  |  |  |  |
| Prepare National circumstances |
| 1. Validate the gaps of information identified under stocktaking | X | X |  |  |  |  |  |  |  |  |  |  |
| 2. Identify the respective sources of information and Collect data and information from them | X | X |  |  |  |  |  |  |  |  |  |  |
| 3. Fill the gaps, update and add the new information |  | X | X |  |  |  |  |  |  |  |  |  |
| 4. Draft national circumstances sections relevant to each thematic area. |  |  | X | X |  |  |  |  |  |  |  |  |
| 5. Draft the National Circumstances section under the SNC |  |  |  | X |  |  |  |  |  |  |  |  |
| 6. Circulate the National Circumstances section for comment, get comments. |  |  |  | X |  |  |  |  |  |  |  |  |
| 7. Finalize the National Circumstances section under the SNC |  |  |  | X |  |  |  |  |  |  |  |  |
| Update the GHG inventory |
| 1. Convene the GHG inventory team | X | X |  |  |  |  |  |  |  |  |  |  |
| 2.Identify and mobilize national experts in targeted sectors and related areas of relevance |  | X | X | X |  |  |  |  |  |  |  |  |
| 3. Review the existing information on the previous GHG inventory and familiarize with guidelines |  | X | X | X |  |  |  |  |  |  |  |  |
| 4. Identify methodologies for developing GHG inventory estimates |  | X | X | X |  |  |  |  |  |  |  |  |
| 5. Develop draft GHG Inventory Plan |  | X | X | X |  |  |  |  |  |  |  |  |
| 6. Collect the necessary activity data from the available sources |  | X | X | X | X |  |  |  |  |  |  |  |
| 7. Prepare a draft inventory of GHG |  | X | X | X | X |  |  |  |  |  |  |  |
| 8. Develop key sources analysis and inventory and undertake uncertainty assessment |  | X | X | X | X |  |  |  |  |  |  |  |
| 9. Circulate inventory for internal review |  |  |  | X | X | X |  |  |  |  |  |  |
| 10. Organize a national workshop to present findings of the GHG inventory |  |  |  |  | X | X |  |  |  |  |  |  |
| 11. Incorporate comments received from the review process and finalize the inventory |  |  |  |  |  | X |  |  |  |  |  |  |
| Assessment of measures to mitigate GHG emissions |
| 1. Consider estimates of GHG inventory |  |  |  |  | X | X |  |  |  |  |  |  |
| 2. Compare INC and SNC figures /estimates obtained for the GHG Inventory |  |  |  |  | X | X |  |  |  |  |  |  |
| 2. Collect relevant macro-economic data and set assumptions |  |  |  |  | X | X |  |  |  |  |  |  |
| 3 Develop a revised baseline GHG emission scenario |  |  |  |  |  | X | X | X |  |  |  |  |
| 4. Identify and explain any difference / change to the GHG baseline scenario developed under Sudan’s INC |  |  |  |  |  |  | X | X |  |  |  |  |
| 5. Develop new GHG mitigation measure/technology options to be considered in analysis |  |  |  |  |  |  | X | X | X |  |  |  |
| 6. Develop / update the GHG mitigation scenario analysis for energy and related demand sectors |  |  |  |  |  |  | X | X | X |  |  |  |
| 7. Estimate GHG reduction potential, costs of reduction and penetration rate of each measure |  |  |  |  |  |  | X | X | X |  |  |  |
| 8, Develop / update the GHG abatement scenario for non-energy sectors |  |  |  |  |  |  | X | X | X |  |  |  |
| 9. Identify any difference / change to the abatement scenario developed under INC |  |  |  |  |  |  |  | X | X |  |  |  |
| 10. Develop the draft chapter of the GHG mitigation analysis and circulate it for internal and external reviews |  |  |  |  |  |  |  | X | X | X |  |  |
| 11. Organize a national workshop to present findings from the GHG abatement analysis |  |  |  |  |  |  |  |  | X | X |  |  |
| 12. Review findings and finalize the GHG abatement analysis chapter to be submitted as a part of the SNC |  |  |  |  |  |  |  |  | X | X |  |  |
| 13. Archive and document all the GHG mitigation analysis related studies and estimates |  |  |  |  |  |  |  |  |  | X |  |  |
| Assessment of measures to facilitate adaptation to climate change |
| 1. Decide on the range of the assessment, approaches, tools and methods |  |  | X | X | X |  |  |  |  |  |  |  |
| 2. Identify the type and scope of data and information needed |  |  | X | X | X |  |  |  |  |  |  |  |
| 3. Review the policy process and development context for the selected area |  |  | X | X | X |  |  |  |  |  |  |  |
| 4. Collect and synthesize the necessary data and information. |  |  | X | X | X | X |  |  |  |  |  |  |
| 5. Define current vulnerability and adaptation of the priority area(s) assessed |  |  |  | X | X | X | X |  |  |  |  |  |
| 6. Define Future climate risk and adaptation measures assessed for the priority area. |  |  |  | X | X | X | X |  |  |  |  |  |
| 7. Develop environmental-socio-economic trends and risks |  |  |  | X | X | X | X |  |  |  |  |  |
| 8. Develop adaptation response measures and compile an Adaptation Policy Paper |  |  |  | X | X | X | X |  |  |  |  |  |
| 9. Develop the draft chapter of the V&A and circulate it for internal and external review and comments |  |  |  |  | X | X | X | X |  |  |  |  |
| 10. Organize a national workshop to present findings from the V&A and get comments |  |  |  |  |  |  | X | X |  |  |  |  |
| 11. Sort out the findings and finalize the V&A chapter to be submitted as a part of the SNC |  |  |  |  |  | X | X | X | X |  |  |  |
| 12. Archive and document all the V&A related studies and estimates |  |  |  |  |  |  | X | X | X |  |  |  |
| Assessment of other relevant information to the achievement of the objective of the convention |
| 1. Collect, synthesize and provide the overall information relevant to the Article 6 activities |  |  |  |  |  |  | X | X | X | X |  |  |
| 2. Collect & synthesize information on steps taken to integrate climate change into planning in Sudan. |  |  |  |  |  |  |  | X | X | X |  |  |
| 3. Collect, synthesize and provide information on the research and systematic observation systems |  |  |  |  |  |  |  |  | X | X |  |  |
| 4. Collect, synthesize and provide information on relevant ongoing projects |  |  |  |  |  |  |  |  | X | X |  |  |
| 5. Summarize all the information collected in a draft chapter. Distribute it for review and comments internally. |  |  |  |  |  |  |  |  | X | X |  |  |
| 6. Incorporate comments to the above draft chapter and finalize it as part of the Sudan’s SNC |  |  |  |  |  |  |  |  |  | X |  |  |
| Understand constraints, gaps and related needs identified and reported |
| 1. Review the status of the constraints and gaps from previous studies |  |  |  |  |  |  |  |  | X | X |  |  |
| 2. Identify new constraints and gaps for each thematic area |  |  |  |  |  |  |  |  | X | X |  |  |
| 3. Summarize constraints, gaps and needs identified and draft a synthesis report as a separate chapter |  |  |  |  |  |  |  |  | X | X |  |  |
| 4. Distribute the above draft chapter for comments, and update the document accordingly |  |  |  |  |  |  |  |  |  | X |  |  |
| SNC produced, translated, submitted and disseminated |  |
| 1. Compile a draft of the Sudan’s Second National Communication |  |  |  |  |  |  |  |  |  | X | X |  |
| 2. Circulate the draft for comments and review and incorporate them |  |  |  |  |  |  |  |  |  | X | X |  |
| 3. Endorse the document by the PCU |  |  |  |  |  |  |  |  |  | X | X |  |
| 4. Finalize the Second National Communication of Sudan |  |  |  |  |  |  |  |  |  |  | X | X |
| 5. Publish Sudan’s SNC to the COP of UNFCCC |  |  |  |  |  |  |  |  |  |  | X | X |
| 6. Prepare e-copies of Sudan’s SNC in CD-ROMs |  |  |  |  |  |  |  |  |  |  | X | X |
| 7. Submit officially Sudan’s SNC to the COP of the UNFCCC |  |  |  |  |  |  |  |  |  |  | X | X |
| 8. Organize a national workshop to launch and present the findings of Sudan’s SNC |  |  |  |  |  |  |  |  |  |  | X | X |

# Appendix C. 1: Term of References (TOR)

## TOR for the National Project Coordinator (NPC)

Under close supervision and guidance of the Secretary General of the Higher Council for Environment and Natural Resources (HCENR), UNDP-Khartoum and in consultation with the National Climate Change Committee (NCCC), National Technical Committee (NTC), and close collaboration with the Assistant Project Coordinators (APCs), the Project Coordinator (NPC) is entrusted with the following tasks:

- Ensuring the liaison between the NCCC, UNDP-Khartoum, NTC, and other relevant actors.

- Supervision and ensuring the timely implementation of the project relevant activities as scheduled in the working plan

- Summarizes and synthesizes the results of the project;

- Identifies the follow up activities and mobilizes other resources at the extent possible;

- Identifies and ensures synergy of the SNC with other relevant ongoing / new projects.

- Ensures that the SNC process is in the line with guidance provided by the CoP of the UNFCCC and contributes to the improvement of the UNFCCC reporting process.

- Prepares a detailed work plan for the project and draft terms of reference for the subcontracts (in consultation with the NCCC and UNDP-Khartoum); closely following the project document including:

  - Coordinate national activities and the relevant organizations;

  - Organize support for implementation of project activities (e.g. training, publications, documentation and information dissemination);

  - Contribute to identifying and acquiring the means required for the various activities (financial and human resources);

  - Ensure management of adequate resources and in close coordination with UNDP and the HCENR

  - Initiate activities to mobilize further resources for the project, its sustainability and its future expansion in the region;

  - Undertake regional and global contacts and communications that serve the purpose of the project.

  - Preparation of scientific, technical, evaluation and progress reports

H. in consultation with the other stakeholders, prepare and coordinate the preparation of the Second national communication of the Sudan to the UNFCCC.

Qualifications and Experience

- Preferably Master’s degree in environment-related studies and other related disciplines;

- Good understanding of Sudan’s environment/development issues as well as the three thematic areas under investigations;

- At least ten to twelve years experience in areas relevant to the project;

- Excellent communication (Written and Oral) Skills;

- Demonstrated experience in project management;

- Expertise in putting together results-oriented action plans;

- Demonstrated experience in working with government, donors and the United Nations system;

- Appropriate experience working with government structures at local levels, and working with NGOs and private sector;

- Substantial involvement in climate change scientific, technical and negotiation issues and the initial National Communication is mandatory

- Substantial knowledge of climate change scientific methodologies

- Substantial experience in Government and in inter-departmental procedures preferred

- Familiarity with international negotiations and processes under the UNFCCC preferred

- Familiarity with computers and word processing

## Appendix C. 2. TOR for the Assistant Project Coordinator (APC) for GHG Inventory and Mitigation

Under close supervision and guidance of the Secretary General of the HCENR, the National Project Coordinator (NPC) and UNDP, the Assistant Project Coordinator (APC) is entrusted with the following tasks:

- Assist in the preparation of project work plan and TOR for the subcontracts (in consultation with the NPC);

- Coordinate the work of national experts and institutions (in consultation with the NPC);

- Coordinate GHG inventory and mitigation activities with the related entities and/or organisations.

- Identify elements of sustainability of these activities and establishment of the climate change process in Sudan

- Coordinate other project activities with the related entities and/or organizations.

- .Development and organization of related training programmes;

- Preparation of scientific, technical, evaluation and progress reports

- Undertake national, regional and global contacts and communications that serve the purpose of the project;

- Assisting the NPC with the preparation of the Second national communication;

- other miscellaneous duties

Qualifications and Experience

- Preferably Master’s degree in environment-related studies and other related disciplines;

- Good understanding of Sudan’s environment/development issues as well as the three thematic areas under investigations;

- At least six to eight years experience in areas relevant to the project;

- Excellent communication (Written and Oral) Skills;

- Demonstrated experience in project management;

- Expertise in putting together results-oriented action plans;

- Demonstrated experience in working with government, donors and the United Nations system;

- Appropriate experience working with government structures at local levels, and working with NGOs and private sector;

- Substantial involvement in climate change scientific, technical and negotiation issues and the initial National Communication is mandatory

- Substantial knowledge of methodologies for GHG Inventory and Mitigation (IPCC Revised 1996 Guidelines and Good Practice Guidance, COMAP, LEAP etc)

- Familiarity with international negotiations and processes under the UNFCCC preferred

- Familiarity with computers

## Appendix C. 3. TOR for the Assistant Project Coordinator (APC) for Vulnerability and Adaptation Assessment

Under close supervision and guidance of the Secretary General of the Higher Council for Environment and Natural Resources (HCENR), the National Project Coordinator (NPC) and UNDP-Khartoum, the Assistant Project Coordinator (APC) is entrusted with the following tasks:

- Assist in the preparation of project work plan and TOR for the subcontracts (in consultation with the NPC);

- Coordinate the work of national experts and institutions (in consultation with the NPC);

- Coordinate vulnerability and adaptation assessment activities with the related entities and/or organizations.

- Identify elements of sustainability of these activities and establishment of the climate change process in Sudan

- Coordinate other project activities with the related entities and/or organizations.

- .Development and organization of related training programmes;

- Preparation of scientific, technical, evaluation and progress reports

- Undertake national, regional and global contacts and communications that serve the purpose of the project;

- Assisting the PC with the preparation of the Second national communication;

- Any other duties.

Qualifications and Experience

- Preferably Master’s degree in environment-related studies and other related disciplines;

- Good understanding of Sudan’s environment/development issues as well as the three thematic areas under investigations;

- At least six to eight years experience in areas relevant to the project;

- Excellent communication (Written and Oral) Skills;

- Demonstrated experience in project management;

- Expertise in putting together results-oriented action plans;

- Demonstrated experience in working with government, donors and the United Nations system;

- Appropriate experience working with government structures at local levels, and working with NGOs and private sector;

- Substantial involvement in climate change scientific, techincal and negotiation issues and the initial National Communication is mandatory

- Substantial knowledge of methodologies for Vulnerability and Adaptation assessment (top-down impacts approaches and bottom-up vulnerability and participatory approaches etc)

- Familiarity with international negotiations and processes under the UNFCCC preferred

- Familiarity with computers

## Appendix C. 4. TOR for the Vulnerability and Adaptation Assessment

## Profile of the V&A expert/consultant:

The V&A expert should be very knowledgeable and with hands-on experiences on V&A issues, have a solid understanding of the gaps and needs for developing/improving vulnerability assessments, and have technical expertise in the formulation of adaptation options. The V&A expert should be able to scope technical studies in the V&A area and design an implementation strategy to carry out the different V&A activities within the framework of the NC. He/She should also have a solid understanding of the institutional arrangements and resources required to carry out the V&A work.

Although the NC project document already provides the framework for the V&A studies, the expert should be able to advise on any adjustments if needed, both at the organizational and technical levels, for a successful implementation of the V&A studies.

Activities: In general, the V&A expert/consultant should be responsible for ensuring that the following set of activities is carried out. Emphasis on different activities will depend on the scope of the work already described in the NC project document and/or on the specific activities the V&A expert would be assigned to.

## Policy and institutional issues

1.	Identify the key policy issues the V&A study of the SNC project aims to address, e.g.;

  - to scope the scale of risks associated with projected climate change;

  - to aid in the identification of priorities for adaptation;

  - to support the development of a national adaptation strategy.

2.	Identify the expected output of the V&A study of the SNC project on the basis of the project document, e.g.;

- impacts assessment at the sectoral level for the given priorities identified in the project document;

- a national adaptation strategy, including policies, programs and projects.

3.	Develop a clear strategy to link the V&A outputs to national development planning. This would include, among others:

- assessment of institutional arrangements/stakeholders engagement required to facilitate linking the outcome of the V&A studies to sectoral or national planning;

- framework for assessing how the above linkage can be monitored and measured in the short and long terms, for instance through the development of practical indicators.

## Technical issues

### Scope of the V&A study

1.	Elaborate on the scope (geographic, thematic, sectoral coverage, time horizon) of the V&A study, e.g.;

- designing a strategy to build on but advance what was done within INC, and while applicable, NAPA project;

- elaborating on the scope of studies to address sectors/regions not covered by INC, sectors/regions identified as sensitive/vulnerable to climate change, as per the NC project proposal;

- preparing a detailed workplan for each of the study to be carried out, including a strategy to involve the relevant stakeholders, timeline, etc.;

- designing a strategy, as applicable, to link the V&A studies with previous and ongoing related projects/activities (e.g., land degradation, biodiversity, international waters.)

### Methodological framework

1.	Elaborate on the overall methodological framework for the V&A study as per the project document and in consultation with the project coordinator. In doing so, the V&A expert should ensure that:

- The proposed methodological framework is the most appropriate given the policy questions to be addressed, the characteristics of the study (e.g., sectoral focus, spatial and temporal scales, stakeholders involved, and data requirement, etc.), and data availability;

- In-country expertise required for such a methodological framework is available.   If needed, the V&A expert should develop a strategy to address technical capacity gaps. For instance, by exploring the possibility of applying another framework in which more in-country expertise exists, or by designing a training/technical backstopping strategy, etc.

### Scenarios development

1.	Identify the types of scenarios required to conduct the V&A assessment, e.g., climate, socio-economic, sea level, adaptive capacity, technology, land-use land-cover.

2.	Identify the temporal and spatial resolution needed for these scenarios (e.g., national, sub-national, watershed, community, farm level, multi-decadal average, annual, monthly, daily, mean conditions, extreme events, etc.). In doing so, the expert should justify the choices.

3.	Develop the strategies for developing such scenarios, e.g., model-based, expert judgment, etc.

4.	In the preparation of the scenarios development strategy, the expert should assess the feasibility of the scenario needs and the methods for developing these scenarios, given the characteristics of the studies, and data availability. For instance, the expert would be expected to advice on alternative options to running regional climate models or other resource intensive and time consuming exercises. The V&A expert would also assess whether there is enough in-country expertise to develop such scenarios and/or identify options to address the needs for additional expertise.

### Sectoral assessment (to be considered by each of the sectors to be covered in the V&A study)

1.	Elaborate on the methods and tools, as per the project document, chosen to undertake sectoral assessments, e.g., numerical models, elicitation of expert views, stakeholder consultations, focus groups, etc.  In doing so, the expert will advise on any adjustments needed to the options identified in the project document.

2.	Provide justifications for the selection of the methods/tools considering the research questions, characteristics of the study, and requirements of data and technical expertise of these methods/tools.

3.	Assess in-country expertise required to apply the selected methods/tools and prepare training/technical backstopping strategy as required.

4.	Develop a strategy to integrate findings from sectoral assessment, as needed. For instance, by applying an integrated model, synthesizing sectoral information, etc.

## Technical assistance needs

1.	Develop a technical backstopping/training strategy to strengthen the national capacity needed to carry out the different V&A studies, This would include details on the type of support needed (training courses on particular methodological frameworks/tools, guidance material, technical documents and good practice) and the, timeline for such support.

Appendix D: Letters of Endorsement

# Appendix E: Stakeholders participated in the Stocktaking

Table A-1. Project Budget: GEF Funds Contribution for Activities Implemented by the HCENR

| Name of institutions / stakeholders consulted | Type | Interest | Reasons for inclusion | Role in the self-assessment process |
| --- | --- | --- | --- | --- |
| Ministry of Agriculture & Forests | Government | Federal policies & plans | GHG inventory, GHG mitigation, V & A | Consultation (member of the technical team) & data provision |
| Ministry of Energy | Government | Licensing of minerals exploration Control of oil production, distribution and export | GHG inventory and GHG mitigation | Consultation (member of the technical team) & data provision |
| Ministry of Irrigation and Water Resources | Government | Policies, data, management of water resources | V & A | Consultation, member of the national team |
| Ministry of Health | Government | Policies, research | V & A | Consultation, member of the national team |
| Meteorological Corporation | Government | Recording, analysis & storage of climate data | Vulnerability & adaptation (climate scenarios) | Consultation (member of the technical team) & data provision |
| Forests National Corporation and the Faculty of Forests | Government | Management of forests | GHG inventory, GHG mitigation, V & A | Consultation (members of the technical team) & data provision |
| Range and Pasture Administration | Government | Management of ranges and pastures | GHG inventory, GHG mitigation, V & A | Consultation (member of the technical team) & data provision |
| Ministry of Industry and Elneelain University | Government | Industrial policies and licensing and education | GHG inventory and mitigation | Consultation (member of the technical team) & data provision |
| National Centre for Research | Government | Research | GHG inventory, GHG mitigation, V & A | Consultation (member of the technical team) & data provision |
| Ahfad University for Women | Academia | Higher Education | GHG inventory and mitigation | Consultation (member of the technical team) & data provision |
| Institute of Environmental Studies, faculties of forestry and faculty of Engineering of the University of Khartoum | Academia | Research and Studies | GHG inventory, GHG mitigation, V & A | Consultation (member of the technical team) & data provision |
| The Sudanese Environment Conservation Society | NGO, CSO | Awareness raising, advocacy & research (NGO) | Participatory approaches | Consultation (member of the technical team) & data provision |
| The Environmentalists Society | NGO, CSO | Awareness raising, advocacy & research (NGO) | Participatory approaches | Consultation (member of the technical team) & data provision |
| Industrial chamber | Private sector | Investment and development | GHG mitigation, awareness | consultation |

# Text boxes

Budget		                        USD 405,000

General Management Support Fee________

Total budget:		 USD 405,000 Allocated resources:	 ____________

- Government

- Regular 		 ____________

- Other:

  - Donor (GEF USD) 405,000

  - Donor	_________

  - Donor	_________

- In kind contributions from Government of Sudan  USD 75,000

Unfunded budget:	_________

Programme Period:  July 2007-July 2009

Programme Component: Human Security and Recovery Unit

Project Title: Enabling Activities  for the preparation of  Sudan’s Second National Communication to the  UNFCCC

Proposal ID:          00040754

Project ID:             00046263

Project Duration:	 Three  years

Modality of Implementation: NEX

HCENR

Project Oversight

- MIC

- UNDP

- National climate change committee

Project Stakeholders

Ministries

Public Institutes

Private Institutes

Academia

NGOs

Private Consultants

Steering Committee (NCCC) ou

Outcome

Steering Committee

Project Coordination Unit and   Project Coordinator (s)

National Technical Committee

V & A Team

Sectoral Experts

GHG Inventory and Mitigation Team

Sectoral Experts

- National Circumstances

- Other related information

- Constraints and gaps