Human security initiative for “tensions” reduction, reconciliation and rehabilitation in the Solomon Islands

# Quarterly Progress Report 1 July – 30 September 2015

1. Country Name: 			Solomon Islands

2. Project Number/Code: 		Award ID 00064994, Project ID 00081641

3. Project Title: 	Human security initiative for “tensions” reduction, reconciliation and rehabilitation in the Solomon Islands

4. Executing Agency: 			UNDP (Direct Execution)

5. Period Covered: 			1 July – 30 September 2015

6. Report Prepared by: 			Project Management Unit

7. Project Delivery to date: 		USD$ 309,170.81

8. Summary of Overall Project Progress (during reporting period):

- Confirmation received from UNTFHS for six-month ‘grace’ period for disbursements and implementation for the funds committed by 15 October 2015

- The joint project (JP) coordination mechanisms functional as planned on fortnightly basis

- Project reprogramming with additional funds and extended timelines rejected by UNTFHS

- Independent evaluators deployed and evaluation reports under production

- Total of 14 workshops and multi-stakeholder consultative meetings held

- Intensive five-day fulltime conflict analysis training delivered to 40 male and female professionals representing key peacebuilding stakeholders in Malaita Province

- Provision of civic education and legal literacy training to inmates and abused women/girls initiated through grant agreements with two local NGOs

- School-based promotion of National Consciousness, Identity and Unity initiated through grant agreement with one local NGOs

- Preparations in an advanced stage for initiation of Peacebuilding and Traditional Governance Module at Solomon Islands National University (SINU)

- National Peacebuilding Policy endorsed and implementation initiated at province level

- Provision of assistance initiated for increased reintegration support to the abused women and girls sheltered by the Christian Care Center (CCC)

- Refurbishing on-going for six health centers mandated with psychosocial assistance

- 202 unemployed youth and young adults, out of which, 109 female, benefited from peacebuilding workshops.

- Public at large provided with increased exposure to peacebuilding and national identity messages and prompts through the three-folded ‘Think-peace-Live peace’ campaign

# Detailed Next steps:

Activity 1.2: Workshops for local registration systems in all 3 target provinces/city

Nothing to report - Activity completed

Activity 1.3: Communication strategy/interventions

Nothing to report - Activity completed

Activity 1.4: Peace centers

Infrastructure reconstruction/rehabilitation/refurbishing

Six rural community peace centers in Guadalcanal (construction by MNURP under SIG budget)

Research Center on Traditional Governance & Peacebuilding at SINU

Four health centers Weathercoast

Kilufi Psychiatric Hospital, Malaita

Psychiatric emergencies basic facilities at Honiara Hospital

Scouts grant implementation: installation flag poles and traditional billboards in 20 schools

SINU LOA: equipment for establishing the Peacebuilding and Traditional Governance unit

Symbolic/Social reconstruction for positive behaviors, mindsets, attitudes

DSE grant implementation: pilot civic education

Family Support Center grant: legal literacy handbook

DSE grant implementation: workshop on disability and human rights for local NGOs

SINU LOA implementation: workshop on Social Research Policy for Peacebuilding Policy implementation

Activity 2.1: Establishment of reintegration counselling mechanisms

Study on youth perceptions on community connectors and dividers

Media monitoring survey for conflict trends and dynamics

Activity 2.2: Training on negotiation, conflict resolution and mediation to target communities

Nothing to report - Activity completed

Activity 2.3: Project management

Joint Project Coordination Meeting – one meeting remaining

Activity 2.4: Public awareness -social communication on human security & peaceful co-existence

Nothing to report - Activity completed

| Intended Output 1: Up to 90% of selected stakeholders (local governmental officials, community leaders, representatives of CBOs and Women's Groups) participate in the process of establishing local registration systems to improve local participation. |
| --- |
| Activities | Progress by 30 September 2015 |
| 1.1 Organize a total of 12 provincial workshops to achieve a local consensus on implementation and exit strategies | Nothing to report (Activity completed at the end of 2nd quarter) |
| 1.2. 36 workshops for local registration | Activity completed as at the end of reporting period. The remaining four workshops on registration-related topics were delivered as follows: Consultations with MNURP and CCC on the registration for reintegration of abused women and girls sheltered by CCC. The key session took place on 9 July when the action plan for increased support to the above target group was prepared for endorsement. Its’ implementation was on-going at the end of reporting period. Two consultation sessions with DSE and FSC took place in July for identification of best modalities to select and register inmates at Tetere and Auki for civic education, legal literacy respectively. The consultations resulted in preparations of grant agreements. A series of consultations were held between 10 and 14 August with the Diocese of Malaita for registration and psychosocial recovery of the reported number of 200 Malaitans identified as in critical need for psychosocial recovery. |
| 1.3 Implement advocacy measures for promoting local participation and maintenance of rehabilitated infrastructure | Activity completed as at the end of reporting period. Implementation of the ‘Think peace – Live peace’ awareness and advocacy campaign consisted in: Distribution of 40,000 stickers Advertisement published in Solomon Star and Island Sun Outdoor billboard installed in Honiara on 7 July |

| Intended Output 2: All three target provinces of Guadalcanal, Malaita and Honiara possess 'green' community peace centers as foundation for "tension" reduction |
| --- |
| Activities | Progress by 30 September 2015 |
| 2.1 Rehabilitate/reconstruct 3 community peace centers in each province/city, utilizing environmentally sustainable practices and materials. | Infrastructure rehabilitation: Procurement actions in progress at the end of reporting period for: Minor rehabilitation/refurbishing of six health centers as follows: Mbabanakira, Avuavu and Kuma Primary Health Centers in Weathercoast region of Guadalcanal province Good Samaritan clinic in Guadalcanal Province The psychiatric ward of Honiara National Referral Hospital The National Psychiatric Unit of Kiluufi Hospital, Malaita Province. Minor contribution to the construction of six community peace centers by MNURP. The project was asked to contribute with construction materials: water tanks and fittings, bricks and cement. Symbolic/social rehabilitation: Grant agreements were endorsed with three local NGOs and delivery of the contracted services for symbolic/social reconstruction was initiated as outlined below: Scouts Association: school-based events for promotion of National Consciousness, Identity and Unity Development Service Exchange: civic education for inmates and abused women/girls & one workshop for local NGOs on disability and human rights topics Family Support Center: legal literacy training for inmates and abused women/girls. In connection to the National Peacebuilding Policy (NPP) endorsed by the Cabinet of the Prime Minister mid-July 2015, technical and financial support was made available for initiating NPP implementation as follows: First Meeting of the National Peace Advisory Board on 22 July Three provincial workshops on NPP awareness and mainstreaming for: Honiara City Council on 30 and 31 July Guadalcanal Provincial Government on 5 and 6 August Malaita provincial Government on 26 and 27 August. Provincial action plans for joint implementation of the NPP were under construction at the end of reporting period. International consultancy was deployed in Malaita Province between 10 and 14 August for supporting the Diocese of Malaita and Malaita Peace Desk to progress with trauma-related work of the Diocese. Local case studies on conflict resolution were also compiled during the consultancy. |

| Intended Output 3: Local re-integration counseling mechanism with focus on negotiation, conflict resolution, and mediation, developed and become fully functional |
| --- |
| Activities | Progress by 30 September 2015 |
| 3.1 Establish local re-integration counseling mechanism amongst ex-combatants and their communities | Technical support was made available to: CCC and MNURP for designing the joint action plan for increased reintegration of abused women and girls. The action plan was endorsed on 14 July (specifics on its’ implementation were already referred to the section ‘Intended Output 1.2.’) MNURP and three local NGOs for defining project services to be delivered via grants (specifics already provided under the section ‘Intended Output 2.1’ of this report) MNURP and Solomon Islands National University (SINU) for initiation of Peacebuilding and Traditional Governance Research Unit. An LOA was prepared in this respect. At the end of reporting period, the UNDP-endorsed LOA was pending SINU signature. |
| 3.2 Provide intensive training courses on negotiation, conflict resolution and mediation to target communities | Activity completed as at the end of reporting period. Conflict analysis training was delivered in Auki, between 3 and 7 August, to 40 male and female professionals representing key peacebuilding stakeholders in Malaita Province. The training was delivered by an international consultant. |
| Intended Output4: At least 70% of target beneficiaries successfully obtained knowledge on human security and peaceful co-existence and translate into actions through locally-organized events |
| Activities | Progress by 30 September 2015 |
| 4.1 Conduct public awareness and social communication campaign on human security and peaceful co-existence (28 workshops participated by selected local stakeholders; 12 locally organized events) | Four workshops participated by selected local stakeholders were delivered during reporting period as outlined below: Three peacebuilding workshops delivered on 16, 21 and 24 September 2015. The workshops were organized in cooperation with the Youth-@-Work project of the Secretariat of Pacific Community, in Honiara. 202 unemployed youth and young adults, out of which, 109 female, benefited from peacebuilding workshops. One induction workshop was organized on the occasion of the International Day of Peace, 21 September. The workshop participants were the eight male and female Interns. This series of workshops brings the total of workshops delivered under the project to 25. The remaining three workshops are to be delivered under the Scouts grant agreement. Two locally-organized events were delivered during the reporting period as follows: Street sensitization took place in Honiara on 21 September. The sensitization was conduted by volunteers Flag raising ceremony and unveiling of two traditional billboards took place in Honiara, at Kings George VI on 21 September. The event was supported under the Scouts grant agreement. The total of locally-organized events supported under the project was brought to five. The remaining seven locally-organized events are to be delivered under the Scouts grant agreement in both Malaita and Guadalcanal Provinces. |

10. Updated Quality Log

| Output1: Up to 90% of selected stakeholders (local governmental officials, community leaders, representatives of CBOs and Women's Groups) participate in the process of establishing local registration systems to improve local participation. |
| --- |
| Activity 1.1 | Organize a total of 12 provincial workshops | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | To achieve a local consensus on implementation and exit strategies |
| Description | Workshops with MNURP and its stakeholders (as defined in MNURP Corporate Policy) |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Consensus with MNURP on workshop content/agenda | Review relevant documentation (TORs, MOUs, Handover, etc.) | 31 September 2015 | Achieved | On time | On track |
| Activity 1.2 | Establish local registration systems in all 3 target provinces/city | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | Local registration of people in need for reintegration counselling |
| Description | 36 workshops for local registration in assisted peace centers |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Agreements with providers of reintegration and registration services (modified - Feedback of direct beneficiaries of workshops) | Review of evaluation reports of direct beneficiaries | 31 September 2015 | Partially achieved | Delayed | Under-spent |
| Activity 1.3 | Implement advocacy measures | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | To promote local participation and maintenance of rehabilitated infrastructure |
| Description | To be further operationalized – re-aligned to updated national priorities |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Consensus with MNURP on advocacy measures | Review relevant documentation (TORs, MOUs, Handover, etc.) | 31 September 2015 | Achieved | On time | On track |
| Output 2: All three target provinces of Guadalcanal, Malaita and Honiara possess 'green' community peace centers as foundation for "tension" reduction. |
| Activity 2.1 | Rehabilitate/Reconstruct 3 community peace centers in each province/city | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | Project provinces possess 'green' community peace centres as foundation for "tension" reduction |
| Description | Environmentally sustainable practices and materials (‘Environment’ concept utilized in its most extensive meaning: social and physical) |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Feedback of direct beneficiaries of trainings/workshops | Review of evaluation reports | Not applicable | Achieved | Delayed | Under-spent |
| Consensus of key stakeholders (MNURP and direct beneficiary institutions) on infrastructure support | Review relevant documentation (TORs, MOUs, Handover, etc.) | 31 September 2015 | Achieved | Delayed | Under-spent |
| Technical requirements in grant agreements | Review grantees reports | 31 September 2015 | Achieved | Delayed | Under-spent |
| Output 3: Local re-integration counseling mechanism with focus on negotiation, conflict resolution, and mediation, developed and become fully functional. |
| Activity 3.1 | Establish local re-integration counseling mechanism | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | To ensure peaceful co-existence of ex-combatants and their communities |
| Description | Technical support - UNDP contribution |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Consensus of key stakeholders (MNURP and reintegration experts) on priority targets | Review relevant documentation (TORs, MOUs, Handover, etc.) | 31 September 2015 | Partially achieved | Delayed | On track |
| Activity 3.2 | Provide intensive training courses | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | To enhance capacities of negotiation, conflict resolution and mediation to the target communities |
| Description | Training topics to cover negotiation, conflict resolution, mediation |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Jointly agreed upon conflict expert by MNURP and UNDP | Review relevant documentation (TORs, MOUs, Handover, etc.) | 31 September 2015 | Achieved | On time | On track |
| Output 4: At least 70% of target beneficiaries successfully obtained knowledge on human security and peaceful co-existence and translate into actions through locally-organized events |
| Activity 4.1 | Conduct public awareness and social communication campaign | Start Date: 1 Jan 2015 End Date: 15 Oct 2015 |
| Purpose | To promote human security and peaceful co-existence |
| Description | 28 workshops participated by selected local stakeholders and 12 locally organized events |
| Quality Criteria | Quality Method | Date of Assessment | User Perspective | Timeliness | Resource Usage |
| Feedback of direct beneficiaries of workshops and local events | Review of evaluation reports of direct beneficiaries | 31 September 2015 | Achieved | On time | On track |

11. Updated Issue Log:

| # | Description | Date Identified | Type | Impact & Probability Note:1=low 5=high | Countermeasures / Mngt response | Issue Monitor | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Nothing significant to report (NSTR) | NSTR | NSTR | NSTR | NSTR | NSTR | NSTR | NSTR | NSTR |

12. Updated Risk Log:

| # | Description | Date Identified | Type | Impact & Probability Note:1=low, 5=high | Counter measures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MNURP request for cost-extension | 4 February 2015 | Strategic | 5 | Expedited joint planning of current project and increased working time allocated to tasks related to cost extension Initiated preparations for activation of the UNTFHS procedure for project reprogramming with additional budget and extended timelines | Project Management Unit (PMU) | Project coordinator | 30 Sept. 2015 | Extension request rejected by funding body |
|  | Re-alignment of project services to DCCG Policy | 4 February 2015 | Operational | 5 | Re-aligned within the conceptual and operational limits of current project document / funding contract | PMU | Project coordinator | 13 April 2015 | Resolved |
|  | Delayed procurement | 30 May 2015 | Operational | 5 | Troubleshooting in close liaison with operations/procurement unit and liaison with funding body to clarify the ‘grace’ period for disbursement of funds committed before the project end date | PMU | Project team | 30 Sept. 2015 | On-going |

13. Updated Monitoring Log:

| # | Description | Due Date | Monitoring Action | Impact & Probability Note: 1=low 5=high | Milestone Description | Owner | Submitted, updated by | Last Update | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2014 Annual Joint Progress report | Jan 2015 | Donor Report | 5 | Annual report 2014 | PMU | Project coordinator | Feb 2015 | completed |
| 2 | Evaluation | Oct 2015 | Final Evaluation | 5 | Independent evaluation of joint project | CPR | Project coordinator | Sept. 2015 | delayed |
| 3 | Work Plan | NA | Work Plan | 5 | Re-alignment to DCCG Policy | PMU | Project team | Sept. 2015 | delayed |
| 4 | Six-month action plan | end of Q2, and Q3 | Quarterly progress report | 3 | Action plan as agreed with MNURP for the UNDP sector of the project | PMU | Project team | Sept. 2015 | on going |
| 5 | UNDP sector progress | April and July | Minutes | 4 | Reports to the Joint project Steering Committee (JPSC) and to the Independent Evaluators | PMU | Project coordinator | April 2015 | completed |
| 6 | UNDP sector progress | fortnightly | Minutes | 3 | Reports to the Joint Project Coordination Meetings (JPCM) | PMU | Project team | Sept. 2015 | on going |
| 7 | UNDP sector progress | last week of each month | Report | 4 | Project contribution to UNDP monthly report to in-country donors | PMU | Project team | Sept. 2015 | on going |
| 8 | Project delivery rate review | last week of each month | Briefings / Minutes | 5 | Reports to the UNDP DRR during the monthly coordination meetings with CTAs/Project managers | PMU | Project coordinator | August 2015 | on going |
| 9 | Peacebuilding ads in newspapers | fortnightly | Monitoring report | 4 | Duration May – Oct 2015 | PMU | Project assistant | Sept. 2015 | on going |
| 10 | Peacebuilding ads billboard Honiara | weekly | Monitoring report | 4 | Duration July – Oct 2015 | PMU | Project assistant | Sept. 2015 | on going |
| 11 | Delivery of project products through grant agreements | July | Final reports VBM, DSE, SIDT | 4 | Duration Dec. 2014 – April 2015 | PMU | Project team | Sept. 2015 | on going |
|  |  | December | Final reports FSC, Scouts, DSE | 4 | Duration August – December 2015 | PMU | Project team | Sept. 2015 | on going |

# Footnotes

Request for change, Problem or Other

Environmental, Financial, Operational, Organizational, Political, Regulatory, Strategic or Other