## HSTF AWP-2014
UNDP “Tensions” Reduction, Reconciliation and Rehabilitation (HSI-T3R) in the Solomon Islands - Year 1 (January-December 2014)
CP Outcome: To enhance human security for the selected communities and ex-combatants in the Solomon Islands through reducing “tensions” and promoting peaceful and sustainable measures for their survival and dignity. NDS Objective 1: To Alleviate Poverty and Provide Greater Benefits and opportunities to improve the lives of Solomon Islanders in a peaceful and stable society.
UN organization-specific Annual targets | UN Organisation | Activities | Time frame |  |  |  | Implementing partner | Planned Budget
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of funds | Budget description | Amount
Component I: “Freedom from Fear” Approach - Good Governance, "Tensions" Reduction and Human Security
Objective I-1: To promote reintegration and make it fully functional to meet the needs of the community members and former combatants, for human security and peaceful co-existence
Output I-1.1 Up to 90% of selected stakeholders (local governmental officials, community leaders, representatives of CBOs and Women's Groups) participate in the process of establishing local registration systems to improve local participation | UNDP | I-1.1.1 Organize a total of 12 provincial workshops to achieve a local consensus on implementation and exit strategies |  |  |  |  | UNDP/MNUPR | UNHSTF
|  | Organize provincial and ward level workshop which includes travel of participants to attend the workshops, venue, materials (to focus on leadership, communication, reconciliation, peacebuilding, including Gender and Conflict) | [5 empty] | UNHSTF | Travel: 71600 | 52332
[8 empty] | UNHSTF | Training: 75700 | 62500
[8 empty] | UNHSTF | Supplies: 72500 | 5000
[8 empty] | UNHSTF | Printing: 74200 | 5000
|  | I-1.1.2 Establish local registration systems in all 3 target provinces/city (Not applicable) | [5 empty] | UNHSTF
|  | REVISED: Activity removed at request of government | [5 empty] | UNHSTF
|  | I-1.1.3 Implement advocacy measures for promoting local participation and maintenance of rehabilitated infrastructure (This activity has been merged with Act 2.4) | [5 empty] | UNHSTF
|  | REVISED: This activity has been merged with Act I-2.2.1 | [5 empty] | UNHSTF
|  | Sub total 1-1.1 | [5 empty] | UNHSTF |  | 124832
I-1.2. All three target provinces of Guandalcanal, Malarita and Honiara possess 'green' community peace centres as foundation for "tension" reduction |  | I-1.2.1 Rehabilitate/reconstruct 3 community peace centres in each province/city, utilizing environmentally sustainable practices and materials. (Not Applicable) | [5 empty] | UNHSTF
|  | REVISED: Activity removed at request of government | [5 empty] | UNHSTF
Total Cost for Objective I-1 | [6 empty] | UNDP | UNHSTF
Objective I-2: To promote reintegration and make it fully functional to meet the needs of the community members and former combatants for human security and peaceful co-existence | [7 empty] | UNHSTF
I-2.1. Local re-integration counseling mechanism with focus on negotiation, conflict resolution, and mediation, developed and become fully functional | UNDP/ILO | I-2.1.1 Establish local re-integration counseling mechanism amongst former combatants and their communities |  |  |  |  | UNDP/ ILO | UNHSTF
|  | REVISED 1 - 2.1.1 a) Trama Counseling Methodology mapping for Best Practices promotion (travel, workshop, material development) | [5 empty] | UNHSTF | Travel: 71600 | 26916
|  | b) Trauma Counseling and Dialogue process awareness training | [5 empty] | UNHSTF | Training: 75700 | 55000
c) Enable functioning of local trauma network
|  | I-2.1.2. Provide intensive training courses on negotiation, conflict resolution and mediation to the target communities | [5 empty] | UNHSTF
|  | a) Capacity building and Technical Assistance to the National Peacebuilding Policy | [5 empty] | UNHSTF | Travel: 71600 | 54832
|  | b) Provide Conflict Resolution training for all members of MNURP; and network of civil society peacebuilders | [5 empty] | UNHSTF | Training: 75700 | 60000
[8 empty] | UNHSTF | Supplies: 72500 | 10000
Sub-total of I-2.1 | [7 empty] | UNHSTF |  | 206748
1.2.2. At least 70% of target beneficiaries successfully obtained knowledge on human security and peaceful co-existence and translate into actions through locally-organized events |  | I-2.2.1. Conduct public awareness and social communication campaign on human security and peaceful co-existence. | [5 empty] | UNHSTF
|  | a) Creation/maintenance of Network of Peacebuilders - for joint learning and sharing | [5 empty] | UNHSTF | Company Contracting: 72100 | 39999
|  | b) Diffusion of communication materials/organizing of local events/including schools on non-violent processing of conflict, social cohesion, women and young people in decision-making. | [5 empty] | UNHSTF
|  | c) Network facilitated dialogues | [5 empty] | UNHSTF | Travel: 71600 | 19919
[9 empty] | Printing: 74200 | 20000
[9 empty] | Supplies: 72500 | 20000
[9 empty] | Training: 75700 | 55000
Sub-total of I-2.2 | [7 empty] | UNHSTF |  | 154918
Total Cost for Objective I-2 and I-1 | [7 empty] | UNHSTF
|  | Total Project Management Unit Cost | [5 empty] | UNDP |  | 225000
2014 Total Project Cost | [9 empty] | 711498
|  | 2015 Programmed Funds | [5 empty] | UNDP |  | 21945.38
|  | Overal Total Project Cost | [7 empty] | 733443.38
*The total of the 2nd Tranche is USD$449,498.44. The budget for the Project Management unit is USD$225,000 for 2014. As such, the total 2014 Project Budget is USD$711,498. This budget revison is done for the allocation of Trac Funding to Project Staff Salary for the month of November and December 2014, reflected in the Atlas Generated AWP. A total of USD$21,945.38 is carried forward for 2015 therefore increasing the amount to USD733,443.38

## Project Management Unit (HSTF)
AWP 2014: Detailed Annual Work Plan for Human Security Initiative for “Tensions” Reduction, Reconciliation and Rehabilitation (HSI-T3R) in the Solomon Islands
CP Outcome: To enhance human security for the selected communities and ex-combatants in the Solomon Islands through reducing “tensions” and promoting peaceful and sustainable measures for their survival and dignity. NDS Objective 1: To Alleviate Poverty and Provide Greater Benefits and opportunities to improve the lives of Solomon Islanders in a peaceful and stable society.
UN organization-specific Annual targets | UN Organisation | Activities | Time frame |  |  |  | Implementing partner | Planned Budget
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of funds | Budget description | Amount 9USD)
Output: Establish a Project Management Unit to ensure effective coordination to the project and full capacity support to key Ministries | UNDP | 1:The Project Management Unit is fully established and operational:
|  | 1.1 International Project Coordinator | X | X | X | X | MNURP | UNDP | Coordinator's Salary: 71200 | 106000
|  | Salary & Post Adj Cst IP Staff |  |  |  | X | MNURP | UNDP | Coordinator's Salary: 61300 | 44000
|  | 1.2 UNV | X | X | X | X | MNURP | HSTF | UNV: 71500 | 12000
|  | 1.3 Project Assistants | X | X | X | X | MNURP | UNDP | National Officers: 71400 | 14000
|  | 1.4: Administrative costs | X | X | X | X | MNURP | UNDP | ICT: 72800 | 8000
[9 empty] | Stationery 72500 | 4000
[9 empty] | Office Bills: 73100 | 20000
[9 empty] | Printing Costs: 74200 | 2000
|  | 1.5 Monitor and Evaluate project sites | X | X | X | X | MNURP | UNDP | Meetings: 75700 | 5000
[9 empty] | Travel: 71600 | 10000
225000
TRAC: USD$225,0000
*USD$500,000 is UNDP contributioin to the HSTF project specifically dedicated to the Project Management Unit to ensure effective coordination amongst all partners.
*USD$205,000 is under Trac and USD$20,000 is under UNHSTF to cover UNV costs and ICT
*USD $21,945.38 is carried forward to 2015