## AWP 2019
Climate and Disaster Resillence Annual Work Plan (AWP) for 2019
Atlas Award ID: | 00117398
Atlas Project ID: | 00114192
Project/Programme Title: | Climate and Disaster Resillence
UNDAF Outcome: | PRSP Pillar 2 - Managing Natural Resources Outcome B: By 2018, communities within targeted districts demonstrate increased resilience to natural and man-made disasters.
Related CPD Outcome: | Communities in targeted districts are engaged in design and implementation of gender responsive sustainable NRM and livelihood diversification 2.4 National and local authorities enabled to implement DRM & EWS
Applicable Signature Solution 3: | Enhance national prevention and recovery capacities for resilient societies
Expected Outputs | Planned Activities | Timeframe |  |  |  |  | Planned Budget UNDP TRAC
Baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 | Partner | Funding Souce | Budget Description | Amount (USD)
Ouput 2. Enhanced national and local capacities for disaster risk management | Activity Result 2.3: Strengthen DRM function at both national and district level in S/Leone
Baseline: - Draft DRM Policy - zero popularization of DRM policy - 30 schools trained on DRM - No DDMC's in Karena and Falaba -zero number of trees planted in flood prone communities | Activity 2.3.1: Enhance DRM governance in the Country - support the review of the DRM policy - Support the finalization of DRM policy - Establish DDMC in the newly created districts of Karena and Falaba - Facilitate the development of preparedness and flood plans for Karena and Falaba | x | x | x | x | DMD | Trac | Trainings,Workshops | 15000
Indicators: - # of Consultations held on the DRM policy - # of Popularization meetings held. - # DRM policy reviewed and finalized - # of schoold trained on DRM - # of DDMCs established and trained in DRR - # of trees planted in flood prone communities | Activity 2.3.2: Train 20 schools and one college on DRRM module in 3 districts | X | X | X | X | DMD | TRAC | Trainings,Workshops | 15000
Target: -number of consultations held on the DRM policy - 20 schools and one colleage trained on DRM - At least one DRM policy endorsed - At east four popularization meetings held - At least two DDMC's established and trained on DRR in Karena and Falaba - 1,000 trees planted in flood prone communities. | Activity 2.3.3: Enhanced capacity and knowledge on DRR/CCA of relevant sectors(vulnerable communities -Conduct livelihood activities on back yard garden/planting of 1,000 trees on flood prone communities in three communities. | X | X | X |  | DMD | TRAC | Trainings,Workshops | 50000
| Activity 2.3.4: Public awareness activities on DRR - International DRR week |  |  | X | X | DMD | TRAC | Logistics,Printing | 5000
| Activity 2.3.5: Conduct national simulation exercise based on scenarios(volunteers,DDMCs,MDAs) | X |  |  | X | DMD | TRAC | 75700 Training workshops | 10000
| Activity 2.3.6 Training of DDMC in: Gender mainstreaming of disaster risk management 1.Engage women’s organization for involvement into national DRM programming and implementation -2. Ensure the training of women in DRM activities -3. Enhance gender main streaming in DRM governance and decision-making process | X | X | X | X | DMD | TRAC | 75700 Training workshops | 5080
Project management cost | Activity 2.3.7 NUV seconded to DMD/Salary | X | x | x | X | DMD | TRAC | 72200 Logistics, equipment, transportation | 6000
| Common premises | X | X | X | X |  |  |  | 15000
| Office supplies (furnitures&equipements) | X | X | X | X |  |  |  | 5000
| Project Management Unit specific training needs | X | X | X | X |  |  |  | 2000
| Communication cost 1% | X | X | X | X |  |  |  | 1500
| Travel cost associated with project management & monitoring | X | X | X | X |  |  |  | 10000
| M&E DPC(2%) | X | X | X | X |  |  |  | 3000
| DPC(4.6%) | X | X | X | X |  |  |  | 6900
| Security | x | x | x | x |  |  |  | 520
Total Output 2 | [8 empty] | 150000
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partners, the plan authorizes the responsible parties and project management to manage available resources and achieve set results.
National Counterpart | [7 empty] | UNDP Sierra Leone
John V Rogers | [7 empty] | Samuel Doe
Director/ Disaster Management Department | [7 empty] | Resident Representative
Office of National Security | [7 empty] | UNDP Sierra Leone
Date: | [7 empty] | Date: