## AWP_2021__($340_5K)_(2)
Annual Work Plan for 2021

Project/Programme Title:	Support to Effective Aid Coordination and the implementation of SDGs in Sierra Leone
	BRIEF DESCRIPTION
	The overarching aim of this project is to support the Ministry of Planning and Economic Development (MoPED) and Statistics Sierra Leone (SSL) to further strengthen aid coordination and the implementation of the Sustainable Development Goals (SDGs). The project will also provide upstream policy support to the Government of Sierra Leone (GoSL) on economic, socio-political and institutional factors affecting development in the country. Sierra Leone is among the first countries that endorsed the SDGs and started integrating them in its national programs and domestic policy agenda. The SDGs provide a timely opportunity to overcome critical emerging national challenges in Sierra Leone through its three (3) dimension – economic, social and environmental. They represent key benchmarks to addressing poverty, inequality, and climate chamge, and establishing peace and justice. / Although the SDGs are designed within the global context, they will largely be addressed at the local and national levels where, expectedly, each country will apply its own unique history, culture and institutional and human capabilities. The SDG Agenda calls for many partnerships at all levels, with all stakeholders working in tandem to achieve the goals. It is, therefore, very urgent that national institutions dealing with its implementation must effectively coordinate with a broad array of actors, such as traditional and non-traditional partners, the private sector, local governments, businesses, the media and the civil society landscape. Accountability and transparency will be increasingly important at all levels of society, with revised regulatory mechanisms and policy requirements needed to ensure human, civil and environmental rights. / In addition, the project aims to further support improvement of the institutional, information and technical capacity of the Government to strengthen aid coordination and improve aid effectiveness to most fully implement Busan commitments on effective development cooperation.

UNDAF Outcomes	1B,2A,7A,7B,7C,8A, 6A & 6B(UNDAF+)
UNDP Strategic Plan Outcomes	1,2,3,5
	Outcome 1: Low income and food insecure households have improved access to sustainable income generating opportunities (on-farm and off-farm).
Expected CPD Output	Outcome 2: By 2018, targeted Government institutions, the private sector, and the local communities manage natural resources in a more equitable and sustainable way.
	Outcome 3: Capacity of democratic institutions strengthened to enable good governance.
	Outcome 4: Justice and security sector delivery systems improved in compliance with international human rights standards.
Atlas Award ID:	96024
Atlas Project ID	100043
Expected Outputs	Planned Activities	Timeframe				Responsible Party	Planned Budget
And baseline, associated indicators and annual targets	List activity results and associated actions	Q1	Q2	Q3	Q4		Funding Source	Budget Description	Amount (USD)
Output 1	Activity Result1: Support MTNDP and SDGs implementation supported
Output 1 / MTNDP and SDGs implementation supported / Indicators: / a)# Sensitization workshop on the Mid-term review Baseline MTNDP Target-1 b) # Mid-Term Review. / Baseline - MTNDP produced, launched & operationalised, Target - (1) / c) #District Coodination offices established Baseline-0, Target- 14 / d) Gender mainstreamed in the report analysis: Yes/No Baseline-No report yet, Target- Yes	1.1 Undertake one day sensitization workshop on the Mid-Term review	X	X			MoPED	TRAC	72500 Publications	TBD
	1.2 Review implementation of key policy actions of the MTNDP and its Results Framework	X				MoPED	TRAC	75700 Workshop/training	TBD
	1.3 Write, produce & disseminate MTNDP review report					72500 Publications	6,000.00
	1.4 Produce the Annuals Progress report on Implementation of the MTNDP					72500 Publications	TBD
	Support to strenghten District Development Coordination Committees					TBD
	Support to three Technical staff(PA, TA and Project Admin/Accountant				X	MoPED	TRAC	75700 Workshop/training	48,000.00
	Launch of the brailed SDG					75700 Workshop/training	8,000.00
	Support CO support to VNR process					75700 Workshop/training	10,000.00
	MONITORING				X	MoPED	TRAC		TBD
	Sub-Total: Support to NHDR 2018 preparation					72,000.00
Output 2: Aid Coordination / Indicators: / a) Number of DEPAC meetings. Baseline-1, Target-4. / b) Number of Encyclopidia produced. Baseline-100, Target-200. / c) Number DAR produce. Baseline-100, Target: 1 d) # of DAD Trainings conducted Baseline 2 Target 2	SUPPORT TO BASIC DACO ACTIVITIES
	Organise and coordinate quarterly DEPAC Meetings	X	X	X	X	MoPED	TRAC	75700 Workshop/training	16,000.00
	Support for the development of Encyclopaedia	X	X	X	X	MoPED	TRAC	72500 Publications	10,000.00
	To produce DAR 2020	X	X	X	X	MoPED	TRAC	72500 Publications	10,000.00
	Training on DAD and procurement of Equipment					73300 Software application admin.	10,000.00
	Support for the Development Assistance Database (Maintenance, Hosting )	X	X	X	X	MoPED	TRAC	73300 Software application admin.	19,000.00
	Sub-total: SUPPORT TO BASIC DACO ACTIVITIES					65,000.00
	Upstream Support to Statistics SL
Output 3: Harmonised Data Collection System for SDG Monitoring	Monitor Progress in the implementation and streamlining of the NDP and the SDG’s.	X	X	X		Stat SL	TRAC	75700 Workshop/training	50,000.00

	BASIC SAU SUPPORT TO CORE COUNTRY OFFICE DELIVERABLES					50,000.00
output 4: BASIC SAU SUPPORT TO CORE COUNTRY OFFICE DELIVERABLES a) Indicator: # of SDG Signage produced Baseline # of SDG signage produced in 2018 Target Replace warnout signage & construct new ones on the drive-way to CO b) Indicator: Order and launch GHDR 2021 Baseline: GHDR ordered and launched in 2019 Target: # GHDR report ordered and launched c)Indicator Study on the cost of CGBV on the economy Baseline: 0 Target: 1	SDG popularization (Including the driveway to UNDP CO)					74200Awareness Materials	62,500.00
	Ordering and launching of the Global Human Development Report					75700 Workshop/training	8,000.00
	Study on Cost of SCBV on the Economy					75200 Publications	10,000.00
	Sub-Total: Upstream support & Support to National M & E					80,500.00
Subtotal: Project implementation					267,500.00
Facilities & Administration	Activity 0: Project Management Cost
	Capacity Building/workshops/seminars	X	X	X	X	UNDP	TRAC	71600 training	13,000.00
	End of Project evaluation (NHDR)					75200 Publications	10,000.00
	Stationeries, office equipments and repairs					Stationeries, office equipments and repairs	5,000.00
	Common premises					Pool Fund	29,425.40
	Communication, Media Visibility (1%)	x	x	x	x	UNDP	TRAC	Pool Fund	2,675.00
	DPC 4.6%					TRAC	64398 - Direct Project Cost - Staff	12,305.00
	SUB-TOTAL					72,405.40
					Total	339,905.40

This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partner, the plan authorizes the responsible parties and project management to manage available resources and achieve set results.

	GoSL					UNDP Sierra Leone

	…………………………………………………………………………………
					…………………………………………………………
	Peter Sam-Kpakra / Development Secretary / Ministry of Finance & Economic Development					Pa Lamin Beyai Resident Representative, UNDP
	Date:………………………………………					Date:……………………………………