# Annual Work Plan 2009 [Revised]– UNDP Sierra Leone

Practice Area: Fostering Democratic Governance/State Building Support

Award ID: 00050560

Project ID: 00062526/62988

Project Title:  “Delivering Results and Accelerating Public Sector Reform with Diaspora Resources and Experts from the South”

Country: Sierra Leone

UNDAF Outcome: By 2010, Governance and Human Rights practices have been advanced at all levels and enforcement arrangements are in place.

Expected CPAP Outcome: The quality of national development policy and effectiveness of its implementation enhanced through the transformative leadership support and capacity development.

Expected Outputs: i) Functional Unit to lead and manage the operations of the Trust Fund established; and ii) At least 35 experts identified and provided to fill critical positions; iii) A remittance policy and regulatory framework in place and used

.

Executing Agency:	UNDP

Implementing Partner:				Diaspora Unit, Office of the President

| Agreed by Office of the President/MPPA: | Name:……………………………………………. | Title:………………………………… | Signature:…………………………… |
| --- | --- | --- | --- |
| Agreed by UNDP: | Name:……………………………………………… | Title:………………………………… | Signature:…………………………… |

# ANNUAL WORKPLAN BUDGET SHEET

##### Year 2009

| EXPECTED OUTPUTS (Indicators and Targets) | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Source of Funds | Budget Description | Amount (USD) |
|  |  |  |  |  |  |  |  | Account Code | Description |  |
| 1. Functional Unit to lead and manage the operations of the Trust Fund established Indicators: 1.1 4 key staff monthly salaries paid 1.2 Office supplies procured quarterly 1.3 2 job fairs conducted (USA, SL) 1.4 2 consultative workshops in SL | 1.1 Facilitate staff monthly salaries (Project Manager, Logistics Officer, IT/Database Specialist and Administrative Assistant) 1.2 Procure office supplies 1.3 Internet services | X X X | X X X | X X X | X X X | Diaspora Unit | UNDP BCPR OSI Hewllett Foundation | 71305 72210 | Local Consultants Equipment and Supplies Contractual Services | 23,025 5,000 4,000 |
|  | 1.4 Conduct a job fair in the USA 1.5 Conduct a job fair in Sierra Leone 1.6 Conduct consultative workshops in Sierra Leone 1.7 Advisory provision by experts and M&E | X | X | X | X | Diaspora Unit | UNDP BCPR OSI Hewllett Foundation | 71610 74500 | Travel & Allowance Workshops | 25,000 27,000 |
| 2. At least 35 experts identified and provided to fill critical capacity gaps | 2.1 Conduct a rapid capacity assessment to list required experts 2.2 Validate the expert positions and experts identified 2.3 Facilitate preparation of ToR for approved experts 2.4 Facilitate registration of the ToR in the database | X X X X | X X | X X | X X | Diaspora Unit PSRU/HRMO/MDA’s Project Advisory Committee | UNDP BCPR OSI Hewllett Foundation | 71305 74500 | Local Consultants Workshops | - |
|  | 2.5 Facilitate finalization of operational guidelines/recruitment framework 2.6 Facilitate preparation of standard Sierra Leone Informational package for the experts 2.7 Facilitate placement and monthly payment of diaspora experts | X X X | X | X | X | Diaspora Unit | UNDP BCPR OSI Hewllett Foundation | 71205 71305 71610 | International /Local Consultants Travel & Allowance | 1,470,000 135,000 |
| 3. A remittance policy and regulatory framework in place and used Indicators: 1.1 3 study tours conducted on remittance best practices 1.2 4 regional workshops in SL 1.3 1 national workshop in SL 1.4 A remittance policy, plan of action, benchmarks and coordination mechanism in place | 3.1 Formulation of the coordination mechanism for the remittance 3.2 Develop the national comprehensive Diaspora Remittance strategic framework, policy formulation, plan of action, and benchmarks 3.3 Identify, verify and document all available GOSL controlled assets ( GCAs) slated for privatization 3.4 Facilitate internal consultative workshops (national level and regional level workshops on findings) 3.5 Conduct awareness sessions on the remittance products and services agreed upon by key stakeholders 3.6 Facilitate a study tour to countries implementing a remittance programme (Rwanda, Cape Verdi and Senegal) |  |  | X | X | Diaspora Unit SPU/MoFED | TRAC | 71205 71610 74500 | International Consultants Travel & Allowance Workshops | 171,600 78,400 30,000 -------------- 280,000 |
|  | Total (USD) | 1,969,025 |

# Text boxes

Narrative

While Sierra Leone has made important progress in recovering from violent conflict since 2000, significant areas of the state and the economy remain under-developed. Lack of capacity in critical sectors threatens to undermine not just long-term development, but also the short-term sustainability of peace. With most of the country’s professional capacity residing in the diaspora, an innovative approach is needed in order to bring this capacity back to the country, and apply it.

The government is also aware that leveraging on migrant remittances and creating the enabling environment is a prerequisite for increased investments and overall promotion of socio-economic development in Sierra Leone. It has recognised that in delivering these results and attracting investments by and for its huge Sierra Leonean diasporan community, a remittance strategy and policy framework has to been put in place. This means an expanded role for the Diaspora Unit.

The project therefore aims to deliver the following outputs:

  - Functional Unit to lead and manage the operations of the Trust Fund established;

  - Over 35 experts identified and provided to fill critical positions; and

iii.     Remittance policy and regulatory framework in place and used

The Diaspora Unit, with the support of the Public Sector Reform Unit (PSRU), will manage the project directly in coordination with the relevant Ministries, Departments and Agencies (MDAs). The Strategy and Policy Unit of the Office of the President will provide strategic and policy guidance to ensure its effectiveness and coherence with the Government’s Agenda for Change.

Programme Period: 2008-2009

Programme Component: Fostering Democratic Governance

Project Title: Delivering Results and Accelerating Public Sector Reform with Diaspora Resources and Experts in the South

Project ID: 00062526/62988

Project Duration: 1 year (with possibility of extension)

Management Arrangement: Implementation within the DEX framework

Estimated Annualized Budget:		USD 1,969,025

Allocated resources:

- Government		 ____________

- Regular:

- Other: Capacity Development for Reform Trust Fund (USD 1,689,025)

- In kind contributions  Government of Sierra Leone

Unfunded budget:	USD 280,000