## AWP UNDP
Annual Work Plan (AWP) for 2016
Atlas Award ID: | 93486
Atlas Project ID: | 97693
Project/Programme Title: | Climate Change Induced Coastal Risk Management in Sierra Leone
UNDAF Outcome: | PRSP Pillar 2 - Managing Natural Resources Outcome A: By 2018, targeted Government institutions, the private sector, and local communities manage natural resources in a more equitable and sustainable way. Outcome B: By 2018, communities within targeted districts demonstrate increased resilience to natural and man-made disasters.
Related CPD Outcome: | 5: Countries are able to reduce the likelihood of conflict and lower the risk of natural disasters, including from climate change
Expected Outputs | Planned Activities | Timeframe |  |  |  | Responsible Party | Planned Budget GEF LDCF
And baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Souce | Budget Description | Amount (USD) | Note | Revised Budget | 2017 budget
Output 1: Project preparation grant to finalize the UNDP-GEF project document for project “Adapting to Climate Change Induced Coastal Risks management in Sierra Leone Baseline - GEF CEO approved Project Identification Form - UNDP approved Project Initiation Plan -No pre-feasibility assessment of proposed targeted communities - No economic analysis of proposed targeted communities -No institutional capacity plan developed Indicators - # of consultations held for the development of reports on coastal protection and adaptation, gender mainstreaming analysis, economic analysis of target communities, institutional capacity assessment report - # of consultations held for stakeholders’ input into the prodoc Target -Development of the project document for the endorsement of the GEF CEO | - Recruitment of lead consultant and team - Conduct inception workshop - Conduct pre-feasibility assessment of proposed targeted communities - Conduct socio-economic and gender analysis of proposed targeted communities - Develop an institutional capacity plan developed - Conduct validation workshop | X | X | X | x | UNDP | GEF | 71300 (Local Consultant) | 69000 |  | 68433 | 15000
[8 empty] | 75700 (Workshop) | 17000 |  | 2544 | 4000
[8 empty] | 71200 (international Consultant) | 42250 |  | 68054 | 33437
[8 empty] | 71400 (Contractural Services, Individual) | 9000 |  | 0 | 0
[8 empty] | 71600 (Travel) | 47500 |  | 92 | 500
[8 empty] | 72500 (Supplies) | 12250 |  | 5440 | 2500
[8 empty] | 74500 (Miscellaneous Expenses) | 3000 |  | 0 | 0
Total of Output 1 | [8 empty] | 200000 |  | 144563 | 55437
Total 2016 Project Budget | [8 empty] | 200000 |  | 144563
This Annual Work Plan (AWP) is based on Results Management Guidelines (RMG) of UNDP. Once signed by UNDP and the Implementing Partners, the plan authorizes the responsible parties and project management to manage available resources and achieve set results. | [12 empty] | `
UNDP Sierra Leone
Carine Yengayenge
Country Director (ai)
UNDP Sierra Leone
Date: | [13 empty] | 0

## Sheet1
Inception Workshop at Hill Vallley - 2544 | 2544
Adverts for consultancies - 5430 | 5432 | 5540
Total Consultancy fees - 136,487 | 136487
DSA to Yusif for trip with DR. Spencer - 92 | 92
Stationeries for inception Wkshop - 108 | 108
144663
55337