{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":36,"n_cols":9,"rows_kept":36,"cut":false,"hidden":false,"merged":[[10,0,13,0],[18,0,21,0],[23,0,24,0],[25,0,25,8],[22,0,22,8],[14,0,14,9],[15,0,16,0],[26,0,28,0],[29,0,29,8],[17,0,17,8],[32,0,32,8],[33,0,35,0],[30,0,31,0],[0,0,0,8],[9,0,9,9],[3,6,6,6],[3,8,6,9],[3,0,6,0],[3,1,6,2],[3,3,6,3],[3,4,6,4],[3,5,6,5],[1,0,1,8],[2,0,2,8],[7,0,8,0],[3,7,6,7]]}
["Annual M&E Plan, 2020"]
["Portfolio/Project Name: Local Economic Development"]
["UNDP Sierra Leone"]
["Expected Results ","Indicators (With annual Baselines\nand Targets)",null,"M&E Event with\nData Collection \nMethods","Time or Schedule\nand Frequency","Responsibilities","Means of Verification: Data\nSource and Type","Resources","Risks and Assumptions"]
[]
[]
[]
["CPD Output 4.1: Vulnerable groups (poor women, youth and PWDs) are enabled to gain access to basic and financial services for business development and job creation ","1. Indicator: # of people accessing basic services disaggregated by target groups: (a) Men, b) Women, c) Youth, d) PWDs\nBaseline: a) 900: b) 0, c) 0, d) 0, \nTarget:  3,000: a) 900, b) 600, c) 1350, d)150  ",null,"Field visit, Interviews etc.","Annually","UNDP","Partner (Ministry of Social Welfare, LCs) reports",5000]
[null,"2. Indicator: # of SMEs owned by women, youths and PWDs accessing financial services: a) Women, b) Youth, c) PWDs                                                                                      Baseline: a) 382, b) 702, c) 61  \nTarget: a) 1,125, c) 2,070, d) 180                                                              \n\n\n",null,"Survey, Field visit","Annually","UNDP","Partner report",5000]
["Portfolio/Project Output 1:  Access to finances increased to enhance financial inclusion and job creation for vulnerable groups"]
["Activity Result 1: Financial inclusion enhanced for vulnerable groups","Indicator:  # of Baseline study report that inform policy and action & improves access to finance  \nBaseline: 0\nTarget: 1\n\n ",null,"Record review; Interview; Field visit","Quarterly","Project & portfolio Managers, ","Baseline report, Draft lending Policy.",2000,"Baseline report contains data that support policy and actions that improve access to finances"]
[null,"Indicator: # of new Lending policies drafted that are gender responsive     \nBaseline: 0\nTarget: 1\n\n",null,"Record review; Interview","Quarterly","Project & portfolio Managers, ","Lending Policy document,",2000,"draft policy is submitted for review"]
[null,"Indicator: # of Persons (disaggregated by Gender, PWDs) accessing financial services for the first time in target communities who started their own SMEs   \nBaseline: 2000\nTarget: Additional 200",null,"Field visit, Interviews etc.","Quarterly","Project & portfolio Managers, ","Participant list",2000,"Participants comply with data collection request and requirements"]
[null,"Indicator:  # of jobs created for vulnerable groups in target communities  \nBaseline:  5,680 \nTarget: Additional 568\n\n",null,"Direct observation; Interviews","Quarterly","Project & portfolio Managers, ","Activity report, project locations",2000,"Partners have and are willing to share updated information on activity implemetation"]
["Portfolio/Project Output 2:  Youth Conneckt Hubs Established and Operationalised to facilitate innovative youth skills development"]
["Activity Result 2: Youth connect hubs established","Indicator: # of Youth Connect Hubs established by Dec. 2020                 \nBaseline: 0\nTarget: At least 4 Youth Conneckt hubs established by Dec. 2020.      ",null,"Record Review; Direct observation; field visit","Quarterly","Project & portfolio Managers, ","Partiticipants Register, Photos of  hub activities",2000,"Data submitted upon request"]
[null,"Indicator: # of Youth Connect Hubs that are operational\nBaseline: 0\nTarget: 4",null,"Interviews, field visit","Quarterly","Project & portfolio Managers, ","NAYCOM, NYS, MOYA reports",2000,"Targeted interviewees comply with interview appointment"]
["Portfolio/Project Output 3: Knowledge-based of key community stakeholders and councils staff strenghtened on designing, financing, building and operating revenue generating facilities through the PPP arrangement "]
["Activity Result 3: Community stakeholders have increased capacity to design, finance and operate revenue generating facilities through PPP arrangement\n","Indicator: # of community stakeholders (disaggregated by sex) and council staff with adequate capacity to design & operate revenue generating facilities produced through PPP arrangements;  \nBaseline: 420\nTarget: At least 105 additional facilities established by Dec. 2020  \n\n\n",null,"Record Review; ; field visit","Quarterly","Project & portfolio manager, M&E Officer","Participants register; LC report, PPP unit report",2000,"Participants register and activity report are submitted for review"]
[null,"Indicator: # of Revenue generating facilities established by LCs and targeted community stakeholders                                                                                                     Baseline: 8                                                                                                                             Target: At least 5 additional facilities established by Dec. 2020       ",null,"field visit; Direct observation; ","Quarterly","Project, Portfolio manager, M&E Officer","  Photos; Partner report",2000,"There is availability of camera to capture field photos"]
[null,"Indicator:  # of market facilities outsourced to private partners in Freetown through PPP arrangements;       \nBaseline: 0\nTarget:  At least 8 MF outsourced                                                                                                                                                                                                                                                               ",null,"Interviews; field visit","Quarterly","Project, Portfolio manager, M&E Officer","PPP unit implementation report, ",2000,"Partner report is available upon request for review"]
[null,"Indicator:  # of CADASTRE system set up and is functional  \nBaseline: 1\nTarget: At least 2 ",null,"field visit; Direct observation; ","Quarterly","Project, Portfolio manager, M&E Officer","Photos, Local Council report",2000,"Stakeholders are willing to provide information on PPP intervention in their localities"]
["Portfolio/Project Output 4: Strengthened regulations for the effective implementation of public private partnerships in the country.                                               "]
["Activity Result 4: Regulations that support PPP implementation reviewed and endorsed","Indicator: # of regulations on PPP reviewed and endorsed by parliament     \nBaseline: 1\nTarget: At least 1 more PPP regulation/policy strengthened",null,"Record review","Quarterly","Project, Portfolio manager, M&E Officer","Draft regulation on PPP",2000,"Draft regulation is available at the end of the period for review"]
[null,"Indicator:  # of PPP focal person cells established and functional           \nBaseline: 0\nTarget: 2",null,"Direct observation; Interviews, Field visit","Quarterly","Project, Portfolio manager, M&E Officer","Cell points, Photos",2000,"Cell points are easily accessible"]
["Portfolio/Project Output 5: Empowerment & Entrepreneurship Programme scaled up in Sierra Leone "]
["Activity Result 5: Youth have increased options and incentives to engage  in entreprenuer activities ","Indicator: # of youth capacitated in innovative entrepreneur skills by Dec. 2020 \nBaseline: 0 \nTarget: 2000 (Female 60%: Male 40%)",null,"field visit, Record review","Quarterly","Project & portfolio Managers, ","Participants list,  partner reports, ",2000,"Partner report and participants list are available upon request for review"]
[null,"Indicator: # of new jobs and other livelihood opportunities created through this program by Dec. 2020    \nBaseline: 420\nTarget: Additional 105",null,"Field visit, Interviews, Record review","Quarterly","Project & portfolio Managers, M&E Officer","Activity report, photos, partner report,",2000]
[null,"Indicator:   # of youth empowerment initiatives supported.   \nBaseline: 0\nTarget: At least 2 initiatives supported",null,"Interiews, data review","Quarterly","Project & portfolio Managers, ","partner (MOYA NAYCOM) reports",2000,"Annual progress report is prepared and submitted for review"]
["Portfolio/Project Output 6:  Vulnerable groups, especially PWDs have improved entrepreneural, financial literacy and employability skills and are socially protected from discrimination;"]
["Activity Result 6: PWDs and vulnerable groups capacitated in entreprenuer, financial literacy and employability skills","Indicator:  # of vulnerable groups capacitated in:                                                 I. Entrepreneural skills, ii. Financial Literacy and iii. employability skills       \nBaseline: 40\nTarget: At least 5 additional groups capacitated by Dec. 2020 ",null,"Record Review; field visit; Interviews","Quarterly","Project & portfolio Managers,","Beneficiary list; Photos",2000,"Participants list was prepared and submitted for review"]
[null,"Indicator: % of targeted PWDs who created their own employment at the end of the period      \nBaseline: 10%\nTarget: 12%",null,"Direct observation, field visit","Quarterly","M&E Officer, Project manager","Survey report",2000,"Survey report is accesible for review"]
["Portfolio/Project Output 7: critical gaps in vulnerable communities on COVID-19 response enhanced/complemented "]
["Activity Result: Critical gaps in COVID-19 response complemented in target communities","Indicator: # of outreach gender aware communication strategies developed and implemented to sensitized vulnerable communities on COVID 19 response   \nBaseline: 0\nTarget: At least 3 (Radio, poster, manual etc.) gender responsive COVID-19 outreach strategies developed and implemented;",null,"Review of communication strategy; Direct observation; Field visit","Quarterly","M&E Officer, Project manager","Communication materials, Recordings of radio programs",2000,"Communication materials are accessible for review"]
[null," Indicator: # of visually impaired persons supported with COVID 19 sensitization messages using braille  \nBaseline: 0\nTarget:  At least 1000 visually impaired persons supported with COVID-19 messages on braille;(disagregated by sex)                                                                                                                               ",null,"Interviews; field visit; Record review","Quarterly","M&E Officer, Project manager","Activity report; Participants list",2000,"Beneficiaries show willingness to be interviewed"]
[null," Indicator: # of vulnerable HHs supported with food and protective kits, based on the needs of women and men (Disagrgated by female and male headed HHs.)       \nBaseline: 0\nTarget: At least 3,750 (2250 Male headed HHs: 1500 Female headed HHs) households in 8 districts reached with food & non food items & hygeine kits.     ",null,"Field visit; direct observation; Interviews","Quarterly","M&E Officer, Project manager","Participants list; Activity report; Photos",2000,"beneficiary list shows Gender disaggregation"]

{"sheet":"Sheet2","index":1,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["UNDAF Outcome: Vulnerable\ngroup benefit from strengthened legal and policy frameworks, and have improved access to security and rule-of-law institutions. (Outcome 4, 2013-2017 UNDAF\n"]

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}