{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":31,"n_cols":9,"rows_kept":31,"cut":false,"hidden":false,"merged":[[28,0,30,0],[14,0,16,0],[23,0,23,8],[24,0,26,0],[18,0,18,9],[27,0,27,8],[11,0,12,0],[13,0,13,8],[19,0,22,0],[3,7,6,7],[0,0,0,8],[10,0,10,9],[3,6,6,6],[3,8,6,9],[3,0,6,0],[3,1,6,2],[3,3,6,3],[3,4,6,4],[3,5,6,5],[1,0,1,8],[2,0,2,8],[7,0,9,0]]}
["Annual M&E Plan, 2020"]
["Portfolio/Project Name: NRM, CC. MITIGATION, ADAPTATION & DISASTER RESILIENCE COVID 19 RESPONSE"]
["UNDP Sierra Leone"]
["Expected Results ","Indicators (With annual Baselines\nand Targets)",null,"M&E Event with\nData Collection \nMethods","Time or Schedule\nand Frequency","Responsibilities","Means of Verification: Data\nSource and Type","Resources","Risks and Assumptions"]
[]
[]
[]
["CPD Output 1.1:  Relevant MDAs have strengthened capacities to enforce inclusive regulations and gender-responsive policies on conservation of protected areas in coastal and urban planning and development","Indicator: : # of newly endorsed policies by parliament on coastal communities and protected areas that are gender responsive\nBaseline: 1 Policy on protected area is in place\nTarget: At least 2 newly endorsed policies are in place by Dec. 2020\n\n\n",null,"Policy review","Annually","UNDP","Policy document",3000,"Policy document is submission upon request for review"]
[null,"Indicator: # of MDAs with strengthened capacities to enforce regulations and policies in coastal and protected areas  \nBaseline: 2\nTarget: 2",null,"Field visit; Interviews, Direct observation","Annually","M&E focal point, UNDP","NPAA, EPA's report",3000,"Partners are willing to be interviewed and to share activity update with the monitor"]
[null,"Indicator:  # of MDAs with technical and operational capacities to implement urban planning\nBaseline: 0\nTarget: 1",null,"Interviews","Annually","M&E focal point, UNDP","MLHP",2000]
["Portfolio/Project Output 1: Relevant Ministries/department/agencies have strengthened  capacities ( MDAs) to enforce inclusive regulations and gender-responsive policies on conservation of protected areas in coastal and urban planning and development"]
["Activity Result 1: National framework developed for effective management of coastal and protected areas ","Indicator: # of gender-responsive policies developed that enforce regulations in coastal and protected areas\nBaseline: 1 Policy is in place\nTarget: at least one new Coastal management policy developed by Dec. 2020\n\n ",null,"Policy review","Quarterly","Project Manager; M&E Focal point","completed Policy document",1000,"National framework document is in place and provided upon request"]
[null,"Indicator: # of MDAs with strengthened capacitaty to enforce regulations and policies on coastal and protected areas \nBaseline: 2\nTarget: The capacity of at least 2 MDA's (EPA, NPAA) strengthened to enforce regulations on proptected or coastal areas",null,"Field visit; Interviews,  ","Quarterly","Project Manager; M&E Focal point","EPA, NPAA reports",3000,"Report submitted on time"]
["Portfolio/Project Output 2: Capacity of MDAs in natural resources management at national and local levels strengthened to ensure sustainable use of environmental resources including livelihoods "]
["Activity Result 2: Natural resources management improved to meet best practices","Indicator:  # of water resources management policies developed that incorporated Water Resource Management (IWRM) principles                                 \nBaseline: 1 Policy is in place \nTarget: At least 3 water Policies with IWRM principles developed by Dec. 2020\n\n",null,"Record Review; field visit","Quarterly","Project Manager; M&E Focal point","Policy document, minutes of consultative meetings, ",2000,"Policy document is submission upon request for review"]
[null,"Indicator: # of NWRM communication strategy developed and implemented                                                                                                             Baseline: 0                                                                                                                           Target: At least 1 NWRM communication strategy developed and implemented",null,"Record Review","Quarterly","Project Manager; M&E Focal point","NWRM Communication strategy guideline",null,"Timely submission of strategy framework for review"]
[null,"Indicator: Area (Acre) of reclaimed mined out land transformed into farming plots\nBaseline: 10 Acres of reclaimed mined out land is available \nTarget: At least 10 Acres of reclaimed mined out land cultivated for Agricultural livelihoods\n\n\n",null,"Direct Observation; Interviews; Field visit","Quarterly","Project Manager; M&E Focal point","Photos of farm; activity report, ",3000,"Project site is accessible for observation"]
[null,"Indicator: # of artisanal miners trained on improved farming techniques, disaggregated by sex                                                                                                      Baseline:  40                                                                                                                  Target: At least 50 trained by Dec. 2020                                                                                            ",null,"Record Review","Quarterly","Project Manager; M&E Focal point","Participants list, Partner report",2000,"Participants list available for review"]
["Portfolio/Project Output 3:  Preparedness system in place at community level to mitigate the impact of natural and manmade disasters."]
["Activity Result 3:Community level preparedness mechanisms established","Indicator: # of gender balanced Ward Disaster Management Comittee  established (WDMC) and trained on DRR  \nBaseline: 0 \nTarget: At least 15 WDMCs  established and trained on DRR in 2 districts.\n\n ",null,"field visit; Interviews; Direct observation","Quarterly","Project Manager; M&E Focal point","Participants list",2000,"Participants list available for review"]
[null,"Indicator: # of gender responsive DRRM School handbook validated \nBaseline: 0\nTarget: At least 1 DRRM hand book for schools validated\n\n",null,"Record review, Field visit; Interviews","Quarterly","Project Manager; M&E Focal point","Participants list; Validated handbook",null,"Participants list available for review"]
[null,"Indicator: Extent to which the National DRM policy is revised and finalised (1- outdated DRM Policy; 2-policy revision initiated; 3-policy revised; 4-DRM Policy finalized; 5-policy validated; 6-Policy popularized)    Baseline: 2-DRM Policy revision initiated                                                                     Target:  4, 5 and 6 (policy finalised, validated and popularized)",null,"Policy review","Quarterly","Project Manager; M&E Focal point","Validated DRM Policy",null,"DRM policy document is avaible for review"]
[null,"Indicator: # of Instituions capacitated to disseminate early warning information to coastal communities.                                                                       Baseline: Had capacitated 1 Agency                                                                                                  Target:  At least 2 additional MDAs capacitated to disseminate early warning information in coastal communities ",null,"Field visit; Interviews","Quarterly","Project Manager; M&E Focal point","Partner activity report",2000,"Partners are willing to be interviewed and to share early warning activity update with the monitor"]
["Portfolio/Project Output 4:  Resource mobilization Efforts enhanced to increase access to carbon financing "]
["Activity Result 4: Resources mobilization windows identified","Indicator: # of new financing windows for carbon financing identified and approached for probable funding\nBaseline: No carbon financing windows approached yet\nTarget: At least 3 carbon financing windows identified & approached by Dec. 2020 ",null,"Interviews/Record review","Quarterly","Project Manager; M&E Focal point","Notification letter, Minute of meeting held",2000,"Notification letter and minute well documented"]
[null,"Indicator: # of proposals developed to attract carbon financing\nBaseline: 0 proposal\nTarget: At least 3 proposals developed by end of Dec. 2020",null,"Proposal review; Interview","Quarterly","Project Manager; M&E Focal point","Proposals",null,"Proposal is well documented and submitted for review"]
[null,"Indicator: Carbon Financing Framework in place (Yes/No)\nBaseline: No Carbon Financing Framework in place\nTarget: At least 1 Carbon Financing Framework is in place (Yes)",null,"Record Review","Quarterly","Project Manager; M&E Focal point","Carbon financing framework document",1000,"Framework document is accessible for review"]
["Portfolio/Project Output 5: COVID19 response capacity of DDMCs increased to support community mitigation efforts"]
["Activity Result 5:                          COVID 19 protective kits installed at community level and mitigation efforts upscaled","Indicator: # of DDMC and community members provided with COVID 19 protective kits (hand washing stations; Hand sanitizer, soap and tissue paper) \nBaseline: 0  \nTarget: At least 5,000 persons (DDMCs and community members) benefit from start-up kits provided by undp  ",null,"Field visit; Direct observation; Record review","Quarterly","Project Manager; M&E Focal point","Photos of protective kits, participants list",3000,"There is good camera to capture on the spot activity photos"]
[null,"Indicator: # of volunteers and DDMC members (disaggregated by sex) trained on COVID19 awareness raising                                                                \nBaseline: 0 volunteer & DDMC's have capacity to conduct awareness raising on COVID19                                                                                             \nTarget: At least 75 (M-40; F-30) volunteers and 375 (M-200; F-175) DDMCs members capacitated on COVID19 awareness raising ",null,"Field visit; Interviews","Quarterly","Project Manager; M&E Focal point","Partner activity report; Participants list",3000,"Report & participants list submitted on time for review"]
[null,"Indicator: # of persons in target communities sensitized via text messages on COVID19 prevention.\nBaseline: 0  \nTarget: At least 1 million persons reached via text messages on COVID 19  sensitization.",null,"Text messages review","Quarterly","Project Manager; M&E Focal point","Mobile messages",null,"Text messages archived for review "]

{"sheet":"Sheet2","index":1,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["UNDAF Outcome: Vulnerable\ngroup benefit from strengthened legal and policy frameworks, and have improved access to security and rule-of-law institutions. (Outcome 4, 2013-2017 UNDAF\n"]

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}