## 0.list (hidden)
SheetName | DataCellAddress | Desc
BasicData | E18
BasicData | E19
BasicData | F21
BasicData | F22
BasicData | F23
BasicData | F24
BasicData | F25
BasicData | F26
BasicData | F27
BasicData | F28
BasicData | F29
BasicData | F30
BasicData | F31
BasicData | F32
BasicData | F33
BasicData | F34
BasicData | F35
BasicData | F40
BasicData | F42
BasicData | F43
BasicData | F44
BasicData | F45
BasicData | F46
BasicData | F47
BasicData | F48
BasicData | F50
BasicData | F51
BasicData | F53
BasicData | F54
BasicData | F55
BasicData | E59
BasicData | E63
BasicData | E64
BasicData | E66
BasicData | E67
BasicData | E69
BasicData | E70
BasicData | E72
BasicData | E73
BasicData | E77
RTA | D27
RTA | D30
RTA | C34
RTA | C37
RTA | C40
RTA | C44
RTA | C47
RTA | C50
RTA | C52
RTA | C53
UNDP CO | D15
UNDP CO | C19
UNDP CO | C22
UNDP CO | C25
UNDP CO | C29
UNDP CO | C32
UNDP CO | C35
UNDP CO | D37
UNDP CO | D38
UNDP CO | D39
UNDP CO | D40
UNDP CO | D41
UNDP CO | C45
UNDP CO | C46
DO | C641 | Merged
DO | D641 | Merged
DO | E641 | Merged
DO | F641 | Merged
DORating | F27
DORating | G27
DORating | F34
DORating | G34
DORating | F41
DORating | G41
DORating | F48
DORating | G48
DORating | F55
DORating | G55
DORating | F62
DORating | G62
DORating | G66
IP | C218 | Merged
IP | D218 | Merged
IP | E218 | Merged
IPRating | F27
IPRating | G27
IPRating | F34
IPRating | G34
IPRating | F41
IPRating | G41
IPRating | F48
IPRating | G48
IPRating | F55
IPRating | G55
IPRating | F62
IPRating | G62
IPRating | G66
Adjustments | G16
Adjustments | G17
Adjustments | E21
Adjustments | F21
Adjustments | G21
Adjustments | E22
Adjustments | F22
Adjustments | G22
Adjustments | E23
Adjustments | F23
Adjustments | G23
Adjustments | E24
Adjustments | F24
Adjustments | G24
Adjustments | E25
Adjustments | F25
Adjustments | G25
Adjustments | G31
Adjustments | G32
Adjustments | E35
Adjustments | F35
Adjustments | E36
Adjustments | F36
Adjustments | E37
Adjustments | F37
Adjustments | E44
Adjustments | F44
Adjustments | E45
Adjustments | F45
Adjustments | E46
Adjustments | F46
Adjustments | E47
Adjustments | F47
Adjustments | E48
Adjustments | F48
Adjustments | E49
Adjustments | F49
Adjustments | E50
Adjustments | F50
Adjustments | E51
Adjustments | F51
Adjustments | E52
Adjustments | F52
Adjustments | E53
Adjustments | F53
Adjustments | D58 | Merged
Adjustments | E58 | Merged
Adjustments | F58 | Merged
Adjustments | G58 | Merged
Finance | D18
Finance | E19
Finance | D25
Finance | E26
Finance | D31
Finance | E32
Finance | D37
Finance | E38
Finance | D41
Finance | E42
Finance | E43
Finance | E48
Communications and KM | D16
Communications and KM | D20
Communications and KM | D24
Communications and KM | D28
Partnerships | D15
Partnerships | D16
Partnerships | D17
Partnerships | D18
Partnerships | D19
Partnerships | D23
Gender | E13
Gender | E14
Gender | D16
Gender | D17
Gender | E18
Gender | E20
Gender | C25 | Merged
Gender | D25 | Merged
Gender | E25 | Merged
CCM TT | D14
CCM TT | D25
CCM TT | D26
CCM TT | D27
CCM TT | D28
CCM TT | D29
CCM TT | D30
CCM TT | D31
CCM TT | D32
CCM TT | D33
CCM TT | D35
CCM TT | D36
CCM TT | D37
CCM TT | D42
CCM TT | D43
CCM TT | D44
CCM TT | D45
CCM TT | D46
CCM TT | D47
CCM TT | D48
CCM TT | D49
CCM TT | D50
CCM TT | D52
CCM TT | D54
CCM TT | D55
CCM TT | D56
CCM TT | D57
CCM TT | D58
CCM TT | D59
CCM TT | D60
CCM TT | D62
CCM TT | D63
CCM TT | D64
CCM TT | D65
CCM TT | D70
CCM TT | D71
CCM TT | D72
CCM TT | D73
CCM TT | D74
CCM TT | D75
CCM TT | D76
CCM TT | D77
CCM TT | D78
CCM TT | D80
CCM TT | D81
CCM TT | D82
CCM TT | D84
CCM TT | D86
CCM TT | D87
CCM TT | D88
CCM TT | D89
CCM TT | D94
CCM TT | D95
CCM TT | D96
CCM TT | D98
CCM TT | D99
CCM TT | D100
CCM TT | D103
CCM TT | D104
CCM TT | D105
CCM TT | D106
CCM TT | D107
CCM TT | D108
CCM TT | D109
CCM TT | D110
CCM TT | D111
CCM TT | D112
CCM TT | D115
CCM TT | D116
CCM TT | D117
CCM TT | D118
CCM TT | D119
CCM TT | D120
CCM TT | D121
CCM TT | D122
CCM TT | D123
CCM TT | D124
CCM TT | D126
CCM TT | D127
CCM TT | D128
CCM TT | D129
CCM TT | D134
CCM TT | D135
CCM TT | D136
CCM TT | D137
CCM TT | D138
CCM TT | D139
CCM TT | D140
CCM TT | D141
CCM TT | D143
CCM TT | D144
CCM TT | D145
CCM TT | D147
CCM TT | D148
CCM TT | D149
CCM TT | D150
CCM TT | D152
CCM TT | D153
CCM TT | D154
CCM TT | D155
CCM TT | D160
CCM TT | D161
CCM TT | D162
CCM TT | D163
CCM TT | D165
CCM TT | D166
CCM TT | D168
CCM TT | D169
CCM TT | D170
CCM TT | D171
CCM TT | D176
CCM TT | D177
CCM TT | D178
CCM TT | D179
CCM TT | D180

## 0.listCells (hidden)
SheetName | DataCellAddress | Desc | SheetName from 2011 template | DataCellAddress | MergedAddress | Desc | DataTitle | Length | Not checked | SheetName | DataCellAddress | MergedAddress | Desc | DataTitle | Length
BasicData | E18 |  | BasicData | E18 |  | Number |  | 3 |  | BasicData | E30 |  | Text |  | 3
BasicData | E19 |  | BasicData | E19 |  | Number |  | 3 |  | BasicData | E31 |  | Text |  | 3
BasicData | F21 |  | BasicData | E20 |  | Text |  | 3 |  | BasicData | E32 |  | Text |  | 3
BasicData | F22 |  | BasicData | E21 |  | Text |  | 3 |  | BasicData | E33 |  | Text |  | 3
BasicData | F23 |  | BasicData | E22 |  | Text |  | 3 |  | BasicData | E34 |  | Text |  | 3
BasicData | F24 |  | BasicData | E23 |  | Text |  | 3 |  | BasicData | E35 |  | Text |  | 3
BasicData | F25 |  | BasicData | E24 |  | Text |  | 3 |  | BasicData | E36 |  | Text |  | 3
BasicData | F26 |  | BasicData | E25 |  | Text |  | 3 |  | BasicData | E37 |  | Text |  | 3
BasicData | F27 |  | BasicData | E26 |  | Text |  | 3 |  | BasicData | E38 |  | Text |  | 3
BasicData | F28 |  | BasicData | E27 |  | Text |  | 3 |  | BasicData | E39 |  | Text |  | 3
BasicData | F29 |  | BasicData | E28 |  | Text |  | 3 |  | BasicData | E40 |  | Text |  | 3
BasicData | F30 |  | BasicData | E29 |  | Text |  | 3 |  | BasicData | E41 |  | Text |  | 3
BasicData | F31 |  | BasicData | E30 |  | Text |  | 3 |  | BasicData | E42 |  | Text |  | 3
BasicData | F32 |  | BasicData | F70 |  | Text |  | 3 |  | BasicData | E43 |  | Text |  | 3
BasicData | F33 |  | BasicData | F71 |  | Text |  | 3 |  | BasicData | E44 |  | Text |  | 3
BasicData | F34 |  | BasicData | F72 |  | Text |  | 3 |  | BasicData | E45 |  | Text |  | 3
BasicData | F35 |  | BasicData | F74 |  | Text |  | 3 |  | BasicData | E46 |  | Text |  | 3
BasicData | F40 |  | BasicData | F75 |  | Text |  | 3 |  | BasicData | E47 |  | Text |  | 3
BasicData | F42 |  | BasicData | F76 |  | Text |  | 3 |  | BasicData | E48 |  | Text |  | 3
BasicData | F43 |  | BasicData | F77 |  | Text |  | 3 |  | BasicData | E49 |  | Text |  | 3
BasicData | F44 |  | BasicData | F78 |  | Text |  | 3 |  | BasicData | E50 |  | Text |  | 3
BasicData | F45 |  | BasicData | F79 |  | Text |  | 3 |  | BasicData | E51 |  | Text |  | 3
BasicData | F46 |  | BasicData | F80 |  | Text |  | 3 |  | BasicData | E52 |  | Text |  | 3
BasicData | F47 |  | BasicData | F82 |  | Text |  | 3 |  | BasicData | E53 |  | Text |  | 3
BasicData | F48 |  | BasicData | F83 |  | Text |  | 3 |  | BasicData | E54 |  | Text |  | 3
BasicData | F50 |  | BasicData | F84 |  | Text |  | 3 |  | BasicData | E55 |  | Text |  | 3
BasicData | F51 |  | BasicData | F85 |  | Text |  | 3 |  | BasicData | E56 |  | Text |  | 3
BasicData | F53 |  | BasicData | F86 |  | Text |  | 3 |  | BasicData | E57 |  | Text |  | 3
BasicData | F54 |  | BasicData | F87 |  | Text |  | 3 |  | BasicData | E58 |  | Text |  | 3
BasicData | F55 |  | BasicData | E91 |  | Text |  | 3 |  | BasicData | E59 |  | Text |  | 3
BasicData | E59 |  | BasicData | E95 |  | Text |  | 3 |  | BasicData | E60 |  | Text |  | 3
BasicData | E63 |  | BasicData | E96 |  | Text |  | 3 |  | BasicData | E61 |  | Text |  | 3
BasicData | E64 |  | BasicData | E97 |  | Date |  | 3 |  | BasicData | E62 |  | Text |  | 3
BasicData | E66 |  | BasicData | E99 |  | Text |  | 3 |  | BasicData | E63 |  | Text |  | 3
BasicData | E67 |  | BasicData | E100 |  | Text |  | 4 |  | BasicData | E64 |  | Text |  | 3
BasicData | E69 |  | BasicData | E101 |  | Date |  | 4 |  | BasicData | E65 |  | Text |  | 3
BasicData | E70 |  | BasicData | E103 |  | Text |  | 4 |  | BasicData | E66 |  | Text |  | 3
BasicData | E72 |  | BasicData | E104 |  | Text |  | 4
BasicData | E73 |  | BasicData | E105 |  | Date |  | 4
BasicData | E77 |  | BasicData | E107 |  | Text |  | 4
RTA | D27 |  | BasicData | E108 |  | Text |  | 4
RTA | D30 |  | BasicData | E109 |  | Date |  | 4
RTA | C34 |  | RTA | E17 |  | Number |  | 3
RTA | C37 |  | RTA | C24 |  | Text |  | 3
RTA | C40 |  | RTA | C26 |  | Text |  | 3
RTA | C44 |  | RTA | C27 |  | Text |  | 3
RTA | C47 |  | RTA | C28 |  | Date |  | 3
RTA | C50 |  | UNDP CO | C14 |  | Text |  | 3
RTA | C52 |  | UNDP CO | C17 |  | Text |  | 3
RTA | C53 |  | UNDP CO | C20 |  | Text |  | 3
UNDP CO | D15 |  | UNDP CO | C21 |  | Text |  | 3
UNDP CO | C19 |  | UNDP CO | C22 |  | Date |  | 3
UNDP CO | C22 |  | DO | C16:I636 |  | Text |  | 8
UNDP CO | C25 |  | DORating | G15 |  | Text |  | 3
UNDP CO | C29 |  | DORating | H15 |  | Text |  | 3
UNDP CO | C32 |  | DORating | G18 |  | Text |  | 3
UNDP CO | C35 |  | DORating | H18 |  | Text |  | 3
UNDP CO | D37 |  | DORating | G21 |  | Text |  | 3
UNDP CO | D38 |  | DORating | H21 |  | Text |  | 3
UNDP CO | D39 |  | DORating | G24 |  | Text |  | 3
UNDP CO | D40 |  | DORating | H24 |  | Text |  | 3
UNDP CO | D41 |  | DORating | G27 |  | Text |  | 3
UNDP CO | C45 |  | DORating | H27 |  | Text |  | 3
UNDP CO | C46 |  | DORating | G30 |  | Text |  | 3
DO | C641 | Merged | DORating | H30 |  | Text |  | 3
DORating | F27 |  | IP | D16:D214 |  | Text |  | 8
DORating | G27 |  | IPRating | G15 |  | Text |  | 3
DORating | F34 |  | IPRating | H15 |  | Text |  | 3
DORating | G34 |  | IPRating | G18 |  | Text |  | 3
DORating | F41 |  | IPRating | H18 |  | Text |  | 3
DORating | G41 |  | IPRating | G21 |  | Text |  | 3
DORating | F48 |  | IPRating | H21 |  | Text |  | 3
DORating | G48 |  | IPRating | G24 |  | Text |  | 3
DORating | F55 |  | IPRating | H24 |  | Text |  | 3
DORating | G55 |  | IPRating | G27 |  | Text |  | 3
DORating | F62 |  | IPRating | H27 |  | Text |  | 3
DORating | G62 |  | IPRating | G30 |  | Text |  | 3
DORating | G66 |  | IPRating | H30 |  | Text |  | 3
IP | C218 | Merged | Adjustments | E17 |  | Text |  | 3
IPRating | F27 |  | Adjustments | E20:G24 |  | Text |  | 7
IPRating | G27 |  | Adjustments | E31 |  | Text |  | 3
IPRating | F34 |  | Adjustments | E34:F36 |  | Text |  | 7
IPRating | G34 |  | Finance | D16 |  | Number |  | 3
IPRating | F41 |  | Finance | D17 |  | Text |  | 3
IPRating | G41 |  | Finance | D22 |  | Number |  | 3
IPRating | F48 |  | Finance | D23 |  | Text |  | 3
IPRating | G48 |  | Finance | D27 |  | Number |  | 3
IPRating | F55 |  | Finance | D28 |  | Text |  | 3
IPRating | G55 |  | Finance | D31 |  | Text |  | 3
IPRating | F62 |  | Finance | D32 |  | Text |  | 3
IPRating | G62 |  | Communications and KM | D16 |  | Text |  | 3
IPRating | G66 |  | Communications and KM | D20 |  | Text |  | 3
Adjustments | G16 |  | Communications and KM | D24 |  | Text |  | 3
Adjustments | G17 |  | Partnerships | D15 |  | Text |  | 3
Adjustments | E21 |  | Partnerships | D16 |  | Text |  | 3
Adjustments | F21 |  | Partnerships | D17 |  | Text |  | 3
Adjustments | G21 |  | Partnerships | D18 |  | Text |  | 3
Adjustments | E22 |  | Partnerships | D19 |  | Text |  | 3
Adjustments | F22 |  | Gender | D13 |  | Text |  | 3
Adjustments | G22 |  | Gender | D15 |  | Text |  | 3
Adjustments | E23 |  | Gender | E17 |  | Text |  | 3
Adjustments | F23
Adjustments | G23
Adjustments | E24
Adjustments | F24
Adjustments | G24
Adjustments | E25
Adjustments | F25
Adjustments | G25
Adjustments | G31
Adjustments | G32
Adjustments | E35
Adjustments | F35
Adjustments | E36
Adjustments | F36
Adjustments | E37
Adjustments | F37
Adjustments | E44
Adjustments | F44
Adjustments | E45
Adjustments | F45
Adjustments | E46
Adjustments | F46
Adjustments | E47
Adjustments | F47
Adjustments | E48
Adjustments | F48
Adjustments | E49
Adjustments | F49
Adjustments | E50
Adjustments | F50
Adjustments | E51
Adjustments | F51
Adjustments | E52
Adjustments | F52
Adjustments | E53
Adjustments | F53
Adjustments | D58 | Merged
Finance | D18
Finance | E19
Finance | D25
Finance | E26
Finance | D31
Finance | E32
Finance | D37
Finance | E38
Finance | D41
Finance | E42
Finance | E43
Finance | E48
Communications and KM | D16
Communications and KM | D20
Communications and KM | D24
Communications and KM | D28
Partnerships | D15
Partnerships | D16
Partnerships | D17
Partnerships | D18
Partnerships | D19
Partnerships | D23
Gender | E13
Gender | E14
Gender | D16
Gender | D17
Gender | E18
Gender | E20
Gender | C25 | Merged
CCM TT | D14
CCM TT | D25
CCM TT | D26
CCM TT | D27
CCM TT | D28
CCM TT | D29
CCM TT | D30
CCM TT | D31
CCM TT | D32
CCM TT | D33
CCM TT | D35
CCM TT | D36
CCM TT | D37
CCM TT | D42
CCM TT | D43
CCM TT | D44
CCM TT | D45
CCM TT | D46
CCM TT | D47
CCM TT | D48
CCM TT | D49
CCM TT | D50
CCM TT | D52
CCM TT | D54
CCM TT | D55
CCM TT | D56
CCM TT | D57
CCM TT | D58
CCM TT | D59
CCM TT | D60
CCM TT | D62
CCM TT | D63
CCM TT | D64
CCM TT | D65
CCM TT | D70
CCM TT | D71
CCM TT | D72
CCM TT | D73
CCM TT | D74
CCM TT | D75
CCM TT | D76
CCM TT | D77
CCM TT | D78
CCM TT | D80
CCM TT | D81
CCM TT | D82
CCM TT | D84
CCM TT | D86
CCM TT | D87
CCM TT | D88
CCM TT | D89
CCM TT | D94
CCM TT | D95
CCM TT | D96
CCM TT | D98
CCM TT | D99
CCM TT | D100
CCM TT | D103
CCM TT | D104
CCM TT | D105
CCM TT | D106
CCM TT | D107
CCM TT | D108
CCM TT | D109
CCM TT | D110
CCM TT | D111
CCM TT | D112
CCM TT | D115
CCM TT | D116
CCM TT | D117
CCM TT | D118
CCM TT | D119
CCM TT | D120
CCM TT | D121
CCM TT | D122
CCM TT | D123
CCM TT | D124
CCM TT | D126
CCM TT | D127
CCM TT | D128
CCM TT | D129
CCM TT | D134
CCM TT | D135
CCM TT | D136
CCM TT | D137
CCM TT | D138
CCM TT | D139
CCM TT | D140
CCM TT | D141
CCM TT | D143
CCM TT | D144
CCM TT | D145
CCM TT | D147
CCM TT | D148
CCM TT | D149
CCM TT | D150
CCM TT | D152
CCM TT | D153
CCM TT | D154
CCM TT | D155
CCM TT | D160
CCM TT | D161
CCM TT | D162
CCM TT | D163
CCM TT | D165
CCM TT | D166
CCM TT | D168
CCM TT | D169
CCM TT | D170
CCM TT | D171
CCM TT | D176
CCM TT | D177
CCM TT | D178
CCM TT | D179
CCM TT | D180

## 0.EmptyFields (hidden)
Sheet Name | Data Cell Address
BasicData | E18
BasicData | E19
BasicData | F21
BasicData | F22
BasicData | F23
BasicData | F24
BasicData | F25
BasicData | F26
BasicData | F27
BasicData | F28
BasicData | F29
BasicData | F30
BasicData | F31
BasicData | F32
BasicData | F33
BasicData | F34
BasicData | F35
BasicData | F40
BasicData | F42
BasicData | F43
BasicData | F44
BasicData | F45
BasicData | F46
BasicData | F47
BasicData | F48
BasicData | F50
BasicData | F51
BasicData | F53
BasicData | F54
BasicData | F55
BasicData | E59
BasicData | E63
BasicData | E64
BasicData | E66
BasicData | E67
BasicData | E69
BasicData | E70
BasicData | E72
BasicData | E73
BasicData | E77
RTA | D27
RTA | D30
RTA | C34
RTA | C37
RTA | C40
RTA | C44
RTA | C47
RTA | C50
RTA | C52
RTA | C53
UNDP CO | D15
UNDP CO | C19
UNDP CO | C22
UNDP CO | C25
UNDP CO | C29
UNDP CO | C32
UNDP CO | C35
UNDP CO | D37
UNDP CO | D38
UNDP CO | D39
UNDP CO | D40
UNDP CO | D41
UNDP CO | C45
UNDP CO | C46
DO | C641
DORating | F27
DORating | G27
DORating | F34
DORating | G34
DORating | F41
DORating | G41
DORating | F48
DORating | G48
DORating | F55
DORating | G55
DORating | F62
DORating | G62
DORating | G66

## 0.rpt3 (hidden)
SheetName | VerificationCell | VerificationText |  | Desc | DataTitle | [6 empty] | 1 | Jan
[12 empty] | 2 | Feb
[12 empty] | 3 | Mar
[12 empty] | 4 | Apr
[12 empty] | 5 | May
[12 empty] | 6 | Jun
[12 empty] | 7 | Jul
[12 empty] | 8 | Aug
[12 empty] | 9 | Sep
[12 empty] | 10 | Oct
[6 empty] | 2012 Annual Project Review (APR) / Project Implementation Review (PIR) | [5 empty] | 11 | Nov
[12 empty] | 12 | Dec
BasicData |  |  | E13 | text | Official Project Title | Energy Efficiency in Public Buildings (EEPB) |  | Energy Efficiency in Public Buildings (EEPB)
RTA |  |  | C52 | text | Name: | Lead RTA | [5 empty] | Countries
[6 empty] | Lead Country(ies) | El Salvador |  |  |  |  | El Salvador
BasicData |  |  | F39 | date |  | Planned Closing Date |  | 41578
BasicData |  |  | F40 | date | Revised Planned[2] Closing Date: | Revised Planned Closing Date |  |  | 0 | Jan | 1900
PROJECT SUMMARY
BasicData |  |  | E15 | text | Project Summary: | The Project aims to introduce energy efficiency (EE) measures in public buildings by reducing identified technical, policy and information barriers. The Project envisages to: (i) develop and implement an effective EE policy and regulatory framework and to enhance institution building; (ii) strengthen the in-country technical capacity concerning the design and integration of EE measures in public buildings; (iii) implement an EE programme to achieve energy savings by investments and energy monitoring within the Ministry of Public Health. The Project will be implemented by the National Energy Council (CNE); throughput time is 36 months. The EEPB initiative will result in 42,000 ton CO2 directly and 135,000 tons CO2 indirectly avoided emissions. Total budget is US$ 4.325 mln with US$ 3.35 mln cofinancing (of which US$ 2.195 mln investment). |  | The Project aims to introduce energy efficiency (EE) measures in public buildings by reducing identified technical, policy and information barriers. The Project envisages to: (i) develop and implement an effective EE policy and regulatory framework and to enhance institution building; (ii) strengthen the in-country technical capacity concerning the design and integration of EE measures in public buildings; (iii) implement an EE programme to achieve energy savings by investments and energy monitoring within the Ministry of Public Health. The Project will be implemented by the National Energy Council (CNE); throughput time is 36 months. The EEPB initiative will result in 42,000 ton CO2 directly and 135,000 tons CO2 indirectly avoided emissions. Total budget is US$ 4.325 mln with US$ 3.35 mln cofinancing (of which US$ 2.195 mln investment).
Export complete DO tab making sure to change Word page orientation to landscape
RATING OF PROGRESS TOWARD DEVELOPMENT OBJECTIVE
A. National Project Manager/Coordinator
DORating |  |  | C27 |  |  | Overall 2009 Rating (from 09 PIR)
DORating |  |  | D27 |  |  | Overall 2010 Rating (from 10 PIR)
DORating |  |  | E27 |  |  | Overall 2011 Rating (from 11 PIR)
DORating |  |  | F27 |  |  | 2012 Rating
DORating |  |  | G27 |  |  | Comments
B. UNDP Country Office
DORating |  |  | C34 |  |  | Overall 2009 Rating (from 09 PIR)
DORating |  |  | D34 |  |  | Overall 2010 Rating (from 10 PIR)
DORating |  |  | E34 |  |  | Overall 2011 Rating (from 11 PIR)
DORating |  |  | F34 |  |  | 2012 Rating
DORating |  |  | G34 |  |  | Comments
C. GEF Operational Focal Point
DORating |  |  | C41 |  |  | Overall 2009 Rating (from 09 PIR)
DORating |  |  | D41 |  |  | Overall 2010 Rating (from 10 PIR)
DORating |  |  | E41 |  |  | Overall 2011 Rating (from 11 PIR)
DORating |  |  | F41 |  |  | 2012 Rating
DORating |  |  | G41 |  |  | Comments
D. Project Implementing Partner
DORating |  |  | C48 |  |  | Overall 2009 Rating (from 09 PIR)
DORating |  |  | D48 |  |  | Overall 2010 Rating (from 10 PIR)
DORating |  |  | E48 |  |  | Overall 2011 Rating (from 11 PIR)
DORating |  |  | F48 |  |  | 2012 Rating
DORating |  |  | G48 |  |  | Comments
E. Other Partners
DORating |  |  | C55 |  |  | Overall 2009 Rating (from 09 PIR)
DORating |  |  | D55 |  |  | Overall 2010 Rating (from 10 PIR)
DORating |  |  | E55 |  |  | Overall 2011 Rating (from 11 PIR)
DORating |  |  | F55 |  |  | 2012 Rating
DORating |  |  | G55 |  |  | Comments
F. UNDP-GEF Technical Adviser
DORating |  |  | C62 |  |  | Overall 2009 Rating (from 09 PIR)
DORating |  |  | D62 |  |  | Overall 2010 Rating (from 10 PIR)
DORating |  |  | E62 |  |  | Overall 2011 Rating (from 11 PIR)
DORating |  |  | F62 |  |  | 2012 Rating
DORating |  |  | G62 |  |  | Comments
Export complete IP tab
RATING OF ANNUAL PROGRESS IN PROJECT IMPLEMENTATION
A. National Project Manager/Coordinator
IPRating |  |  | C27 |  |  | Overall 2009 Rating (from 09 PIR)
IPRating |  |  | D27 |  |  | Overall 2010 Rating (from 10 PIR)
IPRating |  |  | E27 |  |  | Overall 2011 Rating (from 11 PIR)
IPRating |  |  | F27 |  |  | 2012 Rating
IPRating |  |  | G27 |  |  | Comments
B. UNDP Country Office
IPRating |  |  | C34 |  |  | Overall 2009 Rating (from 09 PIR)
IPRating |  |  | D34 |  |  | Overall 2010 Rating (from 10 PIR)
IPRating |  |  | E34 |  |  | Overall 2011 Rating (from 11 PIR)
IPRating |  |  | F34 |  |  | 2012 Rating
IPRating |  |  | G34 |  |  | Comments
C. GEF Operational Focal Point
IPRating |  |  | C41 |  |  | Overall 2009 Rating (from 09 PIR)
IPRating |  |  | D41 |  |  | Overall 2010 Rating (from 10 PIR)
IPRating |  |  | E41 |  |  | Overall 2011 Rating (from 11 PIR)
IPRating |  |  | F41 |  |  | 2012 Rating
IPRating |  |  | G41 |  |  | Comments
D. Project Implementing Partner
IPRating |  |  | C48 |  |  | Overall 2009 Rating (from 09 PIR)
IPRating |  |  | D48 |  |  | Overall 2010 Rating (from 10 PIR)
IPRating |  |  | E48 |  |  | Overall 2011 Rating (from 11 PIR)
IPRating |  |  | F48 |  |  | 2012 Rating
IPRating |  |  | G48 |  |  | Comments
E. Other Partners
IPRating |  |  | C55 |  |  | Overall 2009 Rating (from 09 PIR)
IPRating |  |  | D55 |  |  | Overall 2010 Rating (from 10 PIR)
IPRating |  |  | E55 |  |  | Overall 2011 Rating (from 11 PIR)
IPRating |  |  | F55 |  |  | 2012 Rating
IPRating |  |  | G55 |  |  | Comments
F. UNDP-GEF Technical Adviser
IPRating |  |  | C62 |  |  | Overall 2009 Rating (from 09 PIR)
IPRating |  |  | D62 |  |  | Overall 2010 Rating (from 10 PIR)
IPRating |  |  | E62 |  |  | Overall 2011 Rating (from 11 PIR)
IPRating |  |  | F62 |  |  | 2012 Rating
IPRating |  |  | G62 |  |  | Comments
MID-TERM OR TERMINAL EVALUATION INPUT
If a mid-term review or a terminal evaluation was undertaken this reporting period, the Country Office and the UNDP-GEF Technical Adviser provided the following input:
Country Office
UNDP CO |  |  | C35
UNDP-GEF Technical Adviser
RTA |  |  | C50
Export complete Adjustments tab
FINANCE
DISBURSEMENT OF GEF GRANT FUNDS
How much of the total GEF grant as noted in Project Document plus any project preparation grant has been spent so far?
Finance |  |  | D18 |  |  | Estimated cumulative total disbursement of GEF Grant as of 30 June 2012
Finance |  |  | E19 |  |  | Add any comments on GEF Grant Funds
DISBURSEMENT OF CO-FINANCING
How much of the total planned co-financing as noted in the Project Document has been spent so far?
Finance |  |  | D25 |  |  | Estimated cumulative total co-financing disbursed as of 30 June 2012
Finance |  |  | E26 |  |  | Add any comments on co-financing including other types and amounts of additional co-financing such as in-kind, private sector, grants, credits and loans
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized?
Finance |  |  | D31 |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Finance |  |  | E32 |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing
ADDITIONAL LEVERAGED RESOURCES
Have additional resources that were not included in the project documents as co-financing been realized since project document signature? If so, how much?
Finance |  |  | D37 |  |  | Estimated cumulative leveraged resources as of 30 June 2012
Finance |  |  | E38 |  |  | Add any comments on Leveraged Resources.
Other Financial Instruments
Finance |  |  | D41 |  |  | Does the project provide funds to other Financial Instruments?
Finance |  |  | E42 |  |  | Please explain type of non-grant financial mechanism used
Finance |  |  | E43 |  |  | Please discuss developments that occurred this reporting period only
General Comments
Finance |  |  | E48
COMMUNICATIONS AND KM
Tell the Story of Your Project and What has been Achieved this Reporting Period
Communications and KM |  |  | D16
Adaptive Management this Reporting Period
Communications and KM |  |  | D20
Lessons Learned
Communications and KM |  |  | D24
General Comments
Communications and KM |  |  | D28
PARTNERSHIPS
Civil Society Organisations/NGOs
Partnerships |  |  | D15
Indigenous Peoples
Partnerships |  |  | D16
Private Sector
Partnerships |  |  | D17
GEF Small Grants Programme
Partnerships |  |  | D18
Other Partners
Partnerships |  |  | D19
General Comments
Partnerships |  |  | D23
GENDER
Gender |  |  | E13 |  |  | Has a gender or social needs assessment been carried out?
Gender |  |  | E14 |  |  | If a gender or social assessment has been carried out what were the findings?
Gender |  |  | D16 |  |  | Does this project specifically target women or girls as key stakeholders?
Gender |  |  | D17 |  |  | Have there been any changes in specifically targeting women or girls as key stakeholders this reporting period?
If yes, please explain
Gender |  |  | E18
Please discuss any of the points above further or provide any other information on the project’s work on gender equality
Gender |  |  | E20
General Data
CCM TT |  |  | D25 |  |  | Project Title
CCM TT |  |  | D26 |  |  | GEF ID
CCM TT |  |  | D27 |  |  | Agency Project ID
CCM TT |  |  | D28 |  |  | Country
CCM TT |  |  | D29 |  |  | Region
CCM TT |  |  | D30 |  |  | GEF Agency
CCM TT |  |  | D31 |  |  | Date of Council/CEO Approval
CCM TT |  |  | D32 |  |  | GEF Grant (US$)
CCM TT |  |  | D33 |  |  | Date of submission of the tracking tool
CCM TT |  |  | D35 |  |  | Is the project consistent with the priorities identified in National Communications, Technology Needs Assessment, or other Enabling Activities under the UNFCCC?
CCM TT |  |  | D36 |  |  | Is the project linked to carbon finance?
CCM TT |  |  | D37 |  |  | Cofinancing expected (US$)
Objective 1: Transfer of Innovative Technologies
CCM TT |  |  | D43 |  |  | National innovation and technology transfer policy
CCM TT |  |  | D44 |  |  | Innovation and technology centre and network
CCM TT |  |  | D45 |  |  | Applied R&D support
CCM TT |  |  | D46 |  |  | South-South technology cooperation
CCM TT |  |  | D47 |  |  | North-South technology cooperation
CCM TT |  |  | D48 |  |  | Intellectual property rights (IPR)
CCM TT |  |  | D49 |  |  | Information dissemination
CCM TT |  |  | D50 |  |  | Institutional and technical capacity building
CCM TT |  |  | D51 |  |  | Other (please specify)
CCM TT |  |  | D53 |  |  | Number of innovative technologies demonstrated or deployed
Three key technologies for demonstration or deployment
CCM TT |  |  | D55 |  |  | Area of technology 1
CCM TT |  |  | D56 |  |  | Type of technology 1
CCM TT |  |  | D57 |  |  | Area of technology 2
CCM TT |  |  | D58 |  |  | Type of technology 2
CCM TT |  |  | D59 |  |  | Area of technology 3
CCM TT |  |  | D60 |  |  | Type of technology 3
CCM TT |  |  | D61 |  |  | Status of technology demonstration/deployment
CCM TT |  |  | D63 |  |  | Lifetime direct GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D64 |  |  | Lifetime direct post-project GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D65 |  |  | Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2)
CCM TT |  |  | D66 |  |  | Lifetime indirect GHG emissions avoided (top-down) (Tonnes of CO2)
Objective 2: Energy Efficiency
CCM TT |  |  | D71 |  |  | Lighting
CCM TT |  |  | D72 |  |  | Appliances (white goods)
CCM TT |  |  | D73 |  |  | Equipment
CCM TT |  |  | D74 |  |  | Cook stoves
CCM TT |  |  | D75 |  |  | Existing building
CCM TT |  |  | D76 |  |  | New building
CCM TT |  |  | D77 |  |  | Industrial processes
CCM TT |  |  | D78 |  |  | Synergy with phase-out of ozone depleting substances
CCM TT |  |  | D79 |  |  | Other (please specify)
CCM TT |  |  | D81 |  |  | Policy and regulatory framework
CCM TT |  |  | D82 |  |  | Establishment of financial facilities (e.g., credit lines, risk guarantees, revolving funds)
CCM TT |  |  | D83 |  |  | Capacity building
CCM TT |  |  | D85 |  |  | Lifetime energy saved
CCM TT |  |  | D87 |  |  | Lifetime direct GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D88 |  |  | Lifetime direct post-project GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D89 |  |  | Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2)
CCM TT |  |  | D90 |  |  | Lifetime indirect GHG emissions avoided (top-down) (Tonnes of CO2)
Objective 3: Renewable Energy
CCM TT |  |  | D95 |  |  | Heat/thermal energy production
CCM TT |  |  | D96 |  |  | On-grid electricity production
CCM TT |  |  | D97 |  |  | Off-grid electricity production
CCM TT |  |  | D99 |  |  | Policy and regulatory framework
CCM TT |  |  | D100 |  |  | Establishment of financial facilities (e.g., credit lines, risk guarantees, revolving funds)
CCM TT |  |  | D101 |  |  | Capacity building
Installed capacity per technology directly resulting from the project
CCM TT |  |  | D104 |  |  | Wind
CCM TT |  |  | D105 |  |  | Biomass
CCM TT |  |  | D106 |  |  | Biomass
CCM TT |  |  | D107 |  |  | Geothermal
CCM TT |  |  | D108 |  |  | Geothermal
CCM TT |  |  | D109 |  |  | Hydro
CCM TT |  |  | D110 |  |  | Photovoltaic (solar lighting included)
CCM TT |  |  | D111 |  |  | Solar thermal heat (heating, water, cooling, process)
CCM TT |  |  | D112 |  |  | Solar thermal power
CCM TT |  |  | D113 |  |  | Marine power (wave, tidal, marine current, osmotic, ocean thermal)
Lifetime energy production per technology directly resulting from the project (IEA unit converter: http://www.iea.org/stats/unit.asp)
CCM TT |  |  | D116 |  |  | Wind
CCM TT |  |  | D117 |  |  | Biomass
CCM TT |  |  | D118 |  |  | Biomass
CCM TT |  |  | D119 |  |  | Geothermal
CCM TT |  |  | D120 |  |  | Geothermal
CCM TT |  |  | D121 |  |  | Hydro
CCM TT |  |  | D122 |  |  | Photovoltaic (solar lighting included)
CCM TT |  |  | D123 |  |  | Solar thermal heat (heating, water, cooling, process)
CCM TT |  |  | D124 |  |  | Solar thermal power
CCM TT |  |  | D125 |  |  | Marine energy (wave, tidal, marine current, osmotic, ocean thermal)
CCM TT |  |  | D127 |  |  | Lifetime direct GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D128 |  |  | Lifetime direct post-project GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D129 |  |  | Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2)
CCM TT |  |  | D130 |  |  | Lifetime indirect GHG emissions avoided (top-down) (Tonnes of CO2)
Objective 4: Transport and Urban Systems
CCM TT |  |  | D135 |  |  | Bus rapid transit
CCM TT |  |  | D136 |  |  | Other mass transit (e.g., light rail, heavy rail, water or other mass transit; excluding regular bus or minibus)
CCM TT |  |  | D137 |  |  | Logistics management
CCM TT |  |  | D138 |  |  | Transport efficiency (e.g., vehicle, fuel, network efficiency)
CCM TT |  |  | D139 |  |  | Non-motorized transport (NMT)
CCM TT |  |  | D140 |  |  | Travel demand management
CCM TT |  |  | D141 |  |  | Comprehensive transport initiatives (Involving the coordination of multiple strategies from different transportation sub-sectors)
CCM TT |  |  | D142 |  |  | Sustainable urban initiatives
CCM TT |  |  | D144 |  |  | Policy and regulatory framework
CCM TT |  |  | D145 |  |  | Establishment of financial facilities (e.g., credit lines, risk guarantees, revolving funds)
CCM TT |  |  | D146 |  |  | Capacity building
CCM TT |  |  | D148 |  |  | Length of public rapid transit (PRT)
CCM TT |  |  | D149 |  |  | Length of non-motorized transport (NMT)
CCM TT |  |  | D150 |  |  | Number of lower GHG emission vehicles
CCM TT |  |  | D151 |  |  | Number of people benefiting from the improved transport and urban systems
CCM TT |  |  | D153 |  |  | Lifetime direct GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D154 |  |  | Lifetime direct post-project GHG emissions avoided (Tonnes of CO2)
CCM TT |  |  | D155 |  |  | Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2)
CCM TT |  |  | D156 |  |  | Lifetime indirect GHG emissions avoided (top-down) (Tonnes of CO2)
Objective 5: LULUCF
Area of activity directly resulting from the project
CCM TT |  |  | D161 |  |  | Conservation and enhancement of carbon in forests, including agroforestry
CCM TT |  |  | D162 |  |  | Conservation and enhancement of carbon in nonforest lands, including peat land
CCM TT |  |  | D163 |  |  | Avoided deforestation and forest degradation
CCM TT |  |  | D164 |  |  | Afforestation/reforestation
CCM TT |  |  | D166 |  |  | Good management practices developed and adopted
CCM TT |  |  | D167 |  |  | Carbon stock monitoring system established
CCM TT |  |  | D169 |  |  | Lifetime direct GHG emission avoided (Tonnes of CO2)
CCM TT |  |  | D170 |  |  | Lifetime indirect GHG emission avoided (Tonnes of CO2)
CCM TT |  |  | D171 |  |  | Lifetime direct carbon sequestration (Tonnes of CO2)
CCM TT |  |  | D172 |  |  | Lifetime indirect carbon sequestration (Tonnes of CO2)
Objective 6: Enabling Activities
CCM TT |  |  | D177 |  |  | National Communication
CCM TT |  |  | D178 |  |  | Technology Needs Assessment
CCM TT |  |  | D179 |  |  | Nationally Appropriate Mitigation Actions
CCM TT |  |  | D180 |  |  | Other
CCM TT |  |  | D181 |  |  | Does the project include Measurement, Reporting and Verification (MRV) activities?

## 0rpt3Obj (hidden)
PROGRESS TOWARD DEVELOPMENT OBJECTIVES | [5 empty] | 20
Description | Description of Indicator | Baseline Level | Target Level at end of project | Level at 30 June 2012 | 0
To introduce energy efficiency (EE) measures in existing and new public buildings by creating a conducive policy environment, increasing user awareness, developing performance criteria and standards, and implementing a broad EE pilot within selected public entities. | (I) Package of EE policy instruments; | (I) No policy instruments to promote EE in buildings in place; | (I) Package of policy instruments to promote EE in buildings in place; | ley de EE y plan nacional de ahorro de energia en el sector de gobierno | 0
| (II) Implementation of investment pilot in hospitals; | (II) No investment pilot designed nor implemented; | (II) Investment pilot fully executed and monitored; |  | 0
| (III) Technical standards and guidelines on EE in buildings; | (III) No national standards and guidelines for energy performance of buildings developed; | (III) Technical standards and guidelines on EE in buildings in place; |  | 0
| (IV) EE investment programme implemented by the Government. | (IV) No investment programme for EE technology in public buildings. | (IV) An EE investment programme worth US$ 2mln has been executed in public buildings. |  | 0
Effective policies and regulation regarding energy efficiency (EE) in buildings have been developed and applied to the public sector. | (A) Human capacity added the CNE (person-years); | (A) 0 | (A) Human capacity added 2 person-years (GEF) plus 1 person-year (Government); |  | 0
| (B) National EE strategy for public buildings; | (B) No EE strategy for public buildings defined; | (B) Detailed EE strategy developed focused on public buildings; |  | 0
| (C) Quantified EE targets for public sector; | (C) No quantified EE (energy conservation); | (C) Quantified EE targets set based on detailed baseline information; |  | 0
| (D) Package of EE policy instruments. | (D) No policy instruments to promote EE in buildings in place. | (D) Package of policy instruments to promote EE in buildings in place (e.g. technical standards, minimum energy performance criteria, building materials, design features, minimum efficiency of equipment). |  | 0
Technical capacity concerning the design and integration of EE measures in public buildings has been strengthened. | (A) Adapted EE assessment methodologies; | (A) Limited experience with foreign methodologies and software tools; | (A) Adapted EE assessment methodologies and tools in place, based on detailed input information; |  | 0
| B) Suitable energy performance indicators for buildings; | (B) No consolidated view on regulation strategies and performance indicators for buildings; | (B) Suitable sets of energy performance indicators defined for appropriate building classes; |  | 0
| (C) Technical standards and guidelines on EE in buildings; | (C) No national standards and guidelines for energy performance of buildings developed; | (C) At least 3 technical standards and guidelines on EE in buildings in place; |  | 0
| (D) National workshop on EE in buildings. | (D) No workshop organized. | (D) Workshop organized. |  | 0
An energy efficiency programme has been designed and implemented within public buildings. | (A) Technical and feasibility studies for EE investments; | (A) No studies performed; | (A) Studies prepared and executed for all investments considered; |  | 0
| (B) Implementation of investment pilot in hospitals; | (B) No investment pilot designed nor implemented; | (B) Investment pilot fully executed and monitored; |  | 0
| (C) Implementation of energy monitoring system. | (C) No energy monitoring system in public organization designed nor implemented; | (C) Energy monitoring system prepared, implemented and supervised during project’s lifetime; |  | 0
| (D) EE investment programme implemented by the Government. | (D) No investment programme for EE technology in public buildings. | (D) An EE investment programme worth US$ 2mln has been executed in public buildings. |  | 0
A project monitoring and evaluation plan has been implemented and lessons learnt have been disseminated. | (A) Mid-term Evaluation Report; | (A) No MTE; | (A) MTE completed; |  | 0
| (B) Final Evaluation Report; | (B) No FEV; | (B) FEV completed; |  | 0
| (C) Sharing of project experience. | (C) No sharing of project experiences in El Salvador. | (C) Lessons learnt publication. |  | 0

## 1.Log (hidden)
CELL CHANGED | OLD VALUE | NEW VALUE | TIME OF CHANGE | DATE OF CHANGE
DO $J$84 | luego de haber finalizado el recambio de 274 luminarias entre la Defensoria del Consumidor y el Ministerio de Medio Ambiente y de haber sistematizado las mejores recomendaciones en cuanto a medidas de conservacion de energia, se procedio a publicar las lecciones aprendidas en 5,000 ejemplares de manuales de recomendaciones para el sector gubernamental y tripticos sobre los resultados de los proyectos pilotos de iluminacion eficiente. | luego de haber finalizado el recambio de 274 luminarias entre la Defensoria del Consumidor y el Ministerio de Medio Ambiente y de haber sistematizado las mejores recomendaciones en cuanto a medidas de conservacion de energia, se procedio a publicar las lecciones aprendidas en 5,000 ejemplares de manuales de recomendaciones para el sector gubernamental y tripticos sobre los resultados de los proyectos pilotos de iluminacion eficiente. | 13:36 | 2012-07-12
DORating $G$27 |  | En el primer año de implementación del proyecto de eficiencia energética en edificios públicos EEPB-75672, se ha logrado impulsar medidas que impactaran en los objetivos ambientales establecidos en el mencionado proyecto, en primer lugar se están generando instrumentos legales y técnicos como lo son la Ley de eficiencia energética, normas de adquisición con criterios de eficiencia y el establecimiento de línea base de consumo del sector gobierno, esto ultimo servirá de insumo para elaborar una estrategia o plan nacional de ahorro en el consumo de energía, así mismo se esta trabajando en el fortalecimiento de las capacidades técnicas sobre EE de las Instituciones Estatales esto a través de formar comités de eficiencia energética y capacitar a profesionales de dichos comités sobre temas muy específicos y especializados en EE, el fortalecimiento de las capacidades técnicas también consiste en proporcionales herramientas informáticas para que estos comités puedan realizar una análisis de desempeño energético de sus edificios y establecer los mejores indicadores para éste, además de contar con una herramienta para dar seguimiento a las medidas implementados, lo que servirá para establecer los ahorros producidos y su equivalente en la mitigación de Gases de Efecto Invernadero (GEI). Conjuntamente al fortalecimiento de las capacidades técnicas de las instituciones del Gobierno, el proyecto EEPB desarrollará en coordinación con el Ministerio de Salud y otras instituciones proyectos pilotos por un monto total aproximado de US$150,000 dólares, con el objetivo que dichos proyectos puedan replicarse en otros edificios con condiciones similares. La unión de todas las medidas descritas anteriormente permitirán que el gobierno tenga la capacidad de identificar e implementar medidas de EE y con el apoyo de las normas técnicas y legales que se están desarrollando, se logre una disminución sensible del consumo de energía, lo cual podría rondar en un 20% según estimaciones preliminares. En cuanto a las dificultades encontradas en el logro de objetivos del proyecto, podemos mencionar que Gobierno tiene dificultades para asignar recursos financieros a las instituciones que sirvan para la implementación de proyectos de eficiencia energética, sin embargo, la estrategia propuesta para superar este obstáculo ha sido el proponer a los comités de eficiencia energética que inicie en su implementación aquellas medidas de muy bajo costo y que se puede desarrollar por etapas, para que las inversiones sean escalonadas, además que las medidas impulsadas sean las que poseen los mejores Pay-back, ya que esto permitirá una pronta recuperación de lo invertido para con ello desarrollar otras medidas identificadas, otro de las dificultades encontradas en la implementación del proyecto es el desarrollo de normas de construcción de edificios que impacte en el consumo energético de este sector, esto se debe a que el tema de construcción es responsabilidad de varias instituciones del gobierno ejecutivo y otras de gobiernos locales, entre las que podemos mencionar el Viceministerio de Vivienda y la OPAMSS, lo que hace difícil armonizar los criterios técnicos para el desarrollo de un instrumento normativo en el tema de construcción eficiente, por tanto se esta trabajando en unificar los criterios técnicos a través de una consulta a todos los sectores e instituciones involucrados en el tema de construcción. | 13:36 | 2012-07-12
DORating $G$27 | En el primer año de implementación del proyecto de eficiencia energética en edificios públicos EEPB-75672, se ha logrado impulsar medidas que impactaran en los objetivos ambientales establecidos en el mencionado proyecto, en primer lugar se están generando instrumentos legales y técnicos como lo son la Ley de eficiencia energética, normas de adquisición con criterios de eficiencia y el establecimiento de línea base de consumo del sector gobierno, esto ultimo servirá de insumo para elaborar una estrategia o plan nacional de ahorro en el consumo de energía, así mismo se esta trabajando en el fortalecimiento de las capacidades técnicas sobre EE de las Instituciones Estatales esto a través de formar comités de eficiencia energética y capacitar a profesionales de dichos comités sobre temas muy específicos y especializados en EE, el fortalecimiento de las capacidades técnicas también consiste en proporcionales herramientas informáticas para que estos comités puedan realizar una análisis de desempeño energético de sus edificios y establecer los mejores indicadores para éste, además de contar con una herramienta para dar seguimiento a las medidas implementados, lo que servirá para establecer los ahorros producidos y su equivalente en la mitigación de Gases de Efecto Invernadero (GEI). Conjuntamente al fortalecimiento de las capacidades técnicas de las instituciones del Gobierno, el proyecto EEPB desarrollará en coordinación con el Ministerio de Salud y otras instituciones proyectos pilotos por un monto total aproximado de US$150,000 dólares, con el objetivo que dichos proyectos puedan replicarse en otros edificios con condiciones similares. La unión de todas las medidas descritas anteriormente permitirán que el gobierno tenga la capacidad de identificar e implementar medidas de EE y con el apoyo de las normas técnicas y legales que se están desarrollando, se logre una disminución sensible del consumo de energía, lo cual podría rondar en un 20% según estimaciones preliminares. En cuanto a las dificultades encontradas en el logro de objetivos del proyecto, podemos mencionar que Gobierno tiene dificultades para asignar recursos financieros a las instituciones que sirvan para la implementación de proyectos de eficiencia energética, sin embargo, la estrategia propuesta para superar este obstáculo ha sido el proponer a los comités de eficiencia energética que inicie en su implementación aquellas medidas de muy bajo costo y que se puede desarrollar por etapas, para que las inversiones sean escalonadas, además que las medidas impulsadas sean las que poseen los mejores Pay-back, ya que esto permitirá una pronta recuperación de lo invertido para con ello desarrollar otras medidas identificadas, otro de las dificultades encontradas en la implementación del proyecto es el desarrollo de normas de construcción de edificios que impacte en el consumo energético de este sector, esto se debe a que el tema de construcción es responsabilidad de varias instituciones del gobierno ejecutivo y otras de gobiernos locales, entre las que podemos mencionar el Viceministerio de Vivienda y la OPAMSS, lo que hace difícil armonizar los criterios técnicos para el desarrollo de un instrumento normativo en el tema de construcción eficiente, por tanto se esta trabajando en unificar los criterios técnicos a través de una consulta a todos los sectores e instituciones involucrados en el tema de construcción. | In the first year of implementation of the project of energy efficiency in public buildings EEPB-75672 has been achieved to promote measures that impact on the environmental objectives laid down in the above-mentioned project, first of all are generating legal and technical instruments such as the law on energy efficiency, standards of acquisition with criteria of efficiency and the establishment of baseline consumption of the Government sector, this last will serve as an input to develop a strategy or national plan for savings in energy consumption, likewise is is working on strengthening technical capacities on U.S. State institutions this through train energy efficiency committees and train professionals of these committees on topics very specific and specialized in (EE)the strengthening of the technical capabilities also consists in proportional computing tools to enable these committees to perform an analysis of the energy performance of their buildings and establish the best indicators for this, as well as having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). Along with the strengthening of the technical capacities of government institutions, the EEPB project will develop pilot projects in coordination with the Ministry of health and other institutions for a total amount of approximately US $ 150,000, with the objective that such projects can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures for us and with the support of technical and legal standards that are being developed, achieve a sensitive decrease of energy consumption, which could be around 20% according to preliminary estimates. As to the difficulties encountered in achieving the project's objectives, we can mention that Government struggles to allocate financial resources to the institutions that serve for the implementation of energy efficiency projects, however, the proposed strategy to overcome this obstacle has been proposing to committees of energy efficiency to initiate low-cost measures in its implementation and that can develop through stages, that investments are staggered, also driven measures are which have better Pay-back, since this will allow a speedy recovery of the investment for this developing other measures identified, another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector, this is due to the issue of construction is the responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and London, which makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction instrument, therefore is working to unify the technical through a query criteria to all the sectors and institutions involved in the topic construction. | 13:42 | 2012-07-12
IP $E$16 | Empty Cell | A U.S. draft law in the process of review and approval | 13:48 | 2012-07-12
IP $E$16 | A U.S. draft law in the process of review and approval | A draft law in the process of review and approval | 13:48 | 2012-07-12
IP $E$17 | Empty Cell | A consultancy for setting standards purchasing criteria of energy efficiency in process of implementation | 13:48 | 2012-07-12
IP $E$18 | Empty Cell | A consultancy for establishment of the baseline of energy consumption in the process of implementing government sector | 13:49 | 2012-07-12
IP $E$21 | 90 comites de eficiencia energetica gubernamentales constituidos y trabajando en la identificacion e implementacion de medidas de EE | 90 constituted governmental energy efficiency committees and working on the identification and implementation of measures of U.S. | 13:51 | 2012-07-12
IP $E$21 | 90 constituted governmental energy efficiency committees and working on the identification and implementation of measures of U.S. | 90 constituted governmental energy efficiency committees and working on the identification and implementation of measures of EE | 13:51 | 2012-07-12
IP $E$22 | 30 profesionales capacitados en el primer diplomado de EE con enfoque en edificios. | 30 trained professionals in the first diploma of EE with focus on buildings. | 13:51 | 2012-07-12
IP $E$21 | 90 constituted governmental energy efficiency committees and working on the identification and implementation of measures of EE | 90 constituted governmental energy efficiency committees and working on the identification and implementation of measures of (EE) | 13:52 | 2012-07-12
IP $E$22 | 30 trained professionals in the first diploma of EE with focus on buildings. | 30 trained professionals in the first diploma of (EE) with focus on buildings. | 13:52 | 2012-07-12
IP $E$23 | Una consultoria para el desarrollo de herramienta de analisis del desempeño energeticos de edificos en proceso de ejecucion | A consultancy for the development of buildings in process of implementing energy performance analysis tool | 13:52 | 2012-07-12
IP $E$26 | 2 proyectos pilotos implementados en la Defensoria del Consumidor y Ministerio de Medio Ambiente, consistentes en la sustitucion de 274 luminarias por tecnologias mas eficientes, lo que causó una disminucion aproximada del 20% del consumo total de energia electrica para la Defensoria y un 10% para el MARN. | 2 pilot projects implemented in consumer advocacy and Ministry of environment, consisting of the replacement of 274 luminaires by more efficient technologies, which caused a decrease of approximately 10% and 20% of the total consumption of electrical energy for the DC and MARN | 13:56 | 2012-07-12
IP $E$28 | Identificacion de medidas de eficiencia en 9 comites de eficiencia energetica, en mutua cooperacion con la Universidad Centroamericana UCA | Identification of efficiency measures in 10 public hospitals. | 13:56 | 2012-07-12
IP $E$27 | Identificacion de medidas de eficiencia en 10 hospitales publicos. | Identification of efficiency measures in 9 committees of energy efficiency, in mutual cooperation with the Universidad Centroamericana UCA | 13:57 | 2012-07-12
IP $E$31 | Se ha iniciado el diseño de un sistema de informacion en linea que ayudara a todas las instituciones en la evaluacion y monitoreo de las medidas de EE implementadas | Started the design of a system of information online that will help all institutions in the assessment and monitoring of the implemented energy efficiency measures | 14:02 | 2012-07-12
IP $E$32 | se han publicado 5,000 ejemplares sobre los proyectos pilotos desarrollados, asi como manueles de recomendaciones sobre el uso eficiente de la energia, donde se difunden las lecciones aprendidas sobre el tema | Pilots developed, as well as manual of recommendations on efficient use of energy, which are disseminated lessons learned on the subject have been published 5,000 copies on projects. | 14:03 | 2012-07-12
IPRating $G$27 | Empty Cell | Es importante señalar que como todo proyecto el inicio requiere de contar con las condiciones mínimas de operación, entre lo que se puede mencionar tener contratado al personal operativo y de dirección, dotación de muebles y equipos de oficina al personal contratado, así mismo este personal debe conocer mínimamente los procedimiento que se utilizaran para la adquisición y contratación de bienes y servicios, para el caso del proyectos EEPB-75672 todo lo anterior se dio en un plazo aproximado de seis meses, además fue necesario elaborar los términos de referencia de las consultorías que se implementarían en el primer año de ejecución e iniciar la búsqueda de empresas y consultores individuales que estuvieran interesados en participar en los procesos de solicitud de propuesta, es importante mencionar que no todas las consultorías tuvieron expresiones de interés, aun a pesar que se hicieron publicaciones en medios virtuales e impresos. Todo lo antes descrito obligó a que varias de las consultorías programadas para el año 2011, se programaran para iniciar en el 2012 ya que sus correspondientes contratos fueron firmados al inicio del presente año. El inicio de la consultoría para el establecimiento de la línea base del consumo de energía en el sector de gobierno ha requerido la búsqueda de información energética de todas las instituciones de gobierno, la cual se ha podido conseguir mediante la base de datos de las distribuidoras, pero esta base de datos no tiene un identificador especifico para el gobierno, por lo que la empresa contratada debió hacer una búsqueda exhaustiva del consumo de energía para mas de 7,000 edificios del gobierno, luego nos hemos dado a la tarea de visitar algunas de ellas para complementar la información obtenida de la base de datos, actualmente en esta consultoría estamos por seleccionar una muestra representativa de los edificios identificados para levantar información que servirá para la caracterización del consumo energético en los diferentes ramos del gobierno. De igual forma se ha iniciado la consultoría para establecer la cartera de proyectos pilotos que se desarrollarán en 10 hospitales de la red nacional de salud, para ello luego de tener contratada la empresa que desarrollará las auditorías energéticas a los hospitales mencionados, se han realizado una serie de reuniones de coordinación con el ministerio de salud y los directores de los hospitales seleccionados, actualmente estamos revisando las medidas reflejadas en 4 de los estudios energéticos presentados por la empresa consultora, con lo que pretendemos iniciar de inmediato las mejores medidas que se recomienden, lo cual haremos en consenso con el ministerio de salud. Es importante señalar que estas dos consultoría han presentado ya su primer informe, pero actualmente están superando las observaciones que se les han señalado, para poder iniciar el proceso de pago. La contratación de los servicios de consultoría para elaborar una metodología para la evaluación del desempeño energético de los edificios, necesito mas del tiempo considerado, esto debido a que luego de 3 publicaciones de solicitud de expresiones de interés, no se tuviera los suficientes profesionales para conformar una lista corta para iniciar el proceso de contratación, por lo que se decidió utilizar la estrategia de búsqueda en gremiales empresariales y profesionales a nivel nacional e internacional, lo cual nos permitió iniciar el proceso de contratación y finalizarlo, a la fecha esta consultoría ha iniciado junto con otra que formulará una normativa sobre compras estatales con criterio de eficiencia energética. En términos generales puede mencionarse que el presupuesto programado para el año 2012 esta siendo ejecutado como lo programado, salvo los atrasos en el pago de las dos consultorías que están viendo los temas de la línea base de consumo y la identificación de proyectos pilotos en hospitales, los cuales ya han presentado sus informes para su correspondiente revisión y aprobación. | 14:06 | 2012-07-12
IPRating $G$27 | Es importante señalar que como todo proyecto el inicio requiere de contar con las condiciones mínimas de operación, entre lo que se puede mencionar tener contratado al personal operativo y de dirección, dotación de muebles y equipos de oficina al personal contratado, así mismo este personal debe conocer mínimamente los procedimiento que se utilizaran para la adquisición y contratación de bienes y servicios, para el caso del proyectos EEPB-75672 todo lo anterior se dio en un plazo aproximado de seis meses, además fue necesario elaborar los términos de referencia de las consultorías que se implementarían en el primer año de ejecución e iniciar la búsqueda de empresas y consultores individuales que estuvieran interesados en participar en los procesos de solicitud de propuesta, es importante mencionar que no todas las consultorías tuvieron expresiones de interés, aun a pesar que se hicieron publicaciones en medios virtuales e impresos. Todo lo antes descrito obligó a que varias de las consultorías programadas para el año 2011, se programaran para iniciar en el 2012 ya que sus correspondientes contratos fueron firmados al inicio del presente año. El inicio de la consultoría para el establecimiento de la línea base del consumo de energía en el sector de gobierno ha requerido la búsqueda de información energética de todas las instituciones de gobierno, la cual se ha podido conseguir mediante la base de datos de las distribuidoras, pero esta base de datos no tiene un identificador especifico para el gobierno, por lo que la empresa contratada debió hacer una búsqueda exhaustiva del consumo de energía para mas de 7,000 edificios del gobierno, luego nos hemos dado a la tarea de visitar algunas de ellas para complementar la información obtenida de la base de datos, actualmente en esta consultoría estamos por seleccionar una muestra representativa de los edificios identificados para levantar información que servirá para la caracterización del consumo energético en los diferentes ramos del gobierno. De igual forma se ha iniciado la consultoría para establecer la cartera de proyectos pilotos que se desarrollarán en 10 hospitales de la red nacional de salud, para ello luego de tener contratada la empresa que desarrollará las auditorías energéticas a los hospitales mencionados, se han realizado una serie de reuniones de coordinación con el ministerio de salud y los directores de los hospitales seleccionados, actualmente estamos revisando las medidas reflejadas en 4 de los estudios energéticos presentados por la empresa consultora, con lo que pretendemos iniciar de inmediato las mejores medidas que se recomienden, lo cual haremos en consenso con el ministerio de salud. Es importante señalar que estas dos consultoría han presentado ya su primer informe, pero actualmente están superando las observaciones que se les han señalado, para poder iniciar el proceso de pago. La contratación de los servicios de consultoría para elaborar una metodología para la evaluación del desempeño energético de los edificios, necesito mas del tiempo considerado, esto debido a que luego de 3 publicaciones de solicitud de expresiones de interés, no se tuviera los suficientes profesionales para conformar una lista corta para iniciar el proceso de contratación, por lo que se decidió utilizar la estrategia de búsqueda en gremiales empresariales y profesionales a nivel nacional e internacional, lo cual nos permitió iniciar el proceso de contratación y finalizarlo, a la fecha esta consultoría ha iniciado junto con otra que formulará una normativa sobre compras estatales con criterio de eficiencia energética. En términos generales puede mencionarse que el presupuesto programado para el año 2012 esta siendo ejecutado como lo programado, salvo los atrasos en el pago de las dos consultorías que están viendo los temas de la línea base de consumo y la identificación de proyectos pilotos en hospitales, los cuales ya han presentado sus informes para su correspondiente revisión y aprobación. | It is important to note that as all the home project requires having the minimum conditions of operation, among which we can mention have contracted to the operating personnel and management, provision of furniture and equipment Office to staff recruited, likewise this staff must know minimally procedure to be used for the acquisition and procurement of goods and services, in the case of the EEPB-75672 all projects the above occurred in a period of approximately six months, was also necessary to draw up the terms of reference of consultants that would implement in the first year of implementation and start the search of companies and individual consultants who were interested in participating in request for proposal processes, it is important to mention that not all the consultancies had expressions of interest even though that virtual and print media publications made. Previously described forced several scheduled for 2011, consultancies are rescheduling to start in 2012, since their corresponding contracts were signed at the beginning of this year. The beginning of the consultancy for the establishment of the base line of the consumption of energy in the Government sector has required the search for energy information of all the institutions of Government, which has been able to get through the database of distributors, but this database does not have an identifier specific to the Government the contracted company should do an exhaustive search of the consumption of energy for more than 7,000 government buildings, then we have given the task of visiting some of them to complement the information obtained from the database, currently in this consultancy we are for selecting a representative sample of the identified buildings to raise information that will be used for the characterization of energy consumption in the different branches of the Government. Similarly Consulting has initiated to establish portfolio of pilot projects to be developed in 10 hospitals in the national network of health, so after having contracted the company that will develop energy audits to hospitals mentioned above, a series of coordination meetings with the Ministry of health and the directors of selected hospitals has been made we are currently reviewing the measures reflected in the energy studies submitted by the consulting company, 4 with what we intend to immediately start the best measures that are recommended, which we will do in consensus with the Ministry of health; It is important to note that these two consulting have already submitted its first report, but they are currently exceeding observations which have appointed them, in order to begin the payment process. The recruitment of consulting services to develop a methodology for the evaluation of the energy performance of buildings, need more time considered, this because after 3 publications request for expressions of interest, not take sufficient professionals to form a short list to start the recruitment process, so it was decided to use the search strategy in business and professional associations at the national and international levels which allowed us to start the recruitment process and finish it, to date this consultancy has initiated along with another which may make a regulation on State procurement with energy efficiency criteria. In general terms it may be mentioned that the programmed budget for year 2012 this running pilots in hospitals, which have already submitted their reports to their corresponding review and approval as scheduled, except the arrears in the payment of two consultancies that are seeing topics of line consumption base and the identification of projects. | 14:07 | 2012-07-12
Adjustments $F$44 | El CNE ha propiciado la creacion de instrumentos legales como el decreto ejecutivo 78 del año 2012, en el cual se exige la organización de los comites de eficiencia energetica, esto ayudara a que las instituciones apoyen todas aquellas medidas que se desarrollen en el tema de eficiencia energetica | The CNE has led to the creation of legal instruments as the Executive Decree 78 of the year 2012, in which requires the Organization of committees for energy efficiency; this will help institutions to promote energy efficiency measures that produce savings. | 14:13 | 2012-07-12
Adjustments $F$45 | Se ha trabajado de forma muy coordinada con el Ministerio de Salud Publica con el objetivo que los proyectos pilotos de los hospitales tengan los mejores resultados. | worked in a very coordinated manner with the Ministry of public health, with the aim that the hospitals pilot projects have the best results. | 14:14 | 2012-07-12
Finance $E$19 | los pagos mas significativos son los que se realizaran a las primeras 4 consultorias contratadas alas fechas, las cuales a la fecha ninguna ha recibido pago alguno, solo dos de ellas estan proximas a recibir su primer pago que corresponde al 20% de la suma contratada | most significant payments are to be undertaken in the first 4 consulting contract to date, which to date has received no payment, only two of them are coming soon receive your first payment represents 20% of the amount contracted | 14:16 | 2012-07-12
Finance $E$26 | Esta contrapartida incluye, el aporte dado en especies por el CNE, UCA,GIZ e inversiones realizadas en el tema de eficiencia energetica por algunas instituciones de gobierno. | This contribution includes the support given in kind by the CNE, UCA, GIZ and investments in the issue of energy efficiency by some government institutions. | 14:16 | 2012-07-12
Communications and KM $D$16 | El proyecto ha desarrollado ampliamente las capacidades técnicas de las instituciones gubernamentales, lo cual les permitirá gestionar de mejor manera el consumo de energía, en este proceso se han visto beneficiadas mas de 90 instituciones y han sido capacitados mas de 200 funcionarios, los cuales están trabajando en la identificación de medidas y en la búsqueda de recursos para su implementación, de igual forma se está trabajando en la identificación de medidas de EE en al menos 10 hospitales públicos en los cuales se estarán desarrollando una serie de proyectos pilotos, los cuales producirán ahorros en el consumo de energía, los cuales se traducirán en beneficios económicos y ambientales para dichos hospitales, estos ahorros podrán ser de mucha utilidad para impulsar otras acciones o prioridades de estas instituciones. Se ha iniciado la elaboración de un manual de compras para la adquisición de equipos energéticos de alta eficiencia, lo cual traerá beneficios económicos al estado los cuales podrá reorientar para atender otras necesidades prioritarias. | The project has developed the technical capacities of government institutions, allowing them to manage better the consumption of energy in this process have benefited more than 90 institutions and have been trained over 200 staff members, which are working on the identification of measures and the search for resources for its implementation, in the same way is working on the identification of measures of energy efficiency in at least 10 public hospitals in which a number of projects will be developing pilots which will result in savings in energy consumption, which will be translated in to such hospitals, environmental and economic benefits these savings may be very useful to drive other actions or priorities of these institutions. Started the development of a manual of purchases for the acquisition of energy efficient equipment, which will bring economic benefits to the State which may redirect to other priority needs. | 14:20 | 2012-07-12
Communications and KM $D$20 | Una de las dificultades principales enfrentadas por este proyecto es el desarrollo de las capacidades técnicas en eficiencia energética de un conjunto enorme de instituciones gubernamentales, pues estos demandan de mucho tiempo para que se les oriente en la forma mas adecuada de gestionar el uso óptimo de la energía, durante gran parte de este año se invirtió mucho tiempo en dar el apoyo técnico a los Comités de Eficiencia Energética COEE´s y en el desarrollo de estudios energético para ellos mismos, lo que obligo enfocarse por mucho tiempo en esta iniciativa, afortunadamente el CNE hizo la contratación de una persona exclusivamente para dar apoyo a todas las instituciones que han conformado sus COEE´s, lo que ha permitido al proyecto ver otras prioridades en la ejecución de presente proyecto. | One of the main difficulties faced by this project is the development of technical capacities in energy efficiency of a huge set of governmental institutions, since these require long to make point them in the form most suitable for managing the optimal use of energy, for much of this year it invested long time to give technical support to committees of COEE´s energy efficiency and the energy studies development for themselves, which forced focus for a long time in this initiative, fortunately the CNE made the hiring of a person exclusively to provide support to all the institutions that have shaped their COEE´s, which allowed the project to see other priorities in the implementation of this project. | 14:22 | 2012-07-12
Communications and KM $D$24 | Dado la complejidad en la obtención de la información energética para establecer los ahorros y disminución de emisiones de GEI, hemos determinado que la mejor forma para contabilizar los ahorros es a través de la base de datos de las distribuidoras de energía, para lo cual únicamente necesitamos el Numero de Identificación de Servicio (NIS) de la institución, con ello buscamos la información energética y comparamos con la línea base y con ello establecemos los ahorros correspondientes en un periodo determinado. La organización de pequeños comités de eficiencia energética en las instituciones del gobierno, son claves para impulsar el tema de eficiencia energética y sobre todo para darle sostenibilidad y seguimiento a las medidas desarrolladas, es por ello que se ha impulsado la creación de comités de EE en todas las instituciones del Gobierno Ejecutivo, con lo que se pretende generar ahorros en el consumo de energía. Las medidas de eficiencia energética en los sistemas de iluminación de edificios de oficinas públicas nos ha permitido establecer que en su mayoría causarán ahorros de más del 50% del consumo total de iluminación, mientras que el recambio de gas refrigerante en sistemas de aire acondicionado producirán ahorros de entre 15 y 20%. | Given the complexity in obtaining the energy information to establish savings and reduction of GHG emissions, have determined that the best way to post the savings is through the database of the distributors of energy, for which we only need the number identification service (NIS) of the institution, thus we seek the energy information and compare it with the line basis and thereby establish the corresponding savings in a period determined. The Organization of small committees of energy efficiency in the Government institutions, are key to driving the issue of energy efficiency and above all to ensure sustainability and follow-up measures developed, so it is that has driven the creation of committees of energy efficiency in all the institutions of the Executive Government, which aims to generate savings in energy consumption. The energy efficiency measures in public office buildings lighting systems have enabled us to establish that they will mostly cause savings of more than 50% of the total of lighting, while the replacement of refrigerant in air conditioning systems will produce savings of between 15 and 20%. | 14:25 | 2012-07-12
Gender $E$20 | Empty Cell | Each of the activities undertaken by this project has been an active participation of women, for example, we can mention that there are five women, in the same way in the process of training and integration of energy efficiency committees in the Diploma given to the specialization of professionals on the subject of energy efficiency there were forty women and they are now actively involved in the implementation of energy efficiency measures, this through committees of energy efficiency. | 14:28 | 2012-07-12
DO $J$84 | luego de haber finalizado el recambio de 274 luminarias entre la Defensoria del Consumidor y el Ministerio de Medio Ambiente y de haber sistematizado las mejores recomendaciones en cuanto a medidas de conservacion de energia, se procedio a publicar las lecciones aprendidas en 5,000 ejemplares de manuales de recomendaciones para el sector gubernamental y tripticos sobre los resultados de los proyectos pilotos de iluminacion eficiente. | after having completed the replacement of 274 luminaries from the Consumer Ombudsman and the Ministry of Environment and have systematized the best recommendations for energy conservation measures, we proceeded to publish the lessons learned in 5,000 copies of manuals recommendations for the government sector and triptychs on the results of the pilot projects for efficient lighting. | 14:30 | 2012-07-12
DORating $G$27 | In the first year of implementation of the project of energy efficiency in public buildings EEPB-75672 has been achieved to promote measures that impact on the environmental objectives laid down in the above-mentioned project, first of all are generating legal and technical instruments such as the law on energy efficiency, standards of acquisition with criteria of efficiency and the establishment of baseline consumption of the Government sector, this last will serve as an input to develop a strategy or national plan for savings in energy consumption, likewise is is working on strengthening technical capacities on U.S. State institutions this through train energy efficiency committees and train professionals of these committees on topics very specific and specialized in (EE)the strengthening of the technical capabilities also consists in proportional computing tools to enable these committees to perform an analysis of the energy performance of their buildings and establish the best indicators for this, as well as having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). Along with the strengthening of the technical capacities of government institutions, the EEPB project will develop pilot projects in coordination with the Ministry of health and other institutions for a total amount of approximately US $ 150,000, with the objective that such projects can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures for us and with the support of technical and legal standards that are being developed, achieve a sensitive decrease of energy consumption, which could be around 20% according to preliminary estimates. As to the difficulties encountered in achieving the project's objectives, we can mention that Government struggles to allocate financial resources to the institutions that serve for the implementation of energy efficiency projects, however, the proposed strategy to overcome this obstacle has been proposing to committees of energy efficiency to initiate low-cost measures in its implementation and that can develop through stages, that investments are staggered, also driven measures are which have better Pay-back, since this will allow a speedy recovery of the investment for this developing other measures identified, another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector, this is due to the issue of construction is the responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and London, which makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction instrument, therefore is working to unify the technical through a query criteria to all the sectors and institutions involved in the topic construction. | In the first year of implementation of the project of energy efficiency in public buildings EEPB-75672 has been achieved to promote measures that impact on the environmental objectives laid down in the above-mentioned project, first of all are generating legal and technical instruments such as the law on energy efficiency, standards of acquisition with criteria of efficiency and the establishment of baseline consumption of the Government sector, this last will serve as an input to develop a strategy or national plan for savings in energy consumption, likewise is is working on strengthening technical capacities on U.S. State institutions this through train energy efficiency committees and train professionals of these committees on topics very specific and specialized in (EE) the strengthening of the technical capabilities also consists in proportional computing tools to enable these committees to perform an analysis of the energy performance of their buildings and establish the best indicators for this, as well as having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). Along with the strengthening of the technical capacities of government institutions, the EEPB project will develop pilot projects in coordination with the Ministry of health and other institutions for a total amount of approximately US $ 150,000, with the objective that such projects can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures for us and with the support of technical and legal standards that are being developed, achieve a sensitive decrease of energy consumption, which could be around 20% according to preliminary estimates. As to the difficulties encountered in achieving the project's objectives, we can mention that Government struggles to allocate financial resources to the institutions that serve for the implementation of energy efficiency projects, however, the proposed strategy to overcome this obstacle has been proposing to committees of energy efficiency to initiate low-cost measures in its implementation and that can develop through stages, that investments are staggered, also driven measures are which have better Pay-back, since this will allow a speedy recovery of the investment for this developing other measures identified, another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector, this is due to the issue of construction is the responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and London, which makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction instrument, therefore is working to unify the technical through a query criteria to all the sectors and institutions involved in the topic construction. | 14:34 | 2012-07-12
DO $J$52 | The consulting for the analysis of energetic performance of buildings has already started and will deliver a software that enable the Government institutions to model the energy consumption of its buildings. Also it will model the characteristics of the buildings such as walls, ceilings, windows and any other thermal insulation. The project will use this platform in the design of new public buildings and also will help for all new construction. | The consulting for the analysis of energetic performance of buildings has already started and will deliver a software that will enable the Government institutions to model the energy consumption of its buildings. Also it will model the characteristics of the buildings such as walls, ceilings, windows and any other thermal insulation. The project will use this platform in the design of new public buildings and also will help for all new construction. | 16:28 | 2012-08-15
DO $J$55 | The project has orginized 4 inception workshops for the EE Comitees, with the participation of 189 persons from 90 institutions. It is important to mention that the 24% were women. For the hospital sector, it was organized a special workshop with the participation of 24 staff members from the 10 hospitals elected for implementation. The project also organized a Diploma in EE in Buildings for the technical strenghtening of EE Commitees with the participation of 30 profesionals from 22 public institutions. The Diploma will last for 6 months and it was organized with the colaboration of Universidad Centroamericana, UCA. Besides, the project is supporting the new legal framework in energy efficiency, therefore it organized two workshops with the Presidential House and Secretariat of Legislative Affairs to discuss the Draft of EE Law and many other informal meetings to diffuse its content. | The project has organized 4 inception workshops for the EE Commitees, with the participation of 189 partipants from 90 institutions. It is important to mention that 24% were women. For the hospital sector, it was organized a special workshop with the participation of 24 staff members from the 10 hospitals elected for implementation. The project also organized a Diploma in EE in Buildings for the technical strenghtening of EE Commitees with the participation of 30 profesionals from 22 public institutions. The Diploma will last for 6 months and it was organized with the colaboration of Universidad Centroamericana, UCA. Besides, the project is supporting the new legal framework in energy efficiency, therefore it organized two workshops with the Presidential House and Secretariat of Legislative Affairs to discuss the Draft of EE Law and many other informal meetings to diffuse its content. | 16:30 | 2012-08-15
DO $J$70 | The CNE has created a strategy to develop a national investment plan in energy efficiency. This strategy will strengthen the institutional capacities on EE issues leading them to be organized and be able to manage themselves (with the support of the CNE) its own plan of action and goals. The Energy Efficiency Commitees are the responsables of propose, implement and monitoring the EE mesures in each institution. The project has achieved the target of establish 16 EE Commitees in public institutios and many of them are already implementing and following up the measures established. As part of the $2mln counterpart of investment, institutions has already implemented $155,018.95 in EE actions.Because of the success of this process and as a result of the Austerity Decree issued by te Executive Organ, 75 additional institutions of the Government established their EE Committees. These new Commitees are supervised by the project who has provided them tools to accomplish the content of the Decree. Among the institutions that have reported their EE measures are: Ministry of Finance, Ministry of Environment and Natural Resources, the Consumer Ombudsman's Office, Ministry of Health, Superintendency of Electricity and Telecommunications (SIGET), Ministry of Economy and Social Investment Fund for Local Development (FISDL). | The CNE has created a strategy to develop a national investment plan in energy efficiency. This strategy will strengthen the institutional capacities on EE issues leading them to be organized and be able to manage themselves (with the support of the CNE) its own plan of action and goals. The Energy Efficiency Commitees are the responsibles of propose, implement and monitoring the EE mesures in each institution. The project has achieved the target of establish 16 EE Commitees in public institutios and many of them are already implementing and following up the measures established. As part of the $2mln counterpart of investment, institutions has already implemented $155,018.95 in EE actions.Because of the success of this process and as a result of the Austerity Decree issued by te Executive Organ, 75 additional institutions of the Government established their EE Committees. These new Commitees are supervised by the project who has provided them tools to accomplish the content of the Decree. Among the institutions that have reported their EE measures are: Ministry of Finance, Ministry of Environment and Natural Resources, the Consumer Ombudsman's Office, Ministry of Health, Superintendency of Electricity and Telecommunications (SIGET), Ministry of Economy and Social Investment Fund for Local Development (FISDL). | 16:34 | 2012-08-15
DO $J$70 | The CNE has created a strategy to develop a national investment plan in energy efficiency. This strategy will strengthen the institutional capacities on EE issues leading them to be organized and be able to manage themselves (with the support of the CNE) its own plan of action and goals. The Energy Efficiency Commitees are the responsibles of propose, implement and monitoring the EE mesures in each institution. The project has achieved the target of establish 16 EE Commitees in public institutios and many of them are already implementing and following up the measures established. As part of the $2mln counterpart of investment, institutions has already implemented $155,018.95 in EE actions.Because of the success of this process and as a result of the Austerity Decree issued by te Executive Organ, 75 additional institutions of the Government established their EE Committees. These new Commitees are supervised by the project who has provided them tools to accomplish the content of the Decree. Among the institutions that have reported their EE measures are: Ministry of Finance, Ministry of Environment and Natural Resources, the Consumer Ombudsman's Office, Ministry of Health, Superintendency of Electricity and Telecommunications (SIGET), Ministry of Economy and Social Investment Fund for Local Development (FISDL). |  | 16:34 | 2012-08-15
DO $J$70 |  | Same target as reported in line 19 | 16:34 | 2012-08-15
DO $J$16 | Actually the National Energy Council (CNE, for its acronym in Spanish) has a National Energy Policy and a draft of the Law of National Energy Efficiency. The project has promoted the approval and diffussion of this legal instruments by making lobbying in 2 workshops with the Presidential House and the Secretariat of Legislative Affairs and many informal meetings to difusse this legal framework. It´s expected that the draft Law will be approved by the end of this year by the Legislative Assembly. | Actually the National Energy Council (CNE, for its acronym in Spanish) has a National Energy Policy and a draft of the Law of National Energy Efficiency. The project has promoted the approval and diffussion of this legal instruments by making lobbying in 2 workshops with the Presidential House and the Secretariat of Legislative Affairs and many informal meetings to difuse this legal framework. It´s expected that the draft Law will be approved by the end of this year by the Legislative Assembly. | 14:28 | 2012-08-27
IPRating $G$34 | I agree with the rating of S because the project has achieved very important results until now, and has a good perspective in the financial delivery for 2012. It is very important to point out that in the beginning the project had some delay to start, and this delay, impacted the delivery for this reporting period, but with the actual trend, the lag will be overcomed in 2012.The project has managed the resources in a very effective and efficient way because it has been able to manage, training, monitor, follow and support 90 EE Committees (COEE) in different developmental stages despite the target of the project was the establishment of 16 COEEs. The project responded (using the allocated budget) to an appeal of the Salvadoran Government with the Executive Decree of Austerity and Savings which established as mandatory the energy conservation in public sector. It is also important to mention that the project has systematized the methodology for the creation of COEEs for future replication in other sectors. Another issue that delayed the implementation was the lack of information the project had to overcome for the establishment of strategies and targets in energy efficiency. For example in El Salvador there wasn´t an inventory of public buildings and an inventory of the electric services contracts that the Government has, also there wasn´t a baseline of the consumption of de public sector and now, with the project these information will be available this year. The energy audits made in 6 hospitals (until now) detected many EE measures and huge potencial savings for the Ministry of Health. The recommendations made by the project will allow this Ministry to define an EE investment plan with a clear projection of savings and diminution of GHG. The project EEPB in this period of time had contributed to remove barriers to energy efficiency with technical trainings, studies, information, advice on technical issues, support to legal framework, establishment of 90 COEEs in public institutions, implementation and monitoring of EE measures in some institutions and investment plan in EE for another, and diffusion and publication of lessons learned. Financially, for this year the project will spend more than $440,000 because it already has commitments for more than $278000 to be payed (consultancies, EE Diploma)before october. The implementation of EE measures are budget this year and represent more than $75000. | I agree with the rating of S because the project has achieved very important results until now, and has a good perspective in the financial delivery for 2012. It is very important to point out that in the beginning the project had some delay to start, and this delay, impacted the delivery for this reporting period, but with the actual trend, the lag will be overcomed in 2012.The project has managed the resources in a very effective and efficient way because it has been able to manage, training, monitor, follow and support 90 EE Committees (COEE) in different developmental stages despite the target of the project was the establishment of 16 COEEs. The project responded (using the allocated budget) to an appeal of the Salvadoran Government with the Executive Decree of Austerity and Savings which established as mandatory the energy conservation in public sector. It is also important to mention that the project has systematized the methodology for the creation of COEEs for future replication in other sectors. Another issue that delayed the implementation was the lack of information the project had to overcome for the establishment of strategies and targets in energy efficiency. For example in El Salvador there wasn´t an inventory of public buildings and an inventory of the electric services contracts that the Government has, also there wasn´t a baseline of the consumption of de public sector and now, with the project these information will be available this year. The energy audits made in 6 hospitals (until now) detected many EE measures and huge potencial savings for the Ministry of Health. The recommendations made by the project will allow this Ministry to define an EE investment plan with a clear projection of savings and diminution of GHG. The project EEPB in this period of time had contributed to remove barriers to energy efficiency with technical trainings, studies, information, advice on technical issues, support to legal framework, establishment of 90 COEEs in public institutions, implementation and monitoring of EE measures in some institutions and investment plan in EE for another, and diffusion and publication of lessons learned. Financially, by the end of 2012, the project will be in line with its budget, because it already has commitments for more than $278000 to be payed (consultancies, EE Diploma)before October. The implementation of EE measures are budget this year and represent more than $75000. | 14:32 | 2012-08-27
BasicData $F$55 | Empty Cell | July 2013 – June 2014 | 10:12 | 2012-09-03
RTA $C$52 | Empty Cell | Raul Alfaro Pelico | 10:13 | 2012-09-03
RTA $C$53 | Empty Cell | raul.alfaro@undp.org | 10:13 | 2012-09-03
DORating $G$27 | During this period, the project of energy efficiency in public buildings EEPB-75672 has promoted EE measures that impact direct and indirectly on the environmental objectives. Accomplishing the Energy Efficiency targets in the Governmental sector (13% of total energy consumption in El Salvador) will reduce significantly the GHG. The contribution of the project to reach this target in this period is: (i) the support and diffusion of legal instruments such as the Bill of Law on Energy Efficiency and the National Energy Policy, (ii) the elaboration of a Procurement Manual with Energy Efficiency Criteria for Government Sector, (iii) the establishment of baseline of energy consumption for the public sector that will serve as an input to develop a strategy of national plan for savings in energy consumption (iv) the energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement, (v) the establishment of 90 new COEEs, although the target for this year was 16 COEEs, but in response to the Executive Decree #78 of Austerity and Savings, the project helped 75 public institutions in the establishment of their COEEs (vi) the strengthening of technical capacities of institutions with training the energy efficiency committees through workshops, meetings and a Diploma in EE in Buildings to train professionals of these committees on very specific topics on EE. (vii) the diminution in energy consumption in Consumer Ombudsman´s Office (10%) and Ministry of Environment and Natural Resources (20%) through the replacement of lamps for more efficient technology. Also the project is already developing computational tools to enable the committees to perform their analysis of the energy performance of their buildings, establish the best energetic indicators and having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). The next immediate step for the EEPB project is the development of pilot projects in coordination with the Ministry of Health and other institutions for a total amount of approximately USD $ 150,000. The results of the implementation can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures with the support of technical and legal standards that are being developed, achieve an important decrease of energy consumption, which could be around 20% according to preliminary estimates. Tthe risks encountered in achieving the project's objectives are about the Government capacity to fund all the energy efficiency measures, however, the proposed strategy to overcome this obstacle has been proposing to COEEs to start with low-cost measures in its implementation and that can develop through stages. The investments are implemented by cost and by the better Pay-back, since this will allow a fast recovery of the investment for developing other measures identified. Another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector. The difficulty is due to the construction sector is responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and Office of Planning of the Metropolitan Area of San Salvador (OPAMSS). This situation makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction. Therefore the project is working to unify the technical criteria with the consultancy of all the sectors and institutions involved in this topic. | During this period, the project of energy efficiency in public buildings EEPB-75672 has promoted EE measures that impact direct and indirectly on the environmental objectives. Accomplishing the Energy Efficiency targets in the Governmental sector (13% of total energy consumption in El Salvador) will reduce significantly the GHG. The contribution of the project to reach this target in this period is: (i) the support and diffusion of legal instruments such as the Bill of Law on Energy Efficiency and the National Energy Policy, (ii) the elaboration of a Procurement Manual with Energy Efficiency Criteria for Government Sector, (iii) the establishment of baseline of energy consumption for the public sector that will serve as an input to develop a strategy of national plan for savings in energy consumption (iv) the energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement, (v) the establishment of 90 new COEEs, although the target for this year was 16 COEEs, but in response to the Executive Decree #78 of Austerity and Savings, the project helped 75 public institutions in the establishment of their COEEs (vi) the strengthening of technical capacities of institutions with training the energy efficiency committees through workshops, meetings and a Diploma in EE in Buildings to train professionals of these committees on very specific topics on EE. (vii) the diminution in energy consumption in Consumer Ombudsman´s Office (10%) and Ministry of Environment and Natural Resources (20%) through the replacement of lamps for more efficient technology. Also the project is already developing computational tools to enable the committees to perform their analysis of the energy performance of their buildings, establish the best energetic indicators and having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). The next immediate step for the EEPB project is the development of pilot projects in coordination with the Ministry of Health and other institutions for a total amount of approximately USD $ 150,000. The results of the implementation can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures with the support of technical and legal standards that are being developed, achieve an important decrease of energy consumption, which could be around 20% according to preliminary estimates. Tthe risks encountered in achieving the project's objectives are about the Government capacity to fund all the energy efficiency measures, however, the proposed strategy to overcome this obstacle has been proposing to COEEs to start with low-cost measures in its implementation and that can develop through stages. The investments are implemented by cost and by the better Pay-back, since this will allow a fast recovery of the investment for developing other measures identified. Another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector. The difficulty is due to the construction sector is responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and Office of Planning of the Metropolitan Area of San Salvador (OPAMSS). This situation makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction. Therefore the project is working to unify the technical criteria with the consultancy of all the sectors and institutions involved in this topic. | 10:13 | 2012-09-03
DORating $G$34 | I agree with the Project Coordinator with a rating of Satisfactory because I think the project has had results of impact during this period. This project has strong challenges trying to remove barriers to energy efficiency in El Salvador. The first and very important contribution of this project is the strengthening of capacities of National Energy Council (CNE, for its acronym in Spanish) specifically the Energy Efficiency Unit which is responsible for the EE promotion in the country. Until now, the project has significant results and it´s having an impact at several levels: (A) National level, supporting and diffusing the new regulatory framework for El Salvador with the National Energy Policy and the Bill of Energy Efficiency Law which is in review in Presidential House. Another output is the establishment of baseline of energy consumption for the public sector that also will serve as an input to develop a strategy of national plan for savings in energy consumption (B) Government level, (i) Establishment of Energy Efficiency committees (COEEs) inside of more than 90 public institutions; (ii) training the COEEs members with workshops, meetings and a Diploma in EE in buildings (iii) monitoring the formulation and implementation of Energy Efficiency Plans, like the experiences of Consumer Ombudsman´s Office (10% reduction in energy consumption) and Ministry of Environment and Natural Resources (20% reduction in energy consumption); (iv) energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement; (v) Developing a Purchasing Manual with EE criteria ; (C) Environmental level, because the project has already reported Tonnes of CO2 avoided and with the EE plans completed and implemented, more GHG will be avoided. The National Energy Council (CNE, for its acronym in Spanish) and the Ministry of Economy supported its strategy of National Energy Efficiency in the outcomes of the project and also the President of El Salvador launched an Austerity and Saving Decree for public sector supported in the actions of EEPB project. The project is developing a Procurement Manual with Energy Efficiency Criteria, for the Government Sector, that will be a standard for the Procurement Units for all the public institutions. During this period, the project had to overcome difficulties like the lack of information about the inventory of public buildings (more than 6500 buildings), the absence of a baseline in the energy consumption of the government sector, the gap in the regulatory framework, changes in the entity responsible for the regulating standards and the poor technical knowledge of institution members about energy issues. Some problems are already solved, and at the end of 2012 most of them will be overcome with the resulting outputs. It is very important to mention that especially the lack of information delayed the execution of the consultancies and the start of implementation actions. These delays will be overtaken in the next months. Another very important contribution of this project is the design of two computing tools for monitoring automatically the energy consumption of the buildings of each institution. This tool enables to make the analysis and record the impact of implemented actions in EE. The other one is the software to evaluate the energetic performance of a building. This software will be useful not only in public sector, but in the future national regulatory framework for the building construction in the country. | I agree with the Project Coordinator with a rating of Satisfactory because I think the project has had results of impact during this period. This project has strong challenges trying to remove barriers to energy efficiency in El Salvador. The first and very important contribution of this project is the strengthening of capacities of National Energy Council (CNE, for its acronym in Spanish) specifically the Energy Efficiency Unit which is responsible for the EE promotion in the country. Until now, the project has significant results and it´s having an impact at several levels: (A) National level, supporting and diffusing the new regulatory framework for El Salvador with the National Energy Policy and the Bill of Energy Efficiency Law which is in review in Presidential House. Another output is the establishment of baseline of energy consumption for the public sector that also will serve as an input to develop a strategy of national plan for savings in energy consumption (B) Government level, (i) Establishment of Energy Efficiency committees (COEEs) inside of more than 90 public institutions; (ii) training the COEEs members with workshops, meetings and a Diploma in EE in buildings (iii) monitoring the formulation and implementation of Energy Efficiency Plans, like the experiences of Consumer Ombudsman´s Office (10% reduction in energy consumption) and Ministry of Environment and Natural Resources (20% reduction in energy consumption); (iv) energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement; (v) Developing a Purchasing Manual with EE criteria ; (C) Environmental level, because the project has already reported Tonnes of CO2 avoided and with the EE plans completed and implemented, more GHG will be avoided. The National Energy Council (CNE, for its acronym in Spanish) and the Ministry of Economy supported its strategy of National Energy Efficiency in the outcomes of the project and also the President of El Salvador launched an Austerity and Saving Decree for public sector supported in the actions of EEPB project. The project is developing a Procurement Manual with Energy Efficiency Criteria, for the Government Sector, that will be a standard for the Procurement Units for all the public institutions. During this period, the project had to overcome difficulties like the lack of information about the inventory of public buildings (more than 6500 buildings), the absence of a baseline in the energy consumption of the government sector, the gap in the regulatory framework, changes in the entity responsible for the regulating standards and the poor technical knowledge of institution members about energy issues. Some problems are already solved, and at the end of 2012 most of them will be overcome with the resulting outputs. It is very important to mention that especially the lack of information delayed the execution of the consultancies and the start of implementation actions. These delays will be overtaken in the next months. Another very important contribution of this project is the design of two computing tools for monitoring automatically the energy consumption of the buildings of each institution. This tool enables to make the analysis and record the impact of implemented actions in EE. The other one is the software to evaluate the energetic performance of a building. This software will be useful not only in public sector, but in the future national regulatory framework for the building construction in the country. | 10:13 | 2012-09-03
DORating $G$27 | During this period, the project of energy efficiency in public buildings EEPB-75672 has promoted EE measures that impact direct and indirectly on the environmental objectives. Accomplishing the Energy Efficiency targets in the Governmental sector (13% of total energy consumption in El Salvador) will reduce significantly the GHG. The contribution of the project to reach this target in this period is: (i) the support and diffusion of legal instruments such as the Bill of Law on Energy Efficiency and the National Energy Policy, (ii) the elaboration of a Procurement Manual with Energy Efficiency Criteria for Government Sector, (iii) the establishment of baseline of energy consumption for the public sector that will serve as an input to develop a strategy of national plan for savings in energy consumption (iv) the energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement, (v) the establishment of 90 new COEEs, although the target for this year was 16 COEEs, but in response to the Executive Decree #78 of Austerity and Savings, the project helped 75 public institutions in the establishment of their COEEs (vi) the strengthening of technical capacities of institutions with training the energy efficiency committees through workshops, meetings and a Diploma in EE in Buildings to train professionals of these committees on very specific topics on EE. (vii) the diminution in energy consumption in Consumer Ombudsman´s Office (10%) and Ministry of Environment and Natural Resources (20%) through the replacement of lamps for more efficient technology. Also the project is already developing computational tools to enable the committees to perform their analysis of the energy performance of their buildings, establish the best energetic indicators and having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). The next immediate step for the EEPB project is the development of pilot projects in coordination with the Ministry of Health and other institutions for a total amount of approximately USD $ 150,000. The results of the implementation can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures with the support of technical and legal standards that are being developed, achieve an important decrease of energy consumption, which could be around 20% according to preliminary estimates. Tthe risks encountered in achieving the project's objectives are about the Government capacity to fund all the energy efficiency measures, however, the proposed strategy to overcome this obstacle has been proposing to COEEs to start with low-cost measures in its implementation and that can develop through stages. The investments are implemented by cost and by the better Pay-back, since this will allow a fast recovery of the investment for developing other measures identified. Another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector. The difficulty is due to the construction sector is responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and Office of Planning of the Metropolitan Area of San Salvador (OPAMSS). This situation makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction. Therefore the project is working to unify the technical criteria with the consultancy of all the sectors and institutions involved in this topic. | During this period, the project of energy efficiency in public buildings EEPB-75672 has promoted EE measures that impact direct and indirectly on the environmental objectives. Accomplishing the Energy Efficiency targets in the Governmental sector (13% of total energy consumption in El Salvador) will reduce significantly the GHG. The contribution of the project to reach this target in this period is: (i) the support and diffusion of legal instruments such as the Bill of Law on Energy Efficiency and the National Energy Policy, (ii) the elaboration of a Procurement Manual with Energy Efficiency Criteria for Government Sector, (iii) the establishment of baseline of energy consumption for the public sector that will serve as an input to develop a strategy of national plan for savings in energy consumption (iv) the energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement, (v) the establishment of 90 new COEEs, although the target for this year was 16 COEEs, but in response to the Executive Decree #78 of Austerity and Savings, the project helped 75 public institutions in the establishment of their COEEs (vi) the strengthening of technical capacities of institutions with training the energy efficiency committees through workshops, meetings and a Diploma in EE in Buildings to train professionals of these committees on very specific topics on EE. (vii) the diminution in energy consumption in Consumer Ombudsman´s Office (10%) and Ministry of Environment and Natural Resources (20%) through the replacement of lamps for more efficient technology. Also the project is already developing computational tools to enable the committees to perform their analysis of the energy performance of their buildings, establish the best energetic indicators and having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). The next immediate step for the EEPB project is the development of pilot projects in coordination with the Ministry of Health and other institutions for a total amount of approximately USD $ 150,000. The results of the implementation can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures with the support of technical and legal standards that are being developed, achieve an important decrease of energy consumption, which could be around 20% according to preliminary estimates. Tthe risks encountered in achieving the project's objectives are about the Government capacity to fund all the energy efficiency measures, however, the proposed strategy to overcome this obstacle has been proposing to COEEs to start with low-cost measures in its implementation and that can develop through stages. The investments are implemented by cost and by the better Pay-back, since this will allow a fast recovery of the investment for developing other measures identified. Another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector. The difficulty is due to the construction sector is responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and Office of Planning of the Metropolitan Area of San Salvador (OPAMSS). This situation makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction. Therefore the project is working to unify the technical criteria with the consultancy of all the sectors and institutions involved in this topic. | 10:13 | 2012-09-03
IPRating $G$27 | In my opinion the project has managed effectively the financial resources and had achieved very good results, overcoming problems not considered in the design without increasing the costs of the project. At the beginning the project had a delay because of the establishment of project team and the training process, but this lag will be overcome in 2012 because the project has contracted the majority of consultancies and have good progress in purchase process. It is also important to say that the work with the EE Committees will provide good results (in EE measures implemented) in this year. It is important to mention that it has been difficult to find experts in some specific areas, not all the consultancies had expressions of interest even though the process was published in newspapers and virtual media. The consultancy for the establishment of the base line of the consumption of energy in the Government sector has required the search for energy information of all the institutions of Government. To get this information it was necessary to use the database of distributors, but this database does not have an identifier specific for the Government and the consulting company had to do an exhaustive search of the consumption of energy for more than 6,500 government buildings. Now, it is almost finished the consultancy with the baseline of energy consumption already estabished and with other very important and useful information to prepare de EE strategy for El Salvador. In the other hand, the consulting to establish the pilot projects to be developed in 10 hospitals in the national network of health had finished 4 energy audits with a list of specific measures in EE, the investments, the GHG avoided,and recommendations for energy conservation. With the results of the consultings, the project had coordinated meetings with the Ministry of Health and the Directors of selected hospitals to make an implementation plan with the measures reflected in the energy studies submitted by the consulting company. The energy audits of 2 more hospitals were finished with the support of Universidad Centroamericana, UCA (also counterpart of this project) and now the studies are under review and analysis to decide the EE measures to implement. The recruitment of consulting services to develop a methodology for the evaluation of the energy performance of buildings, has needed more time than considered, because it was necessary publish 3 times the request for expressions of interest to find professionals.As a summary, the project had difficulties in the execution of the activites programmed for this year, but now it is overcomed and for the end of 2012 there will be running pilots in hospitals, energy efficiency strategy and saving targets achieved, 90 COEEs working in their institutions, 30 professionals trained in EE with a Diploma, EE plans defined, software tools running. Nowdays, the project has financial commitments for more than $278,000 to be paid in the next two months and will continue with the financial execution to complete de Budget for 2012. | In my opinion the project has managed effectively the financial resources and had achieved very good results, overcoming problems not considered in the design without increasing the costs of the project. At the beginning the project had a delay because of the establishment of project team and the training process, but this lag will be overcome in 2012 because the project has contracted the majority of consultancies and have good progress in purchase process. It is also important to say that the work with the EE Committees will provide good results (in EE measures implemented) in this year. It is important to mention that it has been difficult to find experts in some specific areas, not all the consultancies had expressions of interest even though the process was published in newspapers and virtual media. The consultancy for the establishment of the base line of the consumption of energy in the Government sector has required the search for energy information of all the institutions of Government. To get this information it was necessary to use the database of distributors, but this database does not have an identifier specific for the Government and the consulting company had to do an exhaustive search of the consumption of energy for more than 6,500 government buildings. Now, it is almost finished the consultancy with the baseline of energy consumption already estabished and with other very important and useful information to prepare de EE strategy for El Salvador. In the other hand, the consulting to establish the pilot projects to be developed in 10 hospitals in the national network of health had finished 4 energy audits with a list of specific measures in EE, the investments, the GHG avoided,and recommendations for energy conservation. With the results of the consultings, the project had coordinated meetings with the Ministry of Health and the Directors of selected hospitals to make an implementation plan with the measures reflected in the energy studies submitted by the consulting company. The energy audits of 2 more hospitals were finished with the support of Universidad Centroamericana, UCA (also counterpart of this project) and now the studies are under review and analysis to decide the EE measures to implement. The recruitment of consulting services to develop a methodology for the evaluation of the energy performance of buildings, has needed more time than considered, because it was necessary publish 3 times the request for expressions of interest to find professionals.As a summary, the project had difficulties in the execution of the activites programmed for this year, but now it is overcomed and for the end of 2012 there will be running pilots in hospitals, energy efficiency strategy and saving targets achieved, 90 COEEs working in their institutions, 30 professionals trained in EE with a Diploma, EE plans defined, software tools running. Nowdays, the project has financial commitments for more than $278,000 to be paid in the next two months and will continue with the financial execution to complete de Budget for 2012. | 10:14 | 2012-09-03
Adjustments $F$44 | The CNE has led to the creation of legal instruments as the Executive Decree 78 of the year 2012, in which requires the Organization of committees for energy efficiency; this will help institutions to promote energy efficiency measures that produce savings. | The CNE has led to the creation of legal instruments as the Executive Decree 78 of the year 2012, in which requires the Organization of committees for energy efficiency; this will help institutions to promote energy efficiency measures that produce savings. | 10:14 | 2012-09-03
Adjustments $F$45 | worked in a very coordinated manner with the Ministry of public health, with the aim that the hospitals pilot projects have the best results. | Worked in a very coordinated manner with the Ministry of public health, with the aim that the hospitals pilot projects have the best results. | 10:14 | 2012-09-03
Finance $E$19 | The most significant payments will be done during the second half of 2012. There are $278,000 committed in the first 4 consulting , equipment and other process | The most significant payments will be done during the second half of 2012. There are $278,000 committed in the first 4 consulting , equipment and other processes. | 10:15 | 2012-09-03
Communications and KM $D$16 | The project EEPB seeks to break down barriers for energy efficiency in Government sector in El Salvador. The obstacles detected are technical, legal, commercial, lack of information, absence of a baseline, lack of conscience in environmental issues. The project is developing technical capacities in the public institutions through workshops, procurement manuals and a diploma in EE in buildings addressed to public sector. Actually, there are more than 90 Energy Efficiency Committees in the same amount of institutions, establishing and implementing their own EE plans. The activities of the project allowed knowing the energy consumption baseline of Government sector and the inventory of public buildings in El Salvador and this information will permit the construction of a EE National Plan. Also the project is supporting the new legal framework for EE; and it is finishing energy audits in 10 very representative hospitals to define the measures to implement and the guidelines to establish an EE Plan applicable to all the national hospitals in the country. Besides, it is constructing useful software tools to model de thermal and energy consumption of buildings and an online tool to monitor the energy consumption of all the institutions automatically. | The project EEPB seeks to break down barriers for energy efficiency in Government sector in El Salvador. The obstacles detected are technical, legal, commercial, lack of information, absence of a baseline, lack of conscience in environmental issues. The project is developing technical capacities in the public institutions through workshops, procurement manuals and a diploma in EE in buildings addressed to public sector. Actually, there are more than 90 Energy Efficiency Committees in the same amount of institutions, establishing and implementing their own EE plans. The activities of the project allowed knowing the energy consumption baseline of Government sector and the inventory of public buildings in El Salvador and this information will permit the construction of a EE National Plan. Also the project is supporting the new legal framework for EE; and it is finishing energy audits in 10 very representative hospitals to define the measures to implement and the guidelines to establish an EE Plan applicable to all the national hospitals in the country. Besides, it is constructing useful software tools to model de thermal and energy consumption of buildings and an online tool to monitor the energy consumption of all the institutions automatically. | 10:15 | 2012-09-03
BasicData $F$40 | Empty Cell | As planned - no change | 18:31 | 2012-09-07

## 1.KeyData (hidden)
Key Data
| DO Rating | S
| IP Rating | S
| Risk rating | Substantial
| Disbursement GEF funds to end June 2012 | 112440
| Actual co-financing | 0
| Revised closing date | As planned - no change
| Mid-term date | July 2012 – June 2013
| TE date | July 2013 – June 2014
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## 0rpt3IP (hidden)
ANNUAL PROGRESS IN PROJECT IMPLEMENTATION |  |  | 1
Project Outcomes | Outputs reported as of 30 June 2012 | 0

## 0rpt3Adj (hidden)
ADJUSTMENTS
Key Project Milestones
Have significant delays occurred in the project start, inception workshop, Mid-term Review, Terminal Evaluation or project duration? |  |  | Yes
If yes, were these changes reported in a previous APR/PIR? |  |  | No
Key project milestone | Scope of Delay (in months): | Briefly Describe Change or Reason for Change | Briefly describe the implications or consequences this has had on project implementation.
Project Start (i.e. project document signature date) | 6 | In January 2011 was officially started the project EEPB-75672, but the Coordinator was hired in April, in June the Administrative Assistant of the project and in August was hired the Technical Support. Once hired the entire technical team of the project, the induction process begun. | It will be necessary hasten the activities, in order to accomplish the targets at the end of 2013. The project will have a good performance in 2012, that will permit to adjust the activities to finish the outcomes in 2013.
Inception Workshop | 4 | The project inception workshop was done in April, this situation caused a delay of at least 4 months | It will be necessary hasten the activities, in order to accomplish the targets at the end of 2013. The project will have a good performance in 2012, that will permit to adjust the activities to finish the outcomes in 2013.
Mid-term Review
Terminal Evaluation
Project Duration (i.e. project extension)
Adjustments to Project Strategy
Has the project made any changes to its strategy (i.e. logframe/results framework) since the Project Document was signed?
If yes, were these changes reported in a previous APR/PIR?
Change Made to: | Yes/No | Briefly Describe the Change and the Reason for that Change
Project Objective | No
Project Outcomes | No
Project Outputs/Activities | No
Critical Risk Management
| Type of critical risk (only critical risks) as noted in ATLAS risk log | Risk management measures undertaken this reporting period
| Strategic | The CNE has led to the creation of legal instruments as the Executive Decree 78 of the year 2012, in which requires the Organization of committees for energy efficiency; this will help institutions to promote energy efficiency measures that produce savings.
| Environmental | Worked in a very coordinated manner with the Ministry of public health, with the aim that the hospitals pilot projects have the best results.
General Comments

## General Guidance
Adjusted5
Project: Energy Efficiency in Public Buildings (EEPB)
General Guidance
Welcome to the 2012 APR/PIR: This is the annual opportunity to check whether individual projects will meet their intended objective and outcomes, and to adjust strategies where necessary. The completed APR/PIR should be shared with the Project Board and be used to inform the development of annual work plans. Completing and submitting this APR/PIR on time are mandatory requirements of the Global Environment Facility (GEF). Please check with the UNDP Regional Center (RSC or RCU) for specific deadlines.
Please note the following: • Project mid-term reviews (MTRs) or Terminal Evaluations (TEs) completed between the period 1 July 2011 to 30 June 2012 must be submitted as part of the 2012 APR/PIR process. For projects that completed a MTR or TE this reporting period, the GEF Focal Area Tracking Tool must also be completed and submitted this reporting period. The GEF Tracking Tools for Climate Change Mitigation, International Waters, and Chemicals projects are embedded into the 2012 APR/PIR for convenience. The other GEF Focal Area Tracking Tools are available on Teamworks at:
https://undp.unteamworks.org/node/200481
• The APR/PIR must be translated into English. Please check with the UNDP Regional Center (RSC or RCU) for specific guidelines.
Key tips for completing this excel template: • Please complete those cells with white background colour only. The cells in blue are pre-loaded for your information only. • Please follow the guidance outlined in each sheet and keep to the word count. This guidance is also available as a separate word document on Teamworks at:
https://undp.unteamworks.org/node/200481
• For detailed guidance please visit the Teamworks site for daily updates at:
https://undp.unteamworks.org/node/200481
Extra functions: • Click on “Check empty tabs and cells” to quickly review the empty/blank sections of the APR/PIR that still need to be completed. • Click on “Cells recently changed” to quickly review the latest changes made to the APR/PIR. • Click on “Key data” to quickly ensure key data elements have been completed.
Word Reports:
After completing this excel APR/PIR, you may click on “APR/PIR Report” to generate a word version of the APR/PIR.
2012 Annual Project Review (APR)
Project Implementation Report (PIR)
APR/PIR Report
Check empty tabs and cells
Cells recently changed
Key Data

## BasicData
Basic Project Data
Please scroll down to the bottom of this page and complete all sections.
Please complete the cells with white background colour only.
|  | Official Project Title: | Energy Efficiency in Public Buildings (EEPB)
|  | Project Summary: | The Project aims to introduce energy efficiency (EE) measures in public buildings by reducing identified technical, policy and information barriers. The Project envisages to: (i) develop and implement an effective EE policy and regulatory framework and to enhance institution building; (ii) strengthen the in-country technical capacity concerning the design and integration of EE measures in public buildings; (iii) implement an EE programme to achieve energy savings by investments and energy monitoring within the Ministry of Public Health. The Project will be implemented by the National Energy Council (CNE); throughput time is 36 months. The EEPB initiative will result in 42,000 ton CO2 directly and 135,000 tons CO2 indirectly avoided emissions. Total budget is US$ 4.325 mln with US$ 3.35 mln cofinancing (of which US$ 2.195 mln investment).
|  | PIMS Number: | 4244
|  | Atlas Award Number: | 60180
|  | Atlas Project Number (s): | 75672
|  |  | Is this a single country project: | Yes
|  |  | If yes, which country is the project being implemented in? | El Salvador
|  |  | Is this global project: | No
|  |  | Is this a regional or multi-country project: | No
If yes, please list all the countries that the project is being implemented in:
[5 empty] | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: |  | If the MTR |  | Dates | Dates |  |  | 2011-07-01
[5 empty] | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | Already completed TE |  | January 2003 | Prior to July 2006 |  |  | 2011-07-02
[5 empty] | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | July 2011 – June 2012 |  | February 2003 | August 2006 | August | 2006 | 2011-07-03
[5 empty] | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | July 2012 – June 2013 |  | March 2003 | September 2006 | September | 2006 | 2011-07-04
[5 empty] | Andorra |  |  | Ecosystems Management | 4 | 4 | MS | July 2013 – June 2014 |  | April 2003 | October 2006 | October | 2006 | 2011-07-05
[5 empty] | Angola |  |  | International Waters | 5 | 5 | Good | July 2014 – June 2015 |  | May 2003 | November 2006 | November | 2006 | 2011-07-06
[5 empty] | Antigua and Barbuda |  |  | Land Degradation | 6 | 6 |  | July 2015 – June 2016 |  | June 2003 | December 2006 | December | 2006 | 2011-07-07
[5 empty] | Argentina |  |  | Multiple Focal Area |  |  |  | July 2016 – June 2017 |  | July 2003 | January 2007 | January | 2007 | 2011-07-08
[5 empty] | Armenia |  |  | POP |  |  |  | July 2017 – June 2018 |  | August 2003 | February 2007 | February | 2007 | 2011-07-09
|  |  | Other(s): |  | Australia | [6 empty] | July 2018 – June 2019 |  | September 2003 | March 2007 | March | 2007 | 2011-07-10
[5 empty] | Austria | [6 empty] | July 2019 – June 2020 |  | October 2003 | April 2007 | April | 2007 | 2011-07-11
|  |  | Project milestones and timeframe: |  | Azerbaijan | [6 empty] | Submitted in past reporting period |  | November 2003 | May 2007 | May | 2007 | 2011-07-12
|  |  | Project document signature date (project start): | 2010-12-10 | Bahamas | [8 empty] | December 2003 | June 2007 | June | 2007 | 2011-07-13
|  |  | Planned Closing Date: | 2013-10-31 | Bahrain | [8 empty] | January 2004 | July 2007 | July | 2007 | 2011-07-14
|  |  | Revised Planned Closing Date: | As planned - no change | Bangladesh | [8 empty] | February 2004 | August 2007 | August | 2007 | 2011-07-15
|  |  | Project Supervision: |  | Barbados | [8 empty] | March 2004 | September 2007 | September | 2007 | 2011-07-16
|  |  | Dates of Project Steering Committee/Board meetings during reporting period (1 July 2011 - 30 June 2012): |  | Belarus | [8 empty] | April 2004 | October 2007 | October | 2007 | 2011-07-17
[5 empty] | Belgium | [8 empty] | May 2004 | November 2007 | November | 2007 | 2011-07-18
[5 empty] | Belize | [8 empty] | June 2004 | December 2007 | December | 2007 | 2011-07-19
[5 empty] | Benin | [8 empty] | July 2004 | January 2008 | January | 2008 | 2011-07-20
[5 empty] | Bhutan | [8 empty] | August 2004 | February 2008 | February | 2008 | 2011-07-21
[5 empty] | Bolivia (Plurinational State of) | [8 empty] | September 2004 | March 2008 | March | 2008 | 2011-07-22
[5 empty] | Bosnia and Herzegovina | [8 empty] | October 2004 | April 2008 | April | 2008 | 2011-07-23
|  |  | Project Evaluation: |  | Botswana | [8 empty] | November 2004 | May 2008 | May | 2008 | 2011-07-24
|  |  | Was the final Midterm Review report sent to UNDP between 1 July 2011 - 30 June 2012? | No | Brazil | [8 empty] | December 2004 | June 2008 | June | 2008 | 2011-07-25
|  |  | If no, when will the MTR report be finalized and sent to UNDP, or was it submitted in a past reporting period? | July 2012 – June 2013 | Brunei Darussalam | [8 empty] | January 2005 | July 2008 | July | 2008 | 2011-07-26
[5 empty] | Bulgaria | [8 empty] | February 2005 | August 2008 | August | 2008 | 2011-07-27
|  |  | Was the final Terminal Evaluation report sent to UNDP or posted on the UNDP Evaluation Resource Centre between 1 July 2011 - 30 June 2012? | No | Burkina Faso | [8 empty] | March 2005 | September 2008 | September | 2008 | 2011-07-28
|  |  | If yes, was the management response also sent to UNDP or posted on the UNDP Evaluation Resource Centre between those dates? |  | Burundi | [8 empty] | April 2005 | October 2008 | October | 2008 | 2011-07-29
| If no, when will the TE report and management response be finalized and sent to UNDP or posted on the UNDP Evaluation Resource Centre, or was it submitted in a past reporting period? |  |  | July 2013 – June 2014 | Cambodia | [8 empty] | May 2005 | November 2008 | November | 2008 | 2011-07-30
[5 empty] | Cameroon | [8 empty] | June 2005 | December 2008 | December | 2008 | 2011-07-31
|  | Project documentation and information: |  |  | Canada | [8 empty] | July 2005 | January 2009 | January | 2009 | 2011-08-01
|  | If available, please list website address (URL) of the project. This may be used in UNDP communications material. |  |  | Cape Verde | [8 empty] | August 2005 | February 2009 | February | 2009 | 2011-08-02
[5 empty] | Central African Republic | [8 empty] | September 2005 | March 2009 | March | 2009 | 2011-08-03
[5 empty] | Chad | [8 empty] | October 2005 | April 2009 | April | 2009 | 2011-08-04
|  | Project contacts: |  |  | Chile | [8 empty] | November 2005 | May 2009 | May | 2009 | 2011-08-05
|  | National Project Manager/Coordinator |  |  | China | [8 empty] | December 2005 | June 2009 | June | 2009 | 2011-08-06
|  | Name: | Carlos Alberto Najera |  | Colombia | [8 empty] | January 2006 | September 2009 | September | 2009 | 2011-08-07
|  | Email: | cnajera@cne.gob.sv |  | Comoros | [8 empty] | February 2006 | October 2009 | October | 2009 | 2011-08-08
|  | Government GEF OFP (mandatory) |  |  | Congo | [8 empty] | March 2006 | November 2009 | November | 2009 | 2011-08-09
|  | Name: | Herman Rosa Chavez |  | Cook Islands | [8 empty] | April 2006 | December 2009 | December | 2009 | 2011-08-10
|  | Email: | despacho@marn.gob.sv |  | Costa Rica | [8 empty] | May 2006 | January 2010 | January | 2010 | 2011-08-11
|  | Project Implementing Partner (mandatory) |  |  | Côte D'Ivoire | [8 empty] | June 2006 | February 2010 | February | 2010 | 2011-08-12
|  | Name: | Silvia Vides |  | Croatia | [8 empty] | July 2006 | March 2010 | March | 2010 | 2011-08-13
|  | Email: | silvia.vides@undp.org |  | Cuba | [8 empty] | August 2006 | April 2010 | April | 2010 | 2011-08-14
|  | Other Partners (e.g. UNOPS, UNEP, UNIDO…) |  |  | Cyprus | [8 empty] | September 2006 | May 2010 | May | 2010 | 2011-08-15
|  | Name: |  |  | Czech Republic | [8 empty] | October 2006 | June 2010 | June | 2010 | 2011-08-16
|  | Email: |  |  | Democratic People's Republic of Korea | [8 empty] | November 2006 | September 2010 | September | 2010 | 2011-08-17
[5 empty] | Democratic Republic of the Congo | [8 empty] | December 2006 | October 2010 | October | 2010 | 2011-08-18
[5 empty] | Denmark | [8 empty] | January 2007 | November 2010 | November | 2010 | 2011-08-19
|  | General Comments (1200 words). If you have any comments about the data/information on this sheet, please add them here: |  |  | Djibouti | [8 empty] | February 2007 | December 2010 | December | 2010 | 2011-08-20
[5 empty] | Dominica | [8 empty] | March 2007 | January 2011 | January | 2011 | 2011-08-21
[5 empty] | Dominican Republic | [8 empty] | April 2007 | February 2011 | February | 2011 | 2011-08-22
[5 empty] | Ecuador | [8 empty] | May 2007 | March 2011 | March | 2011 | 2011-08-23
[5 empty] | Egypt | [8 empty] | June 2007 | April 2011 | April | 2011 | 2011-08-24
[5 empty] | El Salvador | [8 empty] | July 2007 | May 2011 | May | 2011 | 2011-08-25
[5 empty] | Equatoral Guinea | [8 empty] | August 2007 | June 2011 | June | 2011 | 2011-08-26
[5 empty] | Eritrea | [8 empty] | September 2007 | September 2011 | September | 2011 | 2011-08-27
[5 empty] | Estonia | [8 empty] | October 2007 | October 2011 | October | 2011 | 2011-08-28
[5 empty] | Ethiopia | [8 empty] | November 2007 | November 2011 | November | 2011 | 2011-08-29
[5 empty] | Fiji | [8 empty] | December 2007 | December 2011 | December | 2011 | 2011-08-30
[5 empty] | Finland | [8 empty] | January 2008 | no change |  |  | 2011-08-31
[5 empty] | France | [8 empty] | February 2008 |  |  |  | 2011-09-01
[5 empty] | Gabon | [8 empty] | March 2008 |  |  |  | 2011-09-02
[5 empty] | Gambia | [8 empty] | April 2008 |  |  |  | 2011-09-03
[5 empty] | Georgia | [8 empty] | May 2008 |  |  |  | 2011-09-04
[5 empty] | Germany | [8 empty] | June 2008 |  |  |  | 2011-09-05
[5 empty] | Ghana | [8 empty] | July 2008 |  |  |  | 2011-09-06
[5 empty] | Greece | [8 empty] | August 2008 |  |  |  | 2011-09-07
[5 empty] | Grenada | [8 empty] | September 2008 |  |  |  | 2011-09-08
[5 empty] | Guatemala | [8 empty] | October 2008 |  |  |  | 2011-09-09
[5 empty] | Guinea | [8 empty] | November 2008 |  |  |  | 2011-09-10
[5 empty] | Guinea Bissau | [8 empty] | December 2008 |  |  |  | 2011-09-11
[5 empty] | Guyana | [8 empty] | January 2009 |  |  |  | 2011-09-12
[5 empty] | Haiti | [8 empty] | February 2009 |  |  |  | 2011-09-13
[5 empty] | Honduras | [8 empty] | March 2009 |  |  |  | 2011-09-14
[5 empty] | Hungary | [8 empty] | May 2009 |  |  |  | 2011-09-15
[5 empty] | India | [8 empty] | June 2009 |  |  |  | 2011-09-16
[5 empty] | Indonesia | [8 empty] | July 2009 |  |  |  | 2011-09-17
[5 empty] | Iran (Islamic Republic of) | [8 empty] | September 2009 |  |  |  | 2011-09-18
[5 empty] | Ireland | [8 empty] | October 2009 |  |  |  | 2011-09-19
[5 empty] | Israel | [8 empty] | November 2009 |  |  |  | 2011-09-20
[5 empty] | Italy | [8 empty] | January 2010 |  |  |  | 2011-09-21
[5 empty] | Jamaica | [8 empty] | February 2010 |  |  |  | 2011-09-22
[5 empty] | Japan | [8 empty] | March 2010 |  |  |  | 2011-09-23
[5 empty] | Jordan | [8 empty] | May 2010 |  |  |  | 2011-09-24
[5 empty] | Kazakhstan | [8 empty] | June 2010 |  |  |  | 2011-09-25
[5 empty] | Kenya | [8 empty] | July 2010 |  |  |  | 2011-09-26
[5 empty] | Kiribati | [8 empty] | August 2010 |  |  |  | 2011-09-27
[5 empty] | Kuwait | [8 empty] | September 2010 |  |  |  | 2011-09-28
[5 empty] | Kyrgyzstan | [8 empty] | October 2010 |  |  |  | 2011-09-29
[5 empty] | Lao People’s Democratic Republic | [8 empty] | November 2010 |  |  |  | 2011-09-30
[5 empty] | Latvia | [8 empty] | December 2010 |  |  |  | 2011-10-01
[5 empty] | Lebanon | [8 empty] | January 2011 |  |  |  | 2011-10-02
[5 empty] | Lesotho | [8 empty] | February 2011 |  |  |  | 2011-10-03
[5 empty] | Liberia | [8 empty] | March 2011 |  |  |  | 2011-10-04
[5 empty] | Libyan Arab Jamahiriya | [8 empty] | April 2011 |  |  |  | 2011-10-05
[5 empty] | Liechtenstein | [8 empty] | May 2011 |  |  |  | 2011-10-06
[5 empty] | Lithuania | [8 empty] | June 2011 |  |  |  | 2011-10-07
[5 empty] | Luxembourg | [8 empty] | July 2011 |  |  |  | 2011-10-08
[5 empty] | Madagascar | [8 empty] | August 2011 |  |  |  | 2011-10-09
[5 empty] | Malawi | [8 empty] | September 2011 |  |  |  | 2011-10-10
[5 empty] | Malaysia | [8 empty] | October 2011 |  |  |  | 2011-10-11
[5 empty] | Maldives | [8 empty] | November 2011 |  |  |  | 2011-10-12
[5 empty] | Mali | [8 empty] | December 2011 |  |  |  | 2011-10-13
[5 empty] | Malta | [8 empty] | January 2012 |  |  |  | 2011-10-14
[5 empty] | Marshall Islands | [8 empty] | February 2012 |  |  |  | 2011-10-15
[5 empty] | Mauritania | [8 empty] | March 2012 |  |  |  | 2011-10-16
[5 empty] | Mauritius | [8 empty] | April 2012 |  |  |  | 2011-10-17
[5 empty] | Mexico | [7 empty] | As planned - no change | May 2012 |  |  |  | 2011-10-18
[5 empty] | Micronesia, Federated States of | [7 empty] | June 2012 | June 2012 |  |  |  | 2011-10-19
[5 empty] | Monaco | [7 empty] | July 2012 | July 2012 |  |  |  | 2011-10-20
[5 empty] | Mongolia | [7 empty] | August 2012 | August 2012 |  |  |  | 2011-10-21
[5 empty] | Montenegro | [7 empty] | September 2012 | September 2012 |  |  |  | 2011-10-22
[5 empty] | Morocco | [7 empty] | October 2012 | October 2012 |  |  |  | 2011-10-23
[5 empty] | Mozambique | [7 empty] | November 2012 | November 2012 |  |  |  | 2011-10-24
[5 empty] | Myanmar | [7 empty] | December 2012 | December 2012 |  |  |  | 2011-10-25
[5 empty] | Namibia | [7 empty] | January 2013 | January 2013 |  |  |  | 2011-10-26
[5 empty] | Nauru | [7 empty] | February 2013 | February 2013 |  |  |  | 2011-10-27
[5 empty] | Nepal | [7 empty] | March 2013 | March 2013 |  |  |  | 2011-10-28
[5 empty] | Netherlands | [7 empty] | April 2013 | April 2013 |  |  |  | 2011-10-29
[5 empty] | New Zealand | [7 empty] | May 2013 | May 2013 |  |  |  | 2011-10-30
[5 empty] | Nicaragua | [7 empty] | June 2013 | June 2013 |  |  |  | 2011-10-31
[5 empty] | Niger | [7 empty] | July 2013 | July 2013 |  |  |  | 2011-11-01
[5 empty] | Nigeria | [7 empty] | August 2013 | August 2013 |  |  |  | 2011-11-02
[5 empty] | Niue | [7 empty] | September 2013 | September 2013 |  |  |  | 2011-11-03
[5 empty] | Norway | [7 empty] | October 2013 | October 2013 |  |  |  | 2011-11-04
[5 empty] | Oman | [7 empty] | November 2013 | November 2013 |  |  |  | 2011-11-05
[5 empty] | Pakistan | [7 empty] | December 2013 | December 2013 |  |  |  | 2011-11-06
[5 empty] | Palau | [7 empty] | January 2014 | January 2014 |  |  |  | 2011-11-07
[5 empty] | Panama | [7 empty] | February 2014 | February 2014 |  |  |  | 2011-11-08
[5 empty] | Papua New Guinea | [7 empty] | March 2014 | March 2014 |  |  |  | 2011-11-09
[5 empty] | Paraguay | [7 empty] | April 2014 | April 2014 |  |  |  | 2011-11-10
[5 empty] | Peru | [7 empty] | May 2014 | May 2014 |  |  |  | 2011-11-11
[5 empty] | Philippines | [7 empty] | June 2014 | June 2014 |  |  |  | 2011-11-12
[5 empty] | Poland | [7 empty] | July 2014 | July 2014 |  |  |  | 2011-11-13
[5 empty] | Portugal | [7 empty] | August 2014 | August 2014 |  |  |  | 2011-11-14
[5 empty] | Qatar | [7 empty] | September 2014 | September 2014 |  |  |  | 2011-11-15
[5 empty] | Republic of Korea | [7 empty] | October 2014 | October 2014 |  |  |  | 2011-11-16
[5 empty] | Republic of Moldova | [7 empty] | November 2014 | November 2014 |  |  |  | 2011-11-17
[5 empty] | Romania | [7 empty] | December 2014 | December 2014 |  |  |  | 2011-11-18
[5 empty] | Russian Federation | [7 empty] | January 2015 | January 2015 |  |  |  | 2011-11-19
[5 empty] | Rwanda | [7 empty] | February 2015 | February 2015 |  |  |  | 2011-11-20
[5 empty] | Saint Kitts and Nevis | [7 empty] | March 2015 | March 2015 |  |  |  | 2011-11-21
[5 empty] | Saint Lucia | [7 empty] | April 2015 | April 2015 |  |  |  | 2011-11-22
[5 empty] | Saint Vincent and the Grenadines | [7 empty] | May 2015 | May 2015 |  |  |  | 2011-11-23
[5 empty] | Samoa | [7 empty] | June 2015 | June 2015 |  |  |  | 2011-11-24
[5 empty] | San Marino | [7 empty] | July 2015 | July 2015 |  |  |  | 2011-11-25
[5 empty] | Sao Tome and Principe | [7 empty] | August 2015 | August 2015 |  |  |  | 2011-11-26
[5 empty] | Saudi Arabia | [7 empty] | September 2015 | September 2015 |  |  |  | 2011-11-27
[5 empty] | Senegal | [7 empty] | October 2015 | October 2015 |  |  |  | 2011-11-28
[5 empty] | Serbia | [7 empty] | November 2015 | November 2015 |  |  |  | 2011-11-29
[5 empty] | Seychelles | [7 empty] | December 2015 | December 2015 |  |  |  | 2011-11-30
[5 empty] | Sierra Leone | [7 empty] | January 2016 | January 2016 |  |  |  | 2011-12-01
[5 empty] | Singapore | [7 empty] | February 2016 | February 2016 |  |  |  | 2011-12-02
[5 empty] | Slovakia | [7 empty] | March 2016 | March 2016 |  |  |  | 2011-12-03
[5 empty] | Slovenia | [7 empty] | April 2016 | April 2016 |  |  |  | 2011-12-04
[5 empty] | Solomon Islands | [7 empty] | May 2016 | May 2016 |  |  |  | 2011-12-05
[5 empty] | Somalia | [7 empty] | June 2016 | June 2016 |  |  |  | 2011-12-06
[5 empty] | South Africa | [7 empty] | July 2016 | July 2016 |  |  |  | 2011-12-07
[5 empty] | South Sudan | [7 empty] | August 2016 | August 2016 |  |  |  | 2011-12-08
[5 empty] | Spain | [7 empty] | September 2016 | September 2016 |  |  |  | 2011-12-09
[5 empty] | Sri Lanka | [7 empty] | October 2016 | October 2016 |  |  |  | 2011-12-10
[5 empty] | Sudan | [7 empty] | November 2016 | November 2016 |  |  |  | 2011-12-11
[5 empty] | Suriname | [7 empty] | December 2016 | December 2016 |  |  |  | 2011-12-12
[5 empty] | Swaziland | [7 empty] | January 2017 | January 2017 |  |  |  | 2011-12-13
[5 empty] | Sweden | [7 empty] | February 2017 | February 2017 |  |  |  | 2011-12-14
[5 empty] | Switzerland | [7 empty] | March 2017 | March 2017 |  |  |  | 2011-12-15
[5 empty] | Syrian Arab Republic | [7 empty] | April 2017 | April 2017 |  |  |  | 2011-12-16
[5 empty] | Tajikistan | [7 empty] | May 2017 | May 2017 |  |  |  | 2011-12-17
[5 empty] | Thailand | [7 empty] | June 2017 | June 2017 |  |  |  | 2011-12-18
[5 empty] | The former Yugoslav Republic of Macedonia | [7 empty] | July 2017 | July 2017 |  |  |  | 2011-12-19
[5 empty] | Timor-Leste | [7 empty] | August 2017 | August 2017 |  |  |  | 2011-12-20
[5 empty] | Togo | [7 empty] | September 2017 | September 2017 |  |  |  | 2011-12-21
[5 empty] | Tonga | [7 empty] | October 2017 | October 2017 |  |  |  | 2011-12-22
[5 empty] | Trinidad and Tobago | [7 empty] | November 2017 | November 2017 |  |  |  | 2011-12-23
[5 empty] | Tunisia | [7 empty] | December 2017 | December 2017 |  |  |  | 2011-12-24
[5 empty] | Turkey | [7 empty] | January 2018 | January 2018 |  |  |  | 2011-12-25
[5 empty] | Turkmenistan | [7 empty] | February 2018 | February 2018 |  |  |  | 2011-12-26
[5 empty] | Tuvalu | [7 empty] | March 2018 | March 2018 |  |  |  | 2011-12-27
[5 empty] | Uganda | [7 empty] | April 2018 | April 2018 |  |  |  | 2011-12-28
[5 empty] | Ukraine | [7 empty] | May 2018 | May 2018 |  |  |  | 2011-12-29
[5 empty] | United Arab Emirates | [7 empty] | June 2018 | June 2018 |  |  |  | 2011-12-30
[5 empty] | United Kingdom of Great Britain and Northern Ireland | [7 empty] | July 2018 | July 2018 |  |  |  | 2011-12-31
[5 empty] | United Republic of Tanzania | [7 empty] | August 2018 | August 2018 |  |  |  | 2012-01-01
[5 empty] | United States of America | [7 empty] | September 2018 | September 2018 |  |  |  | 2012-01-02
[5 empty] | Uruguay | [7 empty] | October 2018 | October 2018 |  |  |  | 2012-01-03
[5 empty] | Uzbekistan | [7 empty] | November 2018 | November 2018 |  |  |  | 2012-01-04
[5 empty] | Vanuatu | [7 empty] | December 2018 | December 2018 |  |  |  | 2012-01-05
[5 empty] | Venezuela, Bolivarian Republic of | [7 empty] | January 2019 | January 2019 |  |  |  | 2012-01-06
[5 empty] | Viet Nam | [7 empty] | February 2019 | February 2019 |  |  |  | 2012-01-07
[5 empty] | Yemen | [7 empty] | March 2019 | March 2019 |  |  |  | 2012-01-08
[5 empty] | Zambia | [7 empty] | April 2019 | April 2019 |  |  |  | 2012-01-09
[5 empty] | Zimbabwe | [7 empty] | May 2019 | May 2019 |  |  |  | 2012-01-10
[13 empty] | June 2019 | June 2019 |  |  |  | 2012-01-11
[13 empty] | July 2019 | July 2019 |  |  |  | 2012-01-12
[13 empty] | August 2019 | August 2019 |  |  |  | 2012-01-13
[13 empty] | September 2019 | September 2019 |  |  |  | 2012-01-14
[13 empty] | October 2019 | October 2019 |  |  |  | 2012-01-15
[13 empty] | November 2019 | November 2019 |  |  |  | 2012-01-16
[13 empty] | December 2019 | December 2019 |  |  |  | 2012-01-17
[13 empty] | January 2020 | January 2020 |  |  |  | 2012-01-18
[13 empty] | February 2020 | February 2020 |  |  |  | 2012-01-19
[13 empty] | March 2020 | March 2020 |  |  |  | 2012-01-20
[13 empty] | April 2020 | April 2020 |  |  |  | 2012-01-21
[13 empty] | May 2020 | May 2020 |  |  |  | 2012-01-22
[13 empty] | June 2020 | June 2020 |  |  |  | 2012-01-23
[13 empty] | July 2020 | July 2020 |  |  |  | 2012-01-24
[13 empty] | August 2020 | August 2020 |  |  |  | 2012-01-25
[13 empty] | September 2020 | September 2020 |  |  |  | 2012-01-26
[13 empty] | October 2020 | October 2020 |  |  |  | 2012-01-27
[13 empty] | November 2020 | November 2020 |  |  |  | 2012-01-28
[13 empty] | December 2020 | December 2020 |  |  |  | 2012-01-29
2012-01-30
2012-01-31
2012-02-01
2012-02-02
2012-02-03
2012-02-04
2012-02-05
2012-02-06
2012-02-07
2012-02-08
2012-02-09
2012-02-10
2012-02-11
2012-02-12
2012-02-13
2012-02-14
2012-02-15
2012-02-16
2012-02-17
2012-02-18
2012-02-19
2012-02-20
2012-02-21
2012-02-22
2012-02-23
2012-02-24
2012-02-25
2012-02-26
2012-02-27
2012-02-28
2012-02-29
2012-03-01
2012-03-02
2012-03-03
2012-03-04
2012-03-05
2012-03-06
2012-03-07
2012-03-08
2012-03-09
2012-03-10
2012-03-11
2012-03-12
2012-03-13
2012-03-14
2012-03-15
2012-03-16
2012-03-17
2012-03-18
2012-03-19
2012-03-20
2012-03-21
2012-03-22
2012-03-23
2012-03-24
2012-03-25
2012-03-26
2012-03-27
2012-03-28
2012-03-29
2012-03-30
2012-03-31
2012-04-01
2012-04-02
2012-04-03
2012-04-04
2012-04-05
2012-04-06
2012-04-07
2012-04-08
2012-04-09
2012-04-10
2012-04-11
2012-04-12
2012-04-13
2012-04-14
2012-04-15
2012-04-16
2012-04-17
2012-04-18
2012-04-19
2012-04-20
2012-04-21
2012-04-22
2012-04-23
2012-04-24
2012-04-25
2012-04-26
2012-04-27
2012-04-28
2012-04-29
2012-04-30
2012-05-01
2012-05-02
2012-05-03
2012-05-04
2012-05-05
2012-05-06
2012-05-07
2012-05-08
2012-05-09
2012-05-10
2012-05-11
2012-05-12
2012-05-13
2012-05-14
2012-05-15
2012-05-16
2012-05-17
2012-05-18
2012-05-19
2012-05-20
2012-05-21
2012-05-22
2012-05-23
2012-05-24
2012-05-25
2012-05-26
2012-05-27
2012-05-28
2012-05-29
2012-05-30
2012-05-31
2012-06-01
2012-06-02
2012-06-03
2012-06-04
2012-06-05
2012-06-06
2012-06-07
2012-06-08
2012-06-09
2012-06-10
2012-06-11
2012-06-12
2012-06-13
2012-06-14
2012-06-15
2012-06-16
2012-06-17
2012-06-18
2012-06-19
2012-06-20
2012-06-21
2012-06-22
2012-06-23
2012-06-24
2012-06-25
2012-06-26
2012-06-27
2012-06-28
2012-06-29
2012-06-30
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## RTA
Project: Energy Efficiency in Public Buildings (EEPB)
REGIONAL TECHNICAL ADVISOR
Please complete the cells with white background colour only. Please check data in question 1, answer questions 2 and 3, and complete question 4 only if a MTR or TE was undertaken this reporting period or if this is the FINAL APR/PIR.
1- Please verify and confirm the following key indicators. These cells will be used in the aggregation of data.
|  |  | Key milestones/data: | 2011-2012
|  |  | Project document signature date: | 2010-12-10
|  |  | Planned project closing date: | 2013-10-31
|  |  | Revised project closing date: | As planned - no change
|  |  | Total GEF grant: | 112440
|  |  | Total Co-financing: | 335591
| Key performance indicators for FY 2011: | 2009-2010 | 2010-2011 | 2011-2012
| Cumulative disbursement of GEF grant only as of 30 June 2012: |  |  | 112440
| Total number of critical risks as noted in the ATLAS risk log: |  |  | 2
| Overall DO Rating: |  |  | S
| Overall IP Rating: |  |  | S
| Overall Risk Rating: |  |  | Substantial
| 2- Is this PIR the project’s final PIR? | No |  |  | a. Environmental sustainability
b. Climate resiliency
| 3- Grievances: |  |  |  | c. Gender equality
| Did you address a grievance related to the environmental or social impacts of this project this reporting period? A grievance is defined as “an issue, concern, problem, or claim (perceived or actual) that an individual or community group wants UNDP to address and resolve. Synonymous with complaint". | No |  |  | d. Social equity and inclusiveness
e. Indigenous Peoples
| If yes, please answer the following 5 additional questions: |  |  |  | f. Physical/cultural resources
| I. What environmental or social issue was the grievance related to? |  |  |  | g. Human Rights Based Approach
h. Grievance was not related to an environmental or social issue.
II. How many grievances related to this project did you address?
III. What is the current status of this grievance?
a. Minor
| IV. How would you rate the significance of the grievance? |  |  |  | b. Significant
| a. Minor: the grievance had/has a low impact on the day-to-day implementation of the project. b. Significant: the grievance had/is having a significant impact on the day-to-day implementation of the project, but the project is still expected to achieve its objective. c. Serious: the grievance had/is having a serious impact on the day-to-day implementation of the project, and there is a risk (50% or higher) that the project may not be able to achieve its objective. |  |  |  | c. Serious
V. Please describe the grievance – noting who was involved, what action was taken to resolve the grievance, how much time it took, and what you learned from managing the grievance process (maximum 500 words):
4- Response to findings of FY 2012 MTR or TE, or if this is the FINAL APR/PIR Response to findings of FY12 MTR or TE, or on Final PIR (1200 words). In 1,200 words or less, please address the following points if a mid-term review or terminal evaluation was undertaken this reporting period, or if this is a FINAL APR/PIR: I. Briefly outline the key findings of the MTR or TE, any ratings provided, and the key recommendations and management responses. II. Discuss any problems/issues with the final MTR or TE report or the MTR/TE process. III. Discuss any problems/issues with the GEF Focal Area Tracking Tool. IV. If this is the final APR/PIR, please provide your detailed input to the evaluators who will undertake the project terminal evaluation.
Entering your name here confirms that you have reviewed this PIR and that it is, to your knowledge, complete.
Name: | Raul Alfaro Pelico
Email: | raul.alfaro@undp.org
|  | HS | 1 | HS
|  | S | 2 | S
|  | MS | 3 | MS
|  | MU | 4 | MU
|  | U | 5 | U
|  | HU | 6 | HU
Overall Rating
S | 2 |  |  | OVERALL RATING
S | 2 | 2 | 2 | S
Count of Critical Risk
2
Overall Risk Rating
S2 | Substantial
| Overall Risk Rating | Overall APR/PIR Objective and Implementation Rating |  | # Critical risks
HS0 | Low | HS |  | 0
HS1 | Moderate | HS |  | 1
HS2 | Substantial | HS |  | 2
HS3 | High | HS |  | 3
S0 | Low | S |  | 0
S1 | Moderate | S |  | 1
S2 | Substantial | S |  | 2
S3 | High | S |  | 3
MS0 | Low | MS |  | 0
MS1 | Moderate | MS |  | 1
MS2 | Substantial | MS |  | 2
MS3 | High | MS |  | 3
MU0 | Moderate | MU |  | 0
MU1 | Moderate | MU |  | 1
MU2 | Substantial | MU |  | 2
MU3 | High | MU |  | 3
U0 | Substantial | U |  | 0
U1 | Substantial | U |  | 1
U2 | Substantial | U |  | 2
U3 | High | U |  | 3
HU0 | High | HU |  | 0
HU1 | High | HU |  | 1
HU2 | High | HU |  | 2
HU3 | High | HU |  | 3
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## UNDP CO
Project: Energy Efficiency in Public Buildings (EEPB)
Country Office
Please complete the cells with white background colour only. Please answer question 1 and complete question 2 only if a MTR or TE was undertaken this reporting period or if this is the FINAL APR/PIR.
1. Grievances:
| Did you address a grievance related to the environmental or social impacts of this project this reporting period? A grievance is defined as “an issue, concern, problem, or claim (perceived or actual) that an individual or community group wants UNDP to address and resolve. Synonymous with complaint". | No | a. Environmental sustainability
b. Climate resiliency
| If yes, please answer the following 5 additional questions: |  | c. Gender equality
| I. What environmental or social issue was the grievance related to? |  | d. Social equity and inclusiveness
e. Indigenous Peoples
f. Physical/cultural resources
| II. How many grievances related to this project did you address? |  | g. Human Rights Based Approach
h. Grievance was not related to an environmental or social issue.
III. What is the current status of this grievance?
a. Minor
| IV. How would you rate the significance of the grievance? |  | b. Significant
| a. Minor: the grievance had/has a low impact on the day-to-day implementation of the project. b. Significant: the grievance had/is having a significant impact on the day-to-day implementation of the project, but the project is still expected to achieve its objective. c. Serious: the grievance had/is having a serious impact on the day-to-day implementation of the project, and there is a risk (50% or higher) that the project may not be able to achieve its objective. |  | c. Serious
V. Please describe the grievance – noting who was involved, what action was taken to resolve the grievance, how much time it took, and what you learned from managing the grievance process (maximum 500 words):
2. CO Response to findings of FY 2012 MTR or TE, or if this is the Final APR/PIR (1200 words). In 1,200 or words or less, please address the following points if a mid-term review or terminal evaluation was undertaken this reporting period or if this is the FINAL PIR: I. Briefly outline the key findings of the MTR or TE, any ratings provided, and the key recommendations and management responses. II. Discuss any problems/issues with the final MTR or TE report or the MTR/TE process. III. Discuss any problems/issues with the GEF Focal Area Tracking Tool. IV. If this is the final APR/PIR and the TE process has not finished, please provide your detailed input to the evaluators who will undertake the project terminal evaluation.
| Dates of site visits to project this reporting period: | 2011-07-01
2011-10-01
2012-03-01
2012-05-01
2012-06-01
Entering your name here confirms that you have reviewed this PIR and that it is, to your knowledge, complete.
Name: | Silvia Vides
Email: | silvia.vides@undp.org
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## DO
Project: Energy Efficiency in Public Buildings (EEPB)
| #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF!
Progress Towards Meeting Development Objective (DO)
Each indicator must be updated for this reporting period in the column “Level at 30 June 2012”. Numerical figures must be reported as cumulative from the project start. If there are no changes to report for a given indicator, then enter “N/A” or briefly explain the reason in that column.
If the logframe indicators were revised and approved by the Project Board, please make the corresponding changes in column D below.
Please complete the cells with white background colour only. There is a general comment box at the bottom of this sheet if you would like to provide comments.
| Description | Description of Indicator | Baseline Level | Target Level at end of project | Level at 30 June 2009 | Level at 30 June 2010 | Level at 30 June 2011 | Level at 30 June 2012
Objective | To introduce energy efficiency (EE) measures in existing and new public buildings by creating a conducive policy environment, increasing user awareness, developing performance criteria and standards, and implementing a broad EE pilot within selected public entities. | (I) Package of EE policy instruments; | (I) No policy instruments to promote EE in buildings in place; | (I) Package of policy instruments to promote EE in buildings in place; |  |  |  | Actually the National Energy Council (CNE, for its acronym in Spanish) has a National Energy Policy and a draft of the Law of National Energy Efficiency. The project has promoted the approval and diffussion of this legal instruments by making lobbying in 2 workshops with the Presidential House and the Secretariat of Legislative Affairs and many informal meetings to difuse this legal framework. It´s expected that the draft Law will be approved by the end of this year by the Legislative Assembly.
|  | (II) Implementation of investment pilot in hospitals; | (II) No investment pilot designed nor implemented; | (II) Investment pilot fully executed and monitored; |  |  |  | The project EEPB-75672 has among its results, the implementation of energy efficiency actions in hospital buildings. The project has planned the development of 10 energy studies in the same amount of hospitals. Currently, 4 energy studies have been completed in the following hospitals: BENJAMÍN BLOOM, SAN BARTOLO, JIQUILISCO and BARRIOS. The results of the energy balance reports are under discussion with the Ministry of Health to define the actions to be implemented this year. Likewise the Ministry of Health will respond with counterpart and has already started the implementation by replacement of the lighting systems for greater efficiency (T-8 technology), this has been developed in 4 national hospitals and 4 offices of this Ministry.
|  | (III) Technical standards and guidelines on EE in buildings; | (III) No national standards and guidelines for energy performance of buildings developed; | (III) Technical standards and guidelines on EE in buildings in place; |  |  |  | To achieve this target, the project EEPB-75672 has collected information and made a preliminary consultation to an expert in construction sector, to elaborate the terms of reference for a diagnosis consultancy. The results are expected by the end of the year
|  | (IV) EE investment programme implemented by the Government. | (IV) No investment programme for EE technology in public buildings. | (IV) An EE investment programme worth US$ 2mln has been executed in public buildings. |  |  |  | The CNE has created a strategy to develop a national investment plan in energy efficiency. This strategy will strengthen the institutional capacities on EE issues leading them to be organized and be able to manage themselves (with the support of the CNE). The Energy Efficiency Commitees are the responsibles of the proposal, implementation and monitoring of the EE mesures in each institution. The project has achieved the target of establish 16 EE Commitees in public institutions and many of them are already implementing and following up the measures established. As part of the $2mln counterpart of investment, institutions has already implemented $155,018.95 in EE actions. Because of the success of this process and as a result of the Austerity Decree issued by te Executive Organ, 75 additional institutions of the Government established their EE Committees. These new Commitees are supervised by the project which has provided them tools to accomplish the content of the Decree.
Outcome 1 | Effective policies and regulation regarding energy efficiency (EE) in buildings have been developed and applied to the public sector. | (A) Human capacity added the CNE (person-years); | (A) 0 | (A) Human capacity added 2 person-years (GEF) plus 1 person-year (Government); |  |  |  | During the first implementation year of the project EEPB-75672 professional services of an engineer for the technical support to the project has been hired. The salary for the years 2011 and 2012 will be funded by the project, and in 2013, will be covered by with Government funds.
|  | (B) National EE strategy for public buildings; | (B) No EE strategy for public buildings defined; | (B) Detailed EE strategy developed focused on public buildings; |  |  |  | The consultancy to determine the EE strategy is under implementation and has already presented the first output which is the energy consumption baseline. The strategy will be outlined by the end of 2012. It is important to mention that the project is developing a Procurement Manual with Energy Efficiency Criteria, for the Government Sector. The Manual will be diffused by de UNAC (Regulatory Unit of Procurement and Contracting from Public Sector) as a standard in the Governmental institutions. It will be ready by the end of 2012.
|  | (C) Quantified EE targets for public sector; | (C) No quantified EE (energy conservation); | (C) Quantified EE targets set based on detailed baseline information; |  |  |  | To define the targets it is necessary the baseline information. The consultancy is in implementation and until now it has clearly defined the inventory of Government buildings (6501) and the services of electrical energy that the Government owns (7525 service contract), this information is essencial to determine the energy consumption baseline. Once the study has finished the project will define the sample of buildings to estabish the EE targets and the required recommendations.
|  | (D) Package of EE policy instruments. | (D) No policy instruments to promote EE in buildings in place. | (D) Package of policy instruments to promote EE in buildings in place (e.g. technical standards, minimum energy performance criteria, building materials, design features, minimum efficiency of equipment). |  |  |  | For this reporting period the project has collected information to define the terms of reference for the diagnosis consultancy about the policy instruments adecuated to promote EE in construction sector. The results are expected for the end of this year.
Outcome 2 | Technical capacity concerning the design and integration of EE measures in public buildings has been strengthened. | (A) Adapted EE assessment methodologies; | (A) Limited experience with foreign methodologies and software tools; | (A) Adapted EE assessment methodologies and tools in place, based on detailed input information; |  |  |  | The consulting for the analysis of energetic performance of buildings has already started and will deliver a software that will enable the Government institutions to model the energy consumption of its buildings. Also it will model the characteristics of the buildings such as walls, ceilings, windows and any other thermal insulation. The project will use this platform in the design of new public buildings and also will help for all new construction.
|  | B) Suitable energy performance indicators for buildings; | (B) No consolidated view on regulation strategies and performance indicators for buildings; | (B) Suitable sets of energy performance indicators defined for appropriate building classes; |  |  |  | The indicators are not yet defined, they are under construction in the above mentioned counterpart
|  | (C) Technical standards and guidelines on EE in buildings; | (C) No national standards and guidelines for energy performance of buildings developed; | (C) At least 3 technical standards and guidelines on EE in buildings in place; |  |  |  | This activity and results are not planned for this reported period.
|  | (D) National workshop on EE in buildings. | (D) No workshop organized. | (D) Workshop organized. |  |  |  | The project has organized 4 inception workshops for the EE Commitees, with the participation of 189 partipants from 90 institutions. It is important to mention that 24% were women. For the hospital sector, it was organized a special workshop with the participation of 24 staff members from the 10 hospitals elected for implementation. The project also organized a Diploma in EE in Buildings for the technical strenghtening of EE Commitees with the participation of 30 profesionals from 22 public institutions. The Diploma will last for 6 months and it was organized with the colaboration of Universidad Centroamericana, UCA. Besides, the project is supporting the new legal framework in energy efficiency, therefore it organized two workshops with the Presidential House and Secretariat of Legislative Affairs to discuss the Draft of EE Law and many other informal meetings to diffuse its content.
Outcome 3 | An energy efficiency programme has been designed and implemented within public buildings. | (A) Technical and feasibility studies for EE investments; | (A) No studies performed; | (A) Studies prepared and executed for all investments considered; |  |  |  | During the year 2011 the EEPB project worked in coordination with the Ministry of Health (MINSAL, for its acronym in Spanish), the main partner of this project, in order to determine the hospitals where the pilot projects on energy efficiency will be implemented. MINSAL selected ten public hospitals to develop the energy efficiency and savings measures. The projec funded the energy audits of eight hospitals, the other two audits were supported by Universidad Centroamericana, UCA. There are already six energy audits completed which proposed energy efficiency measures in lighting, air conditioning, pumping systems and boiler systems. The studies of the six hospitals have defined a portfolio of projects need an investment of more than a half million dollars. Therefore, it is necessary to select the EE actions of medium and low investment with the best financial indicators (payback, VAN and TIR). The EE audits for the 4 remaining hospitals are under implementation and will be finished in September 2012.
|  | (B) Implementation of investment pilot in hospitals; | (B) No investment pilot designed nor implemented; | (B) Investment pilot fully executed and monitored; |  |  |  | After having defined the EE actions to be funded in the ten selected hospitals, which is expecting to start working in September 2012.
|  | (C) Implementation of energy monitoring system. | (C) No energy monitoring system in public organization designed nor implemented; | (C) Energy monitoring system prepared, implemented and supervised during project’s lifetime; |  |  |  | The project has already started the construction (with the support of the German cooperation agency, GiZ, a counterpart of the project), of an online system for monitoring and evaluation of the various energy efficiency measures. This system will be able to collect energy information from the EE committees of Government. The information collected by the system will be the monthly energy consumption, inventory of energy-consuming equipment, etc. Another advantage is that it can be reported all measures of EE implemented by the commitee and the impact of them. The objective is that all pilot projects will be monitored with this tool, to be able to measure and evaluate the results they generate. The online system will be working in August of this year.
|  | (D) EE investment programme implemented by the Government. | (D) No investment programme for EE technology in public buildings. | (D) An EE investment programme worth US$ 2mln has been executed in public buildings. |  |  |  | Same target as reported in line 19
Outcome 4 | A project monitoring and evaluation plan has been implemented and lessons learnt have been disseminated. | (A) Mid-term Evaluation Report; | (A) No MTE; | (A) MTE completed; |  |  |  | N/A
|  | (B) Final Evaluation Report; | (B) No FEV; | (B) FEV completed; |  |  |  | N/A
|  | (C) Sharing of project experience. | (C) No sharing of project experiences in El Salvador. | (C) Lessons learnt publication. |  |  |  | With the replacement of 274 luminaries in the Consumer Ombudsman and the Ministry of Environment and Natural Resources were systematized the best recommendations for energy conservation measures. All the information, lessons and results were published in 5,000 copies of manuals recommendations for the government sector and brochures on the results of the pilot projects for efficient lighting.
Outcome 5
Outcome 6
Outcome 7
Outcome 8
Outcome 9
Outcome 10
Outcome 11
Outcome 12
Outcome 13
Outcome 14
Outcome 15
Outcome 16
Outcome 17
Outcome 18
Outcome 19
Outcome 20
Outcome 21
Outcome 22
Outcome 23
Outcome 24
Outcome 25
Outcome 26
Outcome 27
Outcome 28
Outcome 29
Outcome 30
Outcome 31
Outcome 32
Outcome 33
Outcome 34
Outcome 35
Outcome 36
Outcome 37
Outcome 38
Outcome 39
Outcome 40
General Comment.
If you have any comments about the data/information on this sheet, please add them here:
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## DORating
Project: Energy Efficiency in Public Buildings (EEPB)
Rating of Progress Towards Meeting Development Objective (DO)
Please complete cells with white background only.
Select one of the rating categories outlined in the table below to describe cumulative progress toward meeting the project development objective. Please provide an accurate rating and fully justify your rating in the comment box.
|  |  | Rating Definitions |  |  | Rating | Value | Rating | AvgRating | 2 | 2
|  |  | Highly Satisfactory (HS) |  | Project is expected to achieve or exceed all its major global environmental objectives, and yield substantial global environmental benefits, without major shortcomings. The project can be presented as “good practice”. | HS | 1 | HS | RTA Rating | 2 | 0
|  |  | Satisfactory (S) |  | Project is expected to achieve most of its major global environmental objectives, and yield satisfactory global environmental benefits, with only minor shortcomings. | S | 2 | S | OverallRating | 2 | S
|  |  | Moderately Satisfactory (MS) |  | Project is expected to achieve most of its major relevant objectives but with either significant shortcomings or modest overall relevance. Project is expected not to achieve some of its major global environmental objectives or yield some of the expected global environment benefits. | MS | 3 | MS | AverageAll | 2 | 2
|  |  | Moderately Unsatisfactory (MU) |  | Project is expected to achieve its major global environmental objectives with major shortcomings or is expected to achieve only some of its major global environmental objectives. | MU | 4 | MU
|  |  | Unsatisfactory (U) |  | Project is expected not to achieve most of its major global environment objectives or to yield any satisfactory global environmental benefits. | U | 5 | U
|  |  | Highly Unsatisfactory (HU) |  | The project has failed to achieve, and is not expected to achieve, any of its major global environment objectives with no worthwhile benefits. | HU | 6 | HU
National Project Manager/Coordinator: Is the person managing the day to day operations of the project.
MANDATORY RATING MUST BE PROVIDED for projects under implementation in one country or regional projects where appropriate.
Please justify your rating and address the following points in your comments. Please keep word count between 500 words minimum and 1200 words maximum. 1. Explain why you gave a specific rating 2. Note trends, both positive and negative, in achievement of outcomes as per the updated indicators provided in the DO sheet. 3. Fully explain the critical risks that have affected progress. 4. Outline action plan to address projects with DO rating of HU, U or MU.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
|  |  |  | S | During this period, the project of energy efficiency in public buildings EEPB-75672 has promoted EE measures that impact direct and indirectly on the environmental objectives. Accomplishing the Energy Efficiency targets in the Governmental sector (13% of total energy consumption in El Salvador) will reduce significantly the GHG. The contribution of the project to reach this target in this period is: (i) the support and diffusion of legal instruments such as the Bill of Law on Energy Efficiency and the National Energy Policy, (ii) the elaboration of a Procurement Manual with Energy Efficiency Criteria for Government Sector, (iii) the establishment of baseline of energy consumption for the public sector that will serve as an input to develop a strategy of national plan for savings in energy consumption (iv) the energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement, (v) the establishment of 90 new COEEs, although the target for this year was 16 COEEs, but in response to the Executive Decree #78 of Austerity and Savings, the project helped 75 public institutions in the establishment of their COEEs (vi) the strengthening of technical capacities of institutions with training the energy efficiency committees through workshops, meetings and a Diploma in EE in Buildings to train professionals of these committees on very specific topics on EE. (vii) the diminution in energy consumption in Consumer Ombudsman´s Office (10%) and Ministry of Environment and Natural Resources (20%) through the replacement of lamps for more efficient technology. Also the project is already developing computational tools to enable the committees to perform their analysis of the energy performance of their buildings, establish the best energetic indicators and having a tool to track the implemented measures, which will serve to establish the savings produced and its equivalent in mitigating greenhouse Gases (GHG). The next immediate step for the EEPB project is the development of pilot projects in coordination with the Ministry of Health and other institutions for a total amount of approximately USD $ 150,000. The results of the implementation can be replicated in other buildings with similar conditions. The union of all the measures described above, will allow the Government to have the capacity to identify and implement measures with the support of technical and legal standards that are being developed, achieve an important decrease of energy consumption, which could be around 20% according to preliminary estimates. The risks encountered in achieving the project's objectives are about the Government capacity to fund all the energy efficiency measures, however, the proposed strategy to overcome this obstacle has been proposing to COEEs to start with low-cost measures in its implementation and that can develop through stages. The investments are implemented by cost and by the better Pay-back, since this will allow a fast recovery of the investment for developing other measures identified. Another of the difficulties encountered in the implementation of the project is the development of standards for the construction of buildings that impact on the energy consumption in this sector. The difficulty is due to the construction sector is responsibility of several institutions of the Executive Government and other local governments, among which we can mention the Vice-Ministry of housing and Office of Planning of the Metropolitan Area of San Salvador (OPAMSS). This situation makes difficult to harmonize technical approaches to the development of a policy on the issue of efficient construction. Therefore the project is working to unify the technical criteria with the consultancy of all the sectors and institutions involved in this topic. |  |  |  | 2
UNDP Country Office Programme Officer: Is the UNDP programme officer in the UNDP country office who provides oversight and supervision support to the project.
MANDATORY RATING MUST BE PROVIDED for projects under implementation in one country. Not necessary for regional or global projects.
Please justify your rating and address the following points in your comments. Please keep word count between 500 words minimum and 1200 words maximum. 1. Explain why you gave a specific rating. For example, if your rating differs from the rating provided by the project manager please explain why. 2. Note trends, both positive and negative, in achievement of outcomes as per the updated indicators provided in the DO sheet. 3. Fully explain the critical risks that have affected progress. 4. Outline action plan to address projects with DO rating of HU, U or MU.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
|  |  |  | S | I agree with the Project Coordinator with a rating of Satisfactory because I think the project has had results of impact during this period. This project has strong challenges trying to remove barriers to energy efficiency in El Salvador. The first and very important contribution of this project is the strengthening of capacities of National Energy Council (CNE, for its acronym in Spanish) specifically the Energy Efficiency Unit which is responsible for the EE promotion in the country. Until now, the project has significant results and it´s having an impact at several levels: (A) National level, supporting and diffusing the new regulatory framework for El Salvador with the National Energy Policy and the Bill of Energy Efficiency Law which is in review in Presidential House. Another output is the establishment of baseline of energy consumption for the public sector that also will serve as an input to develop a strategy of national plan for savings in energy consumption (B) Government level, (i) Establishment of Energy Efficiency committees (COEEs) inside of more than 90 public institutions; (ii) training the COEEs members with workshops, meetings and a Diploma in EE in buildings (iii) monitoring the formulation and implementation of Energy Efficiency Plans, like the experiences of Consumer Ombudsman´s Office (10% reduction in energy consumption) and Ministry of Environment and Natural Resources (20% reduction in energy consumption); (iv) energy diagnosis for 6 national hospitals with the specific recommendations and measures to implement; (v) Developing a Purchasing Manual with EE criteria ; (C) Environmental level, because the project has already reported Tons of CO2 avoided and with the EE plans completed and implemented, more GHG will be avoided. The National Energy Council (CNE, for its acronym in Spanish) and the Ministry of Economy supported its strategy of National Energy Efficiency in the outcomes of the project and also the President of El Salvador launched an Austerity and Saving Decree for public sector supported in the actions of EEPB project. The project is developing a Procurement Manual with Energy Efficiency Criteria, for the Government Sector that will be a standard for the Procurement Units for all the public institutions. During this period, the project had to overcome difficulties like the lack of information about the inventory of public buildings (more than 6500 buildings), the absence of a baseline in the energy consumption of the government sector, the gap in the regulatory framework, changes in the entity responsible for the regulating standards and the poor technical knowledge of institution members about energy issues. Some problems are already solved, and at the end of 2012 most of them will be overcome with the resulting outputs. It is very important to mention that especially the lack of information delayed the execution of the consultancies and the start of implementation actions. These delays will be overtaken in the next months. Another very important contribution of this project is the design of two computing tools for monitoring automatically the energy consumption of the buildings of each institution. This tool enables to make the analysis and record the impact of implemented actions in EE. The other one is the software to evaluate the energetic performance of a building. This software will be useful not only in public sector, but in the future national regulatory framework for the building construction in the country. |  |  |  | 2
GEF Operational Focal point: Is the government representative in the country designed as the GEF operation focal point.
HIGHLY RECOMMENDED but NOT mandatory for projects under implementation in one country. Not necessary for regional or global projects.
Please justify your rating and address the following points in your comments. Please keep word count between 200 minimum and 500 words maximum. 1. Explain why you gave a specific rating. 2. Note trends, both positive and negative, in achievement of outcomes as per the updated indicators provided in the DO sheet. 3. Provide recommendations for next steps.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
Project Implementing Partner: Is the representative of the executing agency (in GEF terminology). This would be Government (for NEX/NIM execution) or NGO (for CSO Execution) or an official from the Executing Agency (for example UNOPS).
RECOMMENDED but NOT mandatory for projects under implementation in one country and regional projects.
Please justify your rating and address the following points in your comments. Please keep word count between 200 minimum and 500 words maximum. 1. Explain why you gave a specific rating. 2. Note trends, both positive and negative, in achievement of outcomes as per the updated indicators provided in the DO sheet. 3. Provide recommendations for next steps.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
Other Partners: For jointly implemented projects, a representative of the other Agency working with UNDP on project implementation (for example UNEP or the World Bank).
RECOMMENDED but NOT mandatory for jointly implemented projects.
Please justify your rating and address the following points in your comments. Please keep word count between 200 minimum and 500 words maximum. 1. Explain why you gave a specific rating. 2. Note trends, both positive and negative, in achievement of outcomes as as per the updated indicators provided in the DO sheet. 3. Provide recommendations for next steps.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
N/A
UNDP Technical Adviser: Is the UNDP-GEF Technical Adviser
MANDATORY for ALL projects.
Please justify your rating and address the following points in your comments. Please keep word count between 500 words minimum and 1200 words maximum. 1. DO NOT repeat the project objective. 2. Explain why you gave a specific rating. If your rating differs from the rating provided by the UNDP Country Office Programme Officer and/or the Project Manager please explain why. 3. Note trends, both positive and negative, in achievement of outcomes as as per the updated indicators provided in the DO sheet. 4. Fully explain the critical risks that have affected progress. 5. Outline action plan to address projects with DO rating of HU, U or MU.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
|  |  |  | S | The project is making remarkable efforts in transforming the energy efficiency industry in El Salvador, with strong government support and relevant regulatory progress. These efforts are already translating into a significantly high financing and investment drive, for instance in hospitals, that are already setting the project on course to surpass its emission reductions targets right from the start. The exceptional performance shown by the establishment of 90 centers of energy efficiency, in comparison to the targeted 16, would have been rated as “Highly Satisfactory” had the project been at a closure rather than inception stage. Needless to say, the expected trend is that indeed in can set best practice for the Central American region and elsewhere if it follows the same pattern of performance during the life of the GEF-financed, UNDP-supported project. The ongoing support to the energy efficiency bill and national energy policy confirms the strong political buy-in the initiative has already obtained. Therefore, only issues such as lack of unification of energy efficiency standards across sectors (e.g. the construction sector versus other industries) may jeopardize an optimal realization of end-of-project targets and environmental benefits. This would be a regrettable outcome considering the strengthened enabling environment the project is helping set up at the national level. Indeed, direct implementing partners such as the National Energy Council, need to reap the fruits of the momentum created following the establishment of an Energy Efficiency unit responsible for the promotion of energy efficiency in the country. This body can positively contribute to the development of demand-side management measures in public buildings nationwide, and the required capacity development necessary in ensuring that efforts are sustained beyond the project’s lifetime. Beyond the successful training of government agency staff, and the building of knowledge, the regulatory progress (particularly, in the hospital sector) will underpin a stronger private sector development in the area of energy efficiency (industry best practices, standards and labels). Indeed, the promotion of public-private partnerships in this area, as a potential model to adequately strengthen the institutional arrangements required to address country needs, could be translated into more tangible project interventions (as measured by CO2 emission reductions, amounts of investment, number of initiatives underway). Failure to successfully engage the private sector, based on the significant government push would a missed opportunity for relevant technology uptake. The room for improvement is reflected by the number of low-hanging fruits/low-cost or negative marginal abatement costs that energy efficiency opportunities are presenting itself for El Salvador (e.g. housing, other buildings, standards and labels, appliances). On the government side, the available funding for energy efficiency needs to consider these potential cost-efficiencies before making demand-side management measures too dependent on public financing. Notwithstanding, the project is on target to achieve most key objectives, considering its pace of industry transformation and regulatory progress. The sooner the policy processes are finalized, the earlier the current trend of implemented energy efficiency measures for hospitals; the energy efficiency procurement manual; and, the information made available by the energy efficiency consumption baseline; can lead to tangible impacts. |  |  |  | 2
General Comments
If you have any comments about the data/information on this sheet, please add them here:
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## IP
Link to Outcome positions on DO sheet
0
0
0
0
0
Project: Energy Efficiency in Public Buildings (EEPB) | [7 empty] | Project: Energy Efficiency in Public Buildings (EEPB)
0
0
Implementation Progress (IP) | [7 empty] | Progress Towards Meeting Development Objective (DO)
List maximum 4 key outputs delivered this reporting period only. | [7 empty] | Each indicator must be updated for this reporting period in the column “Level at 30 June 2012”. Numerical figures must be reported as cumulative from the project start. If there are no changes to report for a given indicator, then enter “N/A” or briefly explain the reason in that column.
Please complete the cells with white background colour only. There is a general comment box at the bottom of this sheet if you would like to provide comments. | [7 empty] | If the logframe indicators were revised and approved by the Project Board, please make the corresponding changes in column D below.
Please complete the cells with white background colour only. There is a general comment box at the bottom of this sheet if you would like to provide comments.
| Project Outcomes | Outputs reported as of 30 June 2011 | Outputs reported as of 30 June 2012 |  |  |  |  | 0
| Outcome 1 | Effective policies and regulation regarding energy efficiency (EE) in buildings have been developed and applied to the public sector. |  | 37 | DO!C | Effective policies and regulation regarding energy efficiency (EE) in buildings have been developed and applied to the public sector. | Effective policies and regulation regarding energy efficiency (EE) in buildings have been developed and applied to the public sector. | 0
|  |  | Support to new regulatory framework with workshops and meetings to diffuse the National Energy Policy and the Draft of Energy Efficiency Law in process of review and approval. |  |  |  |  | Objective
|  |  | A Procurement Manual with Energy Efficiency Criteria for the Government Sector in implementation |  |  |  |  | 0
|  |  | In process a consultancy for establishment of the baseline of energy consumption in government sector |  |  |  |  | 0
|  |  | An Engineer was hired to add capacity to CNE |  |  |  |  | 0
| Outcome 2 | Technical capacity concerning the design and integration of EE measures in public buildings has been strengthened. |  | 52 | DO!C | Technical capacity concerning the design and integration of EE measures in public buildings has been strengthened. | Technical capacity concerning the design and integration of EE measures in public buildings has been strengthened. | 0
|  |  | 90 governmental energy efficiency committees constituted and working on the identification and implementation of measures of (EE) |  |  |  |  | 0
|  |  | 30 professionals from Government sector in training in the first Diploma of Energy Efficiency in Buildings. |  |  |  |  | 0
|  |  | A consultancy for the development of an analysis tool of the energetic permormance of buildings |  |  |  |  | 0
|  |  | The project organized and held 4 inception workshops for EE Committees, with the participation of 189 persons from 90 institutions, with 24% of the participants being women. |  |  |  |  | 0
| Outcome 3 | An energy efficiency programme has been designed and implemented within public buildings. |  | 67 | DO!C | An energy efficiency programme has been designed and implemented within public buildings. | An energy efficiency programme has been designed and implemented within public buildings. | 0
|  |  | 2 pilot projects implemented in Consumer Ombudsman's Office and Ministry of Environment and Natural Resources, consisting in the replacement of 274 luminaires by more efficient technologies, which caused a decrease of approximately 10% (Consumer Ombudsman's Office) and 20% (Ministry of Environment and Natural Resources) of the total consumption of electrical energy in their buildings. |  |  |  |  | 0
|  |  | Identification of energy efficiency measures in 9 institutions through EE committees in Government sector. |  |  |  |  | 0
|  |  | Identification of energy efficiency measures, recommendations and investments in 6 public hospitals, and the progress of the 4 remaining |  |  |  |  | 0
|  |  | The project started developing an online system for monitoring and evaluation of the various EE measures, with support from GIZ |  |  |  |  | 0
| Outcome 4 | A project monitoring and evaluation plan has been implemented and lessons learnt have been disseminated. |  | 82 | DO!C | A project monitoring and evaluation plan has been implemented and lessons learnt have been disseminated. | A project monitoring and evaluation plan has been implemented and lessons learnt have been disseminated. | 0
|  |  | Initiated the design of a system of information online that will help all institutions in the assessment and monitoring of the implemented energy efficiency measures |  |  |  |  | 0
|  |  | 5000 brochures about the experience and results in the 2 pilots implemented, also a manual of recommendations on efficient use of energy in public sector which describes the lessons learned in this issue. |  |  |  |  | 0
0
0
| Outcome 5 |  |  | 97 | DO!C | 0 |  | 0
0
Outcome 1
0
0
| Outcome 6 |  |  | 112 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 7 |  |  | 127 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 8 |  |  | 142 | DO!C | 0 |  | 0
0
Outcome 2
0
0
| Outcome 9 |  |  | 157 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 10 |  |  | 172 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 11 |  |  | 187 | DO!C | 0 |  | 0
0
Outcome 3
0
0
| Outcome 12 |  |  | 202 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 13 |  |  | 217 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 14 |  |  | 232 | DO!C | 0 |  | 0
0
Outcome 4
0
0
| Outcome 15 |  |  | 247 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 16 |  |  | 262 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 17 |  |  | 277 | DO!C | 0 |  | 0
0
Outcome 5
0
0
| Outcome 18 |  |  | 292 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 19 |  |  | 307 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 20 |  |  | 322 | DO!C | 0 |  | 0
0
Outcome 6
0
0
| Outcome 21 |  |  | 337 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 22 |  |  | 352 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 23 |  |  | 367 | DO!C | 0 |  | 0
0
Outcome 7
0
0
| Outcome 24 |  |  | 382 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 25 |  |  | 397 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 26 |  |  | 412 | DO!C | 0 |  | 0
0
Outcome 8
0
0
| Outcome 27 |  |  | 427 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 28 |  |  | 442 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 29 |  |  | 457 | DO!C | 0 |  | 0
0
Outcome 9
0
0
| Outcome 30 |  |  | 472 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 31 |  |  | 487 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 32 |  |  | 502 | DO!C | 0 |  | 0
0
Outcome 10
0
0
| Outcome 33 |  |  | 517 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 34 |  |  | 532 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 35 |  |  | 547 | DO!C | 0 |  | 0
0
Outcome 11
0
0
| Outcome 36 |  |  | 562 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 37 |  |  | 577 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 38 |  |  | 592 | DO!C | 0 |  | 0
0
Outcome 12
0
0
| Outcome 39 |  |  | 607 | DO!C | 0 |  | 0
0
0
0
0
| Outcome 40 |  |  | 622 | DO!C | 0 |  | 0
0
0
0
0
0
| General Comment. | [6 empty] | 0
| If you have any comments about the data/information on this sheet, please add them here: | [6 empty] | Outcome 13
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 14
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 15
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 16
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 17
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 18
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 19
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 20
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 21
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 22
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 23
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 24
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 25
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 26
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 27
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 28
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 29
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 30
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 31
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 32
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 33
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 34
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 35
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 36
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 37
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 38
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 39
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Outcome 40
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## IPRating
Project: Energy Efficiency in Public Buildings (EEPB)
Rating of Implementation Progress (IP)
Please complete cells with white background only.
Select one of the rating categories outlined in the table below to describe annual progress in project implementation. Please provide an accurate rating and fully justify your rating in the comment box. There is a general comment box at the bottom of this sheet if you would like to provide comments.
|  |  | Rating Definitions |  |  | Rating | Value | Rating | AvgRating | 2 | 2
|  |  | Highly Satisfactory (HS) |  | The project was managed in very effective and efficient manner in accordance with the workplan, schedule and budget. The project can be presented as “good practice”. | HS | 1 | HS | RTA Rating | 2 | 0
|  |  | Satisfactory (S) |  | The project was managed in a reasonably effective and efficient manner, largely in accordance with the workplan, schedule and budget. | S | 2 | S | OverallRating | 2 | S
|  |  | Moderately Satisfactory (MS) |  | The project was managed in an acceptable manner but not fully in accordance with the workplan, schedule and budget. | MS | 3 | MS | AverageAll | 2 | 2
|  |  | Moderately Unsatisfactory (MU) |  | The project was managed in a marginally effective and responsive manner but not fully in accordance with the workplan, schedule and budget. | MU | 4 | MU
|  |  | Unsatisfactory (U) |  | The project was managed in a less than effective manner due to internal or external factors and not in accordance with the workplan, schedule and budget. | U | 5 | U
|  |  | Highly Unsatisfactory (HU) |  | The project was managed in an ineffective manner particularly due to internal factors and clearly not in accordance with the workplan, schedule and budget. | HU | 6 | HU
National Project Manager/Coordinator: Is the person managing the day to day operations of the project.
MANDATORY RATING MUST BE PROVIDED for projects under implementation in one country or regional projects where appropriate.
Please justify your rating and address the following points in your comments. Please keep word count between 500 words minimum and 1200 words maximum. 1. Explain why you gave a specific rating. 2. Summarize annual progress and address timeliness of project output/activity completion in relation to annual workplans. 3. Outline the general status of project expenditures in relation to annual budgets, the effectiveness of project management units in guiding project implementation, the responsiveness of the project board in overseeing project implementation. 4. Outline action plan to address projects with IP rating of HU, U or MU.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
|  |  |  | S | In my opinion the project has managed effectively the financial resources and had achieved very good results, overcoming problems not considered in the design without increasing the costs of the project. At the beginning the project had a delay because of the establishment of project team and the training process, but this lag will be overcome in 2012 because the project has contracted the majority of consultancies and have good progress in purchase process. It is also important to say that the work with the EE Committees will provide good results (in EE measures implemented) in this year. It is important to mention that it has been difficult to find experts in some specific areas, not all the consultancies had expressions of interest even though the process was published in newspapers and virtual media. The consultancy for the establishment of the base line of the consumption of energy in the Government sector has required the search for energy information of all the institutions of Government. To get this information it was necessary to use the database of distributors, but this database does not have an identifier specific for the Government and the consulting company had to do an exhaustive search of the consumption of energy for more than 6,500 government buildings. Now, it is almost finished the consultancy with the baseline of energy consumption already established and with other very important and useful information to prepare de EE strategy for El Salvador. In the other hand, the consulting to establish the pilot projects to be developed in 10 hospitals in the national network of health had finished 4 energy audits with a list of specific measures in EE, the investments, the GHG avoided, and recommendations for energy conservation. With the results of the consulting, the project had coordinated meetings with the Ministry of Health and the Directors of selected hospitals to make an implementation plan with the measures reflected in the energy studies submitted by the consulting company. The energy audits of 2 more hospitals were finished with the support of Universidad Centro Americana, UCA (also counterpart of this project) and now the studies are under review and analysis to decide the EE measures to implement. The recruitment of consulting services to develop a methodology for the evaluation of the energy performance of buildings, has needed more time than considered, because it was necessary publish 3 times the request for expressions of interest to find professionals. As a summary, the project had difficulties in the execution of the activities programmed for this year, but now it is overcome and for the end of 2012 there will be running pilots in hospitals, energy efficiency strategy and saving targets achieved, 90 COEEs working in their institutions, 30 professionals trained in EE with a Diploma, EE plans defined, software tools running. Nowadays, the project has financial commitments for more than $278,000 to be paid in the next two months and will continue with the financial execution to complete de Budget for 2012. |  |  |  | 2
UNDP Country Office Programme Officer: Is the UNDP programme officer in the UNDP country office who provides oversight and supervision support to the project.
MANDATORY RATING MUST BE PROVIDED for projects under implementation in one country. Not necessary for regional or global projects.
Please justify your rating and address the following points in your comments. The QORs and delivery data in the ERBM portfolio project monitoring report should inform your rating. Please keep word count between 500 words minimum and 1200 words maximum. 1. Explain why you gave a specific rating. If your rating differs from the rating provided by the project manager please explain why. 2. Summarize annual progress and address timeliness of project output/activity completion in relation to annual workplans. 3. Outline the general status of project expenditures in relation to annual budgets, the effectiveness of project management units in guiding project implementation, the responsiveness of the project board in overseeing project implementation.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
|  |  |  | S | I agree with the rating of S because the project has achieved very important results until now, and has a good perspective in the financial delivery for 2012. It is very important to point out that in the beginning the project had some delay to start, and this delay, impacted the delivery for this reporting period, but with the actual trend, the lag will be overcome in 2012.The project has managed the resources in a very effective and efficient way because it has been able to manage, training, monitor, follow and support 90 EE Committees (COEE) in different developmental stages despite the target of the project was the establishment of 16 COEEs. The project responded (using the allocated budget) to an appeal of the Salvadoran Government with the Executive Decree of Austerity and Savings which established as mandatory the energy conservation in public sector. It is also important to mention that the project has systematized the methodology for the creation of COEEs for future replication in other sectors. Another issue that delayed the implementation was the lack of information the project had to overcome for the establishment of strategies and targets in energy efficiency. For example in El Salvador there wasn´t an inventory of public buildings and an inventory of the electric services contracts that the Government has, also there wasn´t a baseline of the consumption of de public sector and now, with the project these information will be available this year. The energy audits made in 6 hospitals (until now) detected many EE measures and huge potential savings for the Ministry of Health. The recommendations made by the project will allow this Ministry to define an EE investment plan with a clear projection of savings and diminution of GHG. The project EEPB in this period of time had contributed to remove barriers to energy efficiency with technical trainings, studies, information, advice on technical issues, support to legal framework, establishment of 90 COEEs in public institutions, implementation and monitoring of EE measures in some institutions and investment plan in EE for another, and diffusion and publication of lessons learned. Financially, by the end of 2012, the project will be in line with its budget, because it already has commitments for more than $278000 to be paid (consultancies, EE Diploma) before October. The implementation of EE measures are budget this year and represent more than $75000. |  |  |  | 2
GEF Operational Focal point: Is the government representative in the country designed as the GEF operation focal point.
HIGHLY RECOMMENDED but NOT mandatory for projects under implementation in one country. Not necessary for regional or global projects.
Please justify your rating and address the following points in your comments. Please keep word count between 200 minimum and 500 words maximum. 1. Explain why you gave a specific rating. 2. Note trends, both positive and negative. 3. Provide recommendations for next steps.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
Project Implementing Partner: Is the representative of the executing agency (in GEF terminology). This would be Government (for NEX/NIM execution) or NGO (for CSO Execution) or an official from the Executing Agency (for example UNOPS).
RECOMMENDED but NOT mandatory for projects under implementation in one country and regional projects.
Please justify your rating and address the following points in your comments. Please keep word count between 200 minimum and 500 words maximum. 1. Explain why you gave a specific rating. 2. Note trends, both positive and negative. 3. Provide recommendations for next steps.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
Other Partners: For jointly implemented projects, a representative of the other Agency working with UNDP on project implementation (for example UNEP or the World Bank).
RECOMMENDED but NOT mandatory for jointly implemented projects.
Please justify your rating and address the following points in your comments. Please keep word count between 200 minimum and 500 words maximum. 1. Explain why you gave a specific rating. 2. Note trends, both positive and negative. 3. Provide recommedations for next steps.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
UNDP Technical Adviser: Is the UNDP-GEF Technical Adviser
MANDATORY for ALL projects.
Please justify your rating and address the following points in your comments. The QORs and delivery data in the ERBM portfolio project monitoring report should inform your rating. Please keep word count between 500 words minimum and 1200 words maximum. 1. Explain why you gave a specific rating. If your rating differs from the rating provided by the UNDP Country Office Programme Officer and/or the Project Manager please explain why. 2. Summarize annual progress and address timeliness of project output/activity completion in relation to annual workplans. 3. Outline the general status of project expenditures in relation to annual budgets, the effectiveness of project management units in guiding project implementation, the responsiveness of the project board in overseeing project implementation.
| 2009 Rating | 2010 Rating | 2011 Rating | 2012 Rating | Comments
|  |  |  | S | Project performance is considered satisfactory considering that the project is in first full year of implementation. Although not shown in financial terms, judging from the delivery rates towards the end the reporting period (%7-8), substantive technical/physical delivery has been reported by the project on an annual basis. For instance, by the first quarter of 2012, 9 new committees in energy efficiency were established in government entities (already beyond the midpoint end-of-project target). Indeed, it brings the total number to 16 institutions in total, with committees already conducting energy assessments in their buildings. There are already 29 members of these Committees being trained in the Certificate of Energy Efficiency in Buildings. This progress is underpinned by effective adaptive management carried out by key project counterparts. The results are particularly visible on the regulatory front, with the ongoing support to the energy efficiency bill already translated into the previously noted results within twelve months. In the process, the project is already catalyzing the communication impact, by making continuous efforts to support awareness-raising activities during the reporting period, for instance, by sharing ongoing results in hospitals. Therefore, key targets set forth through to June 30, 2012 are being steadily attained following an integrated implementation oversight of the project board and the project management unit. The project has also built on knowledge and disseminated its own best practices in international fora. Indeed, the progress being made in greenhouse gas monitoring tools and systems, developing performance indicators, and using computerized systems, shows how keen the project management is in making the impacts attained known. Therefore, nationwide efforts to raise awareness on the technical standards being developed are also having a positive dissemination effect. So, although project expenditure in various components may seem slow (e.g. the development of financing mechanisms, or the multi-sectorial strategy), progress reports signal an unprecedented pace of activity, which should be expected to translate in results. In this regard, the setup of the GEF project coordination unit completed in the first semester of 2011, and its integrated planning approach with UNDP enhanced results-based management (ERBM) approaches, under the oversight of NEC is resulting in a more efficient use of project resources. For instance, procurement plans have reflected the focus placed on having the largest consultancies engaged at the beginning of the year, in line with the attainment of key annual targets. This approach has exposed an area that project implementation needs to monitor carefully, i.e. the expected length of internal processes to observe standard UNDP-GEF requirements, e.g. the transaction costs of national Contract, Assets and Procurement (CAP) and regional Advisory Committee for Procurement (ACP) rules and procedures. If their timing are not factored in when carrying out project budgeting exercises, i.e. defining the program of activities (POA) the year, developing the annual work plans (AWP), determining the adequate authorized spending limits (ASL) for the project, technical delivery will hardly translate into financial delivery, like so far this year. It is therefore crucial that key project counterparts (NEC representatives, UNDP country office, GEF project coordination unit) consider this planning approach ahead of the next reporting period, and continue working in an integrated manner as satisfactorily done this period. Indeed, the project it is at a stage where higher rates of implementation are expected (especially, once all procurement processes are completed) than either at the beginning or the end of the project. At post-inception stage, cumulative delivery stands at 13% ($128,000 out of $847,000) with plenty of room for improvement but positive prospects. |  |  |  | 2
General Comments
If you have any comments about the data/information on this sheet, please add them here:
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## Adjustments
Project: Energy Efficiency in Public Buildings (EEPB)
Adjustments to Key Project Milestones and Project Strategy, and Risk Management
Please complete the three sections of this sheet: Key Project Milestones, Adjustments to Project Strategy, and Critical Risk Management.
Please complete the cells with white background colour only.
Key Project Milestones
|  |  | Have significant delays occurred in the project start, inception workshop, Mid-term Review, Terminal Evaluation or project duration? | Yes | Dates |  |  | 0 | Environmental
|  |  | If yes, were these changes reported in a previous APR/PIR? | No | Jan 2003 | Jan | 2003 | 1 | Financial
|  |  | If no, complete the table below. |  | Feb 2003 | Feb | 2003 | 2 | Operational
[5 empty] | Mar 2003 | Mar | 2003 | 3 | Organizational
| Key project milestone | Scope of Delay (in months): | Briefly Describe Change or Reason for Change | Briefly describe the implications or consequences this has had on project implementation. | Apr 2003 | Apr | 2003 | 4 | Political
| Project Start (i.e. project document signature date) | 6 | In January 2011 was officially started the project EEPB-75672, but the Coordinator was hired in April, in June the Administrative Assistant of the project and in August was hired the Technical Support. Once hired the entire technical team of the project, the induction process begun. | It will be necessary hasten the activities, in order to accomplish the targets at the end of 2013. The project will have a good performance in 2012, that will permit to adjust the activities to finish the outcomes in 2013. | May 2003 | May | 2003 | 5 | Regulatory
| Inception Workshop | 4 | The project inception workshop was done in April, this situation caused a delay of at least 4 months | It will be necessary hasten the activities, in order to accomplish the targets at the end of 2013. The project will have a good performance in 2012, that will permit to adjust the activities to finish the outcomes in 2013. | Jun 2003 | Jun | 2003 | 6 | Strategic
| Mid-term Review |  |  |  | Jul 2003 | Jul | 2003 | 7 | Other
| Terminal Evaluation |  |  |  | Aug 2003 | Aug | 2003 | 8
| Project Duration (i.e. project extension) |  |  |  | Sep 2003 | Sep | 2003 | 9
[5 empty] | Oct 2003 | Oct | 2003 | 10
[5 empty] | Nov 2003 | Nov | 2003 | 11
Adjustments to Project Strategy |  |  |  |  | Dec 2003 | Dec | 2003 | 12
Please report any adjustments made to the project strategy, as reflected in the logical framework matrix, since the Project Document signature |  |  |  |  | Jan 2004 | Jan | 2004 | 13
[5 empty] | Feb 2004 | Feb | 2004 | 14
|  |  | Has the project made any changes to its strategy (i.e. logframe/results framework) since the Project Document was signed? | No | Mar 2004 | Mar | 2004 | 15
|  |  | If yes, were these changes reported in a previous APR/PIR? | No | Apr 2004 | Apr | 2004 | 16
|  |  | If no, complete the table below. |  | May 2004 | May | 2004 | 17
| Change Made to: | Yes/No | Briefly Describe the Change and the Reason for that Change |  | Jun 2004 | Jun | 2004 | 18
| Project Objective | No |  |  | Jul 2004 | Jul | 2004 | 19
| Project Outcomes | No |  |  | Aug 2004 | Aug | 2004 | 20
| Project Outputs/Activities | No |  |  | Sep 2004 | Sep | 2004 | 21
[5 empty] | Oct 2004 | Oct | 2004 | 22
[5 empty] | Nov 2004 | Nov | 2004 | 23
Critical Risk Management |  |  |  |  | Dec 2004 | Dec | 2004 | 24
List type of critical risk as noted in the ATLAS risk log and briefly describe actions undertaken this reporting period to address each critical risk. |  |  |  |  | Jan 2005 | Jan | 2005 | More
[5 empty] | Feb 2005 | Feb | 2005
|  | Type of critical risk (only critical risks) as noted in ATLAS risk log | Risk management measures undertaken this reporting period |  | Mar 2005 | Mar | 2005
|  | Strategic | The CNE has led to the creation of legal instruments as the Executive Decree 78 of the year 2012, in which requires the Organization of committees for energy efficiency; this will help institutions to promote energy efficiency measures that produce savings. |  | Apr 2005 | Apr | 2005
|  | Environmental | Worked in a very coordinated manner with the Ministry of public health, with the aim that the hospitals pilot projects have the best results. |  | May 2005 | May | 2005
[5 empty] | Jun 2005 | Jun | 2005
[5 empty] | Jul 2005 | Jul | 2005
[5 empty] | Aug 2005 | Aug | 2005
[5 empty] | Sep 2005 | Sep | 2005
[5 empty] | Oct 2005 | Oct | 2005
[5 empty] | Nov 2005 | Nov | 2005
[5 empty] | Dec 2005 | Dec | 2005
[5 empty] | Jan 2006 | Jan | 2006
[5 empty] | Feb 2006 | Feb | 2006
[5 empty] | Mar 2006 | Mar | 2006
| General Comments |  |  |  | Apr 2006 | Apr | 2006
| If you have any comments about the data/information on this sheet, please add them here: |  |  |  | May 2006 | May | 2006
[5 empty] | Jun 2006 | Jun | 2006
[5 empty] | Jul 2006 | Jul | 2006
[5 empty] | Aug 2006 | Aug | 2006
[5 empty] | Sep 2006 | Sep | 2006
[5 empty] | Oct 2006 | Oct | 2006
[5 empty] | Nov 2006 | Nov | 2006
[5 empty] | Dec 2006 | Dec | 2006
[5 empty] | Jan 2007 | Jan | 2007
[5 empty] | Feb 2007 | Feb | 2007
[5 empty] | Mar 2007 | Mar | 2007
[5 empty] | Apr 2007 | Apr | 2007
[5 empty] | May 2007 | May | 2007
[5 empty] | Jun 2007 | Jun | 2007
[5 empty] | Jul 2007 | Jul | 2007
[5 empty] | Aug 2007 | Aug | 2007
[5 empty] | Sep 2007 | Sep | 2007
[5 empty] | Oct 2007 | Oct | 2007
[5 empty] | Nov 2007 | Nov | 2007
[5 empty] | Dec 2007 | Dec | 2007
[5 empty] | Jan 2008 | Jan | 2008
[5 empty] | Feb 2008 | Feb | 2008
[5 empty] | Mar 2008 | Mar | 2008
[5 empty] | Apr 2008 | Apr | 2008
[5 empty] | May 2008 | May | 2008
[5 empty] | Jun 2008 | Jun | 2008
[5 empty] | Jul 2008 | Jul | 2008
[5 empty] | Aug 2008 | Aug | 2008
[5 empty] | Sep 2008 | Sep | 2008
[5 empty] | Oct 2008 | Oct | 2008
[5 empty] | Nov 2008 | Nov | 2008
[5 empty] | Dec 2008 | Dec | 2008
[5 empty] | Jan 2009 | Jan | 2009
[5 empty] | Feb 2009 | Feb | 2009
[5 empty] | Mar 2009 | Mar | 2009
[5 empty] | Apr 2009 | Apr | 2009
[5 empty] | May 2009 | May | 2009
[5 empty] | Jun 2009 | Jun | 2009
[5 empty] | Jul 2009 | Jul | 2009
[5 empty] | Aug 2009 | Aug | 2009
[5 empty] | Sep 2009 | Sep | 2009
[5 empty] | Oct 2009 | Oct | 2009
[5 empty] | Nov 2009 | Nov | 2009
[5 empty] | Dec 2009 | Dec | 2009
[5 empty] | Jan 2010 | Jan | 2010
[5 empty] | Feb 2010 | Feb | 2010
[5 empty] | Mar 2010 | Mar | 2010
[5 empty] | Apr 2010 | Apr | 2010
[5 empty] | May 2010 | May | 2010
[5 empty] | Jun 2010 | Jun | 2010
[5 empty] | Jul 2010 | Jul | 2010
[5 empty] | Aug 2010 | Aug | 2010
[5 empty] | Sep 2010 | Sep | 2010
[5 empty] | Oct 2010 | Oct | 2010
[5 empty] | Nov 2010 | Nov | 2010
[5 empty] | Dec 2010 | Dec | 2010
[5 empty] | Jan 2011 | Jan | 2011
[5 empty] | Feb 2011 | Feb | 2011
[5 empty] | Mar 2011 | Mar | 2011
[5 empty] | Apr 2011 | Apr | 2011
[5 empty] | May 2011 | May | 2011
[5 empty] | Jun 2011 | Jun | 2011
[5 empty] | Jul 2011 | Jul | 2011
[5 empty] | Aug 2011 | Aug | 2011
[5 empty] | Sep 2011 | Sep | 2011
[5 empty] | Oct 2011 | Oct | 2011
[5 empty] | Nov 2011 | Nov | 2011
[5 empty] | Dec 2011 | Dec | 2011
[5 empty] | Jan 2012 | Jan | 2012
[5 empty] | Feb 2012 | Feb | 2012
[5 empty] | Mar 2012 | Mar | 2012
[5 empty] | Apr 2012 | Apr | 2012
[5 empty] | May 2012 | May | 2012
[5 empty] | Jun 2012 | Jun | 2012
[5 empty] | Jul 2012 | Jul | 2012
[5 empty] | Aug 2012 | Aug | 2012
[5 empty] | Sep 2012 | Sep | 2012
[5 empty] | Oct 2012 | Oct | 2012
[5 empty] | Nov 2012 | Nov | 2012
[5 empty] | Dec 2012 | Dec | 2012
[5 empty] | Jan 2013 | Jan | 2013
[5 empty] | Feb 2013 | Feb | 2013
[5 empty] | Mar 2013 | Mar | 2013
[5 empty] | Apr 2013 | Apr | 2013
[5 empty] | May 2013 | May | 2013
[5 empty] | Jun 2013 | Jun | 2013
[5 empty] | Jul 2013 | Jul | 2013
[5 empty] | Aug 2013 | Aug | 2013
[5 empty] | Sep 2013 | Sep | 2013
[5 empty] | Oct 2013 | Oct | 2013
[5 empty] | Nov 2013 | Nov | 2013
[5 empty] | Dec 2013 | Dec | 2013
[5 empty] | Jan 2014 | Jan | 2014
[5 empty] | Feb 2014 | Feb | 2014
[5 empty] | Mar 2014 | Mar | 2014
[5 empty] | Apr 2014 | Apr | 2014
[5 empty] | May 2014 | May | 2014
[5 empty] | Jun 2014 | Jun | 2014
[5 empty] | Jul 2014 | Jul | 2014
[5 empty] | Aug 2014 | Aug | 2014
[5 empty] | Sep 2014 | Sep | 2014
[5 empty] | Oct 2014 | Oct | 2014
[5 empty] | Nov 2014 | Nov | 2014
[5 empty] | Dec 2014 | Dec | 2014
[5 empty] | Jan 2015 | Jan | 2015
[5 empty] | Feb 2015 | Feb | 2015
[5 empty] | Mar 2015 | Mar | 2015
[5 empty] | Apr 2015 | Apr | 2015
[5 empty] | May 2015 | May | 2015
[5 empty] | Jun 2015 | Jun | 2015
[5 empty] | Jul 2015 | Jul | 2015
[5 empty] | Aug 2015 | Aug | 2015
[5 empty] | Sep 2015 | Sep | 2015
[5 empty] | Oct 2015 | Oct | 2015
[5 empty] | Nov 2015 | Nov | 2015
[5 empty] | Dec 2015 | Dec | 2015
[5 empty] | Jan 2016 | Jan | 2016
[5 empty] | Feb 2016 | Feb | 2016
[5 empty] | Mar 2016 | Mar | 2016
[5 empty] | Apr 2016 | Apr | 2016
[5 empty] | May 2016 | May | 2016
[5 empty] | Jun 2016 | Jun | 2016
[5 empty] | Jul 2016 | Jul | 2016
[5 empty] | Aug 2016 | Aug | 2016
[5 empty] | Sep 2016 | Sep | 2016
[5 empty] | Oct 2016 | Oct | 2016
[5 empty] | Nov 2016 | Nov | 2016
[5 empty] | Dec 2016 | Dec | 2016
[5 empty] | Jan 2017 | Jan | 2017
[5 empty] | Feb 2017 | Feb | 2017
[5 empty] | Mar 2017 | Mar | 2017
[5 empty] | Apr 2017 | Apr | 2017
[5 empty] | May 2017 | May | 2017
[5 empty] | Jun 2017 | Jun | 2017
[5 empty] | Jul 2017 | Jul | 2017
[5 empty] | Aug 2017 | Aug | 2017
[5 empty] | Sep 2017 | Sep | 2017
[5 empty] | Oct 2017 | Oct | 2017
[5 empty] | Nov 2017 | Nov | 2017
[5 empty] | Dec 2017 | Dec | 2017
[5 empty] | Jan 2018 | Jan | 2018
[5 empty] | Feb 2018 | Feb | 2018
[5 empty] | Mar 2018 | Mar | 2018
[5 empty] | Apr 2018 | Apr | 2018
[5 empty] | May 2018 | May | 2018
[5 empty] | Jun 2018 | Jun | 2018
[5 empty] | Jul 2018 | Jul | 2018
[5 empty] | Aug 2018 | Aug | 2018
[5 empty] | Sep 2018 | Sep | 2018
[5 empty] | Oct 2018 | Oct | 2018
[5 empty] | Nov 2018 | Nov | 2018
[5 empty] | Dec 2018 | Dec | 2018
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## Finance
Project: Energy Efficiency in Public Buildings (EEPB)
Financial information: cumulative from project start to 30 June 2012
Please enter full numbers below without commas or decimals or fractions. All figures should be in US$. For example, 50,000 would be entered as 50000 not as 0.05.
Please complete the cells with white background colour only.
DISBURSEMENT OF GEF GRANT FUNDS
| TOTAL GEF GRANT = | 975000
How much of the total GEF grant as noted in Project Document plus any project preparation grant has been spent so far?
| Cumulative total disbursement of GEF Grant as of 30 June 2011 | Estimated cumulative total disbursement of GEF Grant as of 30 June 2012 (i.e.CDR information up to 30 June 2012)
112440
|  | Add any comments on GEF Grant Funds. (word limit=200) | The most significant payments will be done during the second half of 2012. There are $278,000 committed in the first 4 consulting , equipment and other processes.
DISBURSEMENT OF CO-FINANCING
| TOTAL planned Co-financing = | 3115000
How much of the total planned co-financing as noted in the Project Document has been spent so far?
Estimated cumulative total co-financing disbursed as of 30 June 2012
335591
| Add any comments on co-financing including other types and amounts of additional co-financing such as in-kind, private sector, grants, credits and loans (word limit = 200) |  | This contribution includes the support given in kind by the CNE, UCA, GIZ and investments in the issue of energy efficiency by government institutions.
ACTUAL CO-FINANCING: only report on actual co-financing if it was determined during the MTR or TE process.
How much of the total planned co-financing as committed in the Project Document has actually been realized? Note that resources that are not committed as part of the project document but which are mobilized subsequently are not included as co-financing, they are leveraged resources. See section below to report on leveraged resources.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE) as of 30 June 2012
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
ADDITIONAL LEVERAGED RESOURCES
Have additional resources that were not included in the project documents as co-financing been realized since project document signature? If so, how much?
Estimated cumulative leveraged resources as of 30 June 2012
Add any comments on Leveraged Resources. (word limit=200)
Other Financial Instruments
Does the project provide funds to other Financial Instruments? (i.e revolving funds, guaranteed funds, credit lines & feed-in-tariffs etc…)
Please explain type of non-grant financial mechanism used
Please discuss developments that occurred this reporting period only
General Comments
If you have any comments about the data/information on this sheet, please add them here:
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## Communications and KM
Project: Energy Efficiency in Public Buildings (EEPB)
Communications and KM
All projects must complete the first 3 questions in this section.
Please complete the cells with white background colour only.
1. Tell the Story of Your Project and What has been Achieved this Reporting Period
This text will be used for external communications and may be posted on the UNDP-GEF website and the UNDP public website. Please make special mention of the project’s development benefits such as increased income, alternative livelihoods, health benefits for project participants, or other benefits to local communities not reflected elsewhere in the APR/PIR. (Word limit = 200)
The project EEPB seeks to break down barriers for energy efficiency in Government sector in El Salvador. The obstacles detected are technical, legal, commercial, lack of information, absence of a baseline, lack of conscience in environmental issues. The project is developing technical capacities in the public institutions through workshops, procurement manuals and a diploma in EE in buildings addressed to public sector. Actually, there are more than 90 Energy Efficiency Committees in the same amount of institutions, establishing and implementing their own EE plans. The activities of the project allowed knowing the energy consumption baseline of Government sector and the inventory of public buildings in El Salvador and this information will permit the construction of a EE National Plan. Also the project is supporting the new legal framework for EE; and it is finishing energy audits in 10 very representative hospitals to define the measures to implement and the guidelines to establish an EE Plan applicable to all the national hospitals in the country. Besides, it is constructing useful software tools to model de thermal and energy consumption of buildings and an online tool to monitor the energy consumption of all the institutions automatically.
2. Adaptive Management this Reporting Period
This text will be used for internal knowledge management in the respective technical team and region.
One of the main difficulties faced by this project is the development of technical capacities in energy efficiency of a large set of governmental institutions. Each EE Commitee (COEE) needs capacitation and monitoring to elaborate their own EE Plan. In 2012 with de Executive Decree of Austerity and Savings, more than 75 institutions established a COEE, there were already 16, and all are working in its EE plan. The project absorbed the extra work while fulfilling the activities established for 2012.
3. Lessons Learned
This text will be used for internal knowledge management within the respective technical team and region.
In El Salvador there are 7,525 electric service contracts for the 6,501 public buildings. The collection of the information about the energy consumption of each institution is very difficult, that´s why the project decided to use the database of the distributors of energy by the number of identification service (NIS) of each institution. This procedure make the collection and analysis of information more easy and reliable. The organization of small EE committees in each Government institution, is a very important key to manage the energy efficiency issues because allows the staff members to appropriate of their own EE plans and ensure sustainability and follow-up of measures developed. The implementation of more efficient lighting systems in public office buildings allows savings of more than 50% of energy consumption (in lighting) while the replacement of refrigerant in air conditioning systems will produce savings of between 15 and 20%.
General Comments
If you have any comments about the data/information on this sheet, please add them here:
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## Partnerships
Project: Energy Efficiency in Public Buildings (EEPB)
Partnerships
All projects must complete this section. Please enter “N/A” in cells that are not applicable to your project.
Please complete the cells with white background colour only.
Describe innovative aspects of the project in working with (word limit=200 words for each section):
| Civil Society Organisations/NGOs | N/A
| Indigenous Peoples | N/A
| Private Sector | N/A
| GEF Small Grants Programme | N/A
| Other Partners | N/A
General Comments
If you have any comments about the data/information on this sheet, please add them here:
N/A
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## Gender
Project: Energy Efficiency in Public Buildings (EEPB)
Gender Relevance |  |  |  | Yes
All projects must complete this section. Please enter “N/A” in comments cells that are not applicable to your project. Please complete the cells with white background colour only. |  |  |  | No
was previously carried out
|  | Has a gender or social assessment been carried out this reporting period? | No | will be carried out in the future
|  | If a gender or social assessment has been carried out what were the findings? | N/A
| Does this project specifically target women or girls as key stakeholders? | No
| Have there been any changes in specifically targeting women or girls as key stakeholders this reporting period? | No
|  | If yes, please explain | N/A
| Please discuss any of the points above further or provide any other information on the project’s work on gender equality undertaken this reporting period. Some points to consider: impact of project on daily workload of women, # of jobs created for women, impact of project on time spent by women in household activities, impact of project on primary school enrolment for girls/boys, increase in women’s income, etc. Be as specific as possible and provide real numbers (e.g. 100 women farmers participating in sustainable livelihoods programme). |  | In the workshops and trainings for COEEs, there is a 24% of women participation. The project encourages women's participation as a member of the COEEs and consulting processes.
General Comments
If you have any comments about the data/information on this sheet, please add them here:
In all the future process the project will ensure the women participation.
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## Instructions for GEF TT
Project: Energy Efficiency in Public Buildings (EEPB)
Climate Change Mitigation GEF Tracking Tool APR/PIR Template Instructions
All CCM projects are required by the GEF to complete the CCM tracking tool at 3 stages in the project cycle: CEO Endorsement (to set the baseline), mid point in the project cycle, and closing phase. Projects at mid-term and in the closing phase MUST complete the GEF TT embedded in the 2012 APR/PIR. The GEF TT completed at CEO endorsement is completed in a separate file that MUST be uploaded to the UNDP-GEF PIMS system.
CHOOSING ONE GEF 5 OBJECTIVE
Each project is required to complete ONE section of the GEF TT found on the next tab: Objective 1: Transfer of Innovative Technologies or Objective 2: Energy Efficiency or Objective 3: Renewable Energy, or Objective 4: Transport and Urban Systems, or Objective 5: LULUCF, or Objective 6: Enabling Activities
For projects approved in previous GEF phases (i.e. GEF 1, 2, 3 and 4) please align the original objective of the project to one of the current GEF 5 objectives, as noted above. Projects should be informed by the original objectives spelled out in the PIF, based on previous GEF categories and frameworks. In some exceptional cases, a project approved in a previous GEF phase may need to choose more than one GEF-5 objective. For these few projects please fill out all those sections while taking care to avoid duplication of reporting (e.g. GHG emissions need to be properly disaggregated by objective).
SPECIAL NOTE RE OBJECTIVE 1: Transfer of Innovative Technologies should only be filled out if the project was approved in GEF-5 under the Climate Change focal area strategy: Projects supported under this objective will target the demonstrations and deployment of innovative technologies that could have significant impact in the long-run in reducing GHG emissions. GEF support may also involve the demonstrations, deployment, and transfer of priority technologies identified by the recipient countries that are commercially available but have not been adopted in their particular markets. Technologies at the diffusion stage or projects that aim to support wide-scale dissemination of proven and available technologies are not to be supported under this objective; instead, they should be considered under other objectives. The technologies aimed for support by the GEF should be consistent with the priorities identified in the TNAs, national communications to the UNFCCC, or other national policy documents.
CALCULATING GHG EMISSIONS AVOIDED
Please ensure that data is reported in the metrics specified in the GEF CCM tracking tools.
For Energy efficiency and renewable energy projects, GHG emissions avoided should be calculated using the following manual and calculator:
Manual for Energy Efficiency and Renewable Energy Projects
For projects dealing with Transport and Urban Systems, GHG emissions avoided should be calculated using the following manual and calculator:
GHG Benefits Calculator & Manual for Transportation Projects
SPECIAL NOTES ON TRACKING EMISSIONS AVOIDED
MID-TERM APR/PIR
At the mid-term stage, indicate the actual amount realized for: Lifetime direct GHG emissions avoided only. These will mainly be from actual activities funded by the project (GEF and co-financing) such as demonstrations/pilots that are already in operation before the mid-term APR/PIR; as well as projects that are funded through a financing scheme that is developed, funded and operationalized by the GEF project, that are already in operation before the mid-term APR/PIR
Lifetime direct GHG emissions avoided: Lifetime direct GHG emissions avoided are the emissions reductions attributable to the investments made until the mid-term APR/PIR, totaled over the respective lifetime of the investments.
For LULUCF projects, the definition of "lifetime direct" applies. Lifetime length is defined to be 20 years, unless a different number of years is deemed appropriate. For emission or removal factors (tonnes of CO2 eq per hectare per year), use IPCC defaults or country specific factors.
FINAL APR/PIR
Indicate the actual amount realized (as shown in the TE Report) for: Lifetime direct GHG emissions avoided: Lifetime direct GHG emissions avoided are the emissions reductions attributable to the investments made during the project's supervised implementation period, totaled over the respective lifetime of the investments. (These will mainly be from actual activities funded by the project (GEF and co-financing) such as demonstrations/pilots; as well as projects that are funded through a financing scheme that is developed, funded and operationalized by the GEF project, that are in operation during the supervised implementation of the GEF project).
Lifetime direct post-project emissions avoided: Lifetime direct post-project emissions avoided are the emissions reductions attributable to the investments made outside the project's supervised implementation period, but supported by financial facilities put in place by the GEF project, totaled over the respective lifetime of the investments. These financial facilities will still be operational after the project ends, such as partial credit guarantee facilities, risk mitigation facilities, or revolving funds.
Lifetime indirect GHG emissions avoided (top-down and bottom-up): indirect emissions reductions are those attributable to the long-term outcomes of the GEF activities that remove barriers, such as capacity building, innovation, catalytic action for replication. (Either (a) Lifetime indirect GHG emissions avoided (bottom-up); or, (b) Lifetime indirect GHG emissions avoided (top-down), whichever is judged as more accurate; or, (c) Report both figures as the upper and lower values of a range. The amount to be indicated is the total realized as influenced and brought about by the completed activities/interventions of the project but are not under the control of the project.
For LULUCF projects, the definition of "lifetime direct" applies. Lifetime length is defined to be 20 years, unless a different number of years is deemed appropriate. For emission or removal factors (tonnes of CO2 eq per hectare per year), use IPCC defaults or country specific factors.
SPECIAL NOTES ON CALCULATING ENERGY SAVED
Lifetime energy saved should be reported in MJ (Million Joule). Please use the IEA unit converter:
http://www.iea.org/stats/unit.asp
Fuel savings should be converted to energy savings by using the net calorific value of the specific fuel. End-use electricity savings should be converted to energy savings by using the conversion factor for the specific supply and distribution system. Energy savings are then totaled over the respective lifetime of investments.
Lifetime energy savings should be calculated from:
Actual activities funded by the project (GEF and co-financing) such as demonstrations/pilots; as well as projects that are funded through a financing scheme that is developed, funded and operationalized by the GEF project, that are in operation during the supervised implementation of the GEF project; and,
Actual projects implemented after the GEF project and funded by a financing scheme established, funded and operationalized by the GEF project, as well as projects that are assisted under the GEF project (during the GEF project implementation) but are implemented after the completion of the GEF project.
This amount should correspond to the sum of the lifetime direct GHG emissions avoided and lifetime direct post-project GHG emissions avoided.
FURTHER CCM TRACKING TOOL GUIDANCE CAN BE FOUND on Teamworks
2012 Annual Project Review (APR)
Project Implementation Report (PIR)

## CCM TT
Project: Energy Efficiency in Public Buildings (EEPB)
GEF Climate Change Mitigation Tracking Tool
Please complete the cells with white background colour only.
| Is this the mid-term APR/PIR or the FINAL APR/PIR? Please refer to CCM tracking tool instruction tab for details | First APR/PIR | First APR/PIR
Mid-Term APR/PIR
| Special Notes: reporting on lifetime emissions avoided |  | Final APR/PIR
Lifetime direct GHG emissions avoided: Lifetime direct GHG emissions avoided are the emissions reductions attributable to the investments made during the project's supervised implementation period, totaled over the respective lifetime of the investments. Lifetime direct post-project emissions avoided: Lifetime direct post-project emissions avoided are the emissions reductions attributable to the investments made outside the project's supervised implementation period, but supported by financial facilities put in place by the GEF project, totaled over the respective lifetime of the investments. These financial facilities will still be operational after the project ends, such as partial credit guarantee facilities, risk mitigation facilities, or revolving funds. Lifetime indirect GHG emissions avoided (top-down and bottom-up): indirect emissions reductions are those attributable to the long-term outcomes of the GEF activities that remove barriers, such as capacity building, innovation, catalytic action for replication. Please refer to the previous CCM instruction tab for special notes.
Please use the following GEF manual and calculator for EE and RE projects:
Manual for Energy Efficiency and Renewable Energy Projects
Please use the following GEF manual and calculator for transport projects:
Manual for Transportation Projects
For LULUCF projects, the definitions of "lifetime direct and indirect" apply. Lifetime length is defined to be 20 years, unless a different number of years are deemed appropriate. For emission or removal factors (tonnes of CO2eq per hectare per year), use IPCC defaults or country specific factors.
| General Data | Results at mid-point, or result at project closing depending at whether this is the mid-term APR/PIR or final APR/PIR | Yes | 0: no suitable technologies are in place | 0: not an objective/component | 0: not an objective/component | 0: not an objective/component | 0: not an objective/component | 0: not an objective/component | 0: not an objective/component
| Project Title | Energy Efficiency in Public Buildings (EEPB) |  | 1: technologies have been identified and assessed | 1: no policy/regulation/strategy in place | 1: no facility in place | 1: no capacity built | 1: no action | 1: no action | 1: no capacity built
| GEF ID | 3901 |  | 2: technologies have been demonstrated on a pilot basis | 2: policy/regulation/strategy discussed and proposed | 2: facilities discussed and proposed | 2: information disseminated/awareness raised | 2: developing prescriptions for sustainable management | 2: mapping of forests and other land areas | 2: target group informed/awareness raised (e.g. workshops, seminars)
| Agency Project ID | 4244 |  | 3: technologies have been deployed | 3: policy/regulation/strategy proposed but not adopted | 3: facilities proposed but not operationalized/funded | 3: training delivered | 3: development of national standards for certification | 3: compilation and analysis of carbon stock information | 3: target group received substantial training in practical application (e.g. vocational training, course)
| Country | El Salvador |  | 4: technologies have been diffused widely with investments | 4: policy/regulation/strategy adopted but not enforced | 4: facilities operationalized/funded but have no demand | 4: institutional/human capacity strengthened | 4: some of area in project certified | 4: implementation of science based inventory/monitoring system | 4: skillset effectively transferred to target group (e.g. passing examination, certification)
| Region | LCR |  | 5: technologies have reached market potential | 5: policy/regulation/strategy enforced | 5: facilities operationalized/funded and have sufficient demand | 5: institutional/human capacity utilized and sustained | 5: over 80% of area in project certified | 5: monitoring information database publicly available | 5: target group has demonstrated ability to apply skill set or knowledge acquired in training or is able to train others / disseminate knowledge
| GEF Agency | UNDP
| Date of Council/CEO Approval | 2010-07-29
| GEF Grant (US$) | 1000000
| Date of submission of the tracking tool | 2012-09-28
| Is the project consistent with the priorities identified in National Communications, Technology Needs Assessment, or other Enabling Activities under the UNFCCC? | Yes
| Is the project linked to carbon finance? | No
| Cofinancing expected (US$) | 3115000
Objective 1: Transfer of Innovative Technologies (Please refer to the CCM instruction tab for important guidance)
| Please specify the type of enabling environment created for technology transfer through this project | Yes =1, No =0
National innovation and technology transfer policy
Innovation and technology centre and network
Applied R&D support
South-South technology cooperation
North-South technology cooperation
Intellectual property rights (IPR)
Information dissemination
Institutional and technical capacity building
Other (please specify)
Number of innovative technologies demonstrated or deployed
Please specify three key technologies for demonstration or deployment
Area of technology 1
Type of technology 1
Area of technology 2
Type of technology 2
Area of technology 3
Type of technology 3
Status of technology demonstration/deployment
Lifetime direct GHG emissions avoided (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Lifetime direct post-project GHG emissions avoided (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2 eq). Please see special in the CCM instruction tab
Lifetime indirect GHG emissions avoided (top-down) ) (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Objective 2: Energy Efficiency
Please specify if the project targets any of the following areas
| Lighting | Yes
| Appliances (white goods) | No
| Equipment | Yes
| Cook stoves | No
| Existing building | Yes
| New building | Yes
| Industrial processes | No
| Synergy with phase-out of ozone depleting substances | Yes
Other (please specify)
| Policy and regulatory framework | 2: policy/regulation/strategy discussed and proposed
| Establishment of financial facilities (e.g., credit lines, risk guarantees, revolving funds) | 0: not an objective/component
| Capacity building | 3: target group received substantial training in practical application (e.g. vocational training, course)
| Lifetime energy saved (to be reported in MJ, Million Joule). Please use IEA unit converter (Link bellow). Please see special notes on calculating energy saved in the CCM instruction tab | 651300000
http://www.iea.org/stats/unit.asp
| Lifetime direct GHG emissions avoided (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab | 42000
Lifetime direct post-project GHG emissions avoided (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
| Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab | 135000
Lifetime indirect GHG emissions avoided (top-down) ) (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Objective 3: Renewable Energy
Please specify if the project includes any of the following areas
Heat/thermal energy production
On-grid electricity production
Off-grid electricity production
Policy and regulatory framework
Establishment of financial facilities (e.g., credit lines, risk guarantees, revolving funds)
Capacity building
Installed capacity per technology directly resulting from the project
Wind
Biomass
Biomass
Geothermal
Geothermal
Hydro
Photovoltaic (solar lighting included)
Solar thermal heat (heating, water, cooling, process)
Solar thermal power
Marine power (wave, tidal, marine current, osmotic, ocean thermal)
Lifetime energy production per technology directly resulting from the project (IEA unit converter: http://www.iea.org/stats/unit.asp)
Wind
Biomass
Biomass
Geothermal
Geothermal
Hydro
Photovoltaic (solar lighting included)
Solar thermal heat (heating, water, cooling, process)
Solar thermal power
Marine energy (wave, tidal, marine current, osmotic, ocean thermal)
Lifetime direct GHG emissions avoided (Tonnes of CO2)
Lifetime direct post-project GHG emissions avoided (Tonnes of CO2)
Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2)
Lifetime indirect GHG emissions avoided (top-down) (Tonnes of CO2)
Objective 4: Transport and Urban Systems
Please specify if the project targets any of the following areas
Bus rapid transit
Other mass transit (e.g., light rail, heavy rail, water or other mass transit; excluding regular bus or minibus)
Logistics management
Transport efficiency (e.g., vehicle, fuel, network efficiency)
Non-motorized transport (NMT)
Travel demand management
Comprehensive transport initiatives (Involving the coordination of multiple strategies from different transportation sub-sectors)
Sustainable urban initiatives
Policy and regulatory framework
Establishment of financial facilities (e.g., credit lines, risk guarantees, revolving funds)
Capacity building
Length of public rapid transit (PRT)
Length of non-motorized transport (NMT)
Number of lower GHG emission vehicles
Number of people benefiting from the improved transport and urban systems
Lifetime direct GHG emissions avoided (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Lifetime direct post-project GHG emissions avoided (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Lifetime indirect GHG emissions avoided (bottom-up) (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Lifetime indirect GHG emissions avoided (top-down) ) (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Objective 5: LULUCF
Area of activity directly resulting from the project
Conservation and enhancement of carbon in forests, including agroforestry
Conservation and enhancement of carbon in nonforest lands, including peat land
Avoided deforestation and forest degradation
Afforestation/reforestation
Good management practices developed and adopted
Carbon stock monitoring system established
Lifetime direct GHG emission avoided (Tonnes of CO2)
Lifetime indirect GHG emission avoided (Tonnes of CO2)
Lifetime direct carbon sequestered (Tonnes of CO2 eq). Please see special notes in the CCM instruction tab
Lifetime indirect carbon sequestered (Tonnes of CO2 eq). Please see special notes in CCM instruction tab
Objective 6: Enabling Activities
Please specify the number of Enabling Activities for the project (for a multiple country project, please put the number of countries/assessments)
National Communication
Technology Needs Assessment
Nationally Appropriate Mitigation Actions
Other
Does the project include Measurement, Reporting and Verification (MRV) activities?
Note on D103: MW
Note on D104: MW el (for electricity production)
Note on D105: MW th (for thermal energy production)
Note on D106: MW el (for electricity production)
Note on D107: MW th (for thermal energy production)
Note on D108: MW
Note on D109: MW
Note on D110: MW th (for thermal energy production, 1m² = 0.7kW)
Note on D111: MW el (for electricity production)
Note on D112: MW
Note on D115: MWh
Note on D116: MWh el (for electricity production)
Note on D117: MWh th (for thermal energy production)
Note on D118: MWh el (for electricity production)
Note on D119: MWh th (for thermal energy production)
Note on D120: MWh
Note on D121: MWh
Note on D122: MWh th (for thermal energy production)
Note on D123: MWh el (for electricity production)
Note on D124: MWh
Note on D126: tonnes CO2eq (see Special Notes in instruction tab)
Note on D127: tonnes CO2eq (see Special Notes in instruction tab)
Note on D128: tonnes CO2eq (see Special Notes in instruction tab)
Note on D129: tonnes CO2eq (see Special Notes above)
Note on D160: hectares (ha)
Note on D161: hectares (ha)
Note on D162: hectares (ha)
Note on D163: hectares (ha)
2012 Annual Project Review (APR)
Project Implementation Report (PIR)