## OVERALL REPORTING INSTRUCTIONS
OVERALL INSTRUCTIONS
1 | All questions/sections must be responded to before submitting to secretariat. Once the document is uploaded in the relevant folder (as per instruction below) please email the secretariat.
2 | To ensure high quality narrative and results reports please pay attention to the following details: a) A well written, succinct summary that is very clear about what was done during the reporting period and results achieved, with a priority on concrete activities, beneficiaries reached and achievements beyond processes b) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document; c) In case certain indicators are not longer relevant, an explanation for why they are not. d) Factual, evidence-based reporting against the outcome and output indicators presented in the original project document and how they align with the overall SERP joint workplan, and connection to reporting on global-level SERP indicators e) Indicate the relevant SERP monitoring framework global indicators that were contributed to as part of this project. f) An honest analysis of challenges faced, the responses to these challenges and the extent to which these responses were successful or not g) Go beyond generic, standard and well documented features of successful project implementation when reflecting on innovation and focus on what is truly new for you and which could enable replication efforts
3 | You must submit this completed workbook by uploading it in the relevant Project Folder here (https://undp.sharepoint.com/:f:/r/sites/covid19mptfcall1/Shared%20Documents/2020-REPORT?csf=1&web=1&e=j3cc3J). Please note if you are unsure of your project number please refer to http://mptf.undp.org/factsheet/fund/COV00
A | ANNUAL REPORT
DEADLINE: 31 January 2021
4 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
5 | If you received a no-cost extension on your project please do the annual report and in a few months time you can update the annual report to include activities to complete your end of project report.
6 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.
B | END OF PROJECT - FINAL REPORT
DEADLINE: 31 January 2021
7 | ALL projects that received funds in 2020 must complete annual report, HOWEVER if you have your project ending on 31st December 2020 - your FINAL report is your annual report.
8 | Please make sure you use the RBM framework you report here on is as per your approved Prodoc.

## General Information-Annual
Programme Title & Project Number |  | Programme Duration
Programme Title: | Protecting lives of most vulnerable people during COVID-19 | Overall Duration (months) | 6 months
Programme Number (if applicable) |  | Start Date (dd.mm.yyyy) | 20.05.2020
MPTF Office Project Reference Number: | 121710 | Original End Date (dd.mm.yyyy) | 31.12.2020
Country | El Salvador | Current End date(dd.mm.yyyy) | 31.12.2020
Recepient UN Organizations |  | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | UNDP, UNODC | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the Secretary-General's Designate
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Annual
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum) | The project has been strengthening both the Ministry of Health (MINSAL) and the Office of Postal Services in El Salvador. MINSAL is implementing a project for the prevention of complications in patients with pre-existing comorbidities through home delivery of medicines because of the COVID-19 pandemic. It is dangerous for this population to be exposed to COVID-19, and even more, that they do not receive their medication. The project aims to protect the most vulnerable and reduce the number of patients in health centers during the pandemic, while maintaining access to treatment through home delivery of medicines and supplements. The delivery of the medicines is being done through the El Salvador´s Postal Office. The Postal Office is a first-line government institution and is the terrestrial logistics alternative to face the national emergency and supports the Ministry of Health to distribute the medicine kit. The postal staff is responsible for collecting, classifying, and distributing the material provided by the MINSAL. They mail men and women are the personnel who go to each vulnerable person’s home and delivery their medicine. The delivery of medicines requires special equipment and care. Some of the medications need to be at certain temperature in order to guarantee their integrity. Here is where the MPTF project “Protecting Lives of the Most Vulnerable Population” has impact. The project has strengthened the alliance between MINSAL and the Postal Office by providing the right elements for the delivery of medicines. This include, refrigerators, coolers, thermometers, including protection wrapping paper and envelopes. Additionally, the project is strengthening the response of the Postal Service Office in their role of identifying women that have or are suffering violence at home. Considering their access to people in their homes for the delivery of medicines, they even have knowledge of the zones and areas where women that suffer violence can go and search for assistance. A campaign has been created with the Postal Service and with the Attorney General´s Office (PGR). This campaign consists on adding a postmark on all the mail received internationally and delivered nationally with a telephone number of the PGR. The PGR is one of the only two government institutions that delivers psychological, crisis and legal attention to women victims of violence. Through this campaign, 20 cell phones were given to the PGR in order to guarantee the delivery of assistance 24/7. Due to the amount of people and demand of the services required by the PGR, changes are being done in their institution in order to comply with biosafety measures to prevent COVID-19. Special cabins are under construction, that will provide a confidential but also a safe space to give assistance to the population seeking their services
2 | Purpose (and Beneficiaries) | Please include the number of direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups | The direct beneficiaries of the project have been the 61,029 women and 29,117 men, that have chronic illness and have received in their homes their medication. Indirect beneficiaries have been the PGR and the Postal Office, which have improved their services with the equipment and procedures established through the project.
3.1 | Results: Outcome Level | Please include outcome level results achieved | • 32,613 Vulnerable popultation recieved their medicines on time through home delivery system. • 532 Women seeked assistance through the PGR call center • 99 Mail men and 51 women were trained in assisting women who are suffering violence
3.2 | Results: Output Level | Please include output level results achieved | • 1 Campaign was launched to provide information for women victim of violence. • 13 PGR offices were strengthened with biosafety measures and equipment to better assist vulnerable population • 1 call center established, to assist women victims of gender violence. • Postal Services Office strengthen with equipment that guarantees a safe delivery of medications, as well as with the establishment of internal policy and protocols to assist and intervene in cases of women violence. • Facilitated the alliance among three government institutions working together for vulnerable population.
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words) | The project encountered some challenges, especially in the initial months of implementation. Due to the mandatory quarantine, it has been difficult to supply all the equipment that the MINSAL requires for the home delivery of medicines. This has also happened with the biosafety supplies for the Attorney General´s Office. Suppliers and producers are requiring more days to give all the equipment. In order to catch up, process have been accelerated. Another challenge encountered has been the articulation among the MINSAL and the Postal Service Office. Usually these two institutions do not work together, and each one has different needs. However, a letter of agreement has been signed between to institutions for a better coordination. One of the challenges that the project has encountered regarding its beneficiaries are those related to pregnant women. Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project. During the implementation of the project, two hurricanes hit the Central American region. Even though El Salvador was not affected by the storms, the initial predictions were that it would. This caused for that the government institutions and its personnel, to focus in preparing for a new emergency. This caused a delay in the workshops give to the Postal Services and it required an adjustment in the curricula. However, 151 mail men and women participated and gain knowledge on how they can identify and assist women who are suffering from violence.
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words) | This project granted the possibility to work with a non-tradition actor such as the Postal Office. For the first time, this institution has been considered as a strategic partner in a UN project. The work that these men and women do, is extremely valuable, not only because of their roles, but because they know the communities and territories. They are able to reach places that are usually not accessible. The mail women and men are assigned to one area for years, which means that they are key actors, who know the community and it is important include them in projects and initiatives for the insight that they can bring. Due to their closeness to homes and families, they can identify different vulnerability profiles, such as women that are suffering from violence in their home. During the COVID-19 pandemic, this Office has not stopped working and providing services.
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words) | The project has facilitated new alliances among government institutions. A nontraditional alliance has been between the PGR and the Postal Services. For the first time and through the postal seal, and with UNDP intervention, these institutions have collaborated together in a campaign to prevent women violence and to promote the access of the different services of assistance. With the PGR, new funds applications are being submitted to continue supporting this institution, specially the unit of family, through this project policies and biosafety devices will be installed in their offices. However, they require more assistance due to the demand that the institutions have received by the population.
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place | One of the challenges that the project has encountered regarding its beneficiaries are those related to pregnant women. Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project.
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Annual
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1] | 36,313 (266 HIV+, 110 women and 156 men) | During the last trimester of 2020, the number of COVID cases fell, and people were picking up their medicines. The target established refered to all the people reached in one year. | MINSAL reports
Indicator: Number of vulnerable people who receive their medication on time, included STD/HIV-AIDS, disaggregated by sex, age, sexual diversity.
Baseline: 0
Planned Target: 77,000 people (34,000 women y 43,000 men)
Output 1.1: Home delivery (MED Express) system implemented | 36313 | There is a varience in the target since the agreement between MINSAL and the Mail Office, expired during the month of October 2020. Deliveries stopped for one month, however medicines were delivered again starting in November. | MINSAL reports
Indicator 1.1.1 a: Number of delivery medication carried out.
Baseline: 0
Planned Target: 61,029 Women & 29,117 Men | 420 (120 female & 300 male)
Indicator 1.1.1 b: Number of people receiving first-aid equipment, disaggregated by sex, sexual diversity and age. |  |  | MINSAL reports
Baseline: 0
Planned Target: 300
Indicator 1.1.1 c: Proportion of women of reproductive age (aged 15-49 years) with access to contraceptive methods | 0 | Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project. | MINSAL reports
Baseline: 0
Planned Target: 3,000
Indicator 1.1.1 d: Number of pregnant women receiving attention to their specific health needs | 0 | Initially the project considered for pregnant women to be included in the delivery of medicines, however, this has changed for mainly two reasons. The fist one is that pregnant women need to do monthly check ups. If the medication was to be delivered to their residency, they would not be going to their checkups. Secondly, when they do their checkups, they give them on site the medication and they do not have to wait for it to be delivered. This has causes changes in one of the targets of the project. | MINSAL reports
Baseline: 0
Planned Target: 8,600
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Annual
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
https://www.sv.undp.org/content/el_salvador/es/home/presscenter/articles/2020/12/modernas-cabinas-con-bioseguridad-para-atencion-de-audiencias-ju.html
https://twitter.com/pnudsv/status/1333567756197908480?s=21
2. Upload here: Communications and Visibility (OPTIONAL)
Fund's Communication Guidelines is posted here: http://mptf.undp.org/document/download/25941
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board

## General Information-Final
Programme Title & Project Number | Programme Duration
Programme Title: | Overall Duration (months)
Programme Number (if applicable) | Start Date (dd.mm.yyyy)
MPTF Office Project Reference Number: | Original End Date (dd.mm.yyyy)
Country | Current End date(dd.mm.yyyy)
Recepient UN Organizations | Implementing Partners
Organizations that have received direct funding from the MPTF Office under this programme | National counterparts (government, private, NGOs & others) and other International Organizations
Report Cleared By
o Name:
o Title:
o Email address:
The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY
The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY
As per approval of the original project document by the relevant decision-making body/Steering Committee.
If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

## Narrative-Final
# | Questions | Guidance to respondents | Responses
1 | Executive Summary | Please succinctly capture the key activities and concrete/tangible results and any important developments that the COVID-19 MPTF-funded Programme in your country achieved during the reporting period. The Executive Summary should serve as an accessible, simply written, standalone summary of the Programme’s results for this reporting period. It should show how implementation was carried out in the context of COVID-19. (up to 500 words maximum)
2 | Purpose (and Beneficiaries) | Please include the number of both direct and indirect beneficiaries reached. Please disaggregate the data by gender, age and any other groups
3.1 | Results: Outcome Level | Please include outcome level results achieved
3.2 | Results: Output Level | Please include output level results achieved
3.3 | Results: Challenges/Difficulties Encountered and Measures Taken | Please briefly describe, if applicable, any difficulties encountered during the reporting period, concrete measures taken to overcome them and changes introduced (any course corrections that were undertaken or need to be undertaken to achieve the expected results). Further, please draw on the Risk Management Matrix that was included as part of the approved ProDoc (regardless of whether challenges encountered were originally envisioned as risks or not), and highlight which risks materialized and how they were addressed, in very concrete terms. Please reflect on use of the “Do no harm” approach to avoid exacerbating inequalities and vulnerability as a result of the intervention (up to 500 words)
3.4 | Results: Qualitative Assessment and Learning | Please include any specific policy, programmatic and/or operational lessons or findings from the programme that could inform similar responses at country or global levels. Please focus on knowledge generated by the project that is truly new and likely to inform other interventions (in country or beyond) Please include reflections on the implementation of gender markers and any impacts they have had on programming quality and results. (up to 500 words)
3.5 | Results: Partnerships | Please explain how the programme has worked with partners and developed new partnerships and if any catalytic financial or programmatic outcomes have been achieved in this regard. Please focus on new, innovative and/or very practical ways in which these partnerships delivered impact/results and how the financial support from the fund helped, if applicable, to foster these partnerships. And explain if and how the intervention complemented activities funded by other global instruments such as the GHRP, WHO SPRP, and any national level response plans (up to 500 words)
3.6 | Other Assessments or Evaluations (if applicable) | Report on any assessments, evaluations or studies undertaken.
4 | Programmatic Revisions (if applicable) | Indicate any major adjustments in strategies, targets or key outcomes and outputs that took place
5 | Resources (Optional) | • Provide any information on financial management, procurement and human resources. • Indicate if the Programme mobilized any additional resources or interventions from other partners.

## RBM-Final
| Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification
Outcome 1[1]
Indicator:
Baseline:
Planned Target:
Output 1.1
Indicator 1.1.1:
Baseline:
Planned Target:
Indicator 1.1.2:
Baseline:
Planned Target:
Output 1.2
Indicator 1.2.1:
Baseline:
Planned Target:
Indicator 1.2.2:
Baseline:
Planned Target:
Please inlcude all three: Baseline, Planned Target and Achieved Targets
[1] Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

## Communication-Final
1. Impact Stories from the Field
Please submit one impactful story showing how your work has met critical needs in the context of the pandemic and supporting progress towards the SDGs, especially for vulnerable people. Ideally, this story will feature testimonials from the targeted groups. Please also take a moment to highlight any specific results on gender equality and LNOB, as relevant. To share the video as well picture material please make sure you include all credits and upload them in high resolution for Call1 Countries: https://undp.sharepoint.com/sites/covid19mptfcall1/Shared Documents/Forms/AllItems.aspx
2. Upload here: Communications and Visibility (OPTIONAL)
Please include highlights of communications and visibility efforts supported by the Programme during the project implementation, if relevant. (up to 500 words)
To share the video as well picture material please make sure you include all credits and upload them in high resolution Call1 countries.
Submit photographs. Please provide with captions and in high resolution, photographs that capture the programme in action. Strong photographs will be considered for inclusion in the COVID-19 MPTF publications and social media.
Please provide links to any videos that have been produced during implementation.
Please produce and share a social media card(s). See an example below and visit our Trello Board.
See - Fund's Trello Board