## AWP 2022 Master Sheet
Annual Work Plan (AWP) | [12 empty] | Restricted Columns Please Do not Change This Area or Columns
(00125664 Atlas Award ID) - Project/Programme Title -Strategic Planning in Somalia
Year : 2022
SP Outcome (UNDP 2014-2017 Strategic Plan): |  | Countries have strengthened Institutions to progressively deliver universal access to basic services
NPP Cluster: |  | Improved Economic Development
National Priority Programmes: |  | Economic Development Pillar 3; Social Development Pillar 4
NPP Component: |  | National Planning
Related CPD Outcome: |  | CPD Outcome 2: Supporting institutions to improve peace, security, justice, the rule of law and safety of Somalis; and strategic plan; Strengthening accountability and supporting institutions that protect.
CPD indicators, baseline and targets: |  | Output 2.1.2: Sustainable Development Goals compliant national, state and district development frameworks endorsed. Output 2.1.4: National statistical plan that is fully funded and under implementation (Goal 17.18.3)
Related CPD Output/s: |  | Output 2.1: Core functions of government ensure effective efficient transparent and accountable government management | [10 empty] | Output ID | Indicators: | Baseline: | Annual Targets: | Activity Results | Activity Indicators
Tokyo Mutual Accountability Framework (TMAF) Area: |  | Inclusive and Sustained Growth and Developmente Select | [10 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.1: | #REF!
New Deal Area:
Programme Cluster: | [12 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.1: | abc
Project Modality: (NIM/DIM) |  | Implementing Partner (IP): | [10 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.1: | abc
On-budget/Off-budget: |  | On-budget: 1,977,224 | Off-budget: |  |  |  | Funding Modality |  | Total Budget: 1,977,224 |  |  |  | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.1: | abc
[13 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.2: | cba
Output 1 (Atlas Output# 00119970): Federal Planning Framework | [12 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.2: | cba
Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics |  | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. |  |  |  |  | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | [5 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.2: | cba
PLANNED ACTIVITIY | Activity Indicators when Relevant | Actions / Inputs Description | TIMEFRAME |  | RESPONSIBLE PARTY |  | PLANNED BUDGET | [5 empty] | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.3: | cba
List Activity Results | List Activity Indicators | Associated Actions/Results | Q1 | Q2 |  | Executed by | Donor | Fund Code | Budget Account & Description | Budget amount | Funded 2022 | Un-Funded 2022 | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.3: | cba
Activity Result 1.3 M&E Framework supported |  | - Action: Workshops and other logistic support | x | x | 009567 |  | 00012 | 04000 | 75700 - Training, Workshops and Confer | 4000 | 4000 | 0 | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | #REF! | cba
Subtotal Activity Result 1.3 | [9 empty] | 4000 | 4000 | 0 | Output 1 (Atlas Output# 00119970): Federal Planning Framework | Indicators: Development of Standards of Planning in the government at FGS and FMS level; # of FMS strategic plans aligned to NDP 9; Operational establishment of Somali National Bureau of Statistics and level of staffing in the national bureau of statistics | Baseline: No standards for planning in the government at FGS and FMS level in place; 0 FMS strategic plans aligned to NDP 9; Not yet established, law approved. | Annual Targets: Standards for planning in the government at FGS and FMS level developed; 5 FMS strategic plans aligned to NDP 9; Somali National Bureau of Statistics established and adequately staffed. | Activity Result 1.4: | cba
Activity result 1.5 -Support to SNBS |  | National Advisory support for gender statistics/Environment&Governance | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services‐ImpPartn | 25000 | 25000 | 0
|  | Advisory support Environmental statistics International (50 days) | x | x | 001981 |  | Swiss | 30000 | 71200 - International consultant | 42500 | 42500
|  | Advisory support Environmental statistics National (50 days) | x | x | SNBS |  | 00012 | 04000 | 71300 - National Consultant | 10000 | 10000
|  | DPC Swiss | x | x | 001981 |  | Swiss | 30000 | 64300/74500 - DPC | 5525 | 5525
|  | GMS Swiss | x | x | 001981 |  | Swiss | 30000 | 75100 - GMS | 3842 | 3842
|  | Advisory support | x | x | 001981 |  | 00012 | 04000 | 71200 - International consultant | 50000 | 50000
|  | Workshops- First meeting for SDGs committee | x | x | SNBS |  | Swiss | 30000 | 75700 - Training, Workshops and Confer | 19650 | 19650
|  | Workshops - First Voluantry Local Review for FGS | x | x | SNBS |  | Swiss | 30000 | 75700 - Training, Workshops and Confer | 29720 | 29720
|  | Workshops - Second Voluantry Local Review for Civil Society and private sector | x | x | SNBS |  | Swiss | 30000 | 75700 - Training, Workshops and Confer | 18275 | 18275
|  | Workshops - Final Voluntary Local Review for All | x | x | SNBS |  | Swiss | 30000 | 75700 - Training, Workshops and Confer | 33570 | 33570
|  | Advisory support - SDG coordinator (4000 per month for 12 months) | x | x | SNBS |  | Swiss | 30000 | 71800 - Contractual Services‐ImpPartn | 48000 | 48000
|  | Advisory support - Data Analyst (3500 per month 12 months) | x | x | SNBS |  | 00012 | 04000 | 71800 - Contractual Services‐ImpPartn | 42000 | 42000
|  | Advisory support - Monitoring and evaluation Officer (3000 per month 12 month) | x | x | SNBS |  | Swiss | 30000 | 71800 - Contractual Services‐ImpPartn | 36000 | 36000
|  | Advisory support - Temporary Communication and Inforgraphic Specialist (3000 per month 7 months) | x | x | SNBS |  | 00012 | 04000 | 71800 - Contractual Services‐ImpPartn | 21000 | 21000
|  | Advisory support - Temporary report writing specialist (8000 per month 7 months) | x | x | SNBS |  | 00012 | 04000 | 71800 - Contractual Services‐ImpPartn | 56000 | 56000
|  | Advisory support - Project assistant (1500 per month 12 months) | x | x | SNBS |  | Swiss | 30000 | 71800 - Contractual Services‐ImpPartn | 18000 | 18000
|  | Travel costs within country (flights and perdiem) | x | x | SNBS |  | 00012 | 04000 | 71600 - Travel | 18000 | 18000
|  | Travel costs for UN-NYHQ Presenation (5 member delegation) | x | x | SNBS |  | 00012 | 04000 | 71600 - Travel | 25000 | 25000
|  | Production of a documentary clips on SDG for VNR | x | x | SNBS |  | 00012 | 04000 | 74200 - Printing, Publications | 15000 | 15000
|  | Publication of Somalia SDG/VNR Report | x | x | SNBS |  | 00012 | 04000 | 74200 - Printing, Publications | 5000 | 5000
|  | Miscellaneous Cost - bank charges, office utilities (water, electricity, internet, security guards) | x | x | SNBS |  | 00012 | 04000 | 74500 - Misc–Operat Expenditures | 19261 | 19261 | 0
|  | DPC Swiss | x | x | 001981 |  | Swiss | 30000 | 64300/74500 - DPC | 26417.9504 | 26417.9504 | 0
|  | GMS Swiss | x | x | 001981 |  | Swiss | 30000 | 75100 - GMS | 18370.6363 | 18370.6363 | 0
Subtotal Activity Result 1.5: | [9 empty] | 586131.5867 | 586131.5867 | 0
Activity result 1.7. Support Operationalization of NDP 9 |  | - Action: Operationalization of NDP9 for FMS to develop annual plans with clear reporting mechanism | x | x | 009567 | TRAC | 00012 | 04000 | 75700 - Training, Workshops and Confer | 5000 | 5000 | 0
|  | - Action: Advisory support on operationalization of NDP9 (4000 per month 6 months) | x | x | 009567 | TRAC | 00012 | 04000 | 71800 - Contractual Services‐ImpPartn | 24000 | 24000
|  | - Action: Miscellaneous - bank charge | x | x | 001981 | TRAC | 00012 | 04000 | 74500 - Misc–Operat Expenditures | 5000 | 5000 | 0
Subtotal Activity Result 1.7: | [9 empty] | 34000 | 34000 | 0
Output 1 Total: | [9 empty] | 624131.5867 | 624131.5867 | 0 | Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | Activity Result 1.2: | cba
Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | [12 empty] | Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | Activity Result 1.2: | cba
NPP Sub-components
Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level |  | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings |  |  |  |  | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | [5 empty] | Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | #REF! | cba
[13 empty] | Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | Activity Result 1.3: | cba
PLANNED ACTIVITIY | Activity Indicators when Relevant | Actions / Inputs Description | TIMEFRAME |  | RESPONSIBLE PARTY |  | PLANNED BUDGET | [5 empty] | Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | Activity Result 1.3: | cba
List Activity Results | List Activity Indicators | Associated Actions/Results | Q1 | Q2 |  | Executed by | Donor | Fund Code | Budget Account & Description | Budget amount | Funded 2022 | Un-Funded 2022
Activity Result 2.2: NDP Alignment |  | 2.2.1 Pillar Alignment
|  | Advisory support (1 person, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support (Social development Pillar lead, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support (Resilience Pillar lead, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support (Economic Development Pillar lead, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support (Gender and inclusivity lead, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support (Lawyer/Legal Expert, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support Reporting officer, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0
|  | Advisory support for Internal Audit Specialist 6 months | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 39300 | 39300 | 0
|  | Advisory support for Shocks and Risk Reduction Specialist 6 months | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 9000 | 9000 | 0
|  | 2.2.2 NDP Costing | [8 empty] | 0
|  | Advisory support (40 days)/800 USD | x | x | 001981 |  | 00012 | 04000 | 71200 - International Consultants | 32000 | 32000 | 0
2.2.4 AIMS Implementation
|  | Advisory support AIMS (50 days)*800 | x | x | 001981 |  | 00012 | 04000 | 71200 - International Consultants | 40000 | 40000
|  | AIMS management (manager, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.1: | edc
|  | AIMS management (2 assistants, 6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 18000 | 18000 | 0 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.1: | edc
|  | Support rental for AIMS server | x | x | 009567 |  | 00012 | 04000 | 73100 - Rental&Maintenance Premises | 1200 | 1200 | 0 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.1: | edc
Subtotal Activity Result 2.2: | [9 empty] | 283500 | 283500 | 0 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.2: | edc
Activity Result 2.3. support to Investment Promotion |  | Principle Advisor (5000 USD 6 month) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 30000 | 30000 | 0
|  | 2 Senior Advisors (6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 48000 | 48000 | 0
|  | 3 Interns (6 months) | x | x | 009567 |  | 00012 | 04000 | 71800 - Contractual Services-Imp Partner | 9000 | 9000 | 0
|  | Investment Promotion Events | x | x | 009567 |  | 00012 | 04000 | 75700 - Training, Workshops and Confer | 25000 | 25000 | 0
|  | Advisory support for AEGIS prodoc development (30 Days/800 USD) | x | x | 001981 |  | 00012 | 04000 | 71200 - International Consultants | 24000 | 24000 | 0
|  | Facilitate exposure to international and South –South /triangular cooperation best practices, study tour | x | x | 009567 |  | 00012 | 04000 | 75700 - Training, Workshops and Confer | 20000 | 20000 | 0
|  | Miscellaneous - bank charge | x | x | 001981 |  | 00012 | 04000 | 74500 - Misc–Operat Expenditures | 7000 | 7000 | 0
Subtotal Activity Result 2.3: | [9 empty] | 163000 | 163000 | 0 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.2: | edc
Output 2 Total: | [9 empty] | 446500 | 446500 | 0 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.2: | edc
Output 3 (Atlas Output# 00119970): SDG Alignment | [12 empty] | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.2: | edc
NPP Sub-components
Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs |  | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established |  |  |  |  | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | [5 empty] | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 3.3 Support to Somaliland Ministry of Planning & Development – Strengthening of the SDG office | edc
[13 empty] | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.3: | edc
[13 empty] | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.3: | edc
PLANNED ACTIVITIY | Activity Indicators when Relevant | Actions / Inputs Description | TIMEFRAME |  | RESPONSIBLE PARTY |  | PLANNED BUDGET | [5 empty] | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.3: | edc
List Activity Results | List Activity Indicators | Associated Actions/Results | Q1 | Q2 |  | Executed by | Donor | Fund Code | Budget Account & Description | Budget amount | Funded 2022 | Un-Funded 2022 | Output 3 (Atlas Output# 00119970): SDG Alignment | Indicators: # of Guidelines for SDG localization finalized; SDG reporting arrangements developed and operational; Planning capacity of MOPIC Somaliland for SDGs | Baseline: Guidelines not yet made; No consolidated structure for reporting on progress of SDG implementation exists; SDG Unit in MOPIC Somaliland recently established | Annual Targets: Guidelines for SDG localization in Somalia developed and finalized; A participatory and innovative structure for SDG reporting is operational, leading to the first SDG report in Somalia; SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | Activity Result 1.3: | edc
Activity Result 3.3 Support to Somaliland Ministry of Planning & Development – Strengthening of the SDG office |  | - Action: Planning specialist (drafting PRODOC planning) | x | x | 001981 |  | 00012 | 04000 | 71200 - International Consultants | 36000 | 36000 | 0
|  | - Action: Support workshop/discussions with other ministries on the integration of planning in policies, strategies, plans and projects | x | x | 012552 |  | 00012 | 04000 | 75700 - Training, Workshops and Confer | 30000 | 30000 | 0
|  | - Action: Miscellaneous - bank charge | x | x | 001981 |  | 00012 | 04000 | 74500 - Misc–Operat Expenditures | 500 | 500 | 0
Subtotal Activity Result 3.3: | [9 empty] | 66500 | 66500 | 0
Output 3 Total: | [9 empty] | 66500 | 66500 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | #REF! | fgh
Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | [12 empty] | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.1: | fgh
NPP Sub-components | [12 empty] | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.1: | fgh
PLANNED ACTIVITIY | Activity Indicators when Relevant | Actions / Inputs Description | TIMEFRAME |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
List Activity Results | List Activity Indicators | Associated Actions/Results | Q1 | Q2 |  | Executed by | Donor | Fund Code | Budget Account & Description | Budget amount | Funded 2022 | Un-Funded 2022
Activity Result Activity 4.1: Develop longer term support in planning on federal and FMS level |  | - Action: Advisory support (30days)/USD 800 | x | x | 001981 |  | 00012 | 04000 | 71200 - International Consultants | 24000 | 24000 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.1: | fgh
|  | - Action: Advisory support (30 days) | x | x | 009567 |  | 00012 | 04000 | 71300 - National Consultant | 12000 | 12000 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.1: | fgh
|  | - Action: Workshops and other logistic support | x | x | 009567 |  | 00012 | 04000 | 75700 - Training, Workshops and Confer | 10000 | 10000
|  | - Action: Miscellaneous - bank charge | x | x | 001981 |  | 00012 | 04000 | 74500 - Misc–Operat Expenditures | 500 | 500 | 0
Subtotal Activity Result 4.1: | [9 empty] | 46500 | 46500 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.2: | fgh
Output 4 Total: | [9 empty] | 46500 | 46500 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.2: | fgh
Output 6 (Atlas Output# 00119970): Support to Crisis Facility | [12 empty] | Output 2 (Atlas Output# 00119970): Federal Member States Planning Frameworks | Indicators: Aid policy developed; % of projects with full information in AIMS; Regular coordination arrangement on FMS level | Baseline: No Aid Policy yet; AIMS not yet operational; While Puntland has an operational structure, the other FMS only have irregular coordination meetings | Annual Targets: Aid Policy endorsed; At least 50% of the projects entered in AIMS have full information; A regular coordination structure is operational in all 5 FMS | Activity Result 1.2: | cba
PLANNED ACTIVITIY | Activity Indicators when Relevant | Actions / Inputs Description | TIMEFRAME |  | RESPONSIBLE PARTY |  | PLANNED BUDGET | [5 empty] | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.2: | fgh
List Activity Results | List Activity Indicators | Associated Actions/Results | Q1 | Q2 |  | Executed by | Donor | Fund Code | Budget Account & Description | Budget amount | Funded 2022 | Un-Funded 2022 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.3: | fgh
Activity Result 6.1 – Core Staffing |  | - Action: Recovery & Resilience Coordinator | x | x | 009567 |  | 00015 | 30000 | 71200 - International Consultants | 72600 | 72600 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.3: | fgh
|  | - Action: Sr. Coordination Specialist (local hire) | x | x | 009567 |  | 00015 | 30000 | 71800 - Contractual Services-Imp Partner | 25200 | 25200 | 0
|  | - Action: Operations Manager | x | x | 009567 |  | 00015 | 30000 | 71800 - Contractual Services-Imp Partner | 7800 | 7800 | 0
|  | - Action: Communication and reporting specialist to be contracted to design and beautify reports, brochures, social media outreach, etc. (output 1, 3 and national event) | x | x | 009567 |  | 00015 | 30000 | 71800 - Contractual Services-Imp Partner | 10000 | 10000 | 0
|  | - Action: Young Professional Officers for Technical and Logistical Support | x | x | 009567 |  | 00015 | 30000 | 71800 - Contractual Services-Imp Partner | 12800 | 12800 | 0
Subtotal Activity Result 2.1: | [9 empty] | 128400 | 128400 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.3: | fgh
Activity Result 6.2 – SWG on resilience and food security convenes broad range of stakeholders to address specific coordination challenges related to R&R |  | - Action: Convene at least 3 SWG meetings, prepare minutes and actions/decisions and ensure follow up at next SWG meeting and National launching of SWG Final Report | x | x | 009567 |  | 00015 | 30000 | 75700 - Training, Workshops and Confer | 22000 | 22000
Subtotal Activity Result 6.2: | [9 empty] | 22000 | 22000 | 0
Activity Result 6.3 - Support for internal (FGS-FMS) government coordination and joint planning ahead of and following key working group meetings |  | - Action: One 2-page report summarizing where internal gov’t coordination has improved and where it could be further strengthened + documentation collected from the internal coordination process and a documentary of the work on the facility on recovery and resilience | x | x | 009567 |  | 00015 | 30000 | 74200 - Printing, Publications | 14600 | 14600 | 0 | Output 4 (Atlas Output# 00119970): Longer Term Support arrangements to Planning, M&E and Statistics | #REF! | #REF! | #REF! | Activity Result 1.4: | fgh
Subtotal Activity Result 6.3: | [9 empty] | 14600 | 14600 | 0
Activity Result 6.4 - On demand, light touch analytical and guidance notes on R&R themes |  | - Action: 4 2-pagers produced, translated in both English and Somali, and posted on MoPIED website-2-pagers could be used to present latest AIMS data on an R&R theme, review recently produced planning framework and explore linkages with other planning tools, examine cross-cutting theme e.g., durable solutions in relation to a specific shock) | x | x | 009567 |  | 00015 | 30000 | 74200 - Printing, Publications | 2400 | 2400 | 0
Subtotal Activity Result 6.4: | [9 empty] | 2400 | 2400 | 0
Activity Result 6.5 - Government-led capacity building for use of coordination tools |  | - Action: 4 info sessions (half of AIMS) 2 1-page “quick guides” produced in English and Somali- quick guides could cover e.g., the aid architecture, key messages and definitions on UCS agenda, MAF process, intro to durable solutions agenda, etc.) | x | x | 009567 |  | 00015 | 30000 | 74200 - Printing, Publications | 2400 | 2400 | 0
Subtotal Activity Result 6.5: | [9 empty] | 2400 | 2400 | 0
Output 6 Total: | [9 empty] | 169800 | 169800 | 0
Output 5 (Atlas Output# 00119970): Project Management
PLANNED ACTIVITIY | Activity Indicators when Relevant | Actions / Inputs Description | TIMEFRAME |  | RESPONSIBLE PARTY |  | PLANNED BUDGET
List Activity Results | List Activity Indicators | Associated Actions/Results | Q1 | Q2 |  | Executed by | Donor | Fund Code | Budget Account & Description | Budget amount | Funded - 2022 | Un-Funded 2022
Activity Result 5.1: Project Management |  | Portfolio Operations Manager P5 (25%) | x | x | 001981 |  | 00012 | 04000 | 61300 - Salary & Post Adj Cst-IP Staff | 41836.25 | 41836.25 | 0
|  | Portfolio Operations Specialist P3 (25%) | x | x | 001981 |  | 00012 | 04000 | 61300 - Salary & Post Adj Cst-IP Staff | 32526 | 32526 | 0
|  | Portfolio M&E and reporting officer P2 (100%) | x | x | 001981 |  | 00012 | 04000 | 61300 - Salary & Post Adj Cst-IP Staff | 91933 | 91933 | 0
|  | Project Officer | x | x | 001981 |  | 00012 | 04000 | 71400 - Contractual Services - Individual | 30361 | 30361 | 0
|  | Portfolio Operations Assistant (NUNV/SC7) | x | x | 001981 |  | 00012 | 04000 | 71500 - UNV | 18905 | 18905 | 0
|  | Travel | x | x | 001981 |  | 00012 | 04000 | 71600 - Travel | 40000 | 40000 | 0
|  | Professional services | x | x | 001981 |  | 00012 | 04000 | 74100 - Professional services | 30000 | 30000 | 0
|  | Sundry | x | x | 001981 |  | 00012 | 04000 | 74500 - Misc–Operat Expenditures | 2000 | 2000 | 0
|  | Rent | x | x | 001981 |  | 00012 | 04000 | 73100 - Rental&Maintenance Premises | 25000 | 25000 | 0
|  | TOTAL DPC WB 12% as per the agreement | x | x | 001981 |  | 00015 | 30000 | TOTAL DPC of 12% WB for the total USD 456,440 | 54773 | 54773 | 0
|  | TOTAL GMS WB 8% | x | x | 001981 |  | 00015 | 30000 | GMS WB for the total USD456,440 | 40897 | 40897 | 0
Output 5 Total: | [9 empty] | 408231.25 | 408231.25 | 0
PROJECT TOTAL | [9 empty] | 1761662.8367 | 1761662.8367 | 0
Project Tolerance (the permissible deviation from a plan - in terms of time and cost without bringing the deviation to the attention of the the Project Board/Streering Committee:)
Note on K22: Yosief Abraha:
Note on K59: Yosief Abraha:
Note on K93: Yosief Abraha:
Note on K102: Yosief Abraha:
Note on K111: Yosief Abraha:
Note on K129: Yosief Abraha:
Note on M129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: please check

## M&E Plan
Targets
Outcome/Output formulation | Output baseline statement | Indicators | Baseline | 2021 | Mean of Verification (Source of Data) | Frequency of Data Collection | Methods of Data Collection | Estimated Cost
Output 1 ‐ The Planning, M&E and Statistics Framework established | No standards for planning in the government at FGS and FMS level in place and FMS strategic plans not aligned to NDP 9 | (1.1. # Of standards of planning developed for the government at both FMs and FGS levels) Development of Standards of Planning in the government at FGS Number and FMS level; 1.2. # Of FMS and FGS institutions' stratgic plans aligned to NDP 9. | 1.1. No standards for planning in the government at FGS and FMS level in place; | 1.1. Standards for planning in the government at FGS and FMS level developed | TPM & Project progress reports | Quaterly | TPM Questionnaires, Checklist | 155170
|  |  | 1.2. FMS strategic plans not aligned to NDP 9 | 1.2. FMS and FGS institutions' strategic plans are fully alighned to NDP 9 aligned | Field visits and mission reports | Quaterly | FGDs &KIIs
[6 empty] | Quaterly | Field Observations
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Output 2: Federal Member States Planning Frameworks | The Baseline for output 2 will be NDC meets regularly, AIMS developed and launched , No updates of alignment of Pillar activity to NDP 9; Alignment of Pillars to the NDP is uneven, Nonexistence of a regular meeting arrangement between FMS MOPICs and Directors Generals in ministries in each FMS and Nonexistence of a regular meeting platform for FMS and development & humanitarian agencies for alignment of assistance | 2.1. # Of meeting condcuted or held by National Development Council (NDC); 2.2. AIMS operational. 2.3. Existence of an aid policy. 2.4 Alignment of Pillar Activity (as monitored by the PWG) to NDP 9; 2.5. Establishment of a regular meeting arrangement between FMS MOPICs and Directors Generals in ministries in each FMS. 2.6. Establishment of a regular meeting platform for FMS and development & humanitarian agencies for alignment of assistance | . 2.1. NCD meetings are less frequent. | 2.1. NDC meets regularly |  | Quaterly | TPM Questionnaires, Checklist | 473136
|  |  | 2.2. AIMS developed and launched but not factional | 2.2. AIMS operational; | Field visits and mission reports | Quaterly
|  |  | 2.3. No updates of alignment of Pillar activity to NDP 9; | 2.3. Bi-annual updates of alignment of Pillar activity to NDP; |  | Quaterly
|  |  | 2.4 Alignment of Pillars to the NDP is uneven | 2.4: mechanisms in place to analyses and strengthen alignment of Pillars with NDP | TPM & Project progress reports | Quaterly
|  |  | 2.5. Nonexistence of a regular meeting arrangement between FMS MOPICs and Directors Generals in ministries in each FMS; | 2.5. Regular meeting arrangement between FMS MOPICs and Directors Generals in ministries in each FMS established. | TPM & Project progress reports | Quaterly
|  |  | 2.6. Nonexistence of a regular meeting platform for FMS and development & humanitarian agencies for alignment of assistance | 2.5. Regular meeting platform for FMS and development & humanitarian agencies for alignment of assistance established | TPM & Project progress reports | Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Quaterly
Output 3: SDG Alignment | The baseline for output 3 will be Nonexistence of guidelines for SDG localization; Nonexistence of SDG report; and SDG Unit in MOPIC Somaliland recently established | 3.1. Existence of guidelines for SDG localization; 3.2. Development of SDG report; 3.3. Strengthened planning capacity of MOPIC Somaliland | 3.1. Nonexistence of guidelines for SDG localization | 3.1. Guidelines for SDG localization in Somalia developed; | Field visits and mission reports | Quaterly | Field Observations, FGDs & KIIs | 55400
|  |  | 3.2. Nonexistence of SDG report; | 3.2. SDG report in Somalia developed; | TPM & Project progress reports | Quaterly
|  |  | 3.3. SDG Unit in MOPIC Somaliland recently established | 3.3. SDG Unit in MOPIC Somaliland staffed, equipped and training initiated in implementation of iSDG integrated planning model | TPM & Project progress reports | Quaterly
Quaterly
Quaterly
Quaterly
Output 4 : Longer Term Support arrangements to Planning, M&E and Statistics | No dedicated project in support to a long-term support arrangement to planning, M&E and statistics in Somalia developed | . Long-term support arrangements to planning, M&E and Statistics in Somalia agreed upon | No dedicated project in support to a long-term support arrangement to planning, M&E and statistics in Somalia developed | Dedicated project in support to a long-term support arrangement to planning, M&E and statistics in Somalia developed |  |  | TPM Questionnaires, Checklist | 40500
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fill the M&E activities cost of the project in this column

## Procurement Plan
PROCUREMENT PLAN FOR - 2022
Project/Programme Title: Strategic Planning in Somalia
Project ID: 00119970
Item No. | Procurement Category | Non - Standard / Specialist Item (Does not fit into Categories Listed) | Estimated Quantity | Responsible Party | Allocated Amount / Budget/ as per contract | Reference to Project Activity | Chart of Account | Budget Account | Donor/Fund | Desired Delivery Date | Preferred Place of Delivery | Remarks
Consultancies
1 | International Consultant ($1000*30days) | VNR |  |  | 50000 | Activity 1.5 |  | 71200 | 00012/04000 |  |  | Swiss
2 | International Consultant ($1000*30days) | NDP Costing |  |  | 32000 | Activity 2.2.2 |  | 71200 | 00012/04000
3 | International Consultant ($1000*30days) | AIMS |  |  | 40000 | Activity 2.2.4 |  | 71200 | 00012/04000
4 | International Consultant ($1000*50days) | Advisory support for AEGIS prodoc development |  |  | 24000 | Activity 2.3 |  | 71200 | 00012/04000 |  |  | GiZ
5 | International Consultant ($1000*30days) | drafting PRODOC planning Somaliland |  |  | 36000 | Activity 3.3 |  | 71200 | 00012/04000 |  |  | TRAC
6 | International Consultant | drafting PRODOC planning Somalia |  |  | 24000 | Activity 4.1 |  | 71200 | 00012/04000
| SUB-Total 1 |  |  |  | 206000
Professional srvcs
1 | Professional srvcs |  |  |  | 30000 | Activity5 |  | 74100 | 00012/04000
2
| SUB-Total 2 |  |  |  | 30000
Grand Total |  |  |  |  | 236000
Please note that this Procurement Plan is based on UNDP's Programmed and Operations Policies and Procedures (POPP) and the Results Based Management (RBM) guidelines of UNDP. Once signed and approved, the plan authorizes the Procurement Unit of the Supply Chain Management Office to implement it fully in accordance with POPP.
Prepared by Project Manager: Signature Date_________________________________________________________________
Approved by: Deputy Resident Representative (Programme) Signature Date__________________________________________________________________
Approved by: Deputy Resident Representative (Operations) Signature Date_________________________________________________________________

## HR Plan
UNDP Somalia
Human Resources Plan (2022)
Project/Programme Title: Strategic Planning in Somalia
Award ID: 00125664
Project ID: Atlas Project 00119970
No. | Post Title | Incumbent (Name) |  | Status (Vacant/Filled) | Post Number | Type of Contract | Category (National/ International) | Grade | Pro Forma per month | Service Month | Percentage | Estimated Budget | Project Name | Project ID |  | Actvity | Donor | Funds Available (Yes/No) | Expected or actual End of Contract | Required period of extension | Project End date
|  | First | Second | [11 empty] | Output
Number
1 | Portfolio Manager | Laura | Rio | Filled | 153309 | FT | International | P5 | 27890.8333 | 6 | 25% | 41836.25 | PIP Planning | 00125664 | 00119970 | 5 | 00012 | yes
2 | Portfoilo Operations Specialist | Aigul | Zakirova | Filled | 142923 | FT | International | P3 | 21684 | 6 | 25% | 32526 | PIP Planning | 00125664 | 00119970 | 5 | 00012 | yes
3 | M&E &Reporting Officer | Tendai | Chabvuta | Filled | 164313 | TA | International | P2 | 15322.1667 | 6 | 100% | 91933 | PIP Planning | 00125664 | 00119970 | 5 | 00012 | yes
4 | Project Officer | Omar | Isack | Filled | 107490 | SC | National | SC10 | 5060.1667 | 6 | 100% | 30361 | PIP Planning | 00125664 | 00119970 | 5 | 00012 | yes
5 | Portfolio Operations Assistant (NUNV/SC7) | Abdulkadir | Abdala | Filled |  | NUNV | National | NUNV | 3150.8333 | 6 | 100% | 18905 | PIP Planning | 00125664 | 00119970 | 5 | 00012 | yes
Total | [9 empty] | Total |  | 215561.25
| Proposed by (Project): UNDP/Planning |  |  |  |  | Endorsed by: | [8 empty] | Reviewed by HR Unit or DCD Operations:
Signature:_____________________________________
| Signature: ____________________________ |  |  |  |  | Signature: | [8 empty] | Name, Title: Safiou Esso Ouro-Doni, Deputy Country Director (Operations)
83673
| Name, Title: Albert Soer, Portfolio Manager |  |  |  |  | Name, Title: | [8 empty] | Date:__________________________________________
| Date: ________________________________ |  |  |  |  | Date: _________________________________________
2. Terms of Reference (TOR) and COA must be provided by the Project while making the recruitment request at least five months ahead of the preferred date of joining.
3. Organization Chart must be attached to the Annual HR Plan.
#REF!

## Budget by IA(LoAs)
Funding by IA
Implementing Agent | IA Code | AWP Budget | Funded | Unfunded
MoPIED | 009567 | 593300 | 593300
MoP Somaliland | 012552 | 30000 | 30000
SNBS |  | 414476 | 414476
UNDP | 001981 | 723886.8367 | 723886.8367
Total |  | 1761662.8367 | 1761662.8367

## Fund Distribution
Funding by IA
Implementing Agent | Donor Code | AWP Budget | Funded | Unfunded
WB | WB | 265470 | 265470
Swiss | Swiss | 299870.5867 | 299870.5867
UNDP | 00012 | 1196322.25 | 1196322.25
Total |  | 1761662.8367 | 1761662.8367 |  | 0

## DPC
Calculator:
WB |  | USD
Available resources |  | 552110 | Please fill the BLUE box with the Income / AWP
GMS | 8% | 40897.037 | control:
Programmable |  | 511212.963 | 40897.037 | 0
DPC: |  |  | 456440.1455 |  | programmable after DPC
Security | 3% | 13693.2044 | 13693.2044 | 0 | 3% | 0%
Communications | 1% | 4564.4015 | 4564.4015 | 0 | 1% | 0%
M&E | 1% | 4564.4015 | 4564.4015 | 0 | 1% | 0%
Prog Oversight | 3% | 13693.2044 | 13693.2044 | 0 | 3% | 0%
Operations | 4% | 18257.6058 | 18257.6058 | 0 | 4% | 0%
Total DPC | 12% | 54772.8175 | 54772.8175 | 0 | 12% | 0%
Distribution of DPC
DPC-64300 | 70% | 38340.9722
DPC-74500 | 30% | 16431.8452
| Total | 54772.8175 | 552110 | check
Programmable - net |  | 456440.1455
Calculator:
Swiss |  | USD
Available resources |  | 248003.59 | Please fill the BLUE box with the Income / AWP
GMS | 8% | 18370.6363 | control:
Programmable |  | 229632.9537 | 18370.6363 | 0
DPC: |  |  | 203215.0033 |  | programmable after DPC
Security | 4% | 8128.6001 | 8128.6001 | 0 | 4% | 0%
Communications | 1% | 2032.15 | 2032.15 | 0 | 1% | 0%
M&E | 1% | 2032.15 | 2032.15 | 0 | 1% | 0%
Prog Oversight | 3% | 6096.4501 | 6096.4501 | 0 | 3% | 0%
Operations | 4% | 8128.6001 | 8128.6001 | 0 | 4% | 0%
Total DPC | 13% | 26417.9504 | 26417.9504 | 0 | 13% | 0%
Distribution of DPC
DPC-64300 | 70% | 18492.5653
DPC-74500 | 30% | 7925.3851 |  |  |  |  | 22360.0653
| Total | 26417.9504 | 248003.59 | check
Programmable - net |  | 203215.0033 |  |  |  |  | 9582.8851
Calculator:
Swiss |  | USD
Available resources |  | 51867 | Please fill the BLUE box with the Income / AWP
GMS | 8% | 3842 | control:
Programmable |  | 48025 | 3842 | 0
DPC: |  |  | 42500 |  | programmable after DPC
Security | 4% | 1700 | 1700 | 0 | 4% | 0%
Communications | 1% | 425 | 425 | 0 | 1% | 0%
M&E | 1% | 425 | 425 | 0 | 1% | 0%
Prog Oversight | 3% | 1275 | 1275 | 0 | 3% | 0%
Operations | 4% | 1700 | 1700 | 0 | 4% | 0%
Total DPC | 13% | 5525 | 5525 | 0 | 13% | 0%
Distribution of DPC
DPC-64300 | 70% | 3867.5
DPC-74500 | 30% | 1657.5
| Total | 5525 | 51867 | check
Programmable - net |  | 42500