PROGRAMME ANNUAL PROGRESS REPORT

Period: 2018

| Project Name | Programme for Support to Universal Suffrage Elections in the Federal Republic of Somalia UNDP Award ID000107518/ Project ID 000107800 |
| --- | --- |
| Gateway ID | 00108826 (MPTF Project ID) |
| Start date | 1 January 2018 |
| Planned end date (as per last approval) | 31 December 2019 |
| Focal Person | (Name): Filip Warnants |
|  | (Email): Filip.warnants@undp.org |
|  | (Tel): +252 617885579 |
| Participating UN Entities | UNDP and UNSOM (Integrated Electoral Support Group) |
| NDP Pillar | PWG Pillar 1: Inclusive Politics: Achieve a stable and peaceful federal Somalia through inclusive political processes and effective decentralization – SWG-3 Elections |
| Priority | Deepening federalism and state-building, supporting conflict resolution and reconciliation, & preparing for universal elections |
| Milestone |  |
| Location | National Programme – Mogadishu based |
| Gender Marker | 2 |

| Total Budget as per ProDoc | USD 8,571,300 |
| --- | --- |
| MPTF: | USD 4,208,942 |
| Non-MPTF sources: | PBF: 0 |
|  | Trac: 11,865 |
|  | Other:0 |

|  | PUNO | Report approved by: | Position/Title | Signature |
| --- | --- | --- | --- | --- |
| 1. | UNDP | George Conway | Resident Representative (a.i.) |  |

| Total MPTF Funds Received | Total non-MPTF Funds Received |
| --- | --- |
| PUNO | Semi Annual 2018 (2) | Cumulative | Annual 2018 | Semi Annual 2018 (2) | Cumulative | Annual 2018 |
|  | 1 July - 31 Dec 2018 | From prog. start date | 1 Jan – 31 Dec 2018 | 1 July - 31 Dec 2018 | From prog. start date | 1 Jan – 31 Dec 2018 |
| UNDP | 739,784 | 4,208,942 | 4,208,942 | 0 | 11,865 | 11,865 |
| JP Expenditure of MPTF Funds | JP Expenditure of non-MPTF Funds |
| PUNO | Semi Annual 2018 (2) | Cumulative | Annual 2018 | Semi Annual 2018 (2) | Cumulative | Annual 2018 |
|  | 1 July - 31 Dec 2018 | From prog. start date | 1 Jan – 31 Dec 2018 | 1 July - 31 Dec 2018 | From prog. start date | 1 Jan – 31 Dec 2018 |
| UNDP | 1,325,957.03 | 3,375,154.37 | 3,375,154.37 | 0 | 11,865 | 11,865 |

| ANNUAL HIGHLIGHTS The Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR) finalized in 2018 the draft Electoral Law, subject to Cabinet approval and submission to Parliament in 2019. The National Independent Electoral Commission (NIEC) held in 2018 nationwide consultations with approximately 6,000 participants in more than 30 locations in Somalia on required preparations and challenges for ‘one person, one vote’ elections for the next Federal Parliament. Through a desk-study, approximately 1,760 voter catchment areas where mapped out by the NIEC for potential voter catchment areas across the country, followed by a pilot project in the field that identified 111 possible voter registration sites in two districts. In 2018, the NIEC provided temporary registration to 35 newly established political parties. The NIEC refined its strategic plan and developed an action plan for essential activities to be undertaken in 2019 in preparations for voter registration and electoral operations in 2020. |
| --- |
| HIGHLIGHTS OF KEY ACHIEVEMENTS The Joint Programme for Electoral Support assisted in 2018 the NIEC with policy advise on institutional governance, strategic planning, the development of an action plan and the required conceptual preparations with regard to voter registration, the chronogram for electoral operations, drafting of electoral regulations, and the establishment of its field operations structure. The UN Joint programme for Electoral Support further provided technical, logistical and budgetary support to enhance the NIEC’s institutional and operational capacity, and to strengthen the Commission and the Secretariat in its functions of an Electoral Management Body (EMB). In this respect, during a micro-capacity assessment, the NIEC’s institutional capacity was scored successfully on internal governance structures and financial and administrative business processes. A sound administrative structure is a key requirement for a well-functioning electoral administration entity. The UN Joint programme for Electoral Support assisted the NIEC with its engagement with civil society, key stakeholders and political parties. In this respect, the Project provided support to the NIEC’s website, consultations with key partners on the development of a voter education curriculum, and the NIEC’s nation-wide consultations throughout Somalia with national and sub-national actors to facilitate discussions on challenges and preparations for universal elections. These consultations followed the instruction from the National Security Council in November 2017 for the NIEC to reach out to Somali stakeholders in each of the Federal Member States (FMS) and to engage with all partners throughout the country on discussions regarding challenges and preparations for universal elections. It was the first time that the NIEC did a profound and extensive outreach campaign to stakeholders and partners in different towns and cities of all the FMS. In total, the NIEC engaged with more than 6,000 people in up to 30 locations across Somalia and abroad, including regional officials, elders, political associations and parties, religious leaders, women and youth groups, CSOs, and members of the Somali diaspora. With technical expertise, including GIS mapping, the Project worked together with the NIEC to identify approximately 1,760 voter catchment areas across the country, which need to be further explored on the ground on their feasibility to establish voter registration sites. During a pilot project in October in Mogadishu and Jowhar, the NIEC identified 111 potential sites for voter registration centres in two districts. A nationwide mapping exercise of potential voter registration sites is planned for 2019. Assisted by the UN Joint programme for Electoral Support, the Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR) finalized in 2018 the draft Electoral Law. The electoral model for the Federal House of the People is based on the ‘Baidoa Agreement’ by the country’s leaders in June 2018, and includes a multi -party, closed list, proportional representation system for “one person, one vote” suffrage elections. The draft Law has been submitted to Cabinet for approval and is expected to be submitted to Parliament in 2019. |
| SITUATION UPDATE On 18 January 2018, the Council of Ministers of Somalia’s Federal Government endorsed the 2020 Political Roadmap, which sets out a clear trajectory towards universal elections in 2020 as a government’s top priority. The Roadmap interlinks essential political steps regarding the constitutional review, electoral preparations, state-formation and federalism. It outlines responsible partners and processes to be undertaken between 2017 and 2020, for the government to create a conducive political environment for universal elections in 2020. The Roadmap provides “Logical Framework Matrix” for quarterly reviews as a monitoring and evaluation mechanism on the political benchmarks, with quarterly meetings to review progress which includes Somalia’s federal member states and international partners. In its preamble, the Roadmap underscores its thrust to set out the critical steps necessary to achieve direct elections in 2020 that are credible and transparent. They will be the country’s first multi-party universal suffrage elections since half a century. The last elections for the Parliament of Somalia date from 1969. On 27 March, the UN Security Council adopted Resolution 2408 which extends the mandate of UNSOM until 31 March 2019, including electoral support. Resolution 2408 welcomes “the commitments of the Federal Government of Somalia to ‘one person, one vote’ elections in 2020, underscoring the importance of making progress on the political roadmap”. The Resolution further underscores “the importance of UNSOM's support to the Federal Government of Somalia on preparations for the delivery of an inclusive, credible and transparent ‘one person, one vote’ elections in 2020 with a focus on the NIEC at national and sub-national level to fulfil its constitutional mandate in line with the Somali-led Operational Strategic Plan for 2017-2021, the goal of nationwide voter registration by 2019, and coordination of international electoral support to Somalia”. From 13 to 21 May, an UN electoral Needs Assessment Mission to Somalia was deployed to assess developments pertaining to the preparations for multiparty universal suffrage elections in 2020, the ability of UNSOM to fulfil its strengthened electoral mandate and make recommendations for resource requirements. In 2018, as per the NAM recommendation, UN Integrated Electoral Support Group (IESG) deployed under UNSOM electoral advisors to each of the capitals of the different Federal Member States, in order to facilitate the NIEC’s establishment in the field and start with planning and logistical preparations for electoral field operations. In 2018, IESG the welcomed the arrival of its new Deputy Chief Electoral Advisor (UNDP) and Chief Electoral Operations Advisor (UNSOM), while also a new IESG Director was recruited (UNSOM). On 1 October, the Federal Government of Somalia expressed its commitment to implement its Roadmap on Inclusive Politics, including the conduct of ‘one person, one vote’ universal suffrage elections end of 2020. |
| QUARTERLY & ANNUAL PROGRESS REPORT RESULTS MATRIX OUTCOME STATEMENT Somali institutions are enabled to run independent, impartial, transparent and inclusive elections Output 1: NIEC equipped with necessary capacities and structures to prepare for and conduct credible and inclusive elections INDICATOR TARGET PROGRESS ON OUTPUT INDICATOR Reporting Period (2018) CUMULATIVE 1.1 NIEC policies and procedures (governance, finance & admin, operations, electoral, legal, etc.) developed and endorsed to fulfil its mandate to prepare for and conduct electoral operations. 5 2 2 Output 1.2: FMS where NIEC has established sub-national presence. 5 1 0 Sources of evidence: NIEC 5-year Strategic Plan (2017-2021); NIEC quarterly reports to the Federal Parliament; NIEC HACT assessment report; Social Media articles: NIEC Website (www.niec.so); NIEC Facebook page; NIEC twitter; UNSOM/UNDP Facebook page, twitter; Official NIEC presentations at PWG-1/SWG-3 and to donor partners and international community; Official documents signed between UNDP and the NIEC (Work Plan, Letter of Agreement); Training and workshop reports/materials; NIEC advisor reports to UNDP IESG BTOR Output 2: NIEC supported to enhance public awareness of electoral processes, including promotion of women’s participation. 2.1 # of significant engagements the NIEC has rolled out with (sub-) national, including promoting enhanced women participation actors on electoral processes 10 30 30 2.2 NIEC public outreach and voter education plan developed, including focus on women’s participation 1 0 0 Sources of evidence: NIEC quarterly reports to the Federal Parliament and to NSC Published NIEC Consultations Report (Somali + English) Social Media articles: NIEC Website (www.niec.so); NIEC Facebook page; NIEC twitter; UNSOM/UNDP Facebook page, twitter; Media coverage NIEC sub-national consultative process Official NIEC presentations to donor partners and international community; NIEC advisor reports to UNDP IESG BTOR Output 3: Support to the NIEC’s electoral operations 3.1. # of political parties registered N/A 35 35 3.2. VR methodology agreed by partners and VR plan developed 1 NO NO 3.3. # of regions where potential voter registration sites are identified 18 0 0 3.4. Somalia electoral security taskforce Re-established 1 NO NO 3.5 # of by-elections held TBC 33 33 Sources of evidence: NIEC certification political parties NIEC certification of winners of by-elections for federal House of the People NIEC operational plans for VR; updates on GIS mapping of voter catchment areas IESG workshop materials for NIEC Voter Registration (VR) planning Letter to the Minister of Internal Security to initiate electoral security planning and reestablishment of the joint electoral security task force NIEC quarterly reports to the Federal Parliament and to NSC Social Media articles: NIEC Website (www.niec.so); NIEC Facebook page; NIEC twitter; UNSOM/UNDP Facebook page, twitter; Official NIEC presentations to donor partners and international community; NIEC advisor reports to UNDP IESG BTOR and IESG electoral operations planning Output 4: Establishment of permanent NIEC office facilities Construction of phase two of NIEC HQ (Mog) 1 Phase I completed. No funding for phase II. Phase I completed. No funding for phase II. Construction # of NIEC offices in the FMS 5 0 0 sources of evidence NIEC inauguration of completion of Phase1 of its future HQ IESG and UNOPS reports to GOJ for construction of NIEC HQ NIEC quarterly reports to the Federal Parliament Official NIEC presentations to donor partners and international community; IESG BTOR Output 5: Development of an enabling electoral legal electoral framework supported Electoral law adopted 1 0 0 sources of evidence Draft Electoral Law developed by MOIFAR, subject to Cabinet approval and submission to Parliament NSC ‘Baidoa Agreement’ on electoral model IESG briefing papers on electoral systems MOIFAR ELWG reports on consultations and sessions drafting articles of the electoral law MOIFAR advisors BTOR Output 6: Successful Programme management unqualified audit report 1 1 1 sources of evidence Auditor reports Presentation at PWG-1/SWG-3; Minutes PWG-1/SWG-3 Prodoc / AWP / LOA IESG resource mobilization paper |
| NARRATIVE Since the its early inception in 2015, the UN Integrated Electoral Support Group (IESG) provides capacity development support to the NIEC including electoral advice plus technical and budgetary assistance to build a solid and credible independent electoral institution, capable of planning and managing electoral processes according to its mandate and strategic plan. As Somalia did not have any universal elections in the last fifty years, and the preparations for the country’s first universal “one‐person one‐vote” elections since 1969 are an enormously challenging undertaking, institutional capacity development of a strong and independent electoral administration body is a critical foundation. Output 1: NIEC equipped with necessary capacities and structures to prepare for and conduct credible and inclusive elections The Joint Programme continued to provide the technical and administrative capacity building and support of the NIEC Secretariat. A series of institutional capacity development programs were implemented during the past months such as electoral capacity development, operational management support, and organizational development through direct technical engagement with NIEC, on-the-job trainings, and specifically designed workshops. All capacity development support builds on the NIEC’s five-year Strategic Plan (2017-2021); which serves as the institution’s roadmap to prepare for universal elections in Somalia, with key focus on: institutional capacity development; electoral legislation and procedures; informing the electorate; voter registration; a level playing field for candidates, parties, media and observers; the conduct of credible, free and fair elections; and a post-election evaluation before initiating the next cycle. As part of strengthening the NIEC’s administrative and finance systems, the Joint Programme for Electoral Support implements specific aspects of its programme through a Letter of Agreement (LOA) between the NIEC and UNDP. the LOA enables the NIEC to conduct procurement processes for activities of the workplan funded through UNDP. During the reporting period, UNDP initiated a third-party micro-capacity assessment of the NIEC. Micro-capacity assessments evaluate an implementing partner’s financial management systems and internal controls. This applies to all partners UNDP works with globally, including Government institutions, civil society and private sector partners. Micro-assessments are conducted as per UNDP requirements of a ‘Harmonized Approach for Cash Transfers’ (HACT) of implementing partners. The assessments review the institution’s administrative and financial management system and help to decide the appropriate cash transfer modality and related assurance activities. The assessment includes recommendations for capacity development of partners. The report of the NIEC’s micro-capacity assessment rated the NIEC as medium risk and hence can be allowed to utilize cash advances under the LOA with UNDP. From 20 to 24 October 2018, the NIEC convened a five-day intensive strategic review workshop. Officials from the NIEC together with IESG and the US ‘BUILD’ Project and senior facilitators, including the former Chair of the Kenyan Independent Electoral and Boundaries Commission (IEBC) attended the review of NIEC strategic plan workshop. The objective of the workshop was to review the activities in line with the NIEC Strategic Plan and evaluate the progress as well as to assess the NIEC institutional capacity to achieve the goal of universal one-person-one-vote elections to be held in 2020. The review is to emerge with an action plan containing specific project activities and priorities including identified possible collaboration with different partners to achieve maximum output. A follow-up workshop was held in December to finalize the action plan. It was also stressed to build an effective mechanism of coordination and monitoring of the works of the various clusters. The NIEC has prioritised governance as an avenue for continuous learning essential for the establishment of a professional and credible institution, contributing to the transformation of Somalia as the country embarks on a new democratic trajectory. Recognising the importance to practice effective leadership and governance in executing its statutory mandate, the members of the Commission have acknowledged the need for capacity development in the area of governance and leadership. From 15-18 October 2018, the NIEC conducted an Institutional Governance Workshop, attended by NIEC Commissioners and senior management of the Secretariat, and facilitated by two senior experts, including the former Chair of the IEBC who was instrumental in sharing experiences and expertise. The workshop aimed to build the institutional capacity of the NIEC in governance and leadership and to strengthen management, administrative, policies and operations that are essential for the Commission to become accountable and effective institution in executing its responsibilities in a professional, transparent and credible manner. The workshop contributed to a strong foundation integrating global best practices, standards and ethics that demonstrate accountability, transparency and integrity in the operations of the Commission, providing strategic leadership and ethical conduct as they discharge their statutory mandate as articulated in the Provisional Constitution and the NIEC 5-year strategic plan. At the end of the workshop, Chairperson NIEC and Commissioners demonstrated the NIEC's commitment to promoting good governance and practices as they prepare to undertake the mammoth task of delivering the first post-war democratic elections in Somalia. As a member of the association of Arab Electoral Management Bodies, the Chair of the NIEC, Ms. Halima Ibrahim, attended in Istanbul, Turkey, a conference on the promotion of women in electoral administration. The conference was supported by the UNDP’s Regional Hub for Arab States. In 2018 with the support of UNDP, the Chair of the NIEC joined an exploratory mission together with other members of electoral management bodies from the Arab region to observe the municipal elections in Tunisia on 6 May 2018. The programme represented a unique opportunity for the representatives of the Arab EMBs to share best practices and experiences in election processes, was a valuable opportunity for the Tunisia Electoral Commission to showcase its experience to regional colleagues, and for the NIEC of Somalia to enhance its understanding of electoral processes. The Joint Programme for Electoral Support continued with technical and budgetary support to the NIEC to further develop its Secretariat; such as the establishment of a Legal Unit (recruitment of two legal specialists financed through the LOA), a GIS Unit (geographic information system unit – 8 interns), and an IT Unit (4 interns). As a sign of success, both the GIS and IT interns were incorporated after one month into the NIEC’s staffing structure, paid for by the FGS. Furthermore, with support from the Joint Programme, the NIEC deployed an HR specialist to assist with the development of HR guidelines and training of its HR department. Lastly, IESG has been advising the NIEC on how to establish sub-national offices, including drafting TOR for key personnel in the field and reporting lines. In December 2018, the NIEC has recruited four field staff for Puntland and is looking for office space to open its first field office in Garowe. In the coming months, the NIEC will open state offices in all the Federal Member States of Somalia. These offices will spearhead the Commission's electoral operations at state level. The newly-recruited field staff have been invited to attend in Mogadishu in December the NIEC's partnership building workshop. While an orientation was given on the NIEC's mandate, role and electoral operations in the field, the Puntland field staff were introduced to the Commissioners, the different colleagues in HQ, the political party registrar as well as IESG's recently recruited Electoral Field staff in Garowe. To support the NIEC's electoral operations at state level in the field, IESG has been recruiting different national and internationals electoral advisors in the field, based in UNSOM regional offices. IESG has opened 18 field staff positions under the UNSOM budget to assist the NIEC at the field level. International staff are now deployed in Baidoa, Garowe, Jowhar, Kismayo and for Benadir. The recruitment of national field officers is ongoing. A voter registration and procedures advisor has been recruited for IESG HQ. Output 2: NIEC supported to enhance public awareness of electoral processes, including promotion of women’s participation To enhance its engagements in the Federal Member States NIEC in 2018 conducted intensive consultations with sub-national stakeholders in the different regions of the country. Traveling to multiple locations in Puntland, Galmudug, Hirshabelle, South-West and Jubaland, the NIEC organized meetings on electoral issues with regional officials, local administration, traditional elders, aspiring political parties, religion leaders, women, youth groups and other civil society movements. It was the first time that the NIEC traveled this extensively within the country to reach out to stakeholders. These dialogues were part of the 90-days regional consultations the NIEC undertook throughout the country and abroad with different national and sub-national stakeholders to facilitate discussions on the preparations for 2020 universal suffrage elections and how to overcome the challenges, as instructed in November 2017 by the National Security Council (NSC) comprising the leadership of the Federal Government and the Federal Member States. In total, the NIEC conducted consultations in more than 30 different locations across Somalia and abroad. The NIEC reached out to approximately 6,000 people, including regional officials, elders, political parties, religious leaders, women and youth groups, and CSOs. The final consultations were with the Somali diaspora community in the US, Canada, Europe and Kenya. The NIEC briefed the National Security Council on its consultations and findings. The NIEC consultations were widely covered on social media as well as on radio and TV. The Joint Programme for Electoral Support provided budgetary and logistical support to the NIEC’s missions in the FMS, assisted with the development of a facilitation guide, provided editorial and translation support for the publication of the NIEC’s comprehensive ‘Consultations Report’, and assisted with the compilation of a video and a media presentation of the different consultations. In addition, the Joint Programme for Electoral Support has been working closely with the NIEC’s newly established Public Outreach unit, particularly with regarding the development of a public outreach strategy and the active use by the NIEC of its website and Facebook and twitter accounts. In the second half of 2018, the NIEC held different session with national stakeholders and civil society partners to develop a curriculum for voter education. On 27 and 28 November, IESG organised a social media training for the NIEC staff in Mogadishu. The two-day training was attended by NIEC staff including senior managers, and those working on public outreach, operations, and voter registration. The training aimed at enhancing NIEC's public outreach capacity through teaching social media techniques in order to boost the skill of their employees on the use of social media and covered the use of Twitter, Facebook, Instagram, Snapchat, LinkedIn and Pinterest. From 4 to 12 December, the NIEC conducted a joint workshop with national stakeholders on modalities for establishing effective partnerships for implementing the NIEC Strategic Plan. The workshop was attended by civil society organizations and other Somali electoral stakeholders. The workshop was conducted in two phases. The first phase focused on the capacities of the NIEC in managing partnerships, identified potential partners for implementation of the NIEC's Electoral Operations Plan, and designed tools for engagement to assist NIEC with managing these partnerships. The second phase reviewed the NIEC's stakeholders map, developed a shared understanding of the NIEC's strategic direction, and looked at joint work plans with local partners, based on the NIEC's Strategic Plan. The workshop followed up on the NIEC Strategic Plan Review, which was held from 20 to 24 October. Output 3: Support to the NIEC’s electoral operations In 2018, the NIEC reviewed all possibilities and a decision on the preferred methodology was to be consulted with key partners to aid implementation to commence in early 2019. A minimum level of security to allow access will be a key factor for the success of the voter registration process. Joint Programme for Electoral Support organized a workshop for the NIEC on voter registration facilitated by international experts. It was an opportunity for the NIEC to further analyze the outcomes of the Voter Registration Feasibility Study and its implications to inform the strategic and operational decisions in the next months. The workshop included a certified BRIDGE module (Building Resources in Democracy Governance and Elections) on Voter Registration Course, designed and customized to suit the needs of the NIEC. International experts and IESG advisors took participants through an intensive programme covering: Reasons for Registration, Guiding Principles of Voter Registration, Eligibility; Types of Registers, Information Management; Steps to a Final Voter’s List; Operational Considerations; Voter Education; Stakeholders; Information Technology in Voter Registration and Voters Roll Audit. The emphasis was made on the following cross-cutting themes such as access, sustainability, technology, integrity as they relate to the context of the country. During the year 2018, IESG supported the NIEC with the establishment of a GIS unit (geographic information system unit), which will help the NIEC to define voter catchment areas in the country based on satellite images and geographic indicators. The task of the GIS unit includes the mapping of the country into manageable units for electoral purposes, such as voter registration centres or polling centres. In a next phase, physical verification of the voter catchment areas will be required by the NIEC to feed into the upcoming operations plan for voter registration. With regard to the delimitation of the electoral boundaries, the NIEC will depend on the criteria set in the Constitution and the Electoral Law. The identification of voter catchment areas is a first step in the process of establishing future voter registration centres. In the third quarter of 2018, the NIEC had finalized a desk study identifying around 1,760 potential voter catchment areas across the country based on satellite images, GIS data and tentative population estimates. The results of the pilot project will feed into the NIEC's planning of a nationwide verification process of voter catchment areas in the upcoming months. On 5 November, the NIEC and IESG held an initial lesson-learnt workshop to analyse the process and preliminary results of a pilot project mapping out potential voter registration sites. In October, equipped with GIS tools in a district in Mogadishu and one in Jowhar, the NIEC had deployed enumerators to identify on the ground and map out the coordinates and relevant data of 111 potential voter registration points. The two NIEC enumerator teams were deployed simultaneously for a total of 8 days including training, local travel, meeting with district commissioners, data capture of sites, and retrieval of devices used for the operation. This pilot project was designed to verify the technical and operational validity of the proposed field data collection methodology for potential voter From 14 to 17 November, IESG and NIEC directors and senior staff worked together on the development of an electoral operations chronogram in line with the NIEC Strategic Plan. The mapping of voter registration sites is part of the chronogram in anticipation of operational requirements for voter registration in 2020. The NIEC successfully organized in 2018 by-elections for different vacant seats of the Federal House of the People (on 28 January in Jowhar, on 15 February in Kismayo, on 26 February in Mogadishu, on 15 April and 4 September in Dhusamareb, and on 7 October in Garowe), for specific sub-clans from Hirshabelle, Jubaland, for the Somalilanders, Galmudug and Puntland respectively. These were the first electoral operations conducted by the NIEC since its establishment in 2015. The NIEC followed the procedures of the limited franchise electoral process in 2016, including the provision of 51 clan-based voting delegates and a formal candidate campaign period. The UN Integrated Electoral Support Group provided some logistical support and polling and counting training according to the procedures. Details of the sub-clan names, male/female voting delegates, candidates, number of received votes and voting rounds for each of the by-elections are available on the NIEC website http://niec.so/en/election/ In the security sector, the Joint Programme for Electoral Support engages with other UN departments to provide input to the Somalia Security ‘Transition Plan’ which plans for the gradual handover of security responsibility from AMISOM to Somali security institutions in three phases over the next four years, covering the period until elections in 2020/21. Based on good lessons learnt during the 2016 electoral process, IESG in support of the NIEC has been advising to the FGS senior leadership on the need of immediate planning for the elections and to re-establish the Somalia Elections Security Task Force from 2016/17. Output 4: Establishment of permanent NIEC office facilities The NIEC is currently based in Mogadishu on a temporary basis within the Government’s premises of Villa Somalia. The Joint Programme for electoral support has been assisting the NIEC to develop and enhance suitable office space inside Villa Somalia, including exploring assistance to refurbish certain rooms provided by the FGS. In the long-run, the UN Integrated Electoral Support Group helps the NIEC with setting up a permanent and independent headquarters outside Villa Somalia. In this respect, beyond the Multi-Partnership Trust Fund (MPTF), the UNSOM/UNDP joint programme has facilitated the construction of Phase 1 of the NIEC’s future headquarters with bilateral support from the Government of Japan and implemented through UNOPS. On 26 March, the NIEC held a ceremony to inaugurate the reinforced perimeter wall of its future headquarters in Mogadishu. The NIEC Chairperson thanked the UN and Japan for the support received in building the perimeter wall, and reiterated that it is essential for the NIEC to establish its offices outside of Government’s premises to guarantee its independence and operationalization. The mobilization of funds to proceed with construction of the future NIEC headquarters is therefore a top priority. The NIEC is also reaching out to traditional and non-traditional donors to assist in the construction of different components of Phase 2 of its future headquarters, such as a multi-functional data-training-media centre, warehouses for storage of sensitive and non-sensitive electoral materials, and the Commissioners and Secretariat offices. In addition, the NIEC is exploring the possibility to establish sub-national offices at the Federal Member States, something that will require further planning and implementation in the second half of 2018. Output 5: Development of an enabling electoral legal electoral framework supported Throughout 2018, the Joint Programme for Electoral Support has been providing in-depth technical assistance to the Ministry of Interior, Federal Affairs, and Reconciliation (MoIFAR) as well as other key interlocutors from the Federal Government and the Parliament on electoral concepts of the different systems of representation, to enhance the understanding of key components of the country’s electoral law. According to the Roadmap of the Federal Govenrment of Somalia, the Electoral Law had to be developed by December 2018. On 11 November, the Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR) submitted the draft Electoral Law to the Council of Ministers Secretariat. The Electoral Law is an essential priority for the Federal Government of Somalia as it defines the future system of representation and the regulatory framework for the NIEC to organise universal elections. The draft is in line with the 'Baidoa Agreement on the Electoral Model' which was endorsed by the leaders of the Federal Government of Somalia (FGS) and Federal Member State (FMS) in June 2018. The chosen electoral system for the next Federal Parliament is based on a closed list, multi-party system and proportional representation, and includes provisions to enhance women and minorities' representation. The draft included an annex with comments from civil society and political parties. On 6 and 21 November, MoIFAR, supported by the NIEC and other representatives of the federal government presented the draft law to international partners. On 12 December, IESG met with MoIFAR, NIEC and the Office of the President and presented consolidated comments from international partners. While some additional adjustments have been made, the draft law has yet to be discussed by the Council of Ministers, before being submitted to the Federal Parliament; a process that is now envisaged in the first half of 2019. In the run-up of the drafting process of the Law, IESG has developed and shared with partners discussion papers on electoral system issues currently under consideration in the context of Somalia. Through the provision of an ‘Electoral Law Working Group’ (ELWG) to MOIFAR, comprising 5 to 6 national advisors, the Joint Programme for Electoral Support assists the Ministry with understanding electoral concepts, seeking consensus amongst federal and member state partners, and the drafting of the Electoral Law. The ELWG formed together with other actors from the Federal Government and the NIEC an informal federal-level Electoral Task Force (ETF) to provide input and guidance on the development of the draft law. |
| Other Key Achievements N/A |
| Challenges (incl: Delays or Deviations) and Lessons Learnt: The transition from a clan-based system (as in 2016) to ‘one person, one vote’ elections poses big challenges for the country with many uncertainties at this stage. Major challenges identified in the Roadmap for 2020 elections include the development of sound electoral building blocks for this process, such as the establishment of an adequate electoral legal framework, the registration of political parties, an inclusive voter registration exercise, a sound electoral management body, and the set-up of an electoral dispute resolution mechanism. In addition to these core electoral challenges, a wider range of concerns affect the conduct of credible elections in Somalia, such as security, limited capacity and funding, logistical and operational difficulties, the question of the type of federalism the country is moving towards to, and an incomplete legal framework which needs inclusive political decision-making on crucial electoral elements. These factors are not fully part of the scope of the Joint Programme for Electoral Support nor within the direct control of electoral counterparts such as the NIEC. An inclusive politics strategy for this electoral cycle has been formalized to coordinate the higher-level policy issues such as the constitutional review process, the choice of electoral systems, state building, and rule of law. A sub-working group (SWG-3) chaired by the NIEC and the UK was set up in early 2018 as part of the pillar group on Inclusive Politics (PWG-1) co-chaired by EU and Switzerland. To manage programmatic challenges depending on political progress, the Project developed a phased approach to outline donor funding requirements. Funding is linked to achievement of specific milestones and targets in each phase: • Phase 1: development of electoral building blocks, including Electoral Law and NIEC’s institutional capacity (2018 – extended till end of 2019 to ensure continuity) • Phase 2: support to Voter Registration (depending on progress, envisaged from second half of 2019 till mid-2020) • Phase 3: support to Electoral Operations (depending on progress, envisaged from mid-2020 till early 2021) At the end of 2018, partners agreed that Phase 1 would be extended into 2019 to ensure continuity and continuous support for the development of the required electoral building blocks. Stock is to be taken in mid-2019 to assess progress on the key milestones for Phase 1; in particular the adoption of the Electoral Law, the NIEC’s establishment of its offices in the FMS, and the development of comprehensive plan for voter registration. This will enable all partners to assess the scope of support for Phase 2, with focus on voter registration, envisaged to be rolled out in early 2020. Next, upon successful and inclusive Voter Registration, Phase 3 will include the scope and support for elections. For Phase 2 and 3, stock will be taken continuously on progress and achievements of milestones, and the Joint Programme will be reviewed and amended for the next steps and phases in preparation for voter registration of consequently nation-wide universal elections. |
| Gender The UN electoral programme works closely with the UNSOM Gender Unit, UNDP’s Gender Equality and Women Empowerment (UNDP GEWE) project, and civil society organizations including women’s groups to enhance participation of women in electoral processes as potential voters and participants in electoral processes. Targeted activities in support of the NIEC include capacity building of female personnel in electoral administration and field work. The Joint Programme for Electoral Support has been assisting the NIEC to conduct activities and plan projects to promote participation of women in electoral processes – including as potential voters, candidates and election officials, and as overall participants in electoral processes. In 2018, 50% of the national advisors that IESG provided to the NIEC were women. |
| Proportion of gender specific outputs in Joint Programme | Total no. of Outputs | Total no. of gender specific Outputs |
|  | 5 | 0 |
| Proportion of Joint Programme staff with responsibility for gender issues (as of end of 2018) | Total no. of Staff | Total no. of staff with responsibility for gender issues |
|  | 20 | 2 |
| Human Rights Somalia is a signatory of different international and regional treaties and has obliged itself to follow key human rights standards, includes clauses as stipulated in Art 25 of the ICCPR that “every citizen shall have the right and the opportunity, without unreasonable restrictions, to vote and to be elected at genuine periodic elections which shall be by universal and equal suffrage and shall be held by secret ballot, guaranteeing the free expression of the will of the electors. the right of every citizen to vote”. The Joint Programme is designed according to this fundamental right with the aim to move the country from a clan-based limited franchise electoral process as in 2016/17 into universal suffrage elections in 2020/2021. Specific objectives in this regard, amongst other, include enhancing the independence of the NIEC, promoting inclusiveness during the voter registration, and ensuring a level playing field for all actors ensured in the different electoral laws. |
| Has the Joint Programme included a protection risk assessment in its context analysis, including on gender issues, and taken measures to mitigate these risks to ensure they are not exacerbated, or new risks created? | Result (Yes/No) |
|  | Yes |
| No. of Joint Programme outputs specifically designed to address specific protection concerns. | Result (No.) |
|  | 0 |
| No. of Joint Programme outputs designed to build capacity of duty bearers to fulfil their human rights obligations towards rights holders. | Result (Number) |
|  | 4 |
| Other |
| Does the Joint Programmes have a national cost-sharing component (i.e. funds and/or other resources provided by the FGS and/or FMS (including in-kind contributions)? (if ‘Yes’, describe below). | Results (Yes/No) |
|  | No |
| Have FMS(s) been engaged in one or more of the following: design, planning, implementation, coordination and/or monitoring of the Joint Programme. | Results (Yes/No) |
|  | No |
| Describe nature of cost sharing: N/A |
| Communications & Visibility The project disseminates monthly newsletters, which highlight the donor logos, to all partners. Besides regular bilateral meetings with respective donor partners, IESG presented project and electoral updates to the meetings of the Pillar Working Group on Inclusive Governance (PWG-1) and the Sub Working Group on Elections (SWG-3). In addition, the UN Integrated Electoral Support Group (IESG) organized additional coordination meetings with donor partners and other international electoral assistance providers to the NIEC, to share updates and strengthen coordination amongst international partners. Together with the NIEC, IESG has set up an information sharing meeting with international partners, which meets regularly to provide updates and share information and areas of support. In accordance with the EU-UNDP joint Guidelines on Electoral Assistance, the Joint Programme provided each month its input to UNDP’s Global Project for Electoral Cycle Support (GPECS). These monthly global Updates are shared to the EU as part of the EU-UNDP communications and visibility framework for electoral projects. From 20 February until 5 March, the photo exhibition on Electoral Assistance entitled “The Power of Democracy” was launched in the heart of Brussels for a two-weeks period, including a section on Somalia and the ‘2016 electoral process’. The idea of this exhibition is to give visibility and communicate to European citizens the work UNDP, together with the EU, does in the field of governance and in particular regarding electoral support. The overall theme was inclusiveness, with an accent is on the participation of women and youth. See Annex 4 for pictures from the exhibition. The Joint EC-UNDP Task Force on Electoral Assistance, based in Brussels, launched the website on the UN’s electoral assistance to Somalia, supported by the EU. The website aims to inform EU partners and the public at large on the UN’s electoral assistance programme in Somalia, as well as on other EU-supported UNDP electoral projects in the world. https://somalia.ec-undp-electoralassistance.org/ Banners with donor logos, the EU, Germany, Sweden, and the UK/DFID have been designed and used by the NIEC, in particular but not limited to when organizing workshops and posts on social media. A ceremony was held to inaugurate the reinforced perimeter wall of the NIEC’s future headquarters in Mogadishu. The ceremony was attended by officials and press. The NIEC thanked the UN and the Government of Japan for the support to develop its independent electoral premises. |
| Looking ahead Electoral Law On 11 November, the Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR) submitted the draft Electoral Law to the Council of Ministers Secretariat. The Electoral Law is an essential priority for the Federal Government of Somalia as it defines the future system of representation and the regulatory framework for the NIEC to organise universal elections. While it was initially envisaged the Law would be adopted before the end 2018, it is now anticipated that the Cabinet will submit the draft Law to Parliament in 2019, for final discussion and approval. NIEC Capacity Development - Stakeholder engagements The Joint Programme will continue with providing significant capacity development support to the NIEC. In addition to the current activities, focus will be given to the establishment of the NIEC’s offices at the Federal Member States. Furthermore, the NIEC will be assisted with its continued engagement of stakeholders and the development of a public outreach plan and products. Resource mobilization Progress both on the development of the electoral law as well as on the NIEC’s engagement with partners to determine the voter registration methodology - together with the development of a sound and detailed Voter Registration operations plan - will facilitate the discussions in 2019 on further resource mobilization for the preparations of voter registration. Achievements in this regard will inform international partners on the required electoral support in 2019 and 2020. Close coordination between national and international partners (NIEC, UN, donor partners, relevant international stakeholders, electoral partners, key actors of the FGS, etc.) will be required to navigate jointly towards the next phases of preparations for the country’s first universal elections since 1969, starting with the preparations for voter registration. Setting out milestones, stock-taking of critical success factors and review of key results areas are envisaged to be essential to move forward to Somalia’s path of multi-party universal suffrage elections. In terms of programming, it is essential for the Project to work on commitments from international partners, to ensure that the preparations for voter registration remain on track hand-in-hand with the NIEC strategic plan and decision-making. |

# ANNEX 1.	RISK MANAGEMENT

| Type of Risk | Description of Risk | Mitigating Measures |
| --- | --- | --- |
| Political | There is a risk that the past ‘clan-based’ 2016 electoral process, and political uncertainties, including on federalism, constitution and political inclusiveness, could draw away focus, willingness and resources from the preparations and capacity development required for universal elections. | The Government issued in January 2018 its Roadmap for elections in 2020/2021, confirming its commitment to universal suffrage elections. This commitment was also underscored in the FGS-FMS NSC meetings in February and June 2018. The renewed mandate of UNSOM underscores the UN’s support to universal elections. Based on the recommendations of the NAM, a new Programme outlines the parameters of UN support to universal elections, broken down in different essential building blocks. |
| Political | Risk that protracted discussion on the electoral legal framework, in particular the adoption of the Electoral Law, would jeopardize the electoral timeline and the affect the preparations for voter registration. | MoIFAR has finalized draft Electoral Law and submitted to Cabinet. Submission to Parliament and adoption is envisaged for the first half of 2019. International partners to take stock mid-2019 on progress. |
| Political | Risk that limited government capacity and unknown access and effectiveness at the sub-national level affects sound programme implementation, supervision, monitoring and evaluation | The JP for Electoral Support assists the NIEC with its engagements with the FMS and the establishment of sub-national electoral offices. |
| Political/Strategic/ operational/security/ financial | Risk that sound planning for voter registration will be undermined due to an unfinalized electoral law, protracted political discussions on registration of voters, operational challenges, security concerns, and funding constraints | The JP for Electoral Support has developed a phased approach, where scaling up for voter registration is dependent on achievement of essential milestones. Delays in this regard might affect the overall timeline for electoral operations in end 2020. |
| Security | Risk that political instability, lack of political will, political capacity, and conflicts (including AS) derail the process towards universal elections | Close coordination with security sector, including joint deployment of international security advisor in ROLSIG to provide de-politized polling centre threat assessments. Letter to MoIS to initiate electoral security and reestablish SESTF |
| Operational | Risk that the complexity of conducting operations in Somalia would affect sound programme implementation, supervision, monitoring and evaluation | The JP for electoral support is designed to provide tailored international capacity development to the NIEC, with international advisors in specific electoral niches. |
| Political | Risk that the electoral regulatory framework would not be developed in time affecting progress towards universal elections | The JP for electoral support is designed to provide tailored international advisers one electoral systems, guiding the counterparts throughout entire drafting process of the Law. |
| Security | Security conditions adversely impact the frequency with which UN advisers can work closely with government partners and other stakeholders. | UN to use alternative means such as videoconferencing. The Joint Programme is working with other actors, including agencies, programmes and projects that support the Somali Support to establishment of a security framework and an elections security task force. |
| Financial | Long-term sustainability of electoral processes in Somalia could become an issue if the national electoral management bodies (NIEC) does not receive sufficient funding through the government budget and is dependent on international funding. | The Joint Programme works together with the NIEC, donor partners and other stakeholders to include an adequate budget for the NIEC in the Government’s annual budget. The Joint Programme is extended until 31 December 2019 for the current priorities (reference to IESG resource mobilization paper shared prior to PWG/1) An electoral Needs Assessment Mission (NAM) was conducted that discussed with national and international partners to define the needs for an electoral capacity development framework towards universal elections by 2020. The FGS provided the NIEC a budget in 2018 for its staffing costs and some regular expenses. |
| Inclusive Politics | Risk that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups. | The NAM has underlined inclusivity as a key element for the UN in the preparations for future universal elections. Within the guidance of the Government and federal institutions, project supports consultative forums with the public, and works with media to ensure adequate information sharing and transparency on the process. |
| Inclusive Politics | Risk that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them | The NAM has underlined inclusivity as a key element for the UN in the preparations for future universal elections. Within the guidance of the Government and federal institutions, project supports consultative forums with the public, and works with media to ensure adequate information sharing and transparency on the process. |
| Inclusive Politics | Risk that duty-bearers do not have the capacity to meet their obligations in the Project | The UN strategy on future universal elections looks into rights-holders and their capacity to claim their rights. |
| Inclusive Politics | Risk that rights-holders do not have the capacity to claim their rights | Project activities have gender components, gender plans and these are considered through all project activities. For example, trainings on “Gender Responsive Elections”. There is collaboration amongst UN gender experts and focal persons from the Joint Programme for Electoral Support, the UNSOM/UNDP Rule of Law & Security Institutions Group (ROLSIG), the UN Resident Coordination Office (RCO) and UNDP CO on gender concerns. |
| Inclusive Politics | Risk that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls | Project activities have gender components, gender plans and these are considered through all project activities. For example, trainings on “Gender Responsive Elections”. There is collaboration amongst UN gender experts and focal persons. |

# ANNEX 2.	MONITORING AND OVERSIGHT ACTIVITIES

| Monitoring Activity | Date | Description & Comments | Key Findings / Recommendations |
| --- | --- | --- | --- |
| PWG-1 / SWG-3 steering committee meetings | 12 Feb (SWG-3); 29 May (SWG-3); 30 May (PWG-1) 1 October (Inclusive Politics); 10-11 December SWG3+PWG1) | PWG discussed and approved the 2018 Work Plans and budget funding of the UNDP/UNSOM JP for Electoral Support | Presentations and Meeting minutes |
| NIEC HACT Assessment | April 2018 | Third party institutional micro-capacity assessment of the NIEC to determine fiduciary risk level and UNDP cash transfer modalities | Final report |
| Project DIM Audit | May 2018 | Unqualified findings | Final report |
| IESG Field Missions to Puntland, South-West, Jubbaland | January, May, June | IESG deployed field missions to Garowe, Baidoa and Kismayo in assistance of NIEC establishment of sub-national elections and assessment of possible UN support in the sections fo electoral operations | BTOR |

ANNEX 3.	TRAINING DATA

| # | Target Group | Dates | # of participants | Title of the training | Location of training | Training provider |
| --- | --- | --- | --- | --- | --- | --- |
|  | Ministry. District or UN staff | Others |  |  |  |  |  |
|  |  |  |  | M | F | Total |  |  |  |
|  |  | NIEC | 8-Jan-18 | 5 | 1 | 6 | By-election refresher course | Kismayo, Jowhar & Mogadishu |  |
|  |  | NIEC | 25-Jan-18 | 9 | 3 | 12 | Lessons learnt on the by-election in Jowhar | Mogadishu |  |
|  |  | NIEC | 1-Mar-18 | 4 | 1 | 5 | IT training | Mogadishu |  |
|  |  | NIEC | 24-Feb.-2018 | 5 | 2 | 7 | GIS workshop | Mogadishu |  |
|  |  | NIEC | 14-May-18 | 35 | 12 | 47 | Voter Registration Workshop | Mogadishu |  |
|  |  | NIEC | 5-Jun-18 | 3 | 3 | 6 | Electoral Legal Framework workshop | Mogadishu |  |
|  |  | NIEC | 8-Jul-18 | 7 | 4 | 11 | Institutional Governance Retreat | Mogadishu |  |
|  |  | MoIFA | 19-Jul-18 | 3 | 4 | 7 | Revisions on First Draft of Electoral Law | Mogadishu |  |
|  |  | NIEC | 23-Jul-18 | 8 | 2 | 10 | GIS Master Training of Training | Mogadishu |  |
|  |  | NIEC | 29-Jul-18 | 8 | 0 | 8 | By-election Orientation Workshop | Mogadishu |  |
|  |  | NIEC | 5-Aug-18 | 4 | 0 | 4 | Logistics Workshop | Mogadishu |  |
|  |  | NIEC | 16-Aug-18 | 2 | 2 | 4 | Mentoring, coaching and skills transfer skill workshop | Mogadishu |  |
|  |  | NIEC | 18-Aug-18 | 15 | 6 | 21 | Media and Elections | Mogadishu |  |
|  |  | NIEC | 27-Aug-18 | 16 | 5 | 21 | Civic and Voter Education | Mogadishu |  |
|  |  | NIEC | 23-Sep-18 | 11 | 4 | 15 | Professional Behavior and conduct in workplace | Mogadishu |  |
|  |  | NIEC | 15-Oct-18 | 12 | 5 | 17 | Institutional/Corporate Governance | Mogadishu |  |
|  |  | NIEC | 20-Oct-18 | 23 | 7 | 30 | Strategic Plan Review | Mogadishu |  |
|  |  | NIEC | 5-Nov-18 | 10 | 6 | 16 | GIS Pilot Study Lessons Learnt | Mogadishu |  |
|  |  | NIEC | 14-Nov-18 | 12 | 2 | 14 | Electoral Operations chronogram | Mogadishu |  |
|  |  | NIEC | 27-Nov-18 | 20 | 4 | 24 | Social Media | Mogadishu |  |
|  |  | NIEC | 4-Dec-18 | 38 | 5 | 43 | Building Partnerships for Electoral Management | Mogadishu |  |
| Totals: | 250 | 78 | 321 |  |  |  |

# Footnotes

Uncertified expenditures. Certified annual expenditures can be found in the Annual Financial Report of MPTF Office (http://mptf.undp.org/factsheet/fund/4SO00 )

Fill in only the numbers or yes/no; no explanations to be given here.

Gender Specific Outputs are those that are specifically designed to directly and explicitly contribute to the promotion of Gender Equality and Women’s Empowerment.

Staff members are those contracted to undertaken work for the Joint Programme including full time staff, consultants, advisors, interns, etc. Staff members with responsibility for gender issues are those who have gender related activities included in their Terms of Reference.

International Covenant on Civil and Political Rights (ICCPR) -  ratified by Somalia in 1990

Environmental; Financial; Operational; Organizational; Political; Regulatory; Security; Strategic; Other.