United Nations Development Programme

Country: Republic of Serbia

2018 Annual Work Plan

| Project Title: | Second Biennial Update Report and Third National Communication under the UNFCCC |
| --- | --- |
| UNDAF Outcome(s): | By 2020, there are improved capacities to combat climate change and manage natural resources and communities are more resilient to the effects natural and man-made disasters |
| Expected Output(s): (Those that will result from the project and extracted from the CPD) | Capacities for policy making and implementation of international agreements improved |
| Implementing Partner: | Ministry of Environmental Protection |
| Responsible Parties: | Ministry of Environmental Protection, UNDP |

Agreed by Ministry of Environmental Protection:

Agreed by UNDP:

# Annual Work Plan 2018

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
| And baseline, indicators including annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | 2018 |
| Preparation of Serbia’s Second Biennial Update Report (2BUR) and Third National Communication (3NC) to the UNFCCC. Baseline: The Republic of Serbia submitted its Initial National Communication in 2010, First Biennial Update Report in 2016 and Second National Communication in 2017including at least 10 various awareness raising events organized during the preparation of reports; GHG Inventory in FBUR covered period 2010-2013; GHG Inventory in SNC covered period 2000-2009 and estimations for 2014 year Indicators: 1. Number of trainings and awareness raising activities for stakeholders carried out as part of the biennial reporting process; 2. GHG inventory for the period of 2014 -2016 (2BUR) prepared; 3. GHG inventory for the period of 2010 -2018 (3NC) started Targets: 1. 5 2. yes 3. yes | National Circumstances and other relevant information related to UNFCCC Actions: Awareness raising events related to climate change issues and UNFCCC reporting requirements conducted; Detailed information and data on national circumstances of relevance to climate change mitigation and adaptation compiled and analyzed | x | x | x | x | UNDP | GEF | 71300 Local Consultants 71600 Travel 72800 Equipment 74200 Audio Visual & Print 74500 Miscellaneous 75700 Training & Workshop | 7,000 1,000 12,000 3,000 1,000 2,000 |
|  | National GHG Inventory Actions: GHG inventory for the period of 2014 -2016 (2BUR) prepared; GHG inventory for the period of 2010 -2018 (3NC) started Training for SEPA in applying GHG Inventory Software for non-Annex I Parties (NAIIS) | x | x | x | x | UNDP | GEF | 71200 International Consultants 71300 Local Consultants 71600 Travel 72100 Contr.Services- Companies 74200 Audio Visual & Print 74500 Miscellaneous 75700 Training & Workshop | 5,000 5,000 1,000 5,000 2,000 1,000 1,000 |
|  | Climate Change Mitigation Actions: Mitigation potential in key development sectors (e.g. energy, agriculture, LULUCF, waste, transport and infrastructure) assessed, and abatement measures proposed; Progress on policies and actions to mitigate GHG from 2010, at national, sub-national and local levels assessed | x | x | x | x | UNDP | GEF | 71300 Local Consultants 71600 Travel 72100 Contr.Services- Companies 74200 Audio Visual & Print 74500 Miscellaneous 75700 Training & Workshop | 5,000 1,000 15,000 2,000 550 1,000 |
|  | Vulnerability Assessment & Adaptation to the climate change Actions: Comparative analysis of developed climate change scenarios in previous NCs, with results from existing databases of climate scenarios including assessment of the level of climate change scenarios uncertainty; CC adaptation measures identified and formulated, including cost-benefit and damage and losses analyses |  |  | x | x | UNDP | GEF | 71300 Local Consultants 71600 Travel 72100 Contractual Services- Companies 74200 Audio Visual & Print 74500 Miscellaneous 75700 Training Workshop | 5,000 500 10,000 1,000 1,000 500 |
|  | Domestic MRV Actions: Current state in regard to domestic MRV system analysed; The development process of national institutional arrangements and framework for domestic MRV supported. National MRV system developed and operational | x | x | x | x | UNDP | GEF | 71200 International Consultants 71300 Local Consultants 72100 Contractual Services- Companies 72500 Office Supplies 74500 Miscellaneous | 5,000 5,000 5,000 2,000 500 |
|  | M&E | x | x | x | x | UNDP | GEF | 72100 Contractual Services- Companies | 1,000 |
|  | Project management | x | x | x | x | UNDP | GEF | 71400 Contractual Services Individual 71600 Travel 74500 Miscellaneous 64397 Direct project costs-Staff 74596 Direct Project Cost-GoE | 11,000 1,000 500 2,750 1,150 |
|  | Subtotal Direct Project Costs |  |
|  | General Management Services |  |
|  | TOTAL PROJECT COST | 123,450 |

# Footnotes

DPC included in budget (marked in yellow) DPC calculated as per old ISS costing policy and covers Office and IT costs only, no staff salaries

GMS already collected at the beginning of the project in 2016. GMS in GEF funded projects is taken on the fund level, funds are budgeted net GMS with ASL allocation per CO

# Text boxes

Brief Description

The project aims at enabling the Republic of Serbia to prepare, produce and disseminate its Second Biennial Update Report (2BUR) and Third National Communication (3NC) to the UN Framework Convention on Climate Change (UNFCCC) according to Decisions 17/CP.8, 1/CP.16, 2/CP.17 and other relevant guidance. The 2BUR and 3NC will update and strengthen information provided regarding national circumstances, greenhouse gas inventories, climate change mitigation, vulnerability to climate change and steps taken to adapt to climate change, as well as identify constraints, gaps, and financial, technology and capacity building needs.

In 2018 it is expected to strengthen cross-sector collaboration for the preparation of GHG Inventory, and to improve institutional capacities for the improvement of the National GHG Inventory System including further support to domestic MRV framework.

.

Total resources required         123,450 USD

Total allocated resources:	 123,450 USD

- GEF: 	123,450 USD

Unfunded budget:

In-kind Contributions: 17,500 USD (Government)

5,000 USD (UNDP)

Atlas Award ID:	00099636

Project ID: 	00102933

Start date:	January 2018

End Date		December 2021

Management Arrangements: NIM with UNDP support