UNDP South Sudan

2014 Annual Work Plan

| Project name | Amount |
| --- | --- |
| Transitional Funding Mechanism for Tuberculosis | US$4,800,385 |

| Hon. Aggrey Tisa Sabuni Minister, Ministry of Finance, Commerce, Investment and Economic Planning Government of the Republic of South Sudan | Balázs Horváth Country Director UNDP South Sudan Programme |
| --- | --- |
| Signature: | Signature: |
| Date: | Date: |

United Nations Development Programme

South Sudan

Annual Work plan 2014

| Project Title | Improving and Expanding Tuberculosis Control in South Sudan |
| --- | --- |
| UNDAF Outcome(s): | Key service delivery systems are in place laying the groundwork for increased demand |
| Expected CP Output(s): | Health Sector infrastructure expanded, and pharmaceutical supply chain systems transitions to Government management |
| Implementing Partner: | UNDP |
| Responsible Parties: | National Tuberculosis, Leprosy and Burluli Ulcer Control Programme, Ministry of Health; Catholic Diocese of Torit (CDoT); WHO; Arkangelo Ali Association (AAA); State Ministries of Health; Doctors with Africa-CUAMM |

Agreed by Ministry of Finance, Commerce, Investment and Economic Planning:

Agreed by UNDP:

# Annual Workplan

Year: 2014

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1: Improved Diagnosis of Tuberculosis Baseline: NA Indicator: Percentage of microscopy centers with 100% concordance external quality assurance blinded rechecking Target: 85% Baseline: 46 Indicator: Number of lab personnel doing TB microscopy in South Sudan Target: 88 Baseline:3,305 Indicator: Number of TB patients diagnosed with smear microscopy Target: 4,254 Baseline:10 Indicator: Number and percentage of laboratories showing adequate performance in external quality assurance for smear microscopy among Target: 38 Related CP outcome: Key service delivery systems are in place, laying the groundwork for increased demand Output 2: High Quality DOTS Baseline: 8,924 Indicator: Number of all forms of TB patients notified to the national health authority (NTP) Target: 13,131 Baseline:73% Indicator: Number and percentage of bacteriologically confirmed TB patients including relapses successfully treated (cured plus completed treatment) among new sputum smear positive registered during a specified period Target:82% Baseline: 97% Indicator: Number and percentage of TBMU submitting complete and timely reports according to national guidelines Target: 100% Baseline: 65 Indicator: Number of TB facilities with no stock out of essential TB drugs Target: 70 Baseline:0 Number of TB program reviews conducted Target: 1 Related CP outcome: Key service delivery systems are in place, laying the groundwork for increased demand Output 3: Strengthened Community TB Care Baseline: 0 Indicator: Number of CBOs trained on community TB care Target:20 Baseline:0 Indicator:Number of CBO DOTS reviews and data collection conducted Target:18 Baseline:0 Indicator:Number of bicycles replaced for community mobilizers Target:36 Related CP outcome: Key service delivery systems are in place, laying the groundwork for increased demand | 1. 1 Activity Result Quality assurance of peripheral TB laboratories conducted Activity Action Conduct Quality Assurance visits from state level to periphery centres Activity Action Maintain laboratory personnel for TB diagnosis Activity Action: Conduct Refresher training of 20 laboratory staff on microscopy quality assurance Activity Action: CTRL staff conduct Quality Assurance visits from central level to state | X X X X x | X X X X x | X X X X x | X X X X X | UNDP in support of MOH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM | 72600(Grants) GMS (7%) Activity1 Subtotal | US$42,329 US$2,963 US$45,292 |
|  | 2.1 Activity Result Improve Quality of DOTS 2.1.1 Action Support Human resources for provision of DOT 2.1.2 Action Supervision visits by NTP State/CSOs from State to peripheral TB diagnostic and treatment centres 2.1.3 Action TB review meeting at state level 2.1.4 Action Support TB treatment by procuring essential TB drugs. 2.1.5 Action Conduct TB program review |  |  |  |  | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM | 72600(Grants) GMS (7%) Activity 2 Subtotal | US$3,299,791 US$230,985 US$3,530,776 |
|  |  | X X X X | X X X X X | X X X X | X X X X |  |  |  |  |
|  | 3.1 Activity Result Maintain TB outreach services to underserved populations 3.1.1 Activity Action: Refresher training of CBOs on TB 3.1.2 Activity Action: CBO quarterly DOTS review and data collection 3.1.3 Activity Action: Replace bicycles for community mobilizers | X |  |  |  | UNDP in support of MoH | GFATM | 72600(Grants) GMS (7%) Activity 3 Subtotal | US$155,830 US$10,908 US$166,738 |
|  |  | X X X | X X X | X X | X X |  |  |  |  |
| Output 4: Multi-drug resistant TB & TB/HIV controlled & prevented Baseline: 236 Indicator: Number of sputum specimens transported for culture and DST Target: 1000 Baseline: 100 Indicator: All health products and health equipment procured Target: Related CP outcome: Key service delivery systems are in place, laying the groundwork for increased demand | 4.1 Activity Result: Ensure proper functioning of the CTRL Activity Action: 4.1.1 Transport of 1000 sputum specimen for C/DST Activity Action: 4.1.2 Procurement of health products and health equipment 4.2 Activity Result: Provide integrated TB/HIV services to co-infected patients. 4.2.1. Re-fresher training on PITC. | X | X | X | X | UNDP in support of MoH | GFATM | 72600(Grants) GMS (7%) Subtotal | US$211,095 US$14,777 US$225,872 US$19,600 US$1,372 US$ 20,972 |
|  |  | X X | X X | X X |  |  |  |  |  |
|  | 4.3 Activity Result: Project Management including M&E Activities properly carried out 4.3.1 Activity Action: Supportive environment programme management and administration for PMU and SRs | X | X | X | X | UNDP in support of MoH | GFATM | 61100 (Staff Cost) GMS (7%) Subtotal Rental & Maintenance (common services- premises): 3%: GMS (7%) Contribution (office common security): 1%: GMS (7%) Reimbursement Cost (to UNDP for support services):1%: GMS (7%) | US$534,549 US$37,418 US$571,967 US$133,889 US$9,372 US$44,630 US$3,124 US$44,630 US$3,124 |
| Total Budget |  |  |  |  |  |  |  |  | US$4,800,385 |

# Management Arrangements

The project will be managed under UNDP’s Direct Implementation Modality in close collaboration with the Ministry of Health of South Sudan. The project operates under the oversight of a Project Board which includes the Chair Person of CCM-South Sudan (Country Coordinating Mechanism South Sudan), the UNDP Country Director,the Director General of Community and Public Health, and the Manager of National TB, Leprosy, and Buruli Ulcer Control Programme.  The Project Board will meet on a quarterly basis.The Project Board is responsible for the overall direction and management of the project and has responsibility and authority for the project within the remit of the project mandate.  The Project Board approves all major plans and authorises any major deviation from agreed plans. It is the authority that signs off the completion of each year of the project, as well as authorises the start of the next year. It ensures that required resources are committed, and arbitrates on any conflicts within the project, negotiating solutions to any problems between the project and external bodies.

The Project Board is ultimately responsible for assuring that the project remains on course to deliver the desired outcome of the project as defined in the Project Document. According to the size, complexity and risk of the project, the Project Board may decide to delegate some of this Project Assurance responsibility.

The overall project organization structure is as follows:

The Global Fund Project is part of the Human Development and Inclusive Growth Unit supported by other Units such as Operations and the Programme and Partnership Support Unit (PPSU). In South Sudan, UNDP has been serving as the Principal Recipient of last resort since 2004 for five grants. The PR works in collaboration with national and international partners involved in the fight against tuberculosis. The Global Fund resources are additional to national resources as well as resources provided by other partners.

The PR has a number of Conditions Precedent and Special Terms and Conditions that should be fulfilled during various stages of the programme Grant Agreement. These Conditions Precedent and Special Terms and Conditions are outlined in Sections B and C of the Annex A to the Grant Agreement between Principal Recipient and the Global Fund.

The Country Coordination Mechanism – CCM, performs the oversight function as well as monitoring and evaluation of the Global Fund projects in the country. Different stages of project implementation such as project amendments, phase two continuation requests, no cost extension request, are cleared by and submitted to the Global Fund through the CCM.

The Local Fund Agent – LFA, serves as Global Fund representative in the country. It provides oversight of the project implementation conducts verification of the programmatic and financial reports and makes recommendations to the Global Fund with regards to project progress and disbursement of funds.

The Project management Unit (PMU) of the PR has four major functions.

Project Management: This is composed of a Project Manager and a Project Analyst. The TB Project Manager is fully responsible for the overall coordination of the project activities. The Project Manager and the Analyst work in close collaboration with national counterparts and other stakeholders to implement the project.

Procurement and Supply Management: Presently, this team consists of a Procurement Specialist, Procurement Analyst and an Associate. Under the grant agreement signed between UNDP as PR and the Global Fund, all procurement activities are exclusively done by the PR.

Finance Management: This team is made up of a Finance Specialist, an Analyst and two Finance Associates. The finance team is responsible for budget management.

Monitoring and Evaluation:This team is composed of M&E Specialists and three Analysts based at central level. The team is responsible for monitoring of project activities, review and verification of data and preparation of progress reports to the Donor with the support of the Project Manager.

The PR has subcontracted five agencies to execute this project as follows:

All four implementing partners are responsible for implementing aspects of the programme in all 10 States of South Sudan. The project is aimed at contributing to the improvement of quality of life of the people of South Sudan by dramatically reducing the burden of TB in South Sudan and stop TB Partnerships targets. The major components of the project include pursuing high quality Directly Observed Therapy Short course (DOTS) expansion and enhancement, improving monitoring and evaluation through human resources development and technical assistance at service delivery points and managerial points, introducing programmatic management of drug resistance TB.

The Sub-recipients:

- Arkangelo Ali Association (AAA), a faith-based organization, is one of the sub-recipients of the grant. It is contributing towards the overall goal of reducing mortality and morbidity due to TB by supporting 33 TB management units (TB diagnostic and treatment centers included) in 2014 to provide comprehensive TB care through rehabilitation of needy laboratories, training of laboratory technicians and assistants, outreach campaign to sensitize the community on TB and carry out diagnostic services using mobile laboratories as well as ensuring sufficient drugs in all facilities. Evaluation (both internal and external) of the partner has concluded that it is significantly contributing to the national TB control initiatives.

- World Health Organization (WHO) is a UN organization that is continuing to serve as a sub-recipient of the grant.

- Doctors with Africa-CUAMM & COSV: They are supporting three TB management units and working on ensuring that TB services are provided adequately through maintenance and equipping of TB laboratories.

- Catholic Diocese of Torit (CDOT) is a faith-based organization that has joined the partnership in combating TB in South Sudan. For 2014, the partner will implement activities in two TB management units. Thus, they will provide all the necessary TB services of diagnosis, treatment, care, prevention and control within the facilities and for the catchment population.

- National TB, Leprosy, and Buruli Ulcer Control Programme (NTLBP) is the government department under the Directorate of Preventive Health Services within the Ministry of Health. It is a new SR for this grant since 2011. Since the department at present is fully staffed and equipped in terms of programmatic, financial and operational capacity to implement some of the activities under the grant, it was decided that the NTLBP should take the major portion of the grant’s population. Thus, NTLBP will be taking over 27 health facilities in their portfolio. Capacity assessment of the partner has clearly demonstrated the institution’s capability.

Collaborative Arrangements

The project will be operated synergistically with Transitional Funding Mechanism for HIV/AIDS as there are overlapping areas of management. As such, staff costs are shared; there will be integrated supervision, meetings to enhance project deliverables for both projects being implemented under the same programme.

Audit arrangements

Article 7. b. i. and ii of the Special Terms and Conditions of the Grant Agreement between UNDP and the Global Fund state that:(i) The Principal Recipient shall have annual financial audits conducted of Programme expenditures. Subject to the approval of the Global Fund, which approval shall not be unreasonably withheld, the Principal Recipient shall select an independent auditor to conduct the audits and set the terms of reference pursuant to which they shall be conducted. The cost of such special audit shall be borne by the Programme.

(ii) Should the Global Fund have reason to request a special purpose audit on the use of Global Fund resources, UNDP agrees to be responsible for: (i) securing the appointment of a mutually agreed independent auditor; and (ii) preparing mutually agreed audit Terms of Reference which reflect, as necessary, circumstances giving rise to the Global Fund’s request for said audit. The cost of such special audit shall be borne by the Programme.

The Principal Recipient shall notify the Global Fund promptly in writing of any audits of activities financed by this Agreement initiated by or at the request of an audit authority of the Government of the Host Country or of any other entity.

Agreement on intellectual property rights and use of logo on the project’s deliverables

The Principal Recipient must enter into an agreement with the Global Fund prior to using the Global Fund logo. The logo must be used in accordance with the terms and conditions of that agreement.

# Monitoring Framework And Evaluation

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted (see annex 1), a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- A project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project

- a Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

Annually

- Annual Review Report. An Annual Review Report shall be prepared by the Project Manager and shared with the Project Board and the Outcome Board. As minimum requirement, the Annual Review Report shall consist of the Atlas standard format for the QPR covering the whole year with updated information for each above element of the QPR as well as a summary of results achieved against pre-defined annual targets at the output level.

- Annual Project Review. Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Additionally, in accordance with the Standard Terms and Conditions in the grant agreement between the Principal Recipient and the Global Fund, the project will be monitored as follows:

Six monthly reports

Article 13, b. (1) states that “not later than 45 days after the close of each reporting period of the specific programme grant agreement, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, a periodic report on the Programme. The report shall reflect (i) financial activity during the reporting period in question and cumulatively from the beginning of the Programme until the end of the reporting period; and (ii) a description of progress towards achieving the agreed-upon milestones set forth in Annex A of the Grant Agreement. The Principal Recipient shall explain in the report any variance between planned and actual achievements for the period in question”.

Project Evaluation

The Global Fund Projects are subject to two types of Evaluations. Midterm Evaluations are conducted for projects transitioning from phase I to phase II. Final Evaluations are conducted at the end of phase II of the project. The Round 7 grant is in phase II of project implementation and a final evaluation is planned in early 2014.

Quality Management for Project Activity Results

| OUTPUT 1: High Quality DOTS Expansion and Enhancement |
| --- |
| Activity Result 1 | Quality Assurance of peripheral TB laboratories conducted | Start Date: 1st Jan 2014 End Date: 31stDec 2014 |
| Purpose | To improve diagnosis of TB through supporting quality assured microscopy |
| Description | In order to contribute to high quality DOTS expansion and enhancement in the end, the project will conduct quality assurance activities in at least 10 selected laboratories. |
| Quality Criteria | Quality Method | Date of Assessment |
| Quality Assurance visits have been conducted in 10 TB laboratories and AFB microscopy tests in those sites are quality assured. | Quality assurance reports compiled by the quality assurance officers. | July 2014, November 2014 |
| Refresher training for 20 lab staff conducted on microscopy quality assurance. | Training reports and attendance sheet | July 2014; November 2014 |

| Activity Result 2 | Improved quality of DOTS in all TB diagnostic and treatment facilities. | Start Date: 1st Jan 2014 End Date: 31stDec 2014 |
| --- | --- | --- |
| Purpose | To provide standardized treatment with directly observed treatment scheme and continued patient support. |
| Description | As per the guidelines of the Stop TB Partnership, standardized treatment and patient support is part and parcel of the Directly Observed Therapy Strategy. Thus, the project will contribute to standardized treatment for every TB patient and at the same time identify patient supporters (relatives, neighbours) who can be trained and observe & support the patients in completing the course of treatment.TB review meetings will also be conducted. |
| Quality Criteria | Quality Method | Date of Assessment |
| 253clinical and support staff maintained to provide DOTS at facility level. | Performance update and financial reports from all SRs | July 2014, December 2014 |
| 70 supervision visits carried out to peripheral TB centres | Trip reports; TB registers and quarterly reports | May, September, December 2014 |
| 8 TB review meetings conducted at state level | Feedback on review meetings from proceedings of the meetings | May, August, November 2014 |
| All essential anti-TB drugs are procured and distributed to each facility regularly | Availability of all anti-TB drugs in stores of all TB facilities as reported quarterly | April, August, December 2014 |

| Activity Result 3 | TB outreach services to underserved populations are maintained | Start Date: 1st Jan 2014 End Date: 31stDec 2014 |
| --- | --- | --- |
| Purpose | Improve the current TB treatment success rate through outreach programmes into villages where access to TB facility is denied for different reasons. |
| Description | In order to improve the persistent low level TB treatment success rate in the Republic of South Sudan, underserved populations should be reached out. Underserved populations include remote villages, uniformed population, pastoralists, and displaced population. |
| Quality Criteria | Quality Method | Date of Assessment |
| 20 community based organizations trained on TB outreach. | Training report and feedback from the CBOs | May, November 2014 |
| CBO quarterly DOTS review data collection | Reports on data collection of outreach activities. | April, December 2014 |
| 36 Bicycles for community mobilizers replaced | Reports | November 2014 |

| Activity Result 4 | The Central TB Reference Laboratory functioning properly. | Start Date: 1stJan 2014 End Date: 31stDec 2014 |
| --- | --- | --- |
| Purpose | To identify cases of Multi Drug Resistant TB among Re-treatment patients |
| Description | In order to respond to the challenges of MDR TB, all re-treatment cases will be considered for sputum culture and sensitivity testing. Essential equipment and products will be procured to maintain the functioning of the CTRL. |
| Quality Criteria | Quality Method | Date of Assessment |
| 1000 sputum specimens are transported for culture and DST. | Laboratory reports | April, August, December 2014 |
| Essential health products are procured for the CTRL | Laboratory reports | April, August, November 2014 |

| Activity Result 5 | TB/HIV collaborative activities are carried out properly. | Start Date: 1st Jan 2014 End Date: 31stDec 2014 |
| --- | --- | --- |
| Purpose | To integrate TB/HIV services in all service delivery points |
| Description | TB/HIV integrated services will be delivered in all TB facilities. Staff will be trained on the collaborative activities and there will be a close follow up. |
| Quality Criteria | Quality Method | Date of Assessment |
| Staff trained on TB/HIV. TB/HIV reports made available to NTP. | Training reports and Quarterly reports | May, August, November 2014 |

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed viahttp://www.un.org/Docs/sc/committees/1267/1267ListEng.htm.This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document”.

ANNEX 1: RISK LOG

| Project Title: Transitional Funding Mechanism for Tuberculosis | Award ID: | Date: October 2013 |
| --- | --- | --- |
| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status |
| 1 | Delayed functionality of Central TB Reference Laboratory. | 2013 | Operational | If this risk is to occur, culture and DST cannot be conducted in country; quality assurance activities will be impaired; trained CTRL staff will remain idle P = 4 I = 3 | Actions taken to counter: i)use of in-country mechanical engineers (UNOPS contracted) to accelerate the process; ii)follow up with Global Fund for the fund;iii)Follow up with procurement unit and UNDP HQ | Global Fund Coordinator, Director of Diagnostics | Project Manager | October 2013 | No change. |
| 2 | Community TB Care not fully delivered | October 2013 | Environmental Operational | If this risk occurs, TB treatment success rate will not improve; loss to follow up patients roaming in the community could turn into carriers of MDR TB & thus facilitate transmission of MDR TB strains P=3 I =3 | Countermeasures to be taken: i) identification of CBOs already operating in the villages; ii) identification of highly motivated community mobilizers iii) provision of incentives for CBOs and mobilizers | Project Manager, NTP manager | Project Manager | October 2013 | No change |
| 3 | TB/HIV collaborative activities weakened | October 2013 | Financial Operational | Given the phasing out of a TB/HIV Round 5 project, most activities supported by this project will come to an end. Thus, HIV testing will decline because of lack of test kits, provision of CPT may be compromised, and health education activities may also decline because of lack of funds. P=3 I =2 | Countermeasures: i) Liaise with other donors to provide the basic kits and CPT; ii) coordinate with state HIV coordinators to strengthen collaborative works. | Project manager, NTP manager | Project manager | October 2013 | No change |

Annex II: Project Staffing

|  | Name of Position | Location | International/National | Status | Months | Proforma Cost | Shared to this project | Budgeted in AWP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Output | Activity Result |
| 1 | Coordinator | Juba | National | In post | 12 | 50,857.00 | 16,952.33 | Improved coordination and management of GFATM projects | Technical support and advisory services to GFATM |
| 2 | Project Manager – TB | Juba | International | In post | 12 | 238,286.00 | 119,143.00 | Overall project management and enhanced project delivery | Technical support to the overall project management |
| 3 | M&E Specialist | Juba | International | In post | 12 | 238,286.00 | 79,428.67 | Enhanced M&E capacity, delivery, and data quality | Technical support to the M&E system |
| 4 | Finance Specialist | Juba | International | In post | 12 | 238,286.00 | 39,714.33 | Enhanced Finance capacity, delivery and quality reporting | Technical support, finance services and delivery |
| 5 | Project Analyst (1) TB | Juba | National | In post | 12 | 40,973.42 | 40,973.42 | Support to overall project management and enhanced project delivery | Project Management and delivery |
| 6 | Procurement and Contracting Analyst | Juba | National | In post | 12 | 40,973.42 | 13,657.81 | Support to PSM capacity and delivery | Procurement services |
| 7 | Finance Analyst | Juba | National | In post | 12 | 40,973.42 | 13,657.81 | Support to finance capacity, delivery and quality reporting | Finance services |
| 8 | Finance Associate | Juba | National | In post | 12 | 31,948.00 | 7,863.66 | Support to finance capacity, delivery and quality reporting | Finance services |
| 9 | Procurement Associate | Juba | National | In post | 12 | 31,948.00 | 7,863.66 | Support to PSM capacity and delivery | Procurement services |
| 10 | Asset Associate (1) | Juba | National | In post | 12 | 31,948.00 | 7,863.66 | Support management of health and non health assets | Asset management |
| 11 | Admin Associate (1) | Juba | National | In post | 12 | 31,948.00 | 7,863.66 | Support office administration services | Administrative and secretarial support service |
| 12 | Driver (5) | Juba | National | In post | 12 | 16,627.00 | 24,252.41 | Logistical support to implementation of the project | Logistical services |
| 13 | Security guards | Juba | National | In post | 12 | 16,627.00 | 9,206.22 | Security services to staff, property and premises | Security services |
| 14 | Cleaner | Juba | National | In post | 12 | 16,627.00 | 3,068.74 | Cleaning services to premises | Cleaning services |
| 16 | PSM specialist | Juba | International | In post | 12 | 238,286.00 | 89,782.00 | Strengthen supply chain and drugs management |  |
| 17 | Supply Chain Associate (2) | Juba | National | In Post | 12 | 47,182.00 | 15,727.32 | Strengthen supply chain and drugs management |  |
| 18 | Supply Chain Assistant (3) | Juba | National | In Post | 12 | 43,654.00 | 14,551.44 | Strengthen supply chain and drugs management |  |
| 19 | Warehouse Cleaner (1) | Juba | National | In Post | 12 | 9,206.00 | 3,068.74 | Cleaning services to premises S | Cleaning services |
| 20 | Warehouse Driver | Juba | National | In Post | 12 | 14,551.44 | 4,850.48 |  |  |
| 21 | M&E Analyst | Juba | National | In Post | 12 | 40,973.42 | 13,657.81 |  |  |
|  | TOTAL CHARGED TO THE PROJECT | US$533,147.2 |  |  |

Annex III: Communication Strategy Plan

| Communication Strategic objective: To increase all South Sudan stakeholders awareness, understanding and support for TB Control Programme and to enhance capacity of all local staff to speak with one voice |
| --- |
| Short-term goal: All stakeholders have a common understanding and commitment towards TB and TB/HIV Control in South Sudan, and speak with one voice |
| Short-term objective 2a: To have a clear understanding of TB and TB/HIV Control program concept and to set up a communication structure in South Sudan |
| Activity | Objective | Outcome | Indicator | Timeframe | Responsible | Assumptions | Budget USD |
| Develop and implement a programme for all stakeholders briefings jointly by NTP manager and UNDP project manager | To brief stakeholders on TB control program | Stakeholders aware of TB Control programme (reports also to be shared) | Number and briefings held with all stakeholders | February 24-March 15 2014 | UNDP/NTP/USAID | Stakeholders will take active part in the process of strategic plan revision for TB control program, and mobilization of resources | 12,000 |
| Take part in the World TB Day and campaigns associated with it | To make the public aware of TB control programme and create and encourage behavioural change | Staff aware of the control program through effective communication and general commitment enhanced | The public better informed about TB | Starting with Change Champions/community mobilizers March- April 2014 | UNDP/NTP/other partners |  | 0 |
| Production of information materials for stakeholders & the community | To update stakeholders on new developments and new initiatives; to inform the public on the programmes | Stakeholders and the public are aware of the programmes | Information material produced and disseminated | April- Dec 2014 | UNDP, NTP, other partners/subrecipients | Stakeholders will take active part in the control programmes | 1200 |
| Collaborate with M&E Technical Group to develop effective means of internal communication | Develop new communication tools to ensure effective information sharing | All members of M&E technical group are well informed of TB and HIV control programmes | New communication channels developed | March- Dec. 2014 | M&E staff | M&E TWG has capacity to develop new tools | 0 |
| Regular inputs to UNDP Global Fund Partnership website | Inputs and events posted on the websites | Project managers and M&E staff more engaged in posting reports of various events | Reports posted on the websites | Ongoing | Project Managers & M&E officers | All key stakeholders have access to website | 0 |
| Total for communication | 13,200 |

# Footnotes

The National TB Control Program under Ministry of Health, Government of South Sudan (NTP-MoH-RSS), Arkangelo Ali Association (AAA), Catholic Diocese of Torit (CDOT) and WHO

# Text boxes

2014 AWP budget: US$4,800,385

Total resources required:  US$4,800,385

Total allocated resources:

- Other:

  - GFATM		US$4,800,385

  - Government	_________

Unfunded budget:

In-kind Contributions:

Programme Period:	2012-2016

Programme Component: Human Development and Inclusive Growth

Atlas Award ID:		00064223

Start Date:         1 January 2014

End Date :	31December 2014

PAC Meeting Date:	TBD

Management Arrangements:	Direct Implementation

Brief Description

The Transitional Funding Mechanism for Tuberculosis is a two-year project that has a goal of reducing the burden of TB and TB/HIV in South Sudan as an extension of GFATM Round 7 TB project.The project will maintain the current TB notification of sputum smear positive cases and successfully treat at least 85% of the notified cases by 2015; routine culture and DST among all (100%) TB re-treatment cases during 2014 and 2015 and will improve HIV provider initiated testing and counselling of TB patients from the current 47% (2011) to 85% by end of 2015. This is done through support of the National TB Control Program at central and state levels as well as support provided to over 65 health facilities.

GFATM Coordinator

Project Board

Senior Supplier

UNDP

Executive

CCM South Sudan

Senior Beneficiary

NTLBP, MoH

Project Assurance

Team Leader

Project Support

M&E, Procurement & Finance teams

Project Organisation Structure

TEAM

Project Manager

Project Analyst