UNDP South Sudan

2014 Annual Work Plan

| Project Name | Amount |
| --- | --- |
| Health Systems Strengthening in South Sudan | US$19,462,031.61 |

| Hon. Aggrey Tisa Sabuni Minister Ministry of Finance, Commerce, Investment and Economic Planning Government of the Republic of South Sudan | Mr. Balázs Horváth Country Director UNDP South Sudan |
| --- | --- |
| Signature: | Signature: |
| Date: | Date: |

United Nations Development Programme

South Sudan

Annual Workplan 2014

| Project Title | Health Systems Strengthening in South Sudan |
| --- | --- |
| UNDAF Outcome(s): | Key service delivery systems are in place laying the groundwork for increased demand |
| Expected CP Output(s): | Health Sector infrastructure expanded, and pharmaceutical supply chain systems transitions to Government management |
| Implementing Partner: | UNDP |
| Responsible Parties: | Ministry of Health |

Agreed by Ministry of Finance, Commerce, Investment and Economic Planning:

Agreed by UNDP:

# Annual Workplan

| Year: 2014EXPECTED OUTPUT Related CP outcome: | PLANNED ACTIVITIES | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q 1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1:South Sudan health systems workforce capacities strengthened Baseline: 3 Indicator: number of health institution rehabilitated and renovated Target: 5 Baseline: Teaching institutions have a shortage of teaching aid materials Indicator: Teaching aids for teaching institutions procured Target:5 institutions provided with teaching aid material Baseline: 0 Indicator: Number of sets of adverts through TV, radio and newspaper Target: 2 Baseline: 0 Indicator: Number of National and international tutors recruited Target: 18 Sub Total | 1. Activity Result: 2 teaching institutions rehabilitated and equipped with teaching aids and staff 1.1 Action: Rehabilitate and renovate Maridi and Yei training institutes of nurses, midwives and laboratory technicians. 1.2 Action: Procurement of teaching aids, students text books, anatomical models, computers, projectors, photocopiers 1.3 Action: Mass media advertising for recruitment of student nurses and midwives – TV, radio and newspaper 1.4 Action: Recruitment and salaries for national and international tutors | X X X | X | X | X X | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM/30078 | 72100 (Contractuel Services-Companies) 72300 (Materials & Goods) 61100 (Staff Cost) 71200 (International Consultants) 61100 (National Staff Cost) GMS | US$1,829,174 US$00.00 US$2,500 US$882,444 US$ 189,988.26 US$ 2,904,106.26 |
| Output 2: South Sudan have access to safe and effective drugs Baseline: Preparatory work done for construction of warehouse Indicator: Nasir warehouse V-sat functional Target: Nasir warehouse completed, and 1 V-sat installed. Baseline: 0 Indicator: Number of LMS staff recruited Target:6 Baseline: 0 Indicator: Incinerator procured and installed Target:1 Baseline: Citing of the warehouse has been initiated. Indicator: Riverside warehouse is extended Target: Extension of riverside warehouse completed Sub Total | 2. Activity Result: Health supply chain management systems strengthened 2.0. Action Maintenance of Nasir warehouse V-sat(facilitate direct communication with other implementers at health centres;support data flow; reduces time lag/enhances fast reaction to emergency situation as and when it happens) 2.1 Action: Recruitment of LMIS officers, supportive supervision , training on pharmaceutical management (DSA,, training guidelines, drug analysis, transport cost participants, venue cost, stationery) 2.3 Action: Procure and install Incinerators, Purchase of waste collection boxes, Fuel & maintenance for Hospital incinerator(buring of expired drugs/safe disposal of expired medicines). Waste collection boxes (safe disposal of sharp used needles and instruments - blood lancet - to avoid unwanted cross contamination of diseases) 2.4 Action: Extension of Riverside warehouse | X X X | X X | X X | X X | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM/30078 | 72300 (Materials & Goods) 72600 (Grants) 72300 (Materials & Goods) 72100 (Contractuel Services-Companies) GMS | US$3,000 US$80,660 US$158,035 US$1, 063,680 US$91,376.25 US$1,396,751.25 |
| Output 3: Health Information System strengthened at national and state level Baseline: 5500 registers Indicator: Data collection tools and registers printed Target: 10,000 registers Baseline: 33 Indicator: Facility staff training on tools use at facility level Target: 33 Baseline: 33 Indicator: Central and State M&E staff trained Target: 33 Baseline: 0 Indicator: 3 state M&E offices renovated Target: 3 Baseline: 4 Indicator: Number of M&E supervision visits conducted for all HSS interventions Target: 9 | 3. Activity Result: Health information management systems strengthened 3.1 Action: Printing and dissemination of data collection registers at central, state and county level 3.2 Action: Training of 33 on tools use at facility, county and state level 3.3 Action: Training of 33 M&E staff at central and state level (DHIS computer software training) 3.4 Action: Renovations, equipping of state M&E offices with furniture, transportation, at central and state level 3.5 Action: Monitoring & Evaluation of all the GFATM HSS interventions (1, 2, 3, 4) –annual review meeting and supportive supervision | X X X | X X X | X X | X X | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFAT/30078 | 72100 (Contractuel Services-Companies) 72300 (Materials & Goods) 61100 (Staff Cost) 72100 (Contractual Services-Companies) | US$200,330 US$67,200 US$58,300 US$869,116 US$64,980 |

| Baseline: 2 Indicator: MoH M&E Officers recruited Target: 6 Baseline: 0 Indicator: Mid-Year M&E review workshops conducted Target: 2 Baseline: 0 Indicator: Data quality assessment conducted Target: 1 Sub Total | 3.6 Action: Recruit M&E Officers at MoH and provide them with the necessary equipment and salary. 3.7 Action: Conduct mid-Year M&E Review Process (MoH) 3.8 Action: Data Quality Assessment |  | X | X X X | X | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH |  | 61100 (Staff Cost) 72600 (Grants) GMS | US$81,936 US$38,250 US$5,050 US$96,961.34 US$1,482,123.34 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Output 4: Health systems related service deliveries including laboratory service, safe blood banks, ANC /PMTCT and Community Resource centres strengthened Indicator: number of state laboratories renovated Baseline: 0 Target: 2 Baseline: 0 Indicator: Blood transfusion TA provided Target: 1 Baseline: 0 Indicator: 3 blood banks operational in Juba, Wau and Malakal Target: 3 Baseline: 0 Indicator: 3 national officers recruited Target: 3 | Activity Result 4. Health systems service delivery strengthened 4.1 Action: Perform minor renovations for 2 Laboratories at state hospital level 4.2 Action: Provide technical Assistance to strengthen the capacity of Directorate of Curative medicine to implement and monitor blood transfusion and (UP) by providing training 4.3 Action: Operate 3 State Blood Banks at Juba, Wau & Malakal including recruitment of blood bank staff 4.4 Action: Recruit 3 National Blood Safety Officers and training of health workers in various aspects of blood safety | X X X | X X | X X X | X X | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH |  | 72100 (Contractual Services-Companies) 71200 (International Consultants) 72600 (Grants) 61100 (Staff Cost) | US$1,187,914. US$40,200 US$385,481 US$70,140 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Baseline: 0 Indicator: Volunteer blood donors recruited Target: 200 blood donors recruited Baseline: 0 Indicator: Health workers and auxiliary staff trained Target: 60 Baseline: 0 Indicator: Renovate/rehabilitate ANC and maternity wards Target: 29 Baseline: 0 Indicator: MNCH Health Workers trained on service delivery including PMTCT Target:50 Baseline: 0 Indicator: Community Resource Centres established, equipped, managed Target: 4 Baseline: 0 Indicator: Programme Evaluations conducted Target: 2 Baseline: 0 Indicator: National survey conducted and data outcome obtained Target: 1 Sub Total | 4.5 Action: Promote, recruit and retain volunteer blood donors through mass media 4.6Action: Train health workers and auxiliary staff such as cleaning/laundry staff in health facilities on various aspects of universal precautions & infection prevention practices 4.7 Action: Renovation / Rehabilitation of Antenatal Clinics and maternity wards and procurement of equipment, furniture and supplies, and + Mini Library 4.8 Action: Train MNCH Health Workers on MNCH service delivery including PMTCT 4.9 Action: Establish, Equip Community Resources Centres in South Sudan 4.10 Action: Programme Evaluations (Mid Term & End of Programme 4.11 Action: National Surveys to generate Impact and Outcome data UNDP-GFATM Contribution towards MoH Health facility Survey | X X X X | X X X | X X X X | X X X | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH, CHAS UNDP in support of MoH, CHAS |  | 72600 (Grants) 72600 (Grants) 72100 (Contractual Services-Companies) 72600 (Grants) 72600 (Grants) 72600 (Grants) | US$44,500 US$33,120 US$9,049,650 US$434,250 US$259,368 US$0.0 US$36,000 |

| Sub-Total Output 5: Project Management activities properly implemented Sub Total | 4.13 Action: Supervision of Civil Works 4.14Action: PR PMU Costs Human Resources (UNDP) Infrastructure and Other Equipment Overhead Cost | X X X X | X X X X | X X X X | X X X X | UNDP |  | GMS PMU Security Measures (1%) Implementation Support Service (1%) GMS | US $ 70,275 US$812,756.76 US$12,423,654.76 US$809,493 US$181,887 US$181,887 US$82,129 US$1,255,396 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL Budget |  |  |  |  |  |  |  |  | US$19,462,031.61 |

# Management Arrangements

The project will be managed by UNDP under UNDP’s Direct Implementation DIM) Modality in close collaboration with the MoH. The project is operating under the oversight of a Project Board which includes the Chair Person of CCM-SS (Country Coordinating Mechanism South Sudan), the Country Director for UNDP, the Director General of Community and Public Health, the Director General of Training and Professional Development, the Director General of Planning and Coordination and the Director General of Pharmaceuticals and Equipment. The Project Board will meet on a quarterly basis in Juba. The Project Board is responsible for the overall direction and management of the project and has responsibility and authority for the project within the remit of the project mandate.  The Project Board approves all major plans and authorises any major deviation from agreed plans.  It is the authority that signs off the completion of each year of the project, as well as authorises the start of the next year.  It ensures that required resources are committed, and arbitrates on any conflicts within the project, negotiating solutions to any problems between the project and external bodies.

The Project Board is ultimately responsible for assuring that the project remains on course to deliver the desired outcome of the project as defined in the Project Document. According to the size, complexity and risk of the project, the Project Board may decide to delegate some of this Project Assurance responsibility.

The overall project organisation structure is as follows:

The Global Fund Project is part of the Human Development and Inclusive Growth Unit and is supported by other Units such as the Programme and Partnership Support Unit (PPSU).  In South Sudan, UNDP has been serving as Principal Recipient (PR) of last resort since 2004 for five grants.  The PR works in collaboration with national and international partners involved in the fight against Tuberculosis and HIV/AIDS.  The Global Fund resources are additional to national resources as well as resources provided by other partners.

The PR has a number of Conditions Precedent and Special Terms and Conditions that should be fulfilled during various stages of the programme Grant Agreement.  These Conditions Precedent and Special Terms and Conditions are outlined in Sections B and C of the Annex A to the Grant Agreement between Principal Recipient and the Global Fund.

The Country Coordination Mechanism (CCM) performs the oversight function as well as monitoring and evaluation of the Global Fund projects in the country.  Different stages of project implementation such as project amendments, phase continuation requests and no cost extension requests are cleared by and submitted to the Global Fund through the CCM.

The Local Fund Agent (LFA) serves as Global Fund’s representative in the country.  It provides oversight of the project implementation and conducts verification of the programmatic and financial reports and makes recommendations to the Global Fund with regards to project progress and disbursement of funds.

The Project management Unit (PMU) of the PR has four major functions detailed below:

Project Management: This is comprised of Project Manager and Project Engineers overseeing construction in the respective states.  The Project Manager is fully responsible for the overall coordination of the project activities.  The Project Manager and the Engineers work in close collaboration with national counterparts and other stakeholders to implement this project.

Procurement and Supply Management: This team is headed by a Procurement Analyst supported by an Associate.  The Global Fund procurement team is based in the UNDP country office for oversight and technical support. Under the grant agreement signed between UNDP as PR and the Global Fund, all procurement activities are exclusively done by the PR.

Finance Management: This team is made up of a Finance Specialist, an Analyst and two Finance Associates. The Finance team is responsible for budget management.

Monitoring and Evaluation: This team is composed of one M&E Specialist, two Analysts based at MoH central level, with four Specialists based at state levels. The team is responsible for monitoring of project activities, review and verification of data and preparation of progress reports to the donor.

The PR will potentially subcontract a few agencies to execute this project as follows:

The implementing partners and subcontractor indicated below are responsible for implementing specific aspect of the programme in various states of South Sudan.  The main focus of this grant is on increasing South Sudanese capability to deliver and manage their existing services. It addresses four of the main constraints to effective service delivery, as identified in the national health policy: (1) Lack of skilled manpower at all levels of the health system, (2) Lack of appropriate equipment and supplies, (3) Lack of a well functioning disease surveillance and response system, and (4) Poor infrastructure and support services.

The project will construct, renovate, equip and operate two teaching institutions for nurses, midwives and lab technicians, one Pharmaceutical Waste Incinerators, five State M&E Offices, extension of the Central Medical Store (Riverside Warehouse), two laboratories at state hospital level and 20 Antenatal Clinics and Maternity wards.  The project will also hire an international consultant to strengthen the MoH-RSS capacity in pharmaceutical and supply chain management and recruitment of international tutors for the health training institutions.

Audit arrangements

Article 7. b. i. and ii. of the Special Terms and Conditions of the Grant Agreement between UNDP and the Global Fund state that:

- The Principal Recipient shall have annual financial audits conducted of Program expenditures. Subject to the approval of the Global Fund, which approval shall not be unreasonably withheld, the Principal Recipient shall select an independent auditor to conduct the audits and set the terms of reference pursuant to which they shall be conducted.  The cost of such special audit shall be borne by the Program.

- Should the Global Fund have reason to request a special purpose audit on the use of Global Fund resources, UNDP agrees to be responsible for: (i) securing the appointment of a mutually agreed independent auditor; and (ii) preparing mutually agreed audit Terms of Reference which reflect, as necessary, circumstances giving rise to the Global Fund’s request for said audit.  The cost of such special audit shall be borne by the Program.

Agreement on intellectual property rights and use of logo on the project’s deliverables

The Principal Recipient must enter into an agreement with the Global Fund prior to using the Global Fund logo. The logo must be used in accordance with the terms and conditions of that agreement.

# Monitoring Framework And Evaluation

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted, a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- A project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the Lessons-learned Report at the end of the project

- A Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

:

Annual reports

Annual Reports: Article 13, b. (2) states that Not later than 45 days after the close of each fiscal year of the Principal Recipient, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, an annual financial and programmatic monitoring report (in addition to the six-monthly reports) covering the preceding fiscal year.

Annual Project Review: Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board (the Country Coordinating Mechanism) and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Additionally, in accordance with the Standard Terms and Conditions in the grant agreement between the Principal Recipient and the Global Fund, the project will be monitored as follows:

Six monthly reports

Article 13, b. (1) states that “not later than 45 days after the close of each reporting period of the specific programme grant agreement, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, a periodic report on the Programme. The report shall reflect (i) financial activity during the reporting period in question and cumulatively from the beginning of the Programme until the end of the reporting period; and (ii) a description of progress towards achieving the agreed-upon milestones set forth in Annex A of the Grant Agreement.  The Principal Recipient shall explain in the report any variance between planned and actual achievements for the period in question”.

Midterm and final evaluation

The Global Fund projects are subject to two types of evaluations. Midterm evaluations are conducted for projects transitioning from phase I to phase II.  Final evaluations are conducted at the end of phase II of the project.

Quality Management for Project Activity Results

| OUTPUT 1: South Sudan health systems workforce capacities strengthened |
| --- |
| Activity Result 1 | Health Systems Workforce skills strengthened | Start Date: 1 January 2014 End Date: 31 December 2014 |
| Purpose | To assist the population of South Sudan with skilled health workforce |
| Description | Rehabilitation and renovations of Yei and Maridi Teaching institutions for training of nurses, midwives and laboratory technicians Procurement of equipment and teaching aids for the training institutions Recruitment of student trainees Recruitment of national and international tutors |
| Quality Criteria | Quality Method | Date of Assessment |
| Two teaching institutions renovated and equipped | Assessment of sites renovated and hand over | November 2014, |
| Tutors recruited and working | Recruitment files | April, August, November 2014 |

| OUTPUT 2: South Sudan population have access to safe and effective drugs |
| --- |
| Activity Result 1 | Health supply chain management systems strengthened including Medical Products, vaccines and technology | Start Date: 1 January 2014 End Date: 31 December 2014 |
| Purpose | To ensure that the population of South Sudan has access to safe and effective drugs |
| Description | Training of field staff in Pharmaceutical management Procure, install and operate one Pharmaceutical Waste Incinerators at the national referral lab in Juba |
| Quality Criteria | Quality Method | Date of Assessment |
| Capacity of MOH staff built in pharmaceutical management | Training Report | May 2014 |
| Incinerator procured and installed. | Procurement and finance files | November 204 |

| OUTPUT 3: Health Information System strengthened in order to provide reliable health data |
| --- |
| Activity Result 1 | Health information management systems strengthened | Start Date: 1 January 2014 End Date: 31 December 2014 |
| Purpose | To strengthen the existing Health Information System in order to provide reliable health data |
| Description | Printing and dissemination of data collection registers at central, state and county level, and training on tools use at facility, county and state level Strengthening of the M&E offices in the States, including renovations, furniture, transportation, at central and state level Monitoring & Evaluation of all the GFATM HSS interventions (1, 2, 3, 4) Recruitment of M&E Officers at MoH and equip them with the necessary equipment Mid-Year and M&E Review Process (MoH), annual review meeting and Data Quality Assessment |
| Quality Criteria | Quality Method | Date of Assessment |
| Data collection tools printed, data collection tools and registers printed | Sample tools, dissemination registers, and training reports | May 2014, November 2014 |
| Facility staff training on tools use at facility level | Quarterly M&E field visit reports | April, August, October 2014 |
| Central and State M&E staff trained | Recruitment files and training reports | May 2013 |
| State M&E offices renovated and equipped | Assessment of sites renovated and hand over | August, November 2014 |
| Number of M&E supervision visits conducted for all HSS interventions | Quarterly M&E field visit reports | April, August, October 2014 |
| MoH M&E Officers recruited and working | Recruitment files and trainings conducted | Jan – Dec 2014 |
| Annual M & E Review Process | Review meeting reports | December 2014 |
| Data Quality Assessment | M&E field visit reports | April, August, October 2014 |

| OUTPUT 4: Health systems related service deliveries including laboratory service, safe blood banks, ANC /PMTCT and Community Resource centres strengthened |
| --- |
| Activity Result 1 | Health systems service delivery strengthened | Start Date: 1 January 2014 End Date: 31 December 2014 |
| Purpose | To provide HSS related service deliveries including laboratory service, safe blood banks, ANC /PMTCT strengthening and Community centres |
| Description | Renovate and equip laboratories at state hospital level (equipment, test kits, and supplies) Technical Assistance to strengthen the capacity of Directorate of Curative medicine to implement and monitor blood transfusion and (UP) Promote, recruit and retain of volunteer blood donors through mass media Train health workers and auxiliary staff such as cleaning/laundry staff in health facilities on various aspects of universal precautions & infection prevention practices Renovate Antenatal Clinics and maternity wards and procure equipment , furniture and supplies, and mini library (“blue trunk”) Training of MNCH Health Workers on MNCH service delivery including PMTCT Equip and run of Community Resources Centres Recruit Community Health Centres Managers, and volunteers to promote the centres |
| Quality Criteria | Quality Method | Date of Assessment |
| Laboratories renovated, equipped and supplied with supplies | Assessment of facilities renovated, and supplies provided in line with lab policy | August 2014 |
| Blood transfusion TA provided | Assessment of facilities renovated, and supplies provided, staff recruitment files | Jan – Dec 2014 |
| Blood banks operational in Juba, Wau and Malakal | Assessment reports | Jan – Dec 2014 |
| National officers recruited and working | Recruitment files | Jan – Dec 2014 |
| Volunteer blood donors recruited | Assessment files | Jan – Dec 2014 |
| Health workers trained in blood safety | Training reports | August 2014 |
| Health workers trained in universal precautions and infection control | Training reports | May 2014, August 2014 |
| Maternity wards renovated and equipped | Assessment of facilities renovated, and supplies provided | August 2014, November 2014 |
| ANC clinics renovated and equipped | Assessment of facilities renovated, and supplies provided | August 2014, November 2014 |
| MNCH Health Workers trained on service delivery including PMTCT | Training Reports | May 2014 |
| Community centres constructed, equipped and operational | Assessment of facilities renovated, and supplies provided | Jan – Dec 2014 |
| Programme Evaluations conducted | Assessment files and M & E Reports | Jan – Dec 2014 |

| OUTPUT 5 (PMU): Project Management activities properly implemented |
| --- |
| Activity Result | Strengthened Management and implementation of Round 9 HSS Project | Start Date: 1 January 2014 End Date: 31 December 2014 |
| Purpose | To support management and implementation of HSS interventions in South Sudan |
| Description | HR, infrastructure, capacity building/training, planning and administration, TA |
| Quality Criteria | Quality Method | Date of Assessment |
| Regular reports to CCM | Documented interactions with CCM | May, August, November 2014 |
| Quarterly and annual reviews against annual work plan | Quarterly review meeting reports | May, August, November 2014 |
| Field monitoring trips conducted | Quarterly field monitoring reports | April, August, October 2014 |

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- Put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- Assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document”.

# ANNEXES

Annex 1. RISK LOG

| Project Title: Strengthening Health Systems in South Sudan: GFATM Round 9 | Award ID: 61396 | Date: 16/11/2013 |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status 11/2013 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The project aims to construct/ renovate a total of 30 health facilities in a challenging physical environment in all 10 States of South Sudan. Careful selection of competent contractors and proper planning of various constructions is critical to ensure civil works is not disrupted or delayed due to the rainy seasons and other environmental factors. Security risks might also be a potential problem in some of the states due intertribal conflicts or border conflicts | Since the proposal was written in 2009 | Contextual and environmental | Delayed completion of constructions and adverse impact on the grant performance which will negatively impact the flow of disbursements to the grant | Detailed project work plan developed to ensure timely initiation and completion of various steps in project implementation. Inputs sourced from experts from other agencies with experience in managing similar works in South Sudan | GFATM Coordinator, Project Manager and the MoH-RSS | GFATM Coordinator, Project Manager and the MoH-RSS | November 2012 | The revised BOQs and budget was approved in late September 2013. The expectation of the project was that approvals would be received by July, so as to begin the procurement process. Due to the late approval, and the requirement for concerned parties – UNDP, MOH/CCM – to conduct site assessment for the facilities before tendering in November/December 2014, actual civil work construction will commence by January 2014. However, training in MNCH and procurement of first batch of reagents for Labs and Blood Bank, supplies for teaching institutions, advertisement and recruitment of students to the institutions, finalization of LOA with MOH will be done in Q1 (October –December2014). |

ANNEX 2 Project Staff Costs

|  | Name of Position | Location | International/ | Status | Months | Proforma Cost | Shared to this project | Budgeted in AWP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | National |  |  |  |  | Output | Activity Result |
| 1 | Coordinator | Juba | National | In post | 12 | 107,512.00 | 35,837.00 | Improved coordination and management of GFATM projects | Technical support and advisory services to GFATM |
| 2 | Project Specialist - R9/Project Manager HSS | Juba | National | In post | 12 | 40,973,42 | 40,973,42 | Overall project management and enhanced project delivery | Technical support to the overall project management |
| 3 | Civil Engineers – UNVs (2) | Juba + States | International | 2 in Post | 12 | 160,000.00 | 160,000.00 | Specialized technical support to the project | Site assessment, BOQs, drawings, site supervision |
| 4 | Associate Engineers | Juba + States | National | 5 | 12 | 117,954.90 | 117,954.90 | Specialized technical support to the project | Site assessment, BOQs, drawings, site supervision |
| 5 | M&E Specialist | Juba | International | In post | 12 | 238,286.00 | 59,572.00 | Enhanced M&E capacity, delivery, and data quality | Technical support to the M&E system |
| 6 | Finance Specialist | Juba | International | In post | 12 | 238,286.00 | 59,572.00 | Enhanced Finance capacity, delivery and quality reporting | Technical support, finance services and delivery |
| 7 | M&E Analyst (2) | Juba | National | In post | 12 | 40,973.00 | 20,487.00 | Support to M&E capacity, delivery, and data quality | M&E functions and`A1 delivery |
| 8 | Procurement and Contracting Analyst | Juba | National | In post | 12 | 40,973.00 | 20,487.00 | Support to PSM capacity and delivery | Procurement and contracting services |
| 9 | Finance Analyst | Juba | National | In post | 12 | 40,973.00 | 20,487.00 | Support to finance capacity, delivery and quality reporting | Finance services |
| 10 | Finance Associate (1) | Juba | National | In post | 12 | 23,591.00 | 11,795.00 | Support to finance capacity, delivery and quality reporting | Finance services |
| 11 | Procurement Associate (1) | Juba | National | In post | 12 | 23,591.00 | 5,898.00 | Support to PSM capacity and delivery | Procurement services |
| 12 | Asset Associate (1) | Juba | Vacant | In post | 12 | 23,591.00 | 5,898.00 | Support management of health and non health assets | Asset management |
| 13 | Admin Associate (1) | Juba | National | In post | 12 | 23,591.00 | 5,898.00 | Support office administration services | Administrative and secretarial support service |
| 14 | Driver (6) | Juba | National | In post | 12 | 72,757.00 | 18,189.00 | Logistical support to implementation of the project | Logistical services |
| 15 | Security guards (3) | Juba | National | In post | 12 | 18,412.00 | 4,603.00 | Security services to staff, property and premises | Security services |
| 16 | Cleaner (1) | Juba | National | In post | 12 | 9,206.00 | 2,302.00 | Cleaning services to premises | Cleaning services |
| 17 | Supply Chain Management | Juba | International | In post | 12 | 269,346.00 | 89,782.00 | Strengthen supply chain and drugs management |  |
| 18 | Supply Chain Associate (2) | Juba | National | In post | 12 | 47,182.00 | 11,795.00 | Strengthen supply chain and drugs management |  |
| 19 | Supply Chain Assistant (3) | Juba | National | In post | 12 | 43,654.00 | 10,914.00 | Strengthen supply chain and drugs management |  |
| 20 | Warehouse Cleaner (1) | Juba | National | In post | 12 | 9,206.00 | 2,302.00 | Cleaning services to premises S | Cleaning services |
|  | TOTAL CHARGED TO THE PROJECT | 1,549,084.90 | 663,772.90 |  |  |

Annex 3: Communication Strategy Plan

| Strategic objective: To increase South Sudan’s capability to deliver and managed the health services. |
| --- |
| Activity | Objective | Outcome | Indicator | Timeframe | Responsible | Assumptions | Budget USD |
| Civil works bid opening | To verify and confirm bidders complied with terms and conditions as stipulated. | Participants are aware of the procedures followed. | Number of validated bids | 17 – 20 Jan 2014 | UNDP/GOV/CCM | Stakeholders will participate in the bid opening process | 100 |
| Civil works bid evaluation | Obtain quality contractors | Providers the platform to award contracts to qualified contractors | Number of qualified bidders identified | 24 Feb – 10 March 2014 | UNDP/GOV/CCM | That at least ¾ of the bidders will meet required standards. | 5000 |
| Civil works tender award | The most qualified contractors (technically and financial sound), are awarded contracts | Selected contractors begin to execute works. | Number of contractors engaged in civil works. | 17 March – 24 March 2015 | UNDP | The selected bidders will perform | 0 |
| Supervision and monitoring of Civil works. | To ensure quality, and that works done within stipulated timeframe and the projected costs | Structures are produced according to expectations | Number of structures constructed | 24 April – 30 Sept 2015. | UNDP/GOV/CCM | That contractors will comply with the contract documents | 0 |
| Periodic and regular updates to CCM/MOH | To inform and involve them on the development with civil works, as well as to solicit advice and assistance as appropriate. | MOH/CCM aware and to participate in HSS activities | Number of supervision visits to various project sites | Oct 2013 – 30 Sept 2015 | UNDP | CCM/MOH will participate in civil works monitoring and supervision visist. | 0 |
| Regular inputs to UNDP Global Fund Partnership website | Inputs and events posted on the websites | Project managers and M&E staff more engaged in posting reports of various events | Reports posted on the websites | On-going | Project Managers & M&E officers | All key stakeholders have access to website | 0 |
| Total for communication | 5,100 |

# Footnotes

The Ministry of Health, Republic of South Sudan (MoH-RSS), WHO, CHAS, one SR to manage the recruitment of tutors and student trainees, and various contractors to renovate and construct various structures.

# Text boxes

Brief Description

The main focus of this grant is on increasing South Sudanese capability to deliver and manage their existing services. It addresses four of the main constraints to effective service delivery, as identified in the national health policy, namely (i) lack of skilled manpower at all levels of the health system, (ii) lack of appropriate equipment and supplies, (iii) lack of a well functioning disease surveillance and response systems, and (iv) poor infrastructure and support services.

The project will construct, renovate, equip and support the operations of facilities that strengthen health systems delivery. This will include the renovation of two teaching institutions for nurses, midwives and laboratory technicians, five state M&E offices, two laboratories at state hospital level, and 29 antenatal clinics and maternity wards, the extension of the Central Medical Store (Riverside Warehouse), and procurement of pharmaceutical waste incinerators. The programme will also strengthen the MoH-RSS capacity in pharmaceutical and supply chain management and health training institutions, as well as strengthening the Health Information Management System (HIMS).

2014 AWP budget:                  US$19,462,031.61

Total resources required:        US$19,462,031.61

Total allocated resources:      US$19,462,031.61

- Regular:		   _________

- Other:

  - GFATM	        US$19,462,031.61

  - Government	   _________

Programme Period: 2013 – 2014

Programme Component: Human Development and Inclusive Growth

Atlas Award ID:	61396

Start date:		   1 January 2014

End Date:		   31 December 2014

PAC Meeting Date:	   TBC

Management Arrangements: Direct implementation

GFATM Coordinator

Project Board

Senior Supplier

UNDP

Executive

Ministry of Health-CCM

Senior Beneficiary

Directorate of Community and Public Health, Training and Professional Development, Planning and Coordination, and Medical Services

Project Assurance (Team Leader/Programme Analyst)

Project Support - (M and E, Procurement, and Finance Teams)

Project Organisation Structure

Project Manager Round 9 HSS

Project Engineers