UNDP South Sudan

2015 Annual Work Plan

| Project Name | Amount |
| --- | --- |
| Health Systems Strengthening in South Sudan | US$12,198,685. |

| Hon. David Deng Athorbei Minister, Ministry of Finance and Economic Planning Government of the Republic of South Sudan | Mr. Balázs Horváth Country Director UNDP South Sudan |
| --- | --- |
| Signature: | Signature: |
| Date: | Date: |

United Nations Development Programme

South Sudan

2015 Annual Work Plan

| Project Title | Health Systems Strengthening in South Sudan |
| --- | --- |
| UNDAF Outcome(s): | Outcome 3: Key service delivery systems are in place |
| Expected CP Output(s): | Increased national capacity to provide access to essential service delivery systems for scaling up HIV and TB interventions Strengthened institutional and technical capacity of the health systems at national and sub-national levels |
| Implementing Partner: | UNDP |
| Responsible Parties: | Ministry of Health |

Agreed by Ministry of Finance and Economic Planning:

Agreed by UNDP:

# Annual Work Plan

Year: 2015

| EXPECTED OUTPUTS Related CP outcome: | PLANNED ACTIVITIES | TIME FRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output 1:South Sudan health systems workforce capacities strengthened Baseline: 8 (1 male 7 female) Indicator: Number of national and international tutors recruited and capacity of teaching institutions strengthened Target: 17 Outcome 3: Key service delivery systems are in place | 1. Activity Result: Manpower for teaching institutions engaged and deployed. 1.1 Action: Recruitment and salaries for national and international tutors | X | X | X |  | UNDP in support of MoH | GFATM/30078 | 71200 (International Consultants) 61100 (National Staff Cost) GMS Sub Total | US$532,476 $ 37,273. US$ 569,749. |
| Output 2: South Sudan have access to safe and effective drugs Baseline: 6 incinerators procured and installed Indicator: Incinerator procured and installed Target:1 incinerator will be procured and installed Baseline: 1 Indicator: Riverside warehouse is extended Target: 2 Baseline: 30 (26 male, 4 female) Indicator: Health workers trained on Pharmaceutical Management Target: 55 Outcome 3: Key service delivery systems are in place | 2. Activity Result: Health supply chain management systems strengthened 2.2.1 Action: Procure and install one incinerator at National Lab 2.2.2 Extension of one additional block for riverside warehouse 2.2.3 Training of Health workers on pharmaceutical management |  | X X X | X X |  | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM/30078G | 72100 (Contractual Services-Companies) 72100 (Contractual Services-Companies) 71400 (Staff Cost) GMS Sub Total | US$147, 535 US$1, 047,330 US$36,600 86,203 US$1, 317,668 |
| Output 3: Health Information System strengthened at national and state level Baseline: 33 (25 male, 8 female) Indicator: Number of facility staff re-trained on tools use at facility level Target: 66 Baseline: 33 (31 male; 1female) Indicator: Number of central and state M&E staff re-trained Target:66 Baseline: 5 Indicator: Number of state M&E offices renovated Target: 8 Baseline: 4 Indicator: Number of M&E supervision visits conducted for all HSS interventions Target: 8 | 3.1 Activity Result: Building the capacity of state and national M&E 3.1.1 Action: Refresher training of 33 staff on tools use at facility, county and state level 3.1.2 Action: Refresher training of 33 M&E staff at central and state level (DHIS computer software training) 3.1.3 Action: Renovations, equipping of state M&E offices with furniture at central and state level 3.1.4 Action: Monitoring & Evaluation of all the GFATM HSS interventions (1, 2, 3, 4) –annual review meeting and supportive supervision | X X | X X X X | X |  | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFAT/30078 | 75700 (trainings) 75700 (trainings) 72100 (Contractual Services-Companies) 71600 (travels) | US$33,600 US$58,300 US$247,936 US$64,980 |

| Baseline: 2 (1 male 1 female) Indicator: Number of M&E Officers maintained to support MoH Target: 2 (1 male 1 female) Outcome 3: Key service delivery systems are in place | 3.1.5 Action: Maintain M&E Officers at MoH and provision of the necessary equipment and salary. 3.1.6 Action: Conduct mid-year M&E Review Process (MoH) 3.1.7 Action: Conduct Data Quality Assessment |  | X | X X X |  | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM/30078 | 71400 (Staff Cost) 71600 (travels) GMS Sub Total | US$91,936 US$38,250 US$5,050 US$37,804 US$577,856 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Output 4: Health systems related service deliveries strengthened Baseline: 8 Indicator: Number of state laboratories renovated Target: 10 Baseline: 3 Indicator: Number of blood banks supported Target: 3 Baseline: 30 (20 Male, 10 female) Indicator: Number of health workers trained on blood safety Target: 60 | Activity Result 4. Capacity of laboratory service, safe blood banks, ANC /PMTCT and Community Resource centres strengthened 4.4.1 Action: Perform minor renovations for 2 laboratories at state hospital level 4.4.2 Action: Support operations of 3 State Blood Banks at Juba, Wau & Malakal including recruitment of blood bank staff (Lab Technician, M&E, Cashier and manager) 4.4.3 Action: Training of health workers in various aspects of blood safety | X X | X X | X X X |  | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH | GFATM/30078 | 72100 (Contractual Services-Companies) 74500 (miscellaneous) 71400 (Staff Cost) | US$673,027 US$185,500 US$57,940 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Baseline: 0 Indicator: Number of volunteer blood donors recruited Target: 200 Baseline: 62 (35 male, 27 female) Indicator: Number of health workers and auxiliary staff trained Target: 122 Baseline: 20 Indicator: Number of Renovated/rehabilitated ANC and maternity wards Target: 31 Baseline: 53 (33 male, 20 female) Indicator: Number of MNCH Health Workers trained on service delivery including PMTCT Target:78 Baseline: 4 Indicator: Number of Community Resource Centres managed Target: 4 Baseline: 0 Indicator: End of Programme Evaluations and national survery disseminated Baseline: 1 Indicator: National survey conducted and data outcome obtained Target: 1 | 4.4.4 Action: Promote, recruit and retain volunteer blood donors through mass media 4.4.5 Action: Train health workers and auxiliary staff such as cleaning/laundry staff in health facilities on various aspects of universal precautions & infection prevention practices 4.4.6 Action: Renovation / Rehabilitation of Antenatal Clinics and maternity wards and procurement of equipment, furniture and supplies, and + Mini Library 4.4.7 Action: Train MNCH Health Workers on MNCH service delivery including PMTCT 4.4.8 Action: Provision of community awareness activities and strengthen health services. 4.4.9 Action: Conduct end of Programme Evaluations and National Surveys on service availability | X X | X X X | X X X X |  | UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH UNDP in support of MoH, IAA | GFATM/30078 | 71200 (TA) 75700 (training) 72100 (Contractual Services-Companies) 75700 (training) 72600 (Grants) 71200 (TA) 71200 (TA) GMS | US$35,600 US$33,120 US$5,455,619 US$144,750 US$194,526 US$202,896 |

| Outcome3: Key service delivery systems are in place Output 5: Project Management activities properly implemented | 4.4.10 Action: Supervision of civil works 5.1 Action: PR PMU Costs Infrastructure and Other Equipment PSM Cost Technical Assistance PMU Overhead Cost | X X X X | X X X X X X | X X X X X |  | UNDP | GFATM/30078 | 71600 (Supervision) GMS Sub-Total PMU 73400 (Infrastructure and Other Equipment) 72200 (PSM) 71300 (Technical Assistance) 74500 (PMU Overhead) DPC 7% GMS Sub Total | US$ 345,344 US$512,982. US$7,841,303. US$1,214,675 US$106,500 US$139,564 US$18,900 US$206,175 US$82,512 US$123,783 $1,892,109 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL Budget |  |  |  |  |  |  |  |  | US$12,198,685 |

# Management Arrangements

The project will be managed by UNDP under UNDP’s Direct Implementation (DIM) Modality in close collaboration with the MoH. The project is operating under the oversight of a Project Board which includes the Chair Person of CCM-SS (Country Coordinating Mechanism South Sudan), the Country Director for UNDP, the Director General of Community and Public Health, the Director General of Training and Professional Development, the Director General of Planning and Coordination and the Director General of Pharmaceuticals and Equipment. The Project Board will meet on a quarterly basis in Juba. The Project Board is responsible for the overall direction and management of the project and has responsibility and authority for the project within the remit of the project mandate.  The Project Board approves all major plans and authorises any major deviation from agreed plans.  It is the authority that signs off the completion of each year of the project, as well as authorises the start of the next year.  It ensures that required resources are committed, and arbitrates on any conflicts within the project, negotiating solutions to any problems between the project and external bodies.

The Project Board is ultimately responsible for assuring that the project remains on course to deliver the desired outcome of the project as defined in the Project Document. According to the size, complexity and risk of the project, the Project Board may decide to delegate some of this Project Assurance responsibility.

The overall project organisation structure is as follows:

The Global Fund Project is part of the Human Development and Inclusive Growth Unit and is supported by other Units such as the Programme and Partnership Support Unit (PPSU).  In South Sudan, UNDP has been serving as Principal Recipient (PR) of last resort since 2004 for five grants.  The PR works in collaboration with national and international partners involved in the fight against Tuberculosis and HIV/AIDS.  The Global Fund resources are additional to national resources as well as resources provided by other partners.

The PR has a number of Conditions Precedent and Special Terms and Conditions that should be fulfilled during various stages of the programme Grant Agreement.  These Conditions Precedent and Special Terms and Conditions are outlined in Sections B and C of the Annex A to the Grant Agreement between Principal Recipient and the Global Fund.

The Country Coordination Mechanism (CCM) performs the oversight function as well as monitoring and evaluation of the Global Fund projects in the country.  Different stages of project implementation such as project amendments, phase continuation requests and no cost extension requests are cleared by and submitted to the Global Fund through the CCM.

The Local Fund Agent (LFA) serves as Global Fund’s representative in the country.  It provides oversight of the project implementation and conducts verification of the programmatic and financial reports and makes recommendations to the Global Fund with regards to project progress and disbursement of funds.

The Project management Unit (PMU) of the PR has four major functions detailed below:

Project Management: This is comprised of Project Manager and Project Engineers overseeing construction in the respective states.  The Project Manager is fully responsible for the overall coordination of the project activities.  The Project Manager and the Engineers work in close collaboration with national counterparts and other stakeholders to implement this project.

Procurement and Supply Management: This team is headed by a Procurement Analyst supported by an Associate.  The Global Fund procurement team is based in the UNDP country office for oversight and technical support. Under the grant agreement signed between UNDP as PR and the Global Fund, all procurement activities are exclusively done by the PR.

Finance Management: This team is made up of a Finance Analyst, a Finance Associate, and a Finance Officer. The Finance team is responsible for budget management.

Monitoring and Evaluation: This team is composed of one M&E Specialist, two Analysts based at MoH central level. The team is responsible for monitoring of project activities, review and verification of data and preparation of progress reports to the donor.

The PR will potentially subcontract a few agencies to execute this project as follows:

The implementing partners and subcontractor indicated below are responsible for implementing specific aspect of the programme in various states of South Sudan.  The main focus of this grant is on increasing South Sudanese capability to deliver and manage their existing services. It addresses four of the main constraints to effective service delivery, as identified in the national health policy: (1) Lack of skilled manpower at all levels of the health system, (2) Lack of appropriate equipment and supplies, (3) Lack of a well-functioning disease surveillance and response system, and (4) Poor infrastructure and support services.

The project will construct, renovate, equip and operate one Pharmaceutical Waste Incinerator, three State M&E Offices, extension of the Central Medical Store (Riverside Warehouse), two laboratories at state hospital level and 11  Antenatal Clinics and Maternity wards.  The project will also recruit national tutors for the health training institutions.

Audit arrangements

Article7.b. i. and ii. Of the Special Terms and Conditions of the Grant Agreement between UNDP and the Global Fund state that:

- The Principal Recipient shall have annual financial audits conducted of Program expenditures. Subject to the approval of the Global Fund, which approval shall not be unreasonably withheld, the Principal Recipient shall select an independent auditor to conduct the audits and set the terms of reference pursuant to which they shall be conducted.  The cost of such special audit shall be borne by the Program.

- Should the Global Fund have reason to request a special purpose audit on the use of Global Fund resources, UNDP agrees to be responsible for: (i) securing the appointment of a mutually agreed independent auditor; and (ii) preparing mutually agreed audit Terms of Reference which reflect, as necessary, circumstances giving rise to the Global Fund’s request for said audit.  The cost of such special audit shall be borne by the Program.

Agreement on intellectual property rights and use of logo on the project’s deliverables

The Principal Recipient must enter into an agreement with the Global Fund prior to using the Global Fund logo. The logo must be used in accordance with the terms and conditions of that agreement.

# Monitoring Framework And Evaluation

In accordance with the programming policies and procedures outlined in the UNDP User Guide, the project will be monitored through the following:

Within the annual cycle

- On a quarterly basis, a quality assessment shall record progress towards the completion of key results, based on quality criteria and methods captured in the Quality Management table below.

- An Issue Log shall be activated in Atlas and updated by the Project Manager to facilitate tracking and resolution of potential problems or requests for change.

- Based on the initial risk analysis submitted, a risk log shall be activated in Atlas and regularly updated by reviewing the external environment that may affect the project implementation.

- Based on the above information recorded in Atlas, a Project Progress Reports (PPR) shall be submitted by the Project Manager to the Project Board through Project Assurance, using the standard report format available in the Executive Snapshot.

- A project lessons-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the organization, and to facilitate the preparation of the lessons-learned report at the end of the project

- A Monitoring Schedule Plan shall be activated in Atlas and updated to track key management actions/events

Annual reports

Annual Reports: Article 13, b. (2) states that Not later than 45 days after the close of each fiscal year of the Principal Recipient, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, an annual financial and programmatic monitoring report (in addition to the six-monthly reports) covering the preceding fiscal year.

Annual Project Review: Based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board (the Country Coordinating Mechanism) and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards outputs, and that these remain aligned to appropriate outcomes.

Additionally, in accordance with the Standard Terms and Conditions in the grant agreement between the Principal Recipient and the Global Fund, the project will be monitored as follows:

Six monthly reports

Article 13, b. (1) states that “not later than 45 days after the close of each reporting period of the specific programme grant agreement, the Principal Recipient shall submit to the Global Fund, in form and substance satisfactory to the Global Fund, a periodic report on the Programme. The report shall reflect (i) financial activity during the reporting period in question and cumulatively from the beginning of the Programme until the end of the reporting period; and (ii) a description of progress towards achieving the agreed-upon milestones set forth in Annex A of the Grant Agreement.  The Principal Recipient shall explain in the report any variance between planned and actual achievements for the period in question”.

Midterm and final evaluation

The Global Fund projects are subject to two types of evaluations. Midterm evaluations are conducted for projects transitioning from phase I to phase II.  Final evaluations will be conducted at the end of phase II of the project.

Quality Management for Project Activity Results

| OUTPUT 1: South Sudan health systems workforce capacities strengthened |
| --- |
| Activity Result 1 | Health Systems Workforce skills strengthened | Start Date: 1 January 2015 End Date: 30 September 2015 |
| Purpose | To assist the population of South Sudan with skilled health workforce |
| Description | Recruitment and salaries of national and international tutors |
| Quality Criteria | Quality Method | Date of Assessment |
| Tutors recruited and working | Recruitment files | April, August, November 2015 |

| OUTPUT 2: South Sudan population have access to safe and effective drugs |
| --- |
| Activity Result 1 | Health supply chain management systems strengthened | Start Date: 1 January 2015 End Date: 30 September 2015 |
| Purpose | To ensure that the population of South Sudan has access to safe and effective drugs |
| Description | Procure, install and operate one Pharmaceutical Waste Incinerators at the national referral lab in Juba Extension of Riverside warehouse |
| Quality Criteria | Quality Method | Date of Assessment |
| Incinerator procured and installed. Extension of warehouse accomplished | Assessment of facilities installed and renovated | October 2015 |

| OUTPUT 3: Health Information System strengthened in order to provide reliable health data |
| --- |
| Activity Result 1 | Building the capacity of state and national M&E | Start Date: 1 January 2015 End Date: 30 September 2015 |
| Purpose | To strengthen the existing Health Information System in order to provide reliable health data |
| Description | Training on HMIS tools use for state and national M&E officers Training of M&E staff at central and state level (DHIS computer software training) Strengthening of the M&E offices in the States, including renovations, furniture, transportation, at central and state level Monitoring & Evaluation of all the GFATM HSS interventions (1, 2, 3, 4) Recruitment of M&E Officers at MoH and equip them with the necessary equipment Mid-Year and M&E Review Process (MoH), annual review meeting and Data Quality Assessment |
| Quality Criteria | Quality Method | Date of Assessment |
| Central and State M&E staff trained | Recruitment files and training reports | August 2015 |
| State M&E offices renovated and equipped | Assessment of sites renovated and hand over | July 2015 |
| Number of M&E supervision visits conducted for all HSS interventions | Quarterly M&E field visit reports | March, September,2015 |
| MoH M&E Officers recruited and working | Recruitment files and trainings conducted | Jan – September 2015 |
| Annual M & E Review Process | Review meeting reports | January 2015 |
| Data Quality Assessment | M&E field visit reports | March, July, September 2015 |

| OUTPUT 4: Health systems related service deliveries including laboratory service, safe blood banks, ANC /PMTCT and Community Resource centres strengthened |
| --- |
| Activity Result 1 | Health systems service delivery strengthened | Start Date: 1 January 2015 End Date: 30 September 2015 |
| Purpose | To provide HSS related service deliveries including laboratory service, safe blood banks, ANC/PMTCT strengthening and community centres |
| Description | Renovate and equip laboratories at state hospital level (equipment, test kits, and supplies) Promote, recruit and retain of volunteer blood donors through mass media Train health workers and auxiliary staff such as cleaning/laundry staff in health facilities on various aspects of universal precautions & infection prevention practices Renovate Antenatal Clinics and maternity wards and procure equipment , furniture and supplies, and mini library (“blue trunk”) Training of MNCH Health Workers on MNCH service delivery including PMTCT Equip and run of Community Resources Centres Recruit Community Health Centres Managers, and volunteers to promote the centres |
| Quality Criteria | Quality Method | Date of Assessment |
| Laboratories renovated, equipped and supplied with supplies | Assessment of facilities renovated, and supplies provided in line with lab policy | July 2015 |
| Blood banks operational in Juba, Wau and Malakal | Assessment reports | Jan – September 2015 |
| National officers recruited and working | Recruitment files | Jan – September 2015 |
| Volunteer blood donors recruited | Assessment files | Jan – September 2015 |
| Health workers trained in blood safety | Training reports | August 2015 |
| Health workers trained in universal precautions and infection control | Training reports | May 2015, August 2015 |
| Maternity wards renovated and equipped | Assessment of facilities renovated, and supplies provided | September 2015 |
| ANC clinics renovated and equipped | Assessment of facilities renovated, and supplies provided | September 2015 |
| MNCH Health Workers trained on service delivery including PMTCT | Training Reports | May 2015 |
| Community centres constructed, equipped and operational | Assessment of facilities renovated, and supplies provided | Jan – September 2015 |
| Programme Evaluations conducted | Assessment files and M & E Reports | Jan – September 2015 |

| OUTPUT 5 (PMU): Project Management activities properly implemented |
| --- |
| Activity Result | Strengthened Management and implementation of Round 9 HSS Project | Start Date: 1 January 2015 End Date: 30 September 2015 |
| Purpose | To support management and implementation of HSS interventions in South Sudan |
| Description | HR, infrastructure, capacity building/training, planning and administration, TA |
| Quality Criteria | Quality Method | Date of Assessment |
| Regular reports to CCM | Documented interactions with CCM | February, May, September 2015 |
| Quarterly and annual reviews against annual work plan | Quarterly review meeting reports | May, August, November 2015 |
| Field monitoring trips conducted | Quarterly field monitoring reports | February, May, September 2015 |

# Legal Context

This document together with the CPAP signed by the Government and UNDP which is incorporated by reference constitute together a Project Document as referred to in the SBAA and all CPAP provisions apply to this document.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- Put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- Assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document”.

# ANNEXES

Annex 1. RISK LOG

| Project Title: Strengthening Health Systems in South Sudan: GFATM Round 9 | Award ID: 61396 | Date: 04/12/2014 |
| --- | --- | --- |

| # | Description | Date Identified | Type | Impact & Probability | Countermeasures / Mngt response | Owner | Submitted, updated by | Last Update | Status 12/2014 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | The project aims to construct/ renovate a total of 17 health facilities in a challenging physical environment in six States of South Sudan. Careful selection of competent contractors and proper planning of various constructions is critical to ensure civil works is not disrupted or delayed due to the rainy seasons and other environmental factors. Security risks might also be a potential problem in some of the states due to intertribal conflicts or border conflicts | Dec 2013 | Contextual and environmental | Delayed completion of constructions and adverse impact on the grant performance which will negatively impact the flow of disbursements to the grant | Detailed project supervision plan developed to ensure timely initiation and completion of various steps in project implementation. Inputs sourced from experts from other agencies with experience in managing similar works in South Sudan | GFATM Coordinator, Project Manager and the MoH-RSS | GFATM Coordinator, Project Manager and the MoH-RSS | July 2014 | Approved design of the various facilities to be renovated were advertised in local newspapers and UNDP website in December 2013. Bid opening was done in January 2014 and evaluation of bids was completed in April 2014. However after conflict erupted in the country in December of 2014, renovation of all 11 facilities in Greater Upper Nile was cancelled and reprogrammed. Construction of three M & E offices, two labs and one ANC began in September 2014 and are on-going in Eastern, Central and Warap States. All civil works have been contracted except for two maternity wards that have been retendered. However due to the rainy season and the poor road conditions in several of the country, civil works in Western Bahr el Ghazal and parts of Warap could not begin immediately but to wait until the dry season in January 2015. Training in MNCH for the first quarter of the 5th year has been completed; and subsequent trainings in Universal Precaution and Blood Safety will be conducted in the second quarter (Jan – March 2015). Reagents for Labs and Blood Bank arrived in quarter one. |

ANNEX 2 Project Staff Costs

|  | Name of Position | Location | International/ | Status | Months | Proforma Cost | Shared to this project | Budgeted in AWP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | National |  |  |  |  | Output | Activity Result |
| 1 | GFATM Coordinator-P4 | Juba | International | In post | 12 | 269,346.00 | 35,837.00 | Improved coordination and management of GFATM projects | Technical support and advisory services to GFATM |
| 2 | R9/Project Manager HSS-NOC | Juba | National | In post | 12 | 49,253.47 | 49,253.47 | Overall project management and enhanced project delivery | Technical support to the overall project management |
| 3 | Programme Specialist Quality Assurance | Juba | National | In Post | 12 | 50,857.00 | 16,952.33 | Oversight and quality assurance of the GFATM | Oversight and quality assurance of the GFATM |
| 4 | Civil Engineers – IUNVs (3) | Juba + States | International | 2 in Post | 12 | 240,000.00 | 240,000.00 | Specialized technical support to the project | Site assessment, BOQs, drawings, site supervision |
| 5 | Associate Engineers-8 | Juba + States | National | 8 | 12 | 188,727.83 | 188,727.83 | Specialized technical support to the project | Site assessment, BOQs, drawings, site supervision |
| 5 | M&E Specialist-P3 | Juba | International | In post | 12 | 238,286.00 | 79,428.67 | Enhanced M&E capacity, delivery, and data quality | Technical support to the M&E system |
| 6 | Finance Specialist-P3 | Juba | International | In post | 12 | 238,286.00 | 79,428.67 | Enhanced Finance capacity, delivery and quality reporting | Technical support, finance services and delivery |
| 7 | M&E Analyst-NOB (2) | Juba | National | In post | 12 | 81,946.83 | 27,315.61 | Support to M&E capacity, delivery, and data quality | M&E functions and`A1 delivery |
| 8 | Procurement and Contracting Analyst-NOB | Juba | National | In post | 12 | 40,973.00 | 13,657.81 | Support to PSM capacity and delivery | Procurement and contracting services |
| 9 | Finance Analyst | Juba | National | In post | 12 | 49,253.47 | 16,417.82 | Support to finance capacity, delivery and quality reporting | Finance services |
| 10 | Finance Associate (1) | Juba | National | In post | 12 | 23,591.00 | 7,863.66 | Support to finance capacity, delivery and quality reporting | Finance services |
| 11 | Procurement Associate (1) | Juba | National | In post | 12 | 23,591.00 | 7,863.66 | Support to PSM capacity and delivery | Procurement services |
| 12 | Asset Associate (1) | Juba | Vacant | In post | 12 | 23,591.00 | 7,863.66 | Support management of health and non health assets | Asset management |
| 13 | Admin Associate (1) | Juba | National | In post | 12 | 23,591.00 | 7,863.66 | Support office administration services | Administrative and secretarial support service |
| 14 | Driver (7) | Juba | National | In post | 12 | 101,859.22 | 30,072 | Logistical support to implementation of the project | Logistical services |
| 15 | Security guards (3) | Juba | National | In post | 12 | 27,618.66 | 9,206.22 | Security services to staff, property and premises | Security services |
| 16 | Cleaner (1) | Juba | National | In post | 12 | 9,206.00 | 2,302.00 | Cleaning services to premises | Cleaning services |
| 17 | Supply Chain Management | Juba | International | In post | 12 | 238,286.00 | 47,657.20 | Strengthen supply chain and drugs management | Strengthen supply chain and drugs management |
| 18 | Pharmaceutical Supply Management Specialist (LMS) | Juba | IUNV | vacant | 12 | 80,000 | 16,000.00 | Strengthen inventory management | LMIS |
| 18 | Supply Chain Associate (2) | Juba | National | In post | 12 | 47,182.00 | 9,436.39 | Strengthen supply chain and drugs management | Strengthen supply chain and drugs management |
| 19 | Supply Chain Assistant (3) | Juba | National | In post | 12 | 43,654.00 | 8,730.87 | Strengthen supply chain and drugs management | Strengthen supply chain and drugs management |
| 20 | Warehouse Cleaner (1) | Juba | National | In post | 12 | 9,206.00 | 2,302.00 | Cleaning services to premises S | Cleaning services |
|  | TOTAL CHARGED TO THE PROJECT | US$2,903,392 | US$1,214,675 |  |  |

Annex 3: Communication Strategy Plan

| Strategic objective: To increase South Sudan’s capability to deliver and managed the health services. |
| --- |
| Activity | Objective | Outcome | Indicator | Timeframe | Responsible | Assumptions | Budget USD |
| Civil works bid opening | To verify and confirm bidders complied with terms and conditions as stipulated. | Participants are aware of the procedures followed. | Number of validated bids | 17 – 20 Jan 2014 | UNDP/GOV/CCM | Stakeholders will participate in the bid opening process | 100 |
| Civil works bid evaluation | Obtain quality contractors | Providers the platform to award contracts to qualified contractors | Number of qualified bidders identified | 24 Feb – 10 March 2014 | UNDP/GOV/CCM | That at least ¾ of the bidders will meet required standards. | 5000 |
| Civil works tender award | The most qualified contractors (technically and financially sound), are awarded contracts | Selected contractors begin to execute works. | Number of contractors engaged in civil works. | 17 March – 24 March 2015 | UNDP | The selected bidders will perform | 0 |
| Supervision and monitoring of civil works. | To ensure quality, and that works done within stipulated timeframe and the projected costs | Structures are produced according to expectations | Number of structures constructed | 24 April – 30 Sept 2015. | UNDP/GOV/CCM | That contractors will comply with the contract documents | 0 |
| Periodic and regular updates to CCM/MOH | To inform and involve them on the development with civil works, as well as to solicit advice and assistance as appropriate. | MOH/CCM aware and to participate in HSS activities | Number of supervision visits to various project sites | Oct 2013 – 30 Sept 2015 | UNDP | CCM/MOH will participate in civil works monitoring and supervision visit. | 0 |
| Regular inputs to UNDP Global Fund Partnership website | Inputs and events posted on the websites | Project managers and M&E staff more engaged in posting reports of various events | Reports posted on the websites | On-going | Project Managers & M&E officers | All key stakeholders have access to website | 0 |

# Footnotes

The Ministry of Health, Republic of South Sudan (MoH-RSS), one SR to manage the resource centres, and various contractors to renovate and construct various structures.

# Text boxes

Brief Description

The main focus of this grant is on increasing South Sudanese capability to deliver and manage their existing services. It addresses four of the main constraints to effective service delivery, as identified in the national health policy, namely (i) lack of skilled manpower at all levels of the health system, (ii) lack of appropriate equipment and supplies, (iii) lack of a well-functioning disease surveillance and response systems, and (iv) poor infrastructure and support services.

The project will construct, renovate, equip and support the operations of facilities that strengthen health systems delivery. This will include the renovation of three state M&E offices, two laboratories at state hospital level, 11 antenatal clinics and maternity wards, and the extension of one warehouse at the Central Medical Store (Riverside Warehouse), and procurement of one pharmaceutical waste incinerator. The programme will also strengthen the MoH-RSS capacity in pharmaceutical waste management and health training institutions, as well as strengthening the Health Information Management System (HIMS).

2015 AWP budget US$12,198,685

Total resources required US$12,198,685

Total allocated resources:     US$12,198.685

- Regular:		   _________

- Other:

  - GFATM	    US$12,198,685.

  - Government	   _________

  - Unfunded    US$ 0

Programme Period:  2012 – 2015

Programme Component: Human Development

and Inclusive Growth

Atlas Award ID:       00061396

Start date:	 1 Jan 2015

End Date:	 30 September 2015

PAC Meeting Date:    12 Dec 2014

Management Arrangements: Direct Implementation Modality

GFATM Coordinator

Project Board

Senior Supplier

UNDP

Executive

Ministry of Health-CCM

Senior Beneficiary

Directorate of Community and Public Health, Training and Professional Development, Planning and Coordination, and Medical Services

Project Assurance (Team Leader/Programme Specialist)

Project Support - (M and E, Procurement, and Finance Teams)

Project Organisation Structure

Project Manager Round 9 HSS

Project Engineers