## Budget 2021
UNDP-MoH Financial Agreement
Description | Qty | Budget per year - EUR |  |  | Status | financial request
|  | 2021 | Total expenses + Commitments | Balance 2021
Strengthening MoH infrastructure
Construction and furbishing of a warehouse to store medical and non-medical products | 1 | 388000 | 55000 | 333000 | ongoing | 333000
Rehabilitation and equipment of the warehouses at health center is Lobata, Lemba and Cantagalo | 3 | 25918.3143 | 0 | 25918.3143 | ongoing | 25918.3143 | 0 | 0
Rehabilitation of CGS offices, including 5 new offices, conference room and one meeting room | 1 | 99265.5657 | 98019.5629 | 1246.0028 | ongoing
Rehabilitation and equipment of the room for meetings or work meetings with MSM. | 1 | 8606.1495 | 0 | 8606.1495 | ongoing | 8606.1495
Rehabilitation of the infirmary for TB-MDR | 1 | 8397.4486 | 0 | 8397.4486 | ongoing | 8397.4486
Refurbishment and service of a BSL 3 | 1 | 50818.3645 | 40115 | 10703.3645 | ongoing
Expand and furbish HIV laboratory | 1 | 1696.7383 | 0 | 1696.7383 | ongoing | 1696.7383
Rehabilitation of security cabin in CNE | 1 | 1955.7009 | 0 | 1955.7009 | ongoing | 1955.7009
Strengthening logistics for the new CGS
Procurement of ITC equipment to CGS – ATEA | 1 | 75157.0093 | 75775.46 | -618.4507 | finalized
Procurement of Yamaha Motorcycle, Model DT125 | 6 | 17654.1682 | 17996.28 | -342.1118 | finalized
Technical assistance for the MoH PSM and HIS
Contract to install in Y1 and support maintenance of mSupply software (Y2 & Y3) | 1 | 59768.8769 | 58610 | 1158.8769 | ongoing
TA to reinforce the services packages for key populations (A1, A2 et A3 ; 2 weeks) | 1 | 19710.0247 |  | 19710.0247 | ongoing | 19710.0247
Technical assistance for the MoH PSM and HIS
IBBS (included study to assess the degree of discrimination and stigma of the police, armed forces and public administration including the lack of confidentiality of health professionals in relation to key populations to inform the development of protection policies) Y1 to study and learn about the phenomenon UDI (injecting drug officers) and transgender groups | 1 | 23623.0206 | 0 | 23623.0206 | ongoing | 23623.0206
International technical assistance to support PR in program management, RSS and procurement Y1 and Y2 | 1 | 251003.1786 | 114281.3731 | 136721.8056 | ongoing
TA for the design of the sustainability package (2 weeks) | 1 | 9628.0755 | 0 | 9628.0755 | ongoing
Long term/resident international technical assistance to support the strengthening of the national HMIS and operationalization of DHIS II | 1 | 71591.1814 | 59122 | -3511.7786 | ongoing
TA to support efforts oriented to reach the third 90 % (viral suppression- 2 months and 1 week) | 1 | 32839.7715 | 0 | 32839.7715 | ongoing | 32839.7715
Conduct an HRH review across the three diseases skills audit and workflow analysis and design and integrated needs-based approach that optimizes skills and TA across the three diseases, as well as strengthening the role and building capacity of the community health workers in supporting integrated program management implementation of the three diseases (2 months and 1 week) | 1 | 25439.2523 | 0 | 25439.2523 | ongoing | 25439.2523
PSM strengthening PMU and national systems | 1 | 46728.972 | 0 | 46728.972 | ongoing | 46728.972
sub- Total |  | 1217801.8131 | 518919.676 |  |  | 527915.3928
GMS 7 % UNDP |  | 83958.4289 | 36324.3773 |  |  | 36954.0775
Total |  | 1283364.5563 | 1074163.7293 |  |  | 527915.3928
Descricao | currency | amounts | %
Amount to be received as per Financial Agreement: | EUR | 1283364.56 | 100
Amount received: | EUR | 566647.11 | 44.1532
Pending amount to be received | EUR | 716717.45 | 55.8468
Delivery | EUR | 1074163.7293 | 189.5648
Cash availability: | EUR | 11403.0567 | 1.0616
Financial request (Q4 2021) | Eur | 527915.3928

## Warehouse
| 2021 | [10 empty] | 2022
Activity | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Recruitment of international team of engineers and architect | x | x
Signature of IC contract |  | x
Recruitment of national consultants, civil engineer + architect |  |  | x | [9 empty] | done. $4000
Identification of plot |  |  | x | x | x
Legal documentation |  |  |  |  | x | [7 empty] | done
Verification of infrastructure, validation |  |  |  |  | x
Satellite ubication of the warehouse | [5 empty] | x
Visit topographic | [6 empty] | x
Topographic studies | [6 empty] | x
Visit soil laboratory team | [7 empty] | x
Soil studies | [7 empty] | x |  |  |  |  | Paid 1200 USD
Environmental studies (visit) | [8 empty] | x |  |  |  | National consultant $3000
Conceptual design, final architectural design | [8 empty] | x
Structural design | [8 empty] | x
Electrical design, measures, access | [8 empty] | x
Water supply, access, water flow measures | [8 empty] | x
Sanitary design, special needs | [9 empty] | x | done
Special installations, cold chain, sewer system, air conditioning design | [9 empty] | x | done
Visit from the International team | [9 empty] | x | done
Presentation to the government | [9 empty] | x | done
Bidding process | [10 empty] | x | x
Site visit | [12 empty] | x
Signature of contract | [12 empty] | x
Selection of construction firm | [12 empty] | x
Selection of fiscalization team
Initiation of construction | [13 empty] | x | x | x | x | x | x | x | x | x | x
Fiscalization visits | [13 empty] | x | x | x | x | x | x | x | x | x | x
Initial payment | [13 empty] | x
1 Joint site visits w MoH officials | [13 empty] | x
1 Fiscalization report/approval | [13 empty] | x
Second payment | [13 empty] | x
2 Joint site visits w MoH officials | [15 empty] | x
2 Fiscalization report/approval | [15 empty] | x
Third payment | [15 empty] | x
3 Joint site visits w MoH officials | [17 empty] | x
3 Fiscalization report/approval | [17 empty] | x
Fourth payment | [17 empty] | x
4 Joint site visits w MoH officials | [19 empty] | x
4 Fiscalization report/approval | [19 empty] | x
Fifth payment | [19 empty] | x
5 Joint site visits w MoH officials | [21 empty] | x
5 Fiscalization report/approval | [21 empty] | x
Sixth payment | [21 empty] | x
Final visit | [22 empty] | x
Final fiscalization report /approval of construction | [22 empty] | x
Closing of activities | [22 empty] | x
Inauguration/opening | [22 empty] | x
Final payment (warranty) | [22 empty] | Dec. 2022

## IC LMIS (PSM)
INTERNATIONAL CONSULTANCY FOR THE LMIS (PSM)
ACTIVITIES | 2021 | [10 empty] | 2022
| Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Design of ToR- Draft | bar: 2021 Jun to 2021 Jul
ToR Discuss w CGS procurement unit | bar: 2021 Jul
ToR discuss w director of National Drug Fund (*1) | bar: 2021 Aug
Final draft sent to GPU | bar: 2021 Sep
Discussion with LMIS international expert (Chris Wright) (*2) | bar: 2021 Sep
New ToR circulated | bar: 2021 Sep
Contacts with possible suppliers. Demonstration of software (teams conference) (*3) | 2021 Sep: x; 2021 Nov: done
ToR shared with GPU | 2021 Sep: x; 2021 Nov: done
Selection of LTA process. Identification of shortlist | 2021 Oct: x; 2021 Nov: done
Signature of contract (first phase) | 2021 Oct: x; 2021 Nov: done
PO elaborated (Atlas) | 2021 Oct: x; 2021 Nov: done
PSM software implementation activities in country | bar: 2021 Nov to 2022 Mar
Final evaluation
Final document first phase | bar: 2022 Mar
Final closing document sent to GF | bar: 2022 Apr
(1*) Discussion on ToR with Director of FNM, Dra. Neurice Ramos
(2*) Zoom discussion with Chris Wright and Neurice Ramos, Wadson Cruz and Vania Castro.
(3*) Product demonstration done with mSupply; participation of Wadson Cruz, Vania Castro and Neurice Ramos

## IC BSL
| 2021 | [10 empty] | 2022
| Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Design of ToR- Draft | bar: 2021 Jun
Discuss w Dra. Rosa (Director of Laboratory) | bar: 2021 Jun
Discussion with Technical specialist (Greg Chalkers) | bar: 2021 Jul
Report from AFSL | bar: 2021 Jul
Second draft for BSL reviewed w Dra. Rosa | bar: 2021 Jul
Launching of international recruitment process | bar: 2021 Aug
Deske review | bar: 2021 Sep
Re-launching of international recruitment process | bar: 2021 Sep
Selection process | 2021 Sep: x; 2021 Oct: x; 2021 Nov: done
Negotiation with CDC for calibration of equipment | 2021 Oct: x; 2021 Nov: done
Interviews with applicants | 2021 Oct: x; 2021 Nov: done
Signature of contract | 2021 Oct: x; 2021 Nov: done
Conceptual design, final architectural design | bar: 2021 Nov
Structural design | bar: 2021 Nov
Electrical, water, sanitary design, special instalments, cold room | bar: 2021 Nov
Bill of quantities, unti price analysis, detailed budget, schedule of activities, technical specifications, bid documents, final complete project design | bar: 2021 Nov
Final project design | bar: 2021 Nov

## CGS
| 2021 | [10 empty] | 2022
Activity | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Recruitment of national consultant |  |  |  | x
Report infraestructure analysis |  |  |  | x
Verification visit with MoH, engineers, FNM specialists |  |  |  | x
First project design |  |  |  | x
Conceptual design, final architectural design |  |  |  | x
Structural design |  |  |  |  | x
Electrical, water, sanitary design, special instalments, cold room |  |  |  |  | x | x | x
Bill of quantities, unti price analysis, detailed budget, schedule of activities, technical specifications, bid documents, final complete project design | [6 empty] | x
Final project design
Bidding process | [6 empty] | x | x
Site visits with applicants | [7 empty] | x
Selection of construction firm | [7 empty] | x
Signature of contract | [7 empty] | x
Initiation of construction | [7 empty] | x | done
Biweekly Site visits | [7 empty] | x | x | done
Initial payment | [8 empty] | x | done
1 Fiscalization visits | [8 empty] | x | done
2nd payment | [9 empty] | x | done
2nd Fiscalization visit/report | [9 empty] | x | done
3rd payment | [9 empty] | x
3rd Fiscalization visit/report | [9 empty] | x
4th payment | [9 empty] | x
Final fiscalization visit/report | [9 empty] | x
5th payment | [9 empty] | x
Closing of civil works/report | [9 empty] | x
Inauguration | [10 empty] | x | x
Final payment (warranty) dec. /22

## minor works
| 2021 | [10 empty] | 2022
Activity | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Recruitment of national consultant |  |  |  |  | X
Negotiation with MoH personnel |  |  |  |  | x
Visits to health centers, Tisiology, |  |  |  |  | x
Conceptual design, final architectural design | [5 empty] | x | x
Structural design | [6 empty] | x | x
Verification visit with MoH, engineers, FNM specialists | [7 empty] | x
Conceptual design, final architectural design | [8 empty] | x | done
Structural design | [8 empty] | x | done
Electrical, water, sanitary design, special instalments, cold room | [8 empty] | x | done
Bill of quantities, unti price analysis, detailed budget, schedule of activities, technical specifications, bid documents, final complete project design | [8 empty] | x | done
Final project design | [8 empty] | x | done
Bidding process | [8 empty] | x | in progress
Selection of construction firm | [8 empty] | x
Initiation of construction | [8 empty] | x
First payment | [8 empty] | x
Supervisory site visits/fiscalization report | [9 empty] | x
Second payment | [10 empty] | x
Supervisory site visits/fiscalization report | [10 empty] | x
Third payment | [10 empty] | x
Final supervisory visit/closing report | [11 empty] | x
Warranty (december 2022)

## IC DHIS
INTERNATIONAL CONSULTANCY FOR DHIS II
ACTIVITIES | 2021 | [11 empty] | 2022
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
On-going contract | bar: 2021 Jan
Activities DHIS II | bar: 2021 Jan to 2022 Dec
Reports | bar: 2021 Mar; 2021 Jun to 2021 Jul; 2021 Oct to 2021 Dec; 2022 Mar; 2022 Jul; 2022 Oct; 2022 Dec
Evaluation of quarter activities | bar: 2021 Mar; 2021 Jun to 2021 Jul; 2021 Oct to 2021 Dec
Decision on continuation of activities during 2022 | 2021 Oct: done; 2021 Nov: x
Finalization of on-going contract | bar: 2021 Dec
Evaluation of results | 2021 Oct: ongoing; 2021 Nov: x
Signature of new contract for 2022 | bar: 2022 Jan

## IC IBBS
INTERNATIONAL CONSULTANT TO CONDUCT AN IBBS TO ANALYZE STIGMA IN ARMED FORCES, PRISONERS AND HEALTH PERSONNEL (INPG)
ACTIVITIES | 2021 | [7 empty] | 2022
| May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
Design of ToR- Draft | bar: 2021 Aug to 2021 Sep
Discussion w Dra. Ernestina (Director of INPG) | bar: 2021 Sep
Discussion with Technical specialist (INPG) (*1) | bar: 2021 Oct
Initial draft circulated | bar: 2021 Oct
Finalized document shared with GF and GPU | 2021 Oct: x; 2021 Nov: done
First batch of CVs received | 2021 Oct: x; 2021 Nov: x; 2021 Dec: done
Desk review | 2021 Nov: x; 2021 Dec: x; 2022 Jan: done
Selection process | 2021 Dec: x; 2022 Jan: done
Interviews with applicants | 2021 Dec: x; 2022 Jan: done
Meetings with Antoine Gasasira (GF) | 2021 Dec: x; 2022 Jan: on going
Contract signed | bar: 2022 Jan
consultant in country | bar: 2022 Feb to 2022 Mar
First draft of IBBS consultancy shared | bar: 2022 Apr
Final draft approved by partners | bar: 2022 Apr
Final document shared/approved with MoH | bar: 2022 Apr
Final document shared with GF | bar: 2022 May
(1*) due to calendar constraints, INPG is asking to postpone IC activities to begin on the month of January

## IC Vuln. P
INTERNATIONAL CONSULTANCY TO REINFORCE SERVICE PACKAGE FOR VULNERABLE POPULATIONS
Activity | 2021 |  |  |  |  | 2022
| Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Design of ToR- Draft | bar: 2021 Oct
Discuss w Dra. Ernestina (Director of INPG) | bar: 2021 Oct
Discussion with Technical specialists | bar: 2021 Oct
Initial draft circulated | bar: 2021 Oct
Finalized document shared with GF and GPU | bar: 2021 Oct
First batch of CVs received | bar: 2021 Nov
Desk review | bar: 2021 Nov
Selection process | bar: 2021 Nov
Interviews with applicants | bar: 2021 Nov
coordination with Monica/Antoine | bar: 2022 Jan
Contract signed | bar: 2022 Feb
consultant in country | bar: 2022 Feb
First draft of consultancy shared with partners | bar: 2022 Feb
Final draft approved by MoH | bar: 2022 Mar
Final document shared and approved by GF
(*1) INPG is asking to postpone this IC to begin in January

## IC VIH 90
Conduct a review and propose a strategy to increase adherence to increase treatment adherence and reach the 90-90-90 in HIV
Activities | 2021 | [5 empty] | 2022
| Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Design of ToR- Draft (*1) | [10 empty] | activities finalized | bar: 2021 Aug to 2021 Sep
Discuss w CGS/circulated draft | bar: 2021 Sep
Discussion with RSS (Dr Hugo) | bar: 2021 Sep
Initial draft circulated with inputs | bar: 2021 Sep
Finalized document shared with GPU | bar: 2021 Sep
First batch of CVs received | bar: 2021 Oct to 2021 Dec
Coordination w Antoine/Monice | bar: 2022 Jan
Desk review | bar: 2022 Jan
Selection process | bar: 2022 Jan
Interviews with applicants | bar: 2022 Jan
Contract signed | bar: 2022 Jan
consultant in country | bar: 2022 Feb
First draft of consultancy shared | bar: 2022 Mar
Document discussed with partners | bar: 2022 Mar
Presentation via zoom | bar: 2022 Mar
Final draft approved by GF | bar: 2022 Apr
Final document shared with MoH | bar: 2022 Apr
(*1) following guidelines from TRP review (August 2020), issue # 4

## IC FOR RHR FOR CHSS
Conduct an HRH review across the three diseases and propose an integrated needs-based approach for community health workers CHSS
Activities | 2021 | [5 empty] | 2022
| Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Design of ToR- Draft (*1) | bar: 2021 Aug to 2021 Sep
Discuss w CGS/circulated draft | bar: 2021 Sep
Discussion with RSS (Dr Hugo) | bar: 2021 Sep
Initial draft circulated with inputs | bar: 2021 Sep
Finalized document shared with GPU | bar: 2021 Sep
coordination with Monica/Antoine
First batch of CVs received | bar: 2021 Oct
Desk review | bar: 2021 Oct
Selection process | bar: 2022 Jan to 2022 Feb
Interviews with applicants | bar: 2022 Feb
Contract signed | bar: 2022 Feb
Consultant in country
First draft of HRH for CHSS consultancy shared | bar: 2021 Dec
Document discussed with partners | bar: 2021 Dec
Presentation via zoom | bar: 2021 Dec
Final draft approved by partners | bar: 2022 Jan
Final document shared/approved by MoH | bar: 2022 Feb to 2022 Mar
final draft shared and approved by GF | bar: 2022 Apr
(1*) Following TRP guidelines (August 2020) issue #