## V. Deliverables and Indicators
Annex V. Deliverables and Indicators
Deliverable(s) | INDICATORS | Expected Date of Achievement
Deliverable 1 | 1.1 At least 3 TORs drafted/ prepared to engage collaborators, partners (i.e.Oxford Business School, STDV, TechSoup) | 01/10//2020
Launch of the Boost: Covid-19 Solutions Acceleration Program | 1.2 At least 2 Systems Mapping through Problem Space and Sensemaking Workshops organized with stakeholders and partnering organizations
1.3 Communication plan; media visibility, online tracking and sharing project steps via promotional campaigns prepared and disseminated through the platform and/or other social media handles
1.4 Landing page for Boost designed and published using GUST
1.5 Application form prepared using GUST
1.6 Finishing curriculum and sessions design for Boost: Koç Challenge
Deliverable 2 | 2.1 Selection and announcement of the winner applications finalized and announced in the GUST platform | 2020-01-09
Implementation and Completion of the Accelerator Cycle | 2.2 At least X Mentor networks to be assembled and linked to the Boost program
2.3 Supervision and follow-up of the Boost program; monitoring the progress and outcomes
2.4 At least X meetings/virtual meetings/calls organized to ensure coordination between partners at regional level
2.5 Running Boost program on digital platforms and managing participants
Deliverable 3 | 3.1 At least 20 organizations selected to join the Accelerator Cycle | 31/10/2020
Designation of winning CSOs | 3.2 At least 10 organizations are selected to join the Digital Crowdfunding Academy service line
3.3 At least 5 organizations identified to receive monetary grants
Deliverable 4 | 4.1 At least 5 dissemination activities organized (Offline & online meetings with partners and collaborators, sensemaking activities, expanded demo days, workshops, featuring the project in international forums) (i.e. Event management, experience dissemination and advertisement) | 30/11/2021
Evaluation of the Launch of the Boost: Covid-19 Solutions Acceleration Program
4.2 Digital Mentoring Packages prepared including digital content from mentoring (short videos with coaches, webinars, etc)
4.3 Evaluation (i.e.Impact Evaluation for the overall program)

## VI.Multi-Year Work Plan Budget
EXPECTED DELIVERABLES | PLANNED ACTIVITIES | Timing[1] |  |  | PLANNED BUDGET[2]
|  | Year 1- 2020 | Year 2- 2021 | Year 3 | Budget Description | Amount
|  | July- December 2020 | January- December 2021 | January - August 2022 |  | Year 1 | Year 2 | Year 3 | Total
Deliverable 1: Launch of the Boost: Covid-19 Solutions Acceleration Program | 1.1 Application of system thinking (diversification of risks), sensemaking workshops | X | X | X | 75200- Workshops |  |  |  | 0
| 1.2 Contribution to platform development, the development of visual identity for the Accelerator & Platform Maintenance (i.e. Website and Brand Identity Design for the landing page) |  |  |  | 74100- Media production/IT/Consultant |  | 2200 |  | 2200
| 1.3 Development of Curriculum with executive partners (.i.e. Finishing curriculum and sessions design for Boost: Koç Challenge) |  |  |  | 75200- Workshops |  |  |  | 0
| 1.4 Drafting TORS, partners communication and project management (i.e. Project Manager fee) |  |  |  | 71300- Service Contracts/72100- Individual Consultants | 10000 | 28436 | 25600 | 64036
| 1.5 Assisting management and project development (i.e. Project Assistant fee) |  |  |  | 71300- Service Contracrs |  |  |  | 0
| 1.6 Establishing communications and managing visibility (i.e. Communication Officer fee) |  |  |  | 72100- Individual Consultants |  | 9600 | 10000 | 19600
|  |  | Sub-total Programming activities |  |  | 10000 | 40236 | 35600 | 85836
[5 empty] | 75100- Facilities (GMS 8%) | 800 | 3218.88 | 2848 | 6866.88
| Sub-Total for Deliverable 1 |  |  |  |  | 10800 | 43454.88 | 38448 | 92702.88
Deliverable 2: Completion of the Accelerator Cycle | 2.1 Development of promotional videos, infographics and social media campaigns | X | X | X | 74100- Multimedia/IT |  | 3000 | 3000 | 6000
| 2.2 Partnerships with regional & European accelerators for the delivery of mentorship & coaching over a period of 16 weeks (Impact Hub, Oxford Foundry, K-Works, Start-up Grind) (i.e. Running Accelerator with the executive partners) |  |  |  | 75200- Workshops | 5000 |  | 28000 | 33000
| 2.4 Process design for the accelerator (development of worksheets, overall user-centered journey) and placing it in the digital space (i.e. designing the user-centered learning journey on digital platforms) |  |  |  | 72100- sub- contracts |  | 10000 |  | 10000
| 2.5 Administering the cycle with outreach partner from Turkey ( Low Value Grant agreement with the Support Foundation for Civil Society- STDV ) |  |  |  | 72600- Grants | 5882 | 3000 |  | 8882
| 2.6. Development of intelligence workshops (organizing digital workshops twice during the program to generate learnings across all the platform, and generating insights on future direction) |  |  |  | 72500- Workshops |  | 5100 | 5000 | 10100
|  |  | Sub-total Programming activities |  |  | 10882 | 21100 | 36000 | 67982
[5 empty] | 75100- Facilities (GMS 8%) | 870.56 | 1688 | 2880 | 5438.56
| Sub-Total for Deliverable 2 |  |  |  |  | 11752.56 | 22788 | 38880 | 73420.56
Deliverable 3: Designation of winning CSOs | 3.1 Selection/identification of 20 organizations to join the Accelerator Cycle |  | X | X |  |  | 0 | 2073 | 2073
| 3.2 Selection/identification of at least 10 organizations to join the Digital Crowdfunding Academy service line | [7 empty] | 0
| 3.3 Selection/identification of 5 organizations to receive monetary grants |  |  |  | 72600- Grants |  | 50000 |  | 50000
0
|  |  | Sub-total Programming activities |  |  | 0 | 50000 | 2073 | 52073
[5 empty] | 75100- Facilities (GMS 8%) | 0 | 4000 | 165.84 | 4165.84
| Sub-Total for Deliverable 3 |  |  |  |  | 0 | 54000 | 2238.84 | 56238.84
Deliverable 4: Evaluation of the program | 4.1 5 dissemination activities (Offline & online meetings with partners and collaborators, sensemaking activities, expanded demo days, workshops, featuring the project in international forums) (i.e. Event management, experience dissemination and advertisement) |  | X |  | 72100- Sub-contracts |  |  | 10000 | 10000
| 4.2 Packaging digital content from mentoring (short videos with coaches, webinars, etc) |  |  |  | 74100- Media production/IT |  | 5000 | 5000 | 10000
| 4.3 Evaluation (i.e.Impact Evaluation for the overall program) |  |  |  | 71200- Individual Consultants |  |  | 10000 | 10000
|  |  | Sub-total Programming activities |  |  | 0 | 5000 | 25000 | 30000
[5 empty] | 75100- Facilities (GMS 8%) | 0 | 400 | 2000 | 2400
| Sub-Total for Deliverable 4 |  |  |  |  | 0 | 5400 | 27000 | 32400
| Miscellaneous Expenses |  |  |  |  | 372 | 1000 | 1000 | 2372
[5 empty] | Total | 21254 | 117336 | 99673 | 238263
[5 empty] | GMS 8% | 1700.32 | 9386.88 | 7973.84 | 19061.04
[5 empty] | Grand Total | 22954.32 | 126722.88 | 107646.84 | 259696.04
[1] Specify units of timing depending on the needs of the development service. May be monthly, quarterly or annually.
[2] The budget portion is optional, for when UNDP provides development services on a cost-plus basis