| Project Title | Supporting communities’ resilience through disability inclusion |
| --- | --- |
| Expected CPD outcome | Outcome 1: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and social inclusion |
| Start Date: | 1 January 2020 |
| End Date | 31 December 2021 |
| Implementing Partner: | UNDP |

Brief Description The situation of war-born injuries and resulting impairment and disability is being clearly reported as number one priority for humanitarian response in Syria with 27 per cent increase in number of Persons with Disabilities (PWDs) (Humanitarian Needs Overview, HNO 2016). The transition from injury to impairment is happening in an increased pace under less-favorable medical care environment due to the declining of health services coverage (30 per cent of Public hospital not functioning, Health Resources Availability Monitoring System 3rd Quarter 2016), and the transition to disability is inevitable within the exclusive and disabling environment. It is reported that some 30,000 people suffer from conflict-related trauma injuries every month, roughly 30 per cent of whom develop permanent disability with an estimation of 2.8 million people suffering from different sort and level of disability (15% undergo amputation, 5% spinal cord injuries and 10% peripheral nerve injuries). PWDs including women with disabilities are over burdened by multiple layers of marginalization and vulnerability that require a comprehensive approach that sees disability as an interaction between functional limitations and environmental barriers (physical, social, legislative) and consists of a wide spectrum of services to enable them to actively participate and contribute to socioeconomic development and enjoy their basic human rights. UNDP’s strategy for disability issues is built upon its own experience and learning that PWDs’ quality of life and independence should first start through medical rehabilitation interventions, which is fundamental to practice inclusion in the social, economic and cultural context, and work as an entry point to socioeconomic inclusion of PWDs. It employs an integrated approach that travels between physical rehabilitation and livelihood support interventions while strengthening linkages with labour market and social context. To this end, this project aims to achieve the following three outputs: PWDs functionality and independence enhanced through physical rehabilitation and psychosocial support; PWDs socioeconomic integration enhanced through livelihood support in addition to promoting accessibility to labour market and basics services; and PWDs inclusion enhanced through promoting knowledge sharing, capacity development, awareness raising and innovation. The project has a specific gender focus to ensure gender mainstreaming in response to disability issues.

| Contributing Outcome (UNSF/CPD, RPD or GPD): Country Programme Document Outcomes Outcome 1: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and social inclusion Indicative Output(s): 1.4. Rehabilitation and livelihood opportunities provided to persons with disabilities Programme Period: 24 months from 1 January 2020 till 31 December 2021 Atlas Award ID: 00119352 PAC Meeting Date: | Total resources required EUR 4,000,000 Total allocated resources: EUR 4,000,000 Regular ___ 0_____ Other: Donor EUR 4,000,000 Unfunded budget: ____0_____ In-kind Contributions ____0_____ |
| --- | --- |
| Agreed by (UNDP): |

# Development Challenge

Persons with disabilities (PWDs) are amongst the most vulnerable groups within the society, and they are at particular risks during crisis because they may be invisible, discriminated against and neglected.

According to the World Bank, “Persons with disabilities, as a group, experience worse socioeconomic outcomes than persons without disabilities, such as less education, worse health outcomes, less employment, and higher poverty rates.” These reduced outcomes may be attributed to several institutional and social barriers and in turns they contribute to worse impact on PWDs lifecycle and life span. According to various reports, 10,000 individuals with disabilities die each day as a result of extreme poverty in the global context.

After eight years of crisis in Syria, there has been a peak increase in numbers of injuries, deterioration of health system and immature discharge from hospitals in addition to deficiency and brain drain of skilled human resources specialized in physical rehabilitation; all these factors have contributed to higher and rapid transition from injuries to impairments, and disabilities. It is clearly reported as number one priority of humanitarian needs since 2015 (HNO 2019).

With the deterioration of health services (30 per cent of public hospitals not functioning, Health Resources Availability Monitoring System 3rd Quarter 2016), the transition from injuries to impairments and disabilities is happening in an increased pace and higher severity. It is reported that some 30,000 people suffer conflict-related trauma injuries every month, roughly 30 per cent of whom develop permanent disability with an estimation of 2.8 million people suffering from different sort and level of disability (15% undergo amputation, 5% spinal cord injuries and 10% peripheral nerve injuries).

The tremendous number of war-born injuries and impairments is an ongoing health, and a latent socioeconomic problem. The health problem presents a life-threatening situation either through the direct severe trauma or secondary complications resulting from poor primary health care and insufficient rehabilitation. On the other hand, the latent socioeconomic problems are caused from the fact that human and financial assets in families caring for PWDs who have not received proper medical rehabilitation are severely exhausted and excluded from socioeconomic lives. Gender mainstreaming in disability issues has been one of the least responded area in Syria crisis response.

Before the crisis, the Government of Syria had set priority to develop a comprehensive national plan consisting of needs assessment in addition to strengthening rehabilitation services and mainstreaming of inclusion policies. The process to implement the national plan for disability was progressing steadily.

Despite the above development and adding the effect of the ongoing crisis on increased vulnerability and prevalence of impairment, Syria faced and keeps struggling with number of challenges for the advances for inclusion of PWDs.  This leaves established national services for the rehabilitation and support of PWDs in Syria in the less favoured position to cope with the consequences of the conflict. These challenges can be identified at three levels: i) lack of access to basic services and socioeconomic opportunities and benefits; ii) loss of PWDs functionality and independence; iii) lack of attention, accountability and the Rule of Law to support disability issues.

# Strategy

There has been a growing attention to support PWDs being one of the most vulnerable groups in response to the crisis in Syria. This has been reflected in the consecutive Humanitarian Response Plans as a cross-cutting issue, in addition to specifying projects to targeted PWDs. In this regard, UNDP has been the first responder for PWDs’ needs in Syria since 2014 and the programme has developed from provision of emergency support in the form of distribution of mobility and other disability aids to a more integrated project and comprehensive approach containing various activities spanning from medical rehabilitation to livelihood support and social inclusion.

In line with United Nation Convention on the Rights of Persons with Disabilities (CRPD), UNDP has pioneered to adopt the human right-based approach to disability issues in comparison to the mere medical or charitable model. In the human-right based approach,  disability is seen as an interaction between functional limitation and environmental barriers (physical and social), thus it addresses not only the impairment of body function but also implies designing interventions within a strategic goal to empower PWDs and enable the social system in which they are situated.

The Theory of Change underpinning the UNDP disability programme is based on the understanding that, exclusion is the result of interaction between a) The limited activity level of poorly rehabilitated PWDs and b) Difficulty to access all basic services including socioeconomic opportunities, in addition to c) Weakened regulatory frameworks (Rule of Law) and social incubation.

PWDs’ inclusion in the development agenda is a prerequisite for achieving SDGs in the normal situation when PWDs consists 10 to 15% of the population. In crisis setting however, and in protractive form as in the Syrian crisis, the number as well as severity of impairment and disability raises to consist over 20% of the society. In such cases, it is unavailing to push recovery and support resilience of the society without paying due attention to its PWDs community. Therefore, supporting PWDs towards independence and socioeconomic participation will not be an only direct factor to boost socioeconomic recovery and resilience of PWDs, but also the attenuated burden on the family members will further enhance overall households’ participation in socioeconomic recovery and resilience.

Moreover, it is reported that a healthy and proactive PWDs’ community can play an important role in promoting reconciliation and social cohesion.

Therefore, UNDP’s strategy to support PWDs in Syria is not limited to deal with disability as a cross-cutting issue, but rather it is deeply situated as a holistic approach within its strategy to support the overall resilience of Syrian community.

UNDP’s disability strategy is built upon its own experience and learning that PWDs’ quality of live and independence should start first through medical rehabilitation interventions, which will be fundamental to practice inclusion in the social, economic and cultural context, and work as an entry point to socioeconomic inclusion of PWDs. It employs an integrated approach that travels between physical rehabilitation and livelihood support interventions while strengthening linkages with the labour market and social context.  Gender mainstreaming is also part of its strategic focus of UNDP’s disability programme.

To this end, this project aims to achieve the following three outputs:

- PWDs’ functionality and independence enhanced through physical rehabilitation and psychosocial support;

- PWDs’ socioeconomic integration enhanced through livelihood support in addition to promoting accessibility to labour market basics services; and

- PWDs inclusion enhanced through promoting knowledge sharing, capacity development, awareness raising and innovation

UNDP’s experience indicates that at this stage it is difficult to achieve significant results by mere mainstreamed approaches to socioeconomic inclusion as we need to take into consideration the low accessibility, negative social norms and less-buy in from labour market including private sector that prevents PWDs and especially women from working. With dramatic worsening in vulnerability and poverty indexes in addition to the scarcity of resources, more marginalization is being forced on PWDs, the current situation warrants the necessity of targeted approach.

In this regard, UNDP proposes a twin track approach with significant focus on targeted interventions through the above interlinked outputs in order to create a mediatory environment where PWDs can gain confidence and skills, paving the transition to a more inclusive environment. Customized and innovative interventions will be thought through in designing livelihood activities that focuses on gravitating PWDs especially women with disabilities.  Under both tracks, UNDP aims to mainstream gender as much as possible in a contextualised way.

- Targeted interventions: interventions aimed at benefitting PWDs directly through empowering PWDs, their families and representing organizations through targeted actions to respond to PWDs specific needs. In this track, the interventions will aim to increase the level of function, quality of life and independence of PWDs through provision of physical rehabilitation services such as (prosthetic devices, mobility aids, physical therapy) in addition to psychosocial and livelihood support.

- Mainstreaming interventions (indirect interventions): interventions aimed at benefiting PWDs indirectly by influencing the nature or border systems in which PWDs may be situated and interacting with. In this track, the interventions will work to identify and overcome barriers in the community, society and system level such as physical and attitudinal barriers.

This project will also introduce capacity development components targeted towards service providers and technical staff involved in planning and design of programme and interventions in several areas such as (PSS, Accessibility and Inclusive policies), as well as innovative approaches.  Such investment will ensure sustainable and quality impacts that will service for many in the future.

Based on the twin track approach for interventions, we propose the following scope of interventions that covers the three-dimensional outputs of UNDP strategy for its comprehensive approach.  The selection mechanism and criteria for beneficiaries for this project follows two principles: technical and programmatic selection criteria.

- Technical selection criteria: For each activity under each output, we chose specific selection criteria, especially for the first output (Physical rehabilitation). These criteria are defined based on four major elements:

  - Needs priorities: such as prevalence and severity of specific types of injuries and/or impairment.

  - Gaps and deficiency in services and capacities to serve.

  - Quick impact resulting from intervening on the quality of life of the beneficiary and his/her household member.

  - Relevance to the crisis in terms of reason of the impairment and /or injury.

Based on that, UNDP will mainly target physical disabilities for output 1, however and due to several reports on needs on hearing impairment, there will a component focusing on providing hearing aids in addition to inclusion of persons with hearing difficulties in several socioeconomic activities.

More specifically, amputation cases have been and still a major focus of our intervention, taking  into consideration the four elements mentioned above. Within amputations, we also focus on lower limb cases due to prevalence, capacities and cost efficacy and expected outcome. Mild to moderate types of disabilities will be targeted under physical rehabilitation in order to deliver substantive impact within the available resources and timeframe of our interventions. While for socioeconomic integration, we select PWDs who have graduated from physical rehabilitation programme and have acquired a significant dependency in their life.

- Programmatic selection criteria: After applying technical criteria, we prioritize selection based on UNDP general selection criteria that look into the below three aspects.

- Geographic targeting

For this project, UNDP plans to target geographical locations as per the following criteria:

- Criteria 1: Impact of the armed conflict (high number of injuries and PWDs, deteriorated basic health and social services, and high poverty and unemployment. etc). Due attention will also be given to newly accessible areas such as East Ghouta of Rural Damascus, Southern region and North-East region.

- Criteria 2: For technically demanding projects, conducive areas with proven stability and accessibility to market and technical capacities will be prioritised.

- Criteria 3: Areas that are a target for scaling-up the existing projects.

- Beneficiary targeting

Beside technical criteria, UNDP will solely target civilians with the most acute needs for support. In order to ensure our principle targeting criteria of civilian solely, UNDP coordinates with relevant stakeholders who are in charge of supporting non-civilians and always requests the presentation of civilian ID card when assessing and admitting any beneficiaries to be part of the projects on the ground.

To this end, the below prioritized criteria will be used to identify the most vulnerable about eligible beneficiaries:

- Criteria 1: Internally displaced people (IDPs)

- Criteria 2: People with disrupted livelihoods (housing, source of income, assets, etc.)

- Criteria 3: Females and Women-headed households (families who lost their primary income earner)

- Criteria 5: Youth (both female and male)

Through our experience, we have been overseeing the results of spill-over effect we are directly and indirectly reaching through our interventions when targeting PWDs especially in the socioeconomic integration outputs. Therefore, we have started to acknowledge the impacts of livelihoods support for persons without disability.  Therefore, on top of our main focus on PWDs, the current project targets the members of households with PWDs and other vulnerable population such as women and female-headed households as part of the livelihoods component.

Given the nature of activities, this current project aims to have an average of 40 % women’s participation across various Outputs.  There is an ongoing coordination mechanism to avoid duplication of effort and targeting with national partners and international agencies. For example, being not within our mandate and to avoid any duplication with UNICEF for example, we particularly target beneficiaries from the age range above 16 years old. Yet, in the area of physical rehabilitation namely prosthetic services and physiotherapy, we do accept cases of children after close coordination with relevant stakeholders to fill the gaps of services.

- Implementing partner targeting:

When not implemented directly by UNDP, projects are implemented through local and international partners (NGOs, CBOs, INGO). The selection of local partners is based on UNDP assessment conducted by NGO’s capacity building team, which categorize NGOs on the basis of capacities and risks for partnership and provide direct recommendation and are a part of the committee of low value grant which is the main implementation modality used by UNDP for project activities implementation with Local NGOs. Low value grant is a grant agreement with the ceiling of 150K USD per agreement. The control mechanism set for this type of agreement and transfer of money to local partner is set by the legal binding document signed with the local partner, where mainly grants are released in instalments based on progress of implementation evaluated against financial and technical reports. So far, this modality has been widely used by Syria country office with very low record of any conflicting issue.

Scope of intervention:

- PWDs functionality and independence enhanced through physical rehabilitation and psychosocial support (PSS)

In the area of physical (medical) rehabilitation, national capacities are currently limited and incapable to respond to the increased needs in impairment and disability prevalence rates.

UNDP realized that in order to practice inclusion in the humanitarian and development context, PWDs’ quality of life and independence should be firstly promoted through medical rehabilitation interventions. Therefore, UNDP has invested in providing support to medical rehabilitation as an entry point to socioeconomic inclusion of PWDs.

UNDP will mainly target physical disabilities among persons within the age range of those who can join the active labour market programmes. The services sought are driven from the several needs assessment reports (official and non-official) indicating the dire needs for certain services such as prosthetic devices, mobility aids and physical therapy.

To this end, the support for physical rehabilitation and PSS includes the following areas of interventions that are selected based on the priorities of needs acquired through the results of national study conducted by UNDP, UNICEF and WHO in collaboration with the MOSAL, and the Central Bureau of Statistics in addition to the data coming from our partners on the ground.  Output 1 aims to have an average of 30 % of women’s participation given the high needs of physical rehabilitation for men with disability.

  - Prosthetic services:

In general, there is a lack and limitation on the acquisition of precise numerical data in all areas related to disability, and it is also the case for prosthetic services. One of the earliest reports in 2014 stated the presence of more than 80,000 traumatic amputation cases in needs for prosthetic fitting in Syria. Other studies estimated that 15% of all injuries, that for example in 2016 was reported at 30,000 injury per month, are amputation injuries. Other reported that in previously besieged areas and currently being newly accessible areas such as (East Ghota, Deir-Ez-Zor and East Aleppo) the rate of amputation is one out of eight people. Despite the major interest and efforts of many parties in delivering prosthetic services, the nationally available capacities and services being public, civil or even private sector, are still limited on covering the huge needs. UNDP has been the first actor to provide substantial support in this field since 2015 specially as a UN agency as part of the humanitarian response by strengthening Community-Based Organisations (CBO) capacities in providing prosthetic services to ensure impartiality, diversity and local ownership.

With the support of the previous funding from the Government of Finland, UNDP succeeded to expand its prosthetic service centres by opening two additional centres in the critical and challenging areas of Aleppo and Qamishli. The overall support by UNDP is now covering five centres (Aleppo, Qamishli, two in Damascus and Tartous), four of them (Aleppo, Qamishili, Tartous, and one in Damascus) thus far funded by the Government of Finland.

The cost for establishment and running this service is relatively high when is looked at from a mere economic angle of a cost per head, however, when applying more socioeconomic perspectives, we can understand the level of impact being delivered through this suggested approach.

Tapping into UNDP’s expertise and experience, that built the previous interventions supported by the Government of Finland, UNDP suggests to further expand the support to the current prosthetic services in one way to deliver as much as possible of this valuable service of a comprehensive package including medical consultation, pre-and post-physical therapy and training in addition to PSS through specialized and peer-to peer support especially targeting persons with lower limb amputation.  This component will be implemented with UNDP’s new strategy to create the notion of a hub in the five centres for enhancing integration and comprehensiveness of support to PWDs and a referral system.

The current project consists of supporting the existing workshops to expand the capacity of two recently established centres in Aleppo and Qamishli, and to deliver 275 new prosthetic devices through all centres.

  - Physical therapy (PT):

Through UNDP interventions, PT has been thus far provided in four manners:

  - Through all prosthetic centres to beneficiaries of prosthetic services;

  - Through two prosthetic centres in Damascus and Qamishli to PWDs in general;

  - Through a pilot project in Latakia consisting of delivering home-based PT sessions to persons with severe disabilities; and

  - Through a pilot project in Aleppo providing conditional cash assistance to persons with severe disabilities namely (spinal cord injuries and traumatic brain injuries), conditioned to physical rehabilitation services acquisition.

The first three models have been funded by the Government of Finland during the previous cycle. The current project aims to continue delivering the service to 475 PWDs (275 are from prosthetic services beneficiaries in addition to providing PT services to 200 from other types of disabilities).

  - Disability aids:

UNDP has improved its intervention in disability aids services to distinguish between emergency support for protection and evacuation purposes in comparison to actual physical rehabilitation that contributes to impacting socioeconomic aspects of the beneficiaries. Through previous activities, UNDP pioneered to introduce required skills to handle disability aids, namely wheelchairs services, to national service providers from the MoH and MOSAL. This training provided, for the first-time, to service providers and staff responsible for planning and delivering of this kind of services with the knowledge and skills to promote the service from mere distribution activity to a comprehensive service including selection, measurement, fitting, modification, training and follow-up maintenance.

With this enhanced skills and experience in hand, UNDP has started to inject higher technical content in the disability aids procured for the disability aids interventions.  The results thus far indicate that better integration of PWDs in socially, educationally and economically has been witnessed.

The current project aims to expand the delivery of high-quality disability aids to 1,200 PWDs. Types of disability aids will include (light weight wheelchairs, ultra-light wheelchairs, paediatric wheelchairs, electric wheelchairs), in addition to hearing aids for the first-time given that several reports indicate the dire needs for the support to the hearing impaired. The activity will differ from the existing simple distribution to a more comprehensive service consisting of assessment and customized fitting tailored to each case, in addition to provision of complementary services of case management.  Case management will provide PWDs a package of information in order to raise their awareness about their rights and privileges by laws in addition to conducting orientations and sessions in order to help beneficiaries understand their potentials and identify pathways to realize their needs for various educational, economic or social services.  This type of activity will also be a great opportunity to collect valuable information from PWDs themselves about their needs that will feed our situational analysis and inform our decisions for planning and designing future interventions.

Provision of mobility aids such as wheelchairs (manual and electric) and crutches will be implemented directly by UNDP in coordination with MoSAL and MoH after conducting a thorough needs assessment. UNDP will also articulate around providing emergency support specially in new accessible areas such as (Raqqa and Dier-Az-Zor).

  - Psycho-Social Support (PSS):

Beside delivering mainstreamed PSS services as part of a package of physical rehabilitation interventions, UNDP aims to strengthen PSS interventions to become more systematic and comprehensive, covering the various manifestation and psychosocial needs of PWDs. This intervention will require further assessing the situation and capacities of PSS services in Syria in order to develop UNDP’s strategy in this domain. In this regard, UNDP has conducted a mapping exercise to identify the current landscape of PSS services in Syria and another consultancy is being conducted to further analyse the gaps and opportunities to identify the pathway where UNDP can intervene.

In principle, UNDP has adopted Inter-Agency Steering Committee (IASC) for Mental Health and Psychological Guidelines, and its intervention pyramid for mental health and psychosocial support in emergencies.  Out of four ways of “1. Specialised Services”; “2. Focused, non-specialised supports”; “3. Community and family supports” and “4. Basic services and security”, the interventions will focus on the types 2 and 3, while referral will be sought to link to the type 1 in early detection of severe cases.  The types of interventions will include peer to peer support, light form of counselling, various group and individual activities such as arts and music, etc.  The targeted beneficiaries are 250 PWDs.

In addition, being one of the priority needs reported in several official and non-official reports, and with the apparent lack of expertise, UNDP is looking into integrating capacity development initiative in this domain. The current projects will deploy a PSS expert to support in developing UNDP strategy and interventions on PSS for PWDs. Moreover, various workshops will be conducted to build a knowledgeable local team that can contribute to the implementation of PSS interventions. The capacity development will also target technical staff involved in planning and design of PSS interventions with special focus on PWDs and survivors of trauma.  It will target no less than 10 national staff from major stakeholders and local partners preferably in the form of training of trainers (TOT).  For this activity UNDP will activate triangular collaboration seeking networking with countries with significant experience on PSS such as Finland.  This strategy and practice will feed into the actual implementation as part of support package of physical rehabilitation.

2) PWDs socioeconomic integration enhanced through PWDs socioeconomic integration enhanced through livelihood support in addition to promoting accessibility to labour market and basics services;

This Output first aims at capitalizing on UNDP network of local partners, and experience in livelihoods interventions to empower and build the resilience of PWDs and their families.

The current project will build on a successful model that has been implemented in the previous project where we capitalized on community-based initiatives and support to conduct on-the-job training and apprenticeship in local workshops at the community level.  It was followed-up by enhancing employment opportunities either through support of self-business and business start-ups initiatives via small-grants or productive assets provision, or through facilitating and promoting job matching and job placement in local economic activities while providing necessary incentives to employers to expand their capacities to accommodate for new employees.

Moreover, UNDP, through its area-based approach and local market assessment to provide more evidence-based data, will identify business ideas suitable for the local market in each governorate and feasible employment and job opportunities tailored to PWDs’ needs and abilities, with a focus on specific needs of women with disabilities. UNDP will work through network of local NGOs and CBOs with proven track records of previous successful implementations of economic and livelihood activities.

From UNDP experience, it was quite noticeable the spill-over effect of benefitting persons without disabilities in the process to support PWDs. Therefore, while the main focus will be on provision of livelihood opportunities to PWDs, we also expect to benefit family members of households of PWDs and other persons without disability during the process, while ensuring to maintain high ratio of inclusion to PWDs in this activity.

These projects will target 470 beneficiaries with livelihood support through skills training, vocational training, employment services and creating jobs opportunities.  This Output aims to target an average of 40 % for women with disability.

And in order to enhance PWDs access to employment opportunity, UNDP will look into private sector engagement, seeking triangular collaboration for introducing concepts and approaches to this marginalized area of economic recovery through the following:

- At the country level and tapping into UNDP’s private sector engagement and development work, the project aims to foster private sector consultations and events to raise awareness among private sector and reinforce their inclusion policies of PWDs at their workplace.

- At the regional level, UNDP has been actively participating in the ongoing initiatives of engaging with private sector in Finland to respond to Syria crisis. And through this project, UNDP will explore potential CSR collaboration with Finnish private sector to raise awareness and develop the capacity of Syrian private sector on CSR and socio-economic inclusion of PWDs.

To this end, UNDP will enhance and facilitate dialogue between stakeholders and arrange for capacity development on CSR approaches and solutions within the Syrian context and regulatory frameworks.

Finally, this output also aims to increase PWDs accessibility to basic services and socioeconomic opportunities. UNDP will work on enabling accessibility through addressing physical barriers in public facilities in to enhance PWDs access to social, economic, public services and cultural context with recognized substantive socioeconomic activities. This component will include rehabilitating approximately four locations such as (health centers, schools, shelters, public gardens etc.).  They will be made accessible to PWDs specially with physical impairments including wheelchair users to facilitate their participation in livelihood and other socioeconomic activities.

In addition, in order to scale up the impacts, UNDP will work on building capacities to acquire the skills needed to apply accessibility on broader scale. The project will work on mainstreaming accessibility codes (and universal design if possible) in infrastructure rehabilitation activity, by conducting workshops for advocacy amongst stakeholders and capacity development to technical staff involved in planning, design and implementation of such activities amongst UNDP and stakeholders.

- PWDs inclusion enhanced through promoting knowledge sharing, capacity development, awareness raising and innovation.

Based on the recommendation of Communications for Development (C4D) consultancy conducted in the previous project funded by the Government of Finland, it was reported that there is a dire need to enhance acquisition and access to reliable information about the situation and needs of PWDs and their related services. Therefore, the current project will bring back the attention to gather updated information that can inform the decision of UNDP and other stakeholders in designing their strategy and intervention to tackle disability issues in Syria during and post-crisis.

In light of the lack of up-to-date information about the situation of PWDs and related services, UNDP will arrange for enhancing national, regional and global networking and coordination for knowledge sharing on disability issues. For this purpose, at least one conference on disability inclusion will be facilitated to provide an opportunity to national and regional experts in the field of disability to exchange their information and perspectives. Moreover, UNDP will explore for integrated capacity development initiatives to raise the capacities of national stakeholders on the international standards and guidelines about disability, namely the Conventions on the Rights of Persons with Disabilities (CRPD) and the International Classification of Functioning, Disability and Health (ICF), and will try to connect the recommendation and guidelines of the conventions on the rights of PWDs with sustainable development goals (SGDs).

This component also aims to empower PWDs through C4D approach to foster social perception and behavioural changes about disability issues. To achieve this, UNDP will provide the required technical, technological and operational support to promote PWDs rights through people centred communication channels e.g. (television programme, community theatre, social media). Stemming from C4D consultancy recommendations as well, this component will work on building internal capacity at UNDP and follow-up with a pilot intervention targeting one of the rights of PWDs and will try to link with the outputs of the above-mentioned conference.  To this end, one expert on C4D will be recruited to design UNDP’s strategy and interventions in this domain, in addition to supporting in providing necessary technical training to internal team and other stakeholders.

Moreover, UNDP will build on previous experience that aimed at creating a core team and platform to promote for the rights of persons with disabilities. This experience included training a team from PWDs and persons without disabilities on visual communication skills and social campaigns. This new area of intervention carries a great potential to leverage UNDP work around disability inclusion and spill-over effect to support national efforts to promote for the rights of PWDs in Syria. UNDP will try to link and benefit from the established network carried from the previous engagement with various regional partners during the innovation for development event in early 2019 in Jordan in partnership with the Government of Finland.

Another part of this output, titling as “Innovation for Inclusion”, is exploring innovative ideas and enhance triangle and south-to-south collaboration to bring innovative and sustainable solutions for disability issues in Syria.

Innovation for Inclusion:

- Through this project, UNDP seeks for innovative solutions to address challenges that face PWDs issues in Syria.  Such includes, in addition to C4D, an innovation challenge to call for solutions by PWDs themselves as well as community members and the current project supports for the implementation of pilot ideas.  Successful pilots will be scaled up.

- Innovative new partnerships especially from Finland will be sought through under the project, which will include capacity building for enhancing accessibility, socio-economic inclusion of PWDs and / or PSS, areas that are in the core of UNDP needs-based strategy and where Finland has excelled as a country and society.

This Output aims to have women’s participation at 50 %.

# Results and Partnerships

Expected Results

The project’s main objective is contributing to the inclusion of PWDs in socioeconomic life and support the effort for achieving inclusive sustainable development. This project will contribute to goals 8,10 and 11 from the SDGs by working on promoting inclusive economic growth, facilitating PWDs access the job market and by creating accessible cities and transport systems. The outputs to achieve the above objectives are as follow:

Output 1: PWDs functionality and independence enhanced through physical rehabilitation and psychosocial support

Activity Result 1.1: PWDs physical and mental wellbeing promoted through provision and strengthening medical rehabilitation and PSS services.

    - Strengthen the capacity of at least two local prosthetic workshops targeting primarily the newly established workshops in Aleppo and Qamishli in order to support them towards technical sustainability.

- Provide prosthetic services by supporting at least four local workshops in Damascus, Aleppo, Qamishli and Tartous with required materials and assets to sustain their services to the people in need.

- Provide mobility and disability aids (manual wheelchairs, electric wheelchairs, crutches, walkers, air mattresses and hearing aids) through comprehensive services coupled with case management, PSS and awareness raising.

- Provide rehabilitation treatment for PWDs in need such as (Physical therapy, Occupational therapy, speech therapy etc.) through establishing and/or supporting civil and/or national rehabilitation centres.

- Provide PSS services for beneficiaries from physical rehabilitation

Activity Result 1.2: Internal and partners capacities developed on the PSS for PWDs

- Develop UNDP strategy for intervention in the field of PSS with focus on PWDs with the help of an expert in the field.

- Develop capacities of national staff (experts, social workers, programme managers) in the field of PSS with focus on PWDs.

- Implement PSS in various forms on the ground (as part of Activity 1.1)

Output 2: PWDs socioeconomic integration enhanced through provision of job opportunities in addition to promoting accessibility to labour market and basics services

Activity Result 2.1: PWDs employability, capacity and productivity improved

- Support local NGOs and CBOs in conducting economic and livelihood support projects, where PWDs and their family members in addition to other vulnerable population will benefit from livelihood support through vocational training and jobs’ opportunity creation.

Activity Result 2.2: Capacities developed to enhance PWDs access to labour market and basic services.

- Facilitate dialogue on inclusive socio-economic strategies under private sector engagement and conduct capacity development initiative on corporate social responsibility (CSR) approaches and socio-economic inclusion.

- Conduct capacity development on accessibility codes for PWDs

Activity Result 2.3: PWDs accessibility promoted for better socioeconomic integration.

- Implement projects for rehabilitation of public facility with recognized substantive socioeconomic activities in coordination with the national stakeholders.

Output 3: PWDs inclusion enhanced through promoting knowledge sharing, capacity development, awareness raising and innovation.

Activity Result 3.1: Enhanced knowledge sharing and networking

- Conduct conference/ workshops to re-enforce data collection and knowledge sharing on disability issues

Activity Result 3.2: capacity development on CRPD, ICF and linkage to SDGs

- Conduct workshops to develop the capacities of stakeholder on international guidelines on disability such as the convention on the rights of Persons with Disabilities (CRPD), the international Classification of Functioning, Disability and Health (ICF) and linkage to sustainable Development Goals (SDGs)

Activity Result 3.3: Awareness about the rights of PWDs raised through C4D intervention

- Develop a strategy / project document for UNDP’s C4D on disability

- Conduct workshops / campaign to raise awareness on the rights of PWDS via C4D interventions

Activity Result 3.4: Innovative and sustainable solution for disability inclusion issue explored

- Develop and pilot at least one innovative approach for disability inclusion

- Develop and pilot at least one innovative partnership for disability inclusion

Partnerships

To deliver this project, UNDP will work to develop and maintain several strategic and temporal partnerships at the macro and meso levels. At the macro level, UNDP will coordinate with the key relevant national counterparts to review, adopt and implement Convention on the Rights of Persons with Disabilities (CRPD) guidelines and develop capacities when necessary and applicable to enhance inclusive planning for more sustainable development at the national level. UNDP is also an active and main member of disability working group under the UN cluster coordination system led by the World Health Organization (WHO). During this coordination meetings, UNDP and international partners share updates on related work and achievement and, share technical knowledge and updates, and discuss any possible collaboration.

At the meso level, UNDP will work with local and international partners to implement project’s activities. Selection of these partners is based on UNDP assessment conducted by NGO’s capacity building team, which categorizes NGOs based on the capacity and risk assessments for partnership and provides direct recommendation.

For international partnership, UNDP is looking to expand its network of international partners to enhance quality and spectrum of the work around disability issues, particularly work around accessibility social inclusion and awareness, PSS and innovation.

Lately, given that there are many relevant stakeholders in the region, especially in Lebanon and Jordan, UNDP aims at contributing to knowledge sharing at the regional level to enhance the practices related to PWDs.

Risks and Assumptions

Any crisis presents a challenge to humanitarian and developmental work. The characteristics and context of the Syrian crisis increase these challenges, and present various risks and assumptions that we should manage in implementing the activities. These risks are largely attributed to:

- The protractive nature of the crisis;

- The exhaustion of resources and applied sanctions that affect not only technical choices for on- the-ground implementation, but also operational procedures such as transactions and overseas private sector engagement;

- The brain-drain and low national capacities that affect the advancement of technical discussion and impose major delay on operational procedures that require national approvals;

- Economic deterioration and inflation that resulted in the Syrian pound dropping 11 times of its value prior to the crisis in addition to the discrepancy between market price and official exchange rate which is currently recording the highest rates since the beginning of the crisis.  It  imposes great challenges resulting in increasing cost per unit and cost per head for all kind of interventions. For example: cost per unit for one prosthetic device was estimated in 2016 at 1300 USD. Currently, it is estimated at 1,900 USD. Similarly, cost per head for creating job opportunity used to be estimated at 2000 USD, while currently is over 2500 USD.

| Risk category | Type | Description | Impact & probability | Mitigation measures |
| --- | --- | --- | --- | --- |
| Contextual | Access | Escalation of tension in targeted areas resulting in inaccessibility | P=2 I= 3 | Follow-up security situation and target stabilized locations with the highest vulnerability and severity scales |
|  | Security | Sudden deterioration of security situation | P=1 I = 4 | Follow-up security situation and target stabilized locations with the highest vulnerability and severity scales |
|  | Cultural | Resistance to change at the national and community level | I = 2 P = 1 | Extensive sensitization at all levels |
| Programmatic | Partners | Scarcity of qualified partners | P=4 I=2 | Using network of partners, including the ones that have track records from the previous interventions |
|  | Capacities | Scarcity in technical experts, resulting in difficulties in identifying them | P=4 I=2 | Using network of partners and individuals that UNDP has established to identify experts at early stage of the project |
| Operational | External | Inflation and currency exchange fluctuation rate | P = 3 I = 2 | Plan and expedite in implementation while keeping room for budget flexibility to account for projected exchange rate fluctuation |
|  | External | Sanctions that may cause difficulties in importing needed equipment and materials | P=4 I= 2 | Plan in advance various options of vendors to ensure delivery on time |
|  | External | Difficulties in obtaining visa for experts | P=3 I= 2 | Plan in advance various options of experts and potential technical inputs to ensure delivery of the implementation on time |
|  | Partners | Difficulties in obtaining approvals for partnership with NGOs | P=4 I=3 | Plan in advance various options for partnership and implementation modalities, and shift to Plan B at the early stage, while keeping follow-up and advocacy towards the government |
| Institutional | Misconduct | Potential misuse and misconduct of funding and activities on the ground | P= 3 I= 3 | Capacity building of NGOs, and careful selection of partners based on risk assessment, in addition to close monitoring of financial and operational implementations on the ground |
|  | Coordination | Inadequate attention and accountability among stakeholders on PWDs issues | P = 1 I = 2 | Advocacy and sensitization, and coordination with other relevant agencies and organisations |

Stakeholder Engagement

UNDP is an active and main member of the disability working group under the UN humanitarian response coordination  system. And due to the extensive experience in several domains and areas of disability support, UNDP is frequently contacted and consulted about disability work by national and international partners.  This also provides UNDP with the great overview  about the work being done by many partners and stakeholders.

In particular, UNDP had previously worked jointly with UN agencies such as UNICEF, WHO, UNRWA to implement several projects for PWDs.

Major donors who contributed to UNDP programme since 2014 are: European Commission, the Government of Japan, KfW and the Government of Finland.

Currently, beside UNDP, UNICEF and WHO are the major UN agencies in addition to ICRC who are having clear dedicated programmes to support PWDs in Syria with different level and volume of interventions as summarised below:

UNICEF: Provision of cash assistance to children with disabilities under social protection programme

WHO: Provision of physical rehabilitation support and capacity development mainly through Ministry of Health.

ICRC: Provision of physical rehabilitation support in collaboration with Syrian Arab Red Crescent (SARC).

Other agencies, although interested, they are providing only random mainstreamed support that is not empowered with the necessary technical and financial support to be defined as PWDs support projects or programme.

South-South and Triangular Cooperation (SSC/TrC)

UNDP will identify applicable models in the area of medical rehabilitation and socioeconomic integration especially the one that provide higher impact and outreach while working on limited resources.

Moreover, UNDP will further enhance SSC/TrC cooperation for innovation and knowledge transfer especially in the field of PWDs rights, Accessibility, PSS and C4D. As an output for the latest participation in the workshops on Innovation for Development (I4D) in Jordan, several networking and dialogues has been already established with partner in Jordan (British council), Lebanon (UNDP Lebanon) and INGO and private sector from Finland.  The project will continue to explore such.

Knowledge

There will be production of communication materials in the form of success stories (stories & videos) to highlight the achievement of PWDs in alignment with the country office communication strategy that will give full acknowledgement and visibility of the Government of Finland, design targeted messages to manage expectations, support monitoring and ensure transparency and accountability.  UNDP will capitalize on previous successful initiatives to engage PWDs themselves after providing them with the required skills through training to conduct the above communication activities.

UNDP will also implement C4D approach to foster social changes in community perception and norms about disability issues. To achieve this, UNDP will provide the required technical, technologically and operationally to promote people centred communication channels e.g. (television programme, community theatre, social media).

Moreover, UNDP will work through capacity building initiative to develop training module, materials and guidelines that can be shared with partners for implementation especially in the accessibility and universal design section.

# Project Management

Cost Efficiency and Effectiveness

The previous five years’ experience in designing and implementing projects to support PWDs in Syria has provided UNDP with a set of lessons learnt and best practices that were concluded immediately and embedded into practice that resulted in better utilization of resources and efforts. Such best practices were clearly seen for example in designing a model for prosthetic workshops that was based on resorting to local capacities and market to assemble the required machinery which resulted in significant saving on establishing budget and allowed for better reach out to beneficiaries by investing more money on providing more prosthetic devices. This model continues to be enhanced for further improvement to scale up the work of UNDP prosthetic projects.

The disability programme unit will coordinate closely with UNDP’s infrastructure portfolio and Early Recovery and Livelihoods sector under the Humanitarian Coordination system (Humanitarian Response Plan) to embed and mainstream activities for enabling the physical environment within the various rehabilitation and reconstruction works (schools, hospitals, shelters, public institutions, public gardens etc.).

Project Management

The project will be managed by Disability Inclusion Unit under the supervision and oversight of Economic Development and Livelihood portfolio at the UNDP Syria country office. The unit is currently consisting of two main staff (Project manger and associate) in addition to one consultant on disability rights (who is a person with disability himself), in addition to one technical officer on physical rehabilitation. For this project, we expect to expand the team by adding one more associate to support the operational processes.

The project will be implemented on the national level in the currently accessible governorates being Rural Damascus, Tartous, Homs, Hama, Aleppo, Qamishli, Deir Ezzor, Latakia, Raqqa, Daraa, as well as Damascus, where UNDP has the presence of field offices including Aleppo And Qamishli hubs both  headed by international staff (P5).

In order to enhance coordination and communication, the project plans to establish a “steering committee composed of “UNDP and the Government of Finland”.  The term of reference of this board is per following:

- Conduct at least one annual meetingto review and discuss the progress, key challenges and way-forward of the whole project.

- Request for and agree on other coordination meetings when needed to discuss progress, urgent matters and/or project revision.

- Each side of the committee will follow-up on recommendations and necessary approvals if needed.

Reporting:

The first annual report will be submitted at the end of March 2021, and a full financial report by the end of June 2022 in accordance with the rules for final financial reporting as part of UNDP’s rules and regulations.

# Results Framework

| Intended Outcome as stated in the UNDAF/Country Programme Results and Resource Framework: Humanitarian Response Plan Syria 2018 Objective 3 Increase resilience and access to services Increase resilience and livelihood opportunities and affected people’s access to basic service, especially among the most vulnerable households and communities. |
| --- |
| Outcome indicators as stated in the Country Programme Results and Resources Framework, including baseline and targets: Outcome 1: Households and communities benefit from sustainable livelihood opportunities, including economic recovery and social inclusion |
| Applicable Output(s) from the UNDP Strategic Plan: Strategic Plan outcome 3: STRENGTHEN RESILIENCE TO SHOCKS AND CRISES |
| Project title and Atlas Project Number: Supporting communities’ resilience through disability inclusion. 00119352 |
| EXPECTED OUTPUTS | OUTPUT INDICATORS (all indicators are gender disaggregated) | DATA SOURCE | TARGETS (by frequency of data collection) | DATA COLLECTION METHODS & RISKS |
|  |  |  | Year 1 | Year 2 | FINAL |  |
| Output 1: PWDs functionality and independence enhanced through physical rehabilitation and psychosocial support Gender mainstreaming at an average 30 % | No. of prosthetic workshop supported for scaling up | UNDP Information management system (IMRP) | 1 | 1 | 2 | Monthly updates from the field, reports from partners |
|  | No. of PWDs benefitting from provision of disability aids (Prosthetic devices) | IMRP | 120 | 155 | 275 | Monthly updates from the field, reports from partners |
|  | No. of PWDs benefitting from provision of disability aids (Wheelchairs, crutches, hearing aids, etc…) | IMRP | 500 | 700 | 1200 | Monthly updates from the field, reports from partners |
|  | No. of PWDs benefitted from physical rehabilitation treatment | IMRP | 320 | 155 | 475 | Monthly updates from the field, reports from partners |
|  | No. PWDs benefitting from PSS services | IMRP | 120 | 155 | 275 | Monthly updates from the field, reports from partners |
|  | No. of capacity development workshops conducted on PSS | IMRP | 0 | 1 | 1 | Monthly updates from the field, reports from partners |
|  | No. of persons benefitted from capacity development (on PSS) | IMRP | 0 | 10 | 10 | Monthly updates from the field, reports from partners |
| Output 2: PWDs socioeconomic integration enhanced through livelihood support in addition to promoting accessibility to labour market and basics services Gender mainstreaming at an average 40 % | 2.1 Number of PWDs benefitted from livelihood support | IMRP | 200 | 270 | 470 | Monthly updates from the field, reports from partners |
|  | 2.2 Number of workshops conducted. (For advocacy and raising awareness on PWDs inclusion and access to employment services with special focus on Private sector and CSR) | IMRP | 1 | 0 | 1 | Monthly updates from the field, reports from partners |
|  | 2.3 Number of workshops conducted. (on accessibility codes for PWDs) | IMRP | 1 | 0 | 1 | Monthly updates from the field, reports from partners |
|  | 2.4 Number of public facilities rehabilitated for PWDs accessibility | IMRP | 2 | 2 | 4 | Monthly updates from the field, reports from partners |
| Output 3: PWDs inclusion enhanced through promoting knowledge sharing, capacity development, awareness raising and innovation Gender mainstreaming at an average 50 % | 3.1 Number of conference / events conducted (to enhance coordination and knowledge sharing on disability issues, | IMRP | 0 | 1 | 1 | Monthly updates from the field, reports from partners |
|  | 3.2 Number of workshops conducted (to develop capacities of stakeholders on the guidelines of CRPD and ICF and linkage to SDGs) | IMRP | 1 | 0 | 1 | Monthly updates from the field, reports from partners |
|  | 3.3 Number of C4D project / campaigns conducted | IMRP | 1 | 0 | 1 | Monthly updates from the field, reports from partners |
|  | 3.4 Number of innovations for inclusion projects implemented | IMRP | 0 | 1 | 1 | Monthly updates from the field, reports from partners |
|  | 3.5 Number of innovative partnerships developed | IMRP | 0 | 1 | 1 | Monthly updates from the field, reports from partners |

# Monitoring And Evaluation

In order to ensure adherence to UNDP policies and regulations, quality, efficiency and relevance to this project document resources and targets, and to identify any reputational risks, safety and security issues, risk of conflict of interest, coercion or corruption associated with individuals or entities implementing project’s activities, the following monitoring modalities will be undertaken:

- Site visits

Undertaken by UNDP Project staff or Hub coordinators to monitor the implementation process, progress, milestones/results, as well as public perception and satisfaction. This will include monitoring and feedback systems with the local community, with regular focus group discussions for data analysis and cross-checking. In addition to collecting stories from the field of individuals who have participated in the project complemented by photos andvideos.

- Data and information management system:

UNDP Syria country office has excelled on data management using their own system called information management reporting platform (IMRP), that in addition to collecting regular entry on results plotted against key indicators, it provides several analytical data for tracking and monitoring progress, adherence and quality of work.

- Third Party Monitoring (when applicable):

Undertaken by a consultant or a private firm or a national/international NGOs recruited by UNDP to monitor field activities according to key indicators.

Monitoring Plan

| Monitoring Activity | Purpose | Frequency | Expected Action | Partners (if joint) | Cost (if any) |
| --- | --- | --- | --- | --- | --- |
| Track results progress | Progress data against the results indicators in the RRF will be collected and analysed to assess the progress of the project in achieving the agreed outputs. | Quarterly, or in the frequency required for each indicator. | Through sites visits, slower than expected progress will be addressed by project management. | NA | NA |
| Monitor and Manage Risk | Identify specific risks that may threaten achievement of intended results. Identify and monitor risk management actions using a risk log. This includes monitoring measures and plans that may have been required as per UNDP’s Social and Environmental Standards. Audits will be conducted in accordance with UNDP’s audit policy to manage financial risk. | Quarterly | Through sites visits, risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | NA | NA |
| Learn | Knowledge, good practices and lessons will be captured regularly, as well as actively sourced from other projects and partners and integrated back into the project. | At least annually | Relevant lessons are captured by the project team and used to inform management decisions. | NA | NA |
| Annual Project Impact and Quality Assurance | The quality of the project will be assessed against UNDP’s quality standards to identify project strengths and weaknesses and to inform management decision making to improve the project. Third party M&E company could be used for this task | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | NA | 10,000 |
| Review and Make Course Corrections | Internal review of data and evidence from all monitoring actions to inform decision making. | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | NA | NA |
| Project Report | A progress report will be presented to the Government of Finland, consisting of progress data showing the results achieved against pre-defined annual targets at the output level, the annual project quality rating summary, an updated risk log with mitigation measures, and any evaluation or review reports prepared over the period. | Annually, and at the end of the project (final report) |  | NA | NA |
| Project Review (Steering Committee - the Government of Finland and UNDP Syria) | The project’s governance mechanism (i.e., project board) will hold regular project reviews to assess the performance of the project and review the Multi-Year Work Plan to ensure realistic budgeting over the life of the project. In the project’s final year, the Project Board shall hold an end-of project review to capture lessons learned and discuss opportunities for scaling up and to socialize project results and lessons learned with relevant audiences. | Specify frequency (i.e., at least annually) | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | Steering Committee (the Government of Finland) | NA |

# Multi-Year Work Plan

| EXPECTED OUTPUTS | PLANNED ACTIVITIES | Planned Budget by Year | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Y1 | Y2 |  | Funding Source | Budget Description | Amount (USD) |
| Output 1: PWDs’ required functionality and independence enhanced to engage in socioeconomic activities Gender marker: Baseline: Limited production capacity of available workshops Over 80,000 PWDs in needs prosthetic services. UNDP supported 200 PWDs with prosthetic services in 2018-2019 UNDP supported 800 PWDs with physical therapy in 2018-2019 UNDP supported 1,700 with disability aids in 2018-2019 One workshop conducted in Japan to develop capacities of social workers from national partner (SARC) on PSS Limited internal and national capacity to conduct and evaluate PSS services Indicators: No. of prosthetic workshop supported for scaling up No. of PWDs benefitting from provision of disability aids (Prosthetic devices) No. of PWDs benefitting from provision of disability aids (Wheelchairs, crutches, hearing aids, etc…) No. of PWDs benefitted from physical rehabilitation treatment No. PWDs benefitting from PSS services No. of capacity development workshops conducted on PSS No. of persons benefitted from capacity development (on PSS) Target: 2 workshops supported (prosthetic workshop) 250 PWDs benefitting from prosthetic services 1,200 benefitting from provision of disability aids (Wheelchairs, crutches, hearing aids, etc…) 450 PWDs receiving physical rehabilitation treatment 250 PWDs benefitting from PSS services 1 capacity development workshop conducted on PSS At least 10 people benefitted from capacity development on PSS Gender mainstreaming at an average 30 % | Activity Result 1.1: PWDs physical and mental wellbeing promoted through provision and strengthening medical rehabilitation and PSS services. Actions: Strengthen the capacity of at least two local prosthetic workshops targeting primarily the newly established workshops in Aleppo and Qamishli in order to support them towards technical sustainability. Provide prosthetic services by supporting at least 4 local workshops in Damascus, Aleppo, Qamishli and Tartous with required materials and assets to sustain their services to the people in need. Provide mobility and disability aids (manual wheelchairs, electric wheelchairs, crutches, walkers, air mattresses and hearing aids) through comprehensive services coupled with case management, PSS and awareness raising. Provide rehabilitation treatment for PWDs in need such as (Physical therapy, Occupational therapy, speech therapy etc) through establishing and/or supporting civil and/or national rehabilitation centers. Provide PSS services for beneficiaries from physical rehabilitation | 50 % | 50 % | UNDP | Finland | Grants | 707,500 |
|  |  |  |  |  |  | Materials | 680,000 |
|  |  |  |  |  |  | Contractual services | 20,000 |
|  | Activity Result 1.2: Internal and partners capacities developed on the PSS for PWDs Actions: Develop UNDP strategy for intervention in the field of PSS with focus on PWDs with the help of expert in the field. Develop capacities of national staff (experts, social workers, programme managers) in the field of PSS with focus on PWDs. Implement PSS activities as part of Activity 1.1 | 50 % | 50 % | UNDP | Finland | Consultant | 40,000 |
|  |  |  |  |  |  | contractual services | 25,000 |
|  | Sub-Total for Output 1: | 1,472,500 |
| Output 2: PWDs socioeconomic integration enhanced through livelihood support in addition to promoting accessibility to labour market and basics services Baseline: Exclusion of PWDs from socioeconomic recovery activities. UNDP provided support to 450 persons including PWDs in 2018-2019 Lack of awareness, interest and attention from private sector towards PWDs rights and roles in socioeconomic recovery Lack of capacity and attention towards accessibility rights of PWDs Lack of access for PWDs to labour market and basic service such as disabled friendly transportation means and accessible facilities Indicators: Number of new job opportunities created for PWDs Number of workshops conducted. (For advocacy and raising awareness on PWDs inclusion and access to employment services with special focus on Private sector and CSR) Number of workshops conducted. (on accessibility codes for PWDs) Number of public facilities rehabilitated for PWDs accessibility Target: 470 PWDs benefitted from livelihood support. One workshop conducted to raise private sector awareness and capacity on CSR One Workshops conducted for developing national capacities on accessibility codes for PWDs 4 public facilities rehabilitated for PWDs accessibility. Gender mainstreaming at an average 40 % | Activity Result 2.1: PWDs employability, capacity and productivity improved Actions: Support local NGOs and CBOs in conducting economic and livelihood support projects, where PWDs and their family members in addition to other vulnerable population will benefit from job opportunities. | 50 % | 50 % | UNDP | Finland | grants | 1,000,000 |
|  |  |  |  |  |  | Contractual services | 410,000 |
|  | Activity Result 2.2: Capacities developed to enhance PWDs access to labour market and basic services. Actions: Facilitate dialogue on inclusive socio-economic strategies under private sector engagement and conduct capacity development initiative on corporate social responsibility (CSR) approaches and socio-economic inclusion. Conduct capacity development on accessibility codes for PWDs | 50 % | 50 % | UNDP | Finland | Contractual services | 110,000 |
|  |  |  |  |  |  | Consultant | 8000 |
|  | Activity Result 2.3: PWDs accessibility promoted for better socioeconomic integration. Implement projects for rehabilitation of public facility with recognized substantive socioeconomic activities in coordination with the national stakeholders. | 50 % | 50 % | UNDP | Finland | Contractual services | 150,000 |
|  | Sub-Total for Output 2 | 1,678,000 |
| Output 3: PWDs inclusion enhanced through promoting knowledge sharing, capacity development, awareness raising and innovation. Baseline: Lack of coordination between national and international partners on disability issues Weakened capacities on international standards for disability issues Social attitude is significantly disabled in terms of PWDs inclusion Invisibility and Increased need to highlights on rights of PWDs Indicators: Number of conference / events conducted (to enhance coordination and knowledge sharing on disability issues, Number of workshops conducted (to develop capacities of stakeholders on the guidelines of CRPD and ICF and linkage to SDGs) Number of C4D project / campaigns conducted Number of innovations for inclusion projects implemented Number of innovative partnership developed Target: One conference / event on disability conducted One workshop conducted on CRPD, ICF and linkage to SDGs One C4D project conducted One project for innovation for inclusion implemented One innovative partnership developed Gender mainstreaming at an average 50 % | Activity Result 3.1: Enhanced knowledge sharing and networking Conduct conference/ workshops to re-enforce data collection and knowledge sharing on disability issues | 50 % | 50 % | UNDP | Finland | Contractual services | 45,000 |
|  | Activity Result 3.2: capacity development on CRPD, ICF and linkage to SDGs Actions: Conduct workshops to develop the capacities of stakeholder on international guidelines on disability such as the convention on the rights of Persons with Disabilities (CRPD), the international Classification of Functioning, Disability and Health (ICF) and linkage to sustainable Development Goals (SDGs) | 50 % | 50 % | UNDP | Finland | Contractual services | 45,000 |
|  | Activity Result 3.3: Awareness about the rights of PWDs raised through C4D intervention Develop one strategy / project document for UNDP C4D on disability Conduct workshops / campaign to raise awareness on the rights of PWDs via C4D interventions | 50 % | 50 % | UNDP | Finland | Contractual services | 100,000 |
|  |  |  |  |  |  | Consultant | 50,000 |
|  | Activity Result 3.4: Innovative and sustainable solution for disability inclusion issue explored Develop one innovative project for disability inclusion Develop one innovative partnership for disability inclusion | 50 % | 50 % | UNDP | Finland | Grant | 115,000 |
|  | Sub-Total for Output 3 | 355,000 |
| Evaluation (as relevant) |  | 10,000 |
| Miscellaneous | Communication, Travel, Equipment | 29,770 |
| Technical assurance (Technical Specialist and project team) |  | 200,000 |
| DPC 10% | 10% | 374,528 |
| General Management Support (GMS) | 8 % | 329,584 |
| TOTAL (USD) |  |  |  |  |  |  |  | 4,449,389 USD(4,000,000 EUR @0.899) |

Governance and Management Arrangement

# Footnotes

http://reliefweb.int/sites/reliefweb.int/files/resources/2016_hno_syrian_arab_republic.pdf

http://applications.emro.who.int/docs/COPub_SYR_3Q_2016_EN_19160.pdf?ua=1

http://reliefweb.int/sites/reliefweb.int/files/resources/2017_Syria_hno_161205.pdf

The World Bank. (2012). Disability: Overview. Webaccessed:http://web.worldbank.org/WBSITE/EXTERNAL/TOPICS/EXTSOCIALPROTECTION/EXTDISABILITY/0,,contentMDK:21151218~menuPK:282706~pagePK:210058~piPK:210062~theSitePK:282699,00.html

http://applications.emro.who.int/docs/COPub_SYR_3Q_2016_EN_19160.pdf?ua=1

Humanitarian Needs Overview 2017 http://reliefweb.int/sites/reliefweb.int/files/resources/2017_Syria_hno_161205.pdf

# Text boxes

Project Organisation Structure

UNDP Area Project Coordinator and team

Project Associate

[UNDP]

Senior Supplier

[Finland]

Project Assurance

[UNDP]

Project Support

[UNDP]

Project Manager

[UNDP]

Executive

[UNDP]

Steering Committee