## AWP 2013_X
ANNUAL WORK PLAN – YEAR 3 ( 1 October 2012 – 30 September 2013)
EXPECTED OUTPUTS Add baseline, indica-tors including annual targets. Please use the numbering of outputs as they are in the RRF/ SRF of ProDoc | PLANNED ACTIVITIES List activity results and associated actions. Please use the numbering of outputs as they are in the RRF/SRF of ProDoc |  | Budget Description | Budget Codes | Responsible party | TIMEFRAME |  |  |  | PLANNED BUDGET
| # | Activity |  |  |  | Q 9 01/10/12 -01/12/12 | Q 10 01/01/13 - 31/03/13 | Q 11 01/04/13 - 30/06/13 | Q 12 01/07/13 - 30/09/13
Objective 1 : To consolidate DOTS framework through strengthening programme management, improving TB case detection and diagnosis and ensuring quality treatment
Number of new smear-positive TB cases notified to the national health authorities during the specified period. Baseline: 2011 – 1,137 Target 2013 - 1,500 Number of all TB cases notified to the national health authorities during the specified period Baseline: 2011 – 3,038 Target 2013- 4,500 Number of staff from district and regional TB laboratories trained in microscopy techniques and culture methods. Baseline: 2012 - 29 Target 2013- 20 Number of direct sputum microscopy investigations for TB diagnosis and treatment monitoring. Baseline: 2011 – 85,755 Target 2013- 94,040 Number of culture investigations (manual technique) for confirmation of TB diagnosis and monitoring of treatment. Baseline: 2011 - 2,198 Target 2013- 6,600 Treatment success rate: new smear positive TB cases. Baseline 2010 – 74% Target 2013- 81% Number of TB patients receiving incentives (food parcels) for better adherence to treatment during out-patient phase of 1st line treatment. Baseline 2011 – 2,274 Target 2013- 2,805 | Activity 1.1 :Strengthening management, coordination, monitoring and evaluation of the National Tuberculosis Programme
| 1.1.1 | Training of NTP management staff by attending international conferences abroad (2 participants per year) | Attendance of training courses in various aspects of NTP management and international conferences abroad (Warsaw and Sondalo training courses, European NTP managers' meetings, IUATLD conferences, etc.). Funding for 2 people attending 1 event per year. | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 9604
| 1.1.2 | Training of NTP Regional Units' staff in supervision, monitoring and evaluation | Training for staff of 5 Regional (velayat) NTP Units will be conducted at the NTP Central Unit in different aspects of NTP management (in particular in supervision, monitoring and evaluation) to strengthen capacities of NTP RUs and support decentralization / regionalisation of the NTP management. (10 participants, 1 training in Y3 -Y4) | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 2620
| 1.1.3 a | Quarterly supervision visits by the central NTP Unit ,1 round ( 3 specialists for 3 days in each of 5 regions) | Supervision visits will be conducted by the NTP Central Unit team to 5 velayat centres and selected districts (etraps): quarterly during Years 3-5. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 13470.62
| 1.1.3 b - new | Quarterly monitoring meetings to discuss the results of monitoring visits | To discuss the key findings, plan the next steps and ensure effective implementation of recommendations of supervision / monitoring visits, quarterly meetings will be held at the CTTP. Participants: representatives of the MOH, regional Departments of Health, Ashgabat City Department of Health, CTTP, regional NTP units, Medical Department of the MoI, NRCS, and the UNDP/GF GIU staff. There will be 12 meetings in total (4 per year, in 2013-2015). | M&E IA Code: 001981 Account: 71600 | UNDP |  | x | x | x | 3330
| 1.1.4 | Support to regional (velayat) NTP supervision | Regional (velayat level) supervision visits will be conducted by 5 Regional NTP Units to TB service and PHC facilities in peripheral districts.Visits will be done using the vehicles procured in Phase1, therefore, no budget is needed. | M&E IA Code: 001981 Account: 71600 | UNDP | x |  |  |  | 2466.97
| 1.1.6-new | Procurement of PCs for statistics cabinets of the regional TB hospitals | 5 PC's will be procured for statistical units of the 5 regional TB hospitals, especially in view of the plans to introduce electronic TB manager. | IF IA Code: 001981 Account: 72400, 72800 | UNDP | x |  |  |  | 8567
| 1.1.8 a-new | Procurement of air conditioner for the training center at Balkanabad Regional TB Hospital | 1 air conditioner will be procured for Balkanabad Regional TB hospital | IF IA Code: 001981 Account: 72200 | UNDP | x |  |  |  | 668
| 1.1.8 b-new | Refurbishment of training centers at Lebap and Balkan Regional TB Hospitals | Basic refurbishment is planned for training centers at Lebap ( separate a space within that hall and make minor repairs such as refresher pargeting and painting) and Balkan regions. | IF IA Code: 001981 Account: 72100 | UNDP |  | x |  |  | 17097.57
| 1.1.8 c- new | Procurement of 5 printers for regional training facilities. | 5 printers will be procured for 5 regional training centers. Cost assumption is $300 per printer. | IF IA Code: 001981 Account: 72400 | UNDP |  | x |  |  | 1500
| 1.1.9 | Operational expenses of the NTP Central Unit and Regional Units, 5 % price increase is forecasted starting from Y4 | Operational expenses of the NTP Central Unit and Regional (velayat) Units (communication expenses, internet / e-mail stationery, printing, etc.) | OVER IA Code: 001981 Account: 72500, 74200 | UNDP | x | x | x | x | 10250.6
| 1.1.11 | Training of NTP and TB service staff in upgraded TB recording and reporting system | Staff from the Central and Regional (velayat) NTP units, and key TB service facilities will be trained in the use of revised recording and reporting forms and database management. (15 participants,2 trainings in Y3 - Y5, totally 90 participants) | TR IA Code: 002066 Account: 75700 | WHO |  |  | x | x | 8538
| 1.1.12 | Recruitment of national IT specialist for the management of the national TB database | Local IT specialist will be contracted to assist the NTP in management and maintenance of the national electronic TB database (starting Year 3). | HR IA Code: 002066 Account: 71400 | WHO |  | x | x | x | 6300
| 1.1.13 | Printing of recording and reporting national TB forms | Revised recording and reporting forms and registers will be printed at the end of Year 3 (in quantities sufficient for 2 years) and distributed to all TB service delivery sites. Y3 needs were printed in Phase 1. | M&E IA Code: 001981 Account: 74200 | UNDP |  |  |  | x | 16465.3816
| 1.1.14 | Cost of revision and Russian-Turkmen translation of training materials | Training materials will be developed or revised for all training activities and made available in 2 languages (Turkmen, Russian). | P&A IA Code: 002066 Account: 71300 | WHO |  | x |  |  | 5050
| 1.1.15 a | Conduct M&E training session for TB specialists from 5 velayats and Ashgabat at central level | M&E specialists at central and regional level will be trained and retrained on M&E (18 participants,1 training in Y3 and Y5). | TR IA Code: 002066 Account: 75700 | WHO |  | x |  |  | 5100
| 1.1.5 b-new line | Printing of Ministry of Health order #109, which is a key document regulating all aspects of TB control in Turkmenistan | The new Order #109 includes updates on TB diagnostics, as well as control of MDR-TB. It is requested to print 1000 copies of the Order to distribute among central, regional and district level TB facilities; Ministry of Health and regional departments of health; TB department of Turkmen State University; PHC facilities, Sanitary-Epidemiology Service staff at all levels. The cost estimate is based on the market research done in September 2012. Unit cost $12.00 (1 order of approx.528 pages of A5 format , in Turkmen and Russian languages)*1000 units=$12,000. | P&A IA Code: 001981 Account: 74200 | UNDP |  | x |  |  | 12000
| 1.1.16 -new | External assessment of the TB surveillance system | Lumpsum of $100,000 was allocated for an external assessment of the completeness and quality of the national TB surveillance system and data to improve the estimates and trends of TB burden in the country and measurement of impact. | M&E IA Code: 002066 Account: 71200 | WHO |  |  | x |  | 100000
| 1.1.17 a - new | Development of the National TB M&E Plan | The National M&E Plan is required to provide a framework for implementing and strengthening systems and resources to monitor and evaluate the activities, outcomes, and impact of TB control interventions for years 2013-2015. The Plan will be developed with the assistance of an external consultant and a national expert. The draft Plan will be discussed at a workshop and presented for approval to the Government. | TA IA Code: 002066 Account: 71200 | WHO |  | x |  |  | 9490
| 1.1.17 b- new | Printing of the National TB M&E Plan | Translation and printing of 500 copies of National TB M&E Plan. | P&A IA Code: 001981 Account: 74200 | UNDP |  | 3940 |  |  | 3940
| 1.1.18 a- new | Development of monitoring check-lists for in-patient and out-patient TB facilities | It has been recommended by MESS workshop in September 2012 to develop separate check-lists for in-patient TB facilities and for out-patient facilities (TB cabinets) because of different scope of work and, respectively, different aspects to be monitored. In particular, the new check-lists will include specific component on infection control. 2 national experts will revise the check-lists #2B and 4. Separate check-lists will be developed, including IC and other relevant aspects by type of facility. | TA IA Code: 002066 Account: 71300 | WHO |  |  | x |  | 2400
| 1.1.18 b- new | Development of separate check-lists for monitoring of peripheral (district level) and regional (velayat level) laboratories | Currently lab services are monitored using the check-list #1. However, in view of upgrade of regional labs for culture and DST, it is required to develop check-lists for monitoring of microscopy labs (district level) and culture and DST (velayat level). The existing check-list #1 will be divided to 1A and 1B and updated to incorporate new methods available at regional reference labs. 2 national experts will revise check-list #1 and develop check-lists 1A and 1B. | TA IA Code: 002066 Account: 71300 | WHO |  |  | x |  | 2400
| 1.1.19- new | Technical assistance in revising definitions and TB recording and reporting forms in accordance to the latest WHO recommendations | In 2012, WHO issued the new recommendations for revision of the definitions of TB cases and treatment outcomes (for both sensitive and drug resistant TB cases) and proposed relevant changes in routine country recording and reporting systems. Technical assistance (by an external consultant and local expert) will be contracted in implementation of the new guidance and adjusting the existing recording and recording forms (in Year 1). | TA IA Code: 002066 Account: 71200 | WHO |  |  |  | x | 9090
Activity 1.2 : Strengthening capacities for TB control in the penitentiary sector
| 1.2.1 | Recruitment of international consultant to provide technical assistance to improve accessibility of quality TB diagnosis and treatment for detainees in Y3. | In Year 3, technical assistance (by an external consultant) will be provided to the Medical Department of the Ministry of Internal Affairs to follow up recommendations of the TA in Phase 1, and planning further interventions to improve accessibility of quality TB diagnosis and treatment for detainees, in line with the human right approach. | TA IA Code: 002066 Account: 71200 | WHO |  |  | x |  | 12449
| 1.2.2 | Training in TB management in prisons by attending international conferences abroad | Attendance of training courses in various aspects of TB control in prisons, international conferences abroad and study tours. (3 participants, 1 event in Y3-Y5) | TR IA Code: 002066 Account: 75700 | WHO |  |  | x |  | 15606
| 1.2.3 | Conduct quarterly supervision visits by the Medical department of MIA to the TB treatment site in the penitentiary sector (Mary Prison hospital MRK-15) | Quarterly supervision visits will be conducted by the Medical Department of the Ministry of Internal Affairs to the TB treatment site in the penitentiary sector (Mary velayat) and selected detention sites including pre-trial isolators to monitor case finding and case management practices. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 2040
| 1.2.8 a - new | Monitor for stationary X-ray machine for Mary Prison Hospital | It is planned to procure monitor for the stationary X-Ray equipment which was procured in 2011 for Mary Prison Hospital with the GF grant, as the radiologist who performs investigation is located in a separate room, and monitor is required for control of the X-Ray procedure. | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 14149
| 1.2.8 b-new | PSM costs for monitor for x-ray for Mary Prison Hospital | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700 | UNDP |  | x |  |  | 3077.4075
Activity 1.3 : Strengthening TB laboratory network
| 1.3.1 b | Conduct training of TB regional laboratory staff on conducting culture investigations | Training of staff of regional microscopy laboratories will be conducted at the NRL on culture investigations (1 training in Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO |  |  | x |  | 9062
| 1.3.2 a | Procurement of Reagents for Ziel-Nelsen Microscopy : Sputum smear microscopy investigations | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). ZN was calculated as 75% of this amount, 25% will be done with LED. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 17027.8228
| 1.3.2 c | PSM costs for Reagents for Ziel-Nelsen Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 3703.5515
| 1.3.2 b | Procurement of Reagents for LED Microscopy (Sputum smear microscopy investigations) | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). LED was calculated as 25% of this amount, 75% will be done with ZN. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 9132.8513
| 1.3.2 d | PSM costs for Reagents for LED Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1986.3952
| 1.3.3 a | Procurement of Reagents for Culture investigations (manual technique) | Culture investigations (manual technique on solid media) will be performed by the NRL and regional laboratories in Balkanabad,Lebap and Mary, and later in Dashoguz regions. For confirmation of TB 2 tubes and for monitoring of 1 line treatment -2 tubes,at the end of intensive phase (2-3 months), at 4-5 months and at the end of treatment. In 2013 the need in culture investigations is 11,980. It is estimated that the NTP can cover only 50% of this amount (5,990). In 2014 the esitmated need is 12,220 and the expected coverage - 70% or 8,554 .In 2015, the estimated need is 12,850 and the NTP should be able to perform 80% of the need, or 10,280. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 17047.8
| 1.3.3 b | PSM costs for reagents for Culture investigations (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 3707.8965
| 1.3.7 a | Procurement of respirators for staff of TB laboratories (Individual measures for infection control) | Procurement of high protection respirators to ensure individual measures of infection control at TB laboratories. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 6219.2
| 1.3.7 b | PSM costs for respirators for staff of TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1352.676
| 1.3.8 a - new line | Development of Standard Operating Procedures (SOPs) for cultural and molecular diagnostic tests and Drug Susceptibility Testing. | 2 national experts will develop SOPs (based on SOPs already developed in other countries). SOPs will be revised by the Supra-National Lab in the Netherlands. Training on SOPs will be done within the lab training program planned for phase 2. | TA IA Code: 002066 Account: 71300 | WHO |  |  | x |  | 5640
| 1.3.8 b-new line | Printing and translation of Standard Operating Procedures (SOPs) for cultural and molecular diagnostic tests and Drug Susceptibility Testing. | Translation from Russian to Turkmen and to English will be provided. 100 copies will be printed. | P&A IA Code: 001981 Account: 74200 | UNDP |  |  |  | x | 5500
Activity 1. 4 Improving TB case management
| 1.4.3 | Conduct training for TB nurses using standard DOTS module | DOTS initial training and refreshing training of nurses from TB service institutions (15 participants, 1 training in Y3, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 2515
| 1.4.4 | Recruitment of international consultant to provide technical assistance to NTP in strengthening TB drugs' management in Y3 | Technical assistance (by an external consultant) will be provided to the NTP to strengthen the drug management system including forecasting, ordering, storage, stock monitoring, distribution, monitoring and management of side effects). 1 mission in Y3 | TA IA Code: 002066 Account: 71200 | WHO |  | x |  |  | 13049
| 1.4.5 | Conduct training in TB drugs' management by the NTP Central Unit for TB specialists, key staff and drug managers from the regional level | Training in anti-TB drugs' management will be provided by the NTP Central Unit for TB specialists and drug managers (15 participants, 2 trainings in Y3- Y4) | TR IA Code: 002066 Account: 75700 | WHO |  |  | x | x | 7410
| 1.4.6 b -new | Procurement of air conditioners for drug storage spaces at the DOTS cabinets to ensure adequate temperature for storage of TB drugs. | Procurement of air-conditioners for drug storage spaces at the DOTS cabinets is required to ensure adequate temperature for storage of TB drugs. As per NTP data, there are 160 service delivery points at district level of TB care. The unit price for air-conditioner is about $315. The required budget is therefore 160 * $315 = $50,400 | IF IA Code: 001981 Account: 72200 | UNDP |  |  |  | x | 50400
| 1.4.7 a | Procurement of First Line Anti-TB Drugs , 5 % price increase is forecasted starting from Y4 | 1 line TB drugs will be procured for : Y3 - 4,500 patients (civil- 3,300 and penal- 1,200), Y4- 4,600 patients (civil-3,400 and penal -1,200), Y5- 4,600 patients (civil-3,500 and penal-1,100). For civil patients 87%- I, III category and 13%- II category. For penal patients 50%-I, III category, 50%-II category. | MED IA Code: 001981 Account: 72300 | UNDP |  |  |  | x | 77550.131
| 1.4.7 b | PSM costs for First Line Anti-TB-Drugs (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  |  | x | 19387.5327
| 1.4.8 a | Procurement of (food parcels) for TB patients,as incentives (support to treatment adherence), 5 % price increase is forecasted starting from Y4 | TB patients on 1line treatment during continuation phase receive monthly food parcels. I, III category- 4 parcels per treatment course, II category - 5 parcels per treatment course. The coverage with support is 85%. | LS IA Code: 001981 Account: 72300 | UNDP | x | x |  |  | 344458.66
| 1.4.8 b | Salary of NRCS personnel (project coordinator,project assistant, 5 patronage nurses) 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. [delivery of food packages to DOTS cabinets and monitoring] | The National Red Crescent Society hired staff in Ashgabat and all regions to implement patient support countrywide. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | x | x | x | x | 36843.1776
| 1.4.8 c | Transportation of parcels до DOTS cabinets.[delivery of food packages to DOTS cabinets ] | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | x | x | x | x | 40427.1
| 1.4.8 d | Quarterly monitoring visits by central NRCS [delivery of food packages to DOTS cabinets and monitoring] | Central level of NRCS will conduct quarterly monitoring visits to verify reporting on number of patients receiving food parcels ( 3 days, 2 person to 2 regions) | M&E IA Code: 005742 Account: 71600 | NRCS | x | x | x | x | 8397.6211
| 1.4.8 e | Monthly monitoring visits by regional NRCS [delivery of food packages to DOTS cabinets and monitoring] | Regional level of NRCS will conduct monthly verification of number of patients receiving food parcels, survey on patient satisfaction, and provision of consultation to TB specialists on distribution of food parcels (3 days, 1 person, 2 etraps per month) | M&E IA Code: 005742 Account: 71600 | NRCS | x | x | x | x | 16236.1579
| 1.4.8 f | Procurement of 2 PCs for patronage nurses in Dashoguz and Mary regions .[delivery of food packages to DOTS cabinets and monitoring] | Office equipment is required for reporting and administrative needs, considering the increased workload compared to Phase 1( MDR-TB patients support is added) | IF IA Code: 001981 Account: 72400, 72800,74700 | UNDP |  | x |  |  | 2836.1667
| 1.4.8 g | Internet and telephone communication for NRCS personnel at 5 velayats and Ashgabat.[delivery of food packages to DOTS cabinets and monitoring] | Operational expenses of NRCS (communication expenses, internet) will be covered. | IF IA Code: 005742 Account: 72400 | NRCS | x | x | x | x | 1684.2105
| 1.4.8 h - new line | Procurement of furniture for NRCS patronage nurses offices | Furniture set ( table and cabinet) will be procured for Ashgabat and 4 regional NRCS offices. | IF IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 1755
| 1.4.8 i-new line | Printing of journals for registration of TB patients receiving parcels | Total 90 journals planned to be printed for DOTS cabinets in all regions. | P&A IA Code: 001981 Account: 74200 | UNDP |  | x |  |  | 2684.7
| 1.4.9 a- new | Procurement of medical scales for TB facilities. | Mechanical medical scales will be procured for 5 regional TB hospitals (2 per hospital - 1 for MDR-TB and 1 for other patients), 56 district TB facilities (1 for each), and 11 for penitentiary TB facilities, totally 77 scales (estimated cost US$ 430 including delivery costs). | HP IA Code: 001981 Account: 72200 | UNDP |  |  | x |  | 27194.86
| 1.4.9 b- new | PSM costs for procurement of medical scales | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700 | UNDP |  |  | x |  | 5914.882
| 1.4.9 c- new | Development of guidance on quantification and inventory for sputum smear microscopy reagents and consumables. | Lab specialists performing sputum smear microscopy need written guidance on quantification and inventory for reagents and consumables for Ziehl-Neelsen and luminescent methods. 2 national experts will develop the guideline and practical instructions based on internationally recommended practices. Training will be done within the lab training program planned for phase 2. | TA IA Code: 002066 Account: 71300 | WHO |  |  | x |  | 2400
| 1.4.9 d-new | Printing of guidance on quantification and inventory for sputum smear microscopy reagents and consumables. | 250 copies of guidance will be printed. Unit cost is estimated as $10. | P&A IA Code: 001981 Account: 74200 | UNDP |  |  |  | x | 2500
Activity 1.5 :TB advocacy, communication and social mobilisation (ACSM)
| 1.5.3 | Conduct training workshops for mass media representatives on priority issues of TB control. | Training workshops will be organised for mass media representatives in priority issues of TB control to enhance public awareness and social mobilisation for effective TB control. 1 workshops will be organised for 20 participants in Y3-Y5, before the World TB day. | TR IA Code: 004520 Account: 75700 | Health Information Center |  | x |  |  | 910
| 1.5.4 | Development and printing of TB informational and educational materials. | During Y3, the materials will be redeveloped and printed for 3 and 4. Additionally, the materials will be printed in Y5. | COM IA Code: 001981 Account: 74200 | UNDP | x |  |  | x | 31519.72
| 1.5.5 | Design, produce and broadcast TB informational and educational materials: video (10% increase forecasted starting from Y4) | Video spots will be designed, produced and broadcasted that will aim at increasing public awareness and social mobilisation for better TB control (in Y3-Y5). | COM IA Code: 004520 Account: 74200 | Health Information Center |  |  |  | x | 3000
| 1.5.6 | Operational costs for TB Resource Center at the Ministry of Health Information Centre (5 % increase is forecasted starting from Y4) | Operational expenses of TB resource center (communication expenses, internet) will be covered. | IF IA Code: 004520 Account: 72400 | Health Information Center | x | x | x | x | 12442.35
| 1.5.7 a | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | COM IA Code: 004520 Account: 74200 | Health Information Center |  | x |  |  | 2674.4311
| 1.5.7 b | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | TR IA Code: 004520 Account: 75700 | Health Information Center |  | x |  |  | 2047.5
| 1.5.7 c- new | Informational and educational events and activities, including seminars and round-tables for public associations, media and educators | It is planned to conduct 4 trainings and 1 round table per quarter | TR IA Code: 004520 Account: 75700 | Health Information Center | x |  |  |  | 6211.56
| 1.5.8 | Training workshops for community leaders on TB control | Trainings workshops for community activists will be held to generate public awareness and raise social commitment at community level for fighting TB, with emphasis on reducing TB-related stigmatization and using community and family levers to motivate the patients to complete treatment and avoid the development of drug resistance. NRCS will train 100 people per year (13 participants, 8 trainings in Y3-Y5). | TR IA Code: 005742 Account: 75700 | NRCS |  | x | x | x | 17765.15
Activity 1.6 Collaborative activities for control of TB / HIV co-infection
| 1.6.4 | Training of TB service staff in diagnostic counselling and testing (DCT) for HIV | It is planned to train 90 TB specialists from all velayats and penitentiary sector in HIV diagnostic counselling and testing (DCT) among TB patients in order to improve access to and quality of the service.(15 participants,1 training in Y3, 3 trainings in Y4, 2 trainings in Y5) | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 3469
Objective 2 :To improve the health system performance for effective tuberculosis control
Number of TB and PHC services staff (doctors and nurses) trained and re-trained in DOTS, drug management and MDR-TB management. Baseline: 2011 – 1,168 Target 2013 - 300 | Activity 2.1 Strengthening Primary Health Care involvement in TB control
| 2.1.2 - new | The new national guidelines on TB control for PHC providers will be printed at the beginning of Year 2 and further distributed during training (number of copies needed: 6,000). | Cost of 1 copy: $ 3.0; totally $ 18 000 (in Year 2) for 6000 copies | P&A IA Code: 001981 Account: 74200 | UNDP |  |  | x |  | 18000
| 2.1.3 | Conduct training of trainers for further training of PHC providers on TB control (20 participants in Y3) | The national team of trainers will be strengthened by conducting in-depth training at the NTP Central Unit for selected TB specialists from the regions (velayats) who will further conduct training for PHC providers on TB control. Totally 20 persons will be trained in Year 3. | TR IA Code: 002066 Account: 75700 | WHO |  | x |  |  | 15038
| 2.1.4 | Conduct training of PHC doctors from all regions in TB control (3 days, 20 participants, Q9 - 6 trainings ; 3 days, 15 participants Q11- 1 training, Q 12 - 1 training; Y4-8 trainings, Y5-8 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants, Y3- 6 trainings. Will include general doctors from the penitentiary sector. 1,060 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | x |  | x | x | 27812
| 2.1.5 | Conduct training of PHC nurses from all regions and penitentiary sector in TB control (3 days, 20 participants, Q9-6 trainings; 3 days, 15 participants Q11- 2 training, Q 12 - 1 training; Y4-8 trainings, Y5- 5 trainings) | It is planned to train PHC nurses from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants,Y3- 6 trainings). 1,030 PHC nurses will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | x |  | x | x | 30975
| 2.1.6 a | Printing TB suspects' logbooks for PHC institutions (TB 15) | TB suspects' logbooks (form TB-15) for family doctors will be printed and distributed among PHC institutions. 6000 copies (based on the number of PHC doctors in the country). | P&A IA Code: 001981 Account: 74200 | UNDP |  |  |  | x | 3621.0526
| 2.1.6 b -new | Printing of algorithm for PHC doctors (standard plan of treatment of TB patient) | It is requested to print additional 5000 copies of algorithm. Copies will be distributed to PHC doctors, administration of PHC facilities and TB facilities. Some copies will be reserved for distribution in 2014-2015 for new PHC doctors. Cost estimate is based on the previous similar procurement done in 2011 adjusted to the price fluctuation advised by supplier. The estimated unit cost is $1.03* 5,000 units=5,150. | P&A IA Code: 001981 Account: 74200 | UNDP |  | x |  |  | 5150
| 2.1.8-new | Monitoring of effectiveness of PHC trainings on DOTS | Members of the HSS working group will conduct mini-assessment of effectiveness of the PHC trainings. They will conduct visits to 3 velayats semiannually in Y3-Y4 and once in Y5. Trained PHC staff will be surveyed with the post-test questionnaire with aim to assess how the knowledge "survives" after 3,6, 12 months following training, how the PHC doctors use the knowledge in the daily practice, what gaps remain. The results will be communicated to the trainers and used for adjustment of training modules. | M&E IA Code: 002066 Account: 71600 | WHO |  |  | x | x | 2957.3333
Activity 2.2 Strengthening key health system functions for effective TB control
| 2.2.3 | Recruitment of international consultant to provide technical assistanceto the MOHMI and NTP in improving hospital performance in TB control in Y3 | TB hospitals have to develop and implement IC plans.Technical assistance (by an external and a local expert) will be provided to the Ministry of Health and NTP in improving effectiveness, efficiency and safety (with particular emphasis on infection control in TB hospitals for preventing cross-contamination and development of drug resistance) in in-patient TB hospitals and departments.One consultancy mission is planned in Y3. | TA IA Code: 002066 Account: 71200 | WHO |  | x |  |  | 14251
Activity 2.3 : Introducing Practical Approach to Lung Health (PAL)
| 2.3.2 | Recruitment of local consultant to provide technical assistance in monitoring and evaluation of PAL implementation in the pilot area in Y4 | Local consultant will monitor implementation of PAL activities in the pilot regions. Cost includes fees, travel to pilot areas. | TA IA Code: 002066 Account: 71300 | WHO |  | x | x | x | 6000
| 2.3.3 | Printing of national PAL guidelines | The national guidelines on PAL will be printed (in Year 3) and distributed among all PHC providers: 5,000 copies. | P&A IA Code: 001981 Account: 74200 | UNDP |  |  |  | x | 40043.8596
| 2.3.4 | Organize national workshops for the introduction of PAL inpilot regions, evaluation and further planning | One national workshops will be organised in Years 3 to evaluate project progress, plan future actions and develop recommendations to MOH and NTP for expansion of the approach in the country. | TR IA Code: 002066 Account: 75700 | WHO |  |  | x |  | 10924
Objective 3 :To introduce and expand access to diagnosis and treatment of drug-resistant tuberculosis
TB cases with results for diagnostic drug susceptibility testing for MDR-TB among those eligible Baseline: 2011 – 40.5% Target 2013- 48% Confirmed MDR-TB cases enrolled on treatment: Laboratory-confirmed MDR-TB cases enrolled on 2nd line anti-TB treatment during the specified period of assessment (number) Baseline: N/a Target 2013- 92 Number of MDR-TB patients on out-patient treatment receiving patient support (food incentives) for better adherence to treatment. Baseline: N/a Target 2013- 17 | Activity 3.1.Strengthening national capacities for management of drug-resistant tuberculosis
| 3.1.1 | Support to the Green Light Committee operations (GLC Fee) | GLC monitoring missions and operational support to the GLC in accordance to agreement between the GLC and the Global Fund ($25,000 per year) | P&A IA Code: 001981 Account: 72100 | UNDP |  | x |  |  | 25000
| 3.1.2 | Recruitment of international consultant to provide technical assistance in DR-TB management in Y3 | Technical assistance (by external consultants) will be provided on various aspects of the DR-TB management, such as laboratory diagnosis, clinical management of DR-TB cases, organization of treatment and follow-up during continuation phase, DR-TB treatment in the penitentiary sector, infection control planning (1 mission in Y3). | TA IA Code: 002066 Account: 71200 | WHO |  |  |  | x | 16793
| 3.1.4 | Conduct TOT on DR-TB management | TOT will be conducted to train national trainers, who will then train TB and PHC specialists In their respective regions (20 participants , 1 training in Y3). | TR IA Code: 002066 Account: 75700 | WHO |  | x |  |  | 15038
| 3.1.5 | Conduct local training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff from DR-TB treatment delivery sites | Training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff DR-TB treatment delivery sites (15 participants,2 trainings in 2013. | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x | x | 10420
| 3.1.6 | Conduct local training in MDR-TB management for Primary Health Care services, who will be involved in follow-up of DR-TB patients | Training in MDR-TB management for staff from PHC service who will be involved in follow-up of MDR-TB patients during out-patient phase of treatment with special emphasis on psychosocial support to ensure adherence. 15 participants,2 trainings in 2013. | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x | x | 6580
| 3.1.7 | Conduct training for staff from MDR-TB treatment sites and regional laboratories for infection control | Local training on infection control will be organised for staff from MDR-TB treatment delivery sites and regional laboratories: totally 120 persons to be trained (20 participants, 1 training in 2013). | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 4394
| 3.1.9 a | Renovation of regional reference laboratory in Dashoguz region | Support to infrastructure rehabilitation of the newly established regional reference laboratories which will be involved in DR-TB surveillance and diagnosis in Dashoguz (during Year 3), for ensuring proper workflow amd infection control including installation of the external negative pressure ventilation system. | IF IA Code: 001981 Account: 72100 | UNDP |  |  |  | x | 395154
| 3.1.9 b -new | Procurement of tools for monitoring engineering measures of Infection Control (airflow, UV) | Procurement of anemometers, UV-radiometers and analyzers of voltage for Centre for TB Treatment and Prophylaxis, 5 regional TB hospitals, Project monitoring, Turkmenmedtechnika. | IF IA Code: 001981 Account: 72200, 74700 | UNDP | x |  |  |  | 10411.15
| 3.1.10 a | Procurement of equipment for regional reference laboratory in Dashoguz region | A standard set of laboratory equipment will be procured for the newly established regional reference laboratories Dashoguz (delivery in Year 4). | HP IA Code: 001981 Account: | UNDP |  | x |  |  | 62223.1788
| 3.1.10 b | PSM costs for equipment for regional reference laboratory in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 13533.5414
| 3.1.10 c | Procurement of furniture for regional reference laboratory in Dashoguz region | A standard set of laboratory furniture will be procured for the newly established regional reference laboratories Dashoguz (delivery in Year 4). | HP IA Code: 001981 Account: | UNDP |  |  |  | x | 47633
| 3.1.10 d | Transportation of furniture for regional reference laboratory in Dashoguz region | Transportation costs of 16.53% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  |  | x | 7873.7349
| 3.1.11 | Recruitment of international consultant for the development of Infection Control (IC) plans for MDR-TB sites and bacteriological laboratories in Y3 -Mary and Turkmenabad, Y4- Dashoguz | Technical assistance will be provided for development of IC plans at the regional TB laboratories of BSL 3. Cost includes consultant fees, travel to the regional laboratories and translation costs. | TA IA Code: 002066 Account: 71200 | WHO |  | x | x |  | 36682
| 3.1.13 | Training of NRCS personnel in infection control | Local training on infection control will be organised for the NRCS staff working with the MDR-TB patients (12 participants, 1 training in 2013) | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x |  | 2244
Activity 3.2 Drug resistance surveillance and diagnosis of drug-resistant TB cases
| 3.2.5 a | Procurement of automated MGIT technology (including installation) equipment for DR-TB diagnosis for Dashoguz region (isolation of strains in liquid culture) | Procurement of automated MGIT technology equipment for rapid isolation of strains and liquid culture for accelerated DST to 1st line drugs (BD Bactec MGIT 960 System instrument): 1 machine will be procured for Dashoguz (Year 3). | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 44455.5
| 3.2.5 b | MGIT technology equipment 12 month service contract | Maintence cost is budgeted for 4 MGIT machines ( 3 - procured within Grant and 1 -previously already in place at NRL). | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 37060
| 3.2.5 c | PSM costs for MGIT technology in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 17729.6213
| 3.2.6 a | Procurement of laboratory equipment for DR-TB diagnosis (molecular line probe assay, PCR GenoType MTBDR Plus technology) for Dashoguz region | Procurement of equipment for DR-TB diagnosis (molecular line probe assay, PCR GenoType MTBDR Plus technology), 1 machine will be procured for Dashoguz . | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 14334.8344
| 3.2.6 b | PCR GenoType equipment 12 month service contract | Maintence cost is budgeted for 2 PCR machines. | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 1433.4857
| 3.2.6 c | PSM costs for PCR GenoType MTBDR Plus technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 3429.6096
| 3.2.7 a | Procurement of GeneXperts for Balkan and Ahal regional TB laboratories | 1 GeneXpert machines will be procured for Balkan and 1 for Ahal regional TB hospitals for rapid identification of TB and resistance to rifampicin | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 44286.6095
| 3.2.7 b | GeneXpert 12 month service contract | Maintence cost is budgeted for 6 GeneXpert machines. | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 13285.9829
| 3.2.7 c | PSM costs for GeneXperts for Balkan and Ahal regional TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 12522.0388
| 3.2.8 a | Culture and DST to 1st line drugs for DR-TB diagnosis (automated MGIT technique) | Culture investigations (automated technique on liquid media) will be performed by the NRL and regional laboratories.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 21832.9524
| 3.2.8 b | PSM costs for Culture and DST to 1st line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 4748.6671
| 3.2.9 a | DST to 1st line drugs (manual technique) | DST to 1st line drugs will be performed in culture-positive cases using manual technique on solid media, for quality assurance of automated MGIT technique.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 886.44
| 3.2.9 b | PSM costs for DST to 1st line drugs (manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 192.8007
| 3.2.10 a | Tests for rapid identification of R/H resistance | Identification of strains and express testing for R/H resistance to be performed by the NRL and regional laboratories. In 2013 the estimated number of tests is 1380, in 2014 -2040, 2015-2400. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 22563
| 3.2.10 b | PSM costs for tests for rapid identification of R/H resistance (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 4907.4525
| 3.2.11 a | Tests for rapid detection and MDR screening, GeneXpert technology | Procurement of supplies for tests by automated sample processing, detection of M. tuberculosis and screening for R resistance (GeneXpert technology).In 2013 the estimated number of tests is 2490, in 2014 -3540, 2015-3980) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 29940
| 3.2.11 b | PSM costs for rapid detection and MDR screening GeneXpert technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 6511.95
| 3.2.12 | Cost of missions of SRL experts to the NRL in Ashgabat. | Visits of SRL (National Mycobacteria Reference Laboratory, National Institute of Public Health and the Environment, Bilthoven, The Netherlands) to the NRL with the scope of technical assistance and external laboratory quality assurance (1 mission per Y3-Y5) | TA IA Code: 002066 Account: 71200 | WHO |  |  | x |  | 9897
| 3.2.13 | Cost of on-site training of NRL specialists at the SRL, | NRL specialists will visit the SRL in Bilthoven, Netherlands, for for in-depth on-site training on new techniques (1 trainining for 3 participants per Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 15204
| 3.2.14 | External laboratory quality assurance: shipment of strains to the Supranational Reference Laboratory | With the scope of external laboratory quality assurance of DST to 1st line and 2nd line TB drugs in support of the DR-TB management programme, strains will be shipped quarterly to the Supranational Reference Laboratory (SRL) in Bithoven, Netherlands. | P&A IA Code: 001981 Account: 72100 | UNDP | x | x | x | x | 13100
Activty 3.3 Treatment of drug-resistant TB cases
| 3.3.1 a | Procurement of reagents for culture investigations for MDR-TB patients on treatment (manual technique) | Cultures by manual technique on solid media will be performed for monitoring of treatment of MDR-TB patients.Calculations were done based on National MDR-TB Protocol. In 2013 the estimated number of tests is 660, in 2014 -2244, 2015-4356. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 1894.2
| 3.3.1 b | PSM costs for reagents for culture investigations for MDR-TB patients on treatment ,manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 411.9885
| 3.3.2 a | Procurement of reagents for DST to 2nd line drugs for DR-TB patients on treatment (manual technique) | DST to 2nd line drugs will be performed in all MDR-TB patients on treatment. DST to 2nd line will be conducted in accordance with National MDR-TB Protocol.In 2013 the estimated number of tests is 100, in 2014 -340, 2015-660 | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 6566.2
| 3.3.2 b | PSM costs for reagents for DST to 2nd line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1428.1485
| 3.3.3 a | Procurement of 2nd line anti-TB drugs for MDR-TB patients | 2nd line TB drugs will be procured for 550 patients (Y3-50, Y4-170, Y5-330 patients). The drugs and their quantities are based on the National MDR-TB Protocol. | MED IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 148568.784
| 3.3.3 b | PSM costs for 2nd line anti-TB drugs for MDR-TB patients to the country (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 37142.196
| 3.3.5 a -revised (distributed between 3 lines) | Cost of reagents for electrolyte analysis for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for hypokaliemia side effect of second line treatment. The budget was allocated for reagents, while the tests will be done using electrolyte analyzers, procured under Grant. | HP IA Code: 001981 Account: 72300 | UNDP |  | x | x | x | 1249.3245
| 3.3.5 b- revised (distributed between 3 lines) | PSM costs for reagents for electrolyte analysis | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x | x | x | 271.7281
| 3.3.5 c- revised (distributed between 3 lines) | Cost of clinical investigations for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for side effects of second line treatment: thyroid gland function, hypokaliemia and screened for viral hepatitis. The budget was allocated based on the number of patients and tests as required by the National MDR-TB Protocol. | LS IA Code: 001981 Account: 72100 | UNDP |  |  | x | x | 2042.1053
| 3.3.5 d-new | Procurement of electrolyte analyzers | Montlhy monitoring of levels of Kalium in blood is required during 2nd line treatment with injectable drugs. Currently the NTP has capacity to perform such tests only at central level. The grant will support procurement of electrolye anlyzers for 5 regional TB hosptials. Proxy price per 1 analyzer is $8,500. Thus, total amount required for 5 analyzers is $42,500. | HP IA Code: 001981 Account:72200 | UNDP |  | x |  |  | 34907.6
| 3.3.5 e-new | PSM costs for electrolyte analyzers | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 7592.403
| 3.3.7 а | Procurement of respirators for MDR-TB sites and BK+ departments [Individual measures for infection control] | High protection respirators will be procured for MDR-TB sites and BK+ departments to ensure individual measures of IC ( 69,000 per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 55200
| 3.3.7 b | Procurement of masks for MDR-TB patients | Masks will be procured for MDR-TB patients to ensure IC control measures as required by the National IC guidelines (total 116, 600 masks for 3 years of Phase 2) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 58300
| 3.3.7 c | Procurement of respirators NRCS staff | High protection respirators will be procured for NRCS staff to ensure individual measures of IC ( 1,265 respirators per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 1012
| 3.3.7 d | PSM costs for respirators for MDR-TB sites and BK+ departments, NRCS staff and masks | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 24906.36
| 3.3.9 a - new line | Procurement of respirator fit-testers | The grant provides the NTP with high-protection respirators. It is required to monitor that the medical staff wares respirators correctly. For monitoring this, the PR will procure kits for fit testing (quantitative). The need is 45 kits: 1 CTTP, 5 regional TB hospitals, 37 TB departments, 1 for Central Prison Hospital and 1 for the NRCS, totally 45 kits. Estimated cost of 1 kit is $143.74. | HP IA Code: 001981 Account: 72300 | UNDP |  |  | x |  | 6468.3
| 3.3.9 b - new line | PSM costs of respirators fit-tester | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  | x |  | 1406.8553
Activity 3.4 Patient support programme for drug-resistant TB patients
| 3.4.3 a | Conduct MDR-TB patient patient education and counselling sessions by adherence counsellors | Patient education and counselling sessions will be conducted by adherence counsellors in out-patient basis.Estimated number of sessions: 2 quarter-6 sessions, 13 quarter- 12 sessions, 14-20 quarters- 36 sessions. | TR IA Code: 005742 Account: 75700 | NRCS |  |  |  | x | 1079.1579
| 3.4.3 b | Salary for 5 patronage nurses engaged in counselling sessions and DOT supporting 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. | The National Red Crescent Society plans to hire staff in Ashgabat and regions for councelling sevices. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS |  |  | x | x | 11671.344
| 3.4.4 a | Procurement of incentives (food parcels) for DR-TB patients, 5 % price increase is forecasted starting from Y4 [Support to treatment adherence] | MDR-TB patients on continuation phase (16 month) will be given monthly food parcels as means of motivation to treatment adherence and prevention of hypokaliemia.It is estimated that 85- 90 % of patients will stay on treatment in the first year of treatment and 80-85% on the 2nd year of treatment. Since the country does not have experience with MDR-TB management, these estimates are subject to correction based on the actual needs. | LS IA Code: 001981 Account: 72300 | UNDP |  |  |  | x | 61560
| 3.4.5 | Cost of transportation of visiting DOT supporters for visits DR-TB patients [Support to treatment adherence ] | Patient counsellors will visit MDR-TB patients to provide support. Cost includes transportation. Patients will be also supported by phone communication, which is budgeted under the activity 3.4.8 b. | PSM IA Code: 005742 Account: 72100 | NRCS |  |  |  | x | 547.3684
| 3.4.8 a | Procurement of printers for 5 regional NRCS offices | Office equipment is required for reporting and administrative needs, considering the increased workload compared to Phase 1( MDR-TB patients support is added) | IF IA Code: 001981 Account: 72400 | UNDP |  | x |  |  | 750
| 3.4.8 b | Operational expenses -stationery, telephone communication | Operational expenses of the NRCS (stationery, office supplies) are covered by the Grant. | OVER IA Code: 005742 Account: 72500 | NRCS |  |  |  | x | 510.5263
Objective 4 Project management and administration
| 4.1 a | Salaries for Principal Recipient's PIU staff | The activity includes budget for GIU staff of 9 person (please see cost assumption 4.1) | HR IA Code: 001981 Account: 71400 | UNDP | x | x | x | x | 169099.2
| 4.1 b | Monitoring visits by GIU plan | Supervision visits will be conducted by quarterly by M&E team (M&E specialist and Senior TB Specialist) and by Construction Specialist to the renovation sites in Mary and Dashoguz. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 7688
| 4.2 a | Cost of GIU unit operational expenses | Cost of GIU unit operation expenses- office rent, internet, telephone communication, 5 % increase is forecasted starting from Y4 | OVER IA Code: 001981 Account: 72400, 72500, 73100, 73500 | UNDP | x | x | x | x | 67396.76
| 4.2 b | Cost of GIU unit operational expenses | Cost of GIU unit operational expenses - office supplies, bank and translation charges, 5 % increase is forecasted starting from Y4 | P&A IA Code: 001981 Account: 74200, 74500 | UNDP | x | x | x | x | 9600
| 4.4 a | Cost of external SR audit | External audit will be conducted for 2 SR's on annual basis- NRCS and Health Information Center | P&A IA Code: 001981 Account: 74100 | UNDP |  |  | x |  | 2000
| 4.4 b | SR capacity assesment by international consultant | Capacity assessment will be done by international consultant for the capacity assessment of NRCS ( MDR-TB support activities) | P&A IA Code: 001981 Account: 71200 | UNDP |  | x |  |  | 5410
| 4.5 a | PR capacity building by attending various conferences, seminars, educational workshops for effective grant implementation | Trainings for capacity building of PR staff will be arranged in ( 2 trainings for 3 GIU staff members in Y3-Y5) | TR IA Code: 001981 Account: 75700 | UNDP |  | x |  | x | 22812
| 4.5 b | SR capacity building by participation in seminars, educational workshops for effective grant implementation | Trainings in M&E and Finance for the SR's will be conducted annually during Y3-Y5. Training on monitoring of parcel distribution will be conducted annually in all 5 regions. | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x |  | 8964
| 4.5 c | SR (NRCS) staff capacity building by conducting study visit to MDR TB patient support (Belgrad or Tomsk, Russia) | Training in provision of MDR-TB support will be arranged for NRCS staff (3 participants in Y3) | TR IA Code: 001981 Account: 75700 | UNDP |  | x |  |  | 8808
| 4.5 d | Cost of capacity development activities of national entities to implement national disease response | Lumpsum of $10,000 is foreseen for the capacity development of national entities, and will be detailed after development of plan by UNDP headqurters. | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 10000
| 4.6 | Quality assurance of the 1 and 2 line TB drugs | Quality assurance activities are planned according to QA action plan. Please refer to cost assumption 4.6 | PSM IA Code: 001981 Account: | UNDP | x | x |  |  | 47530.5
| 4.11 | WHO-remuneration for NPO (management and coordination) for 3 years | The salary of the NPO is budgeted for coordination of the activities under SR Agreement, $11,000 per quarter | HR IA Code: 002066 Account: 71400 | WHO |  | x | x | x | 44000
| 4.12 | WHO- administrative charges-7% | 7% is budgeted as administrative charges under SR agreement with WHO | OVER IA Code: 002066 Account: 72100 | WHO |  | x | x | x | 28224.7933
| 4.14 | Salary of TB project coordinator of Health Information center | The salary of TB project Health Information Center will be covered by MOHMI | HR IA Code: 004520 Account: 71400 | Health Information Center | x |  |  |  | 1418.21
| 4.15 | Health Information Center - administrative charges- 5% | 5% is budgeted as administrative charges under SR agreement with Health Information Center | OVER IA Code: 004520 Account: 72100 | Health Information Center | x |  |  |  | 708.04
| 4.18 | UNDP Administrative charges- 7% according to the agreeement between GF and UNDP |  | OVER IA Code: 001981, 002066,004520, 005742 Account: 75100 | UNDP | x | x | x | x | 389418.2079
|  | Grand Total |  |  |  | 914719.5524 | 1112601.1313 | 456848.8971 | 1073202.1688 | 3557371.7497
Note on B54: aylar.hayitjanova: quantities of parcels were revised
Note on B92: aylar.hayitjanova: previously was UNDP

## AWP 2013
ANNUAL WORK PLAN – YEAR 3 ( 1 October 2012 – 30 September 2013)
EXPECTED OUTPUTS Add baseline, indica-tors including annual targets. Please use the numbering of outputs as they are in the RRF/ SRF of ProDoc | PLANNED ACTIVITIES List activity results and associated actions. Please use the numbering of outputs as they are in the RRF/SRF of ProDoc |  | Budget Description | Budget Codes | Responsible party | TIMEFRAME |  |  |  | PLANNED BUDGET
| # | Activity |  |  |  | Q 9 01/10/12 -01/12/12 | Q 10 01/01/13 - 31/03/13 | Q 11 01/04/13 - 30/06/13 | Q 12 01/07/13 - 30/09/13
Objective 1 : To consolidate DOTS framework through strengthening programme management, improving TB case detection and diagnosis and ensuring quality treatment
Number of new smear-positive TB cases notified to the national health authorities during the specified period. Baseline: 2011 – 1,137 Target 2013- 1,500 Number of all TB cases notified to the national health authorities during the specified period Baseline: 2011 – 3,038 Target 2013 - 4,500 Number of staff from district and regional TB laboratories trained in microscopy techniques and culture methods. Baseline: 2012 - 29 Target 2013 - 20 Number of direct sputum microscopy investigations for TB diagnosis and treatment monitoring. Baseline: 2011 – 85,755 Target 2013- 94,040 Number of culture investigations (manual technique) for confirmation of TB diagnosis and monitoring of treatment. Baseline: 2011 - 2,198 Target 2013- 6,600 Treatment success rate: new smear positive TB cases. Baseline 2010 – 74% Target 2013- 81% Number of TB patients receiving incentives (food parcels) for better adherence to treatment during out-patient phase of 1st line treatment. Baseline 2011 – 2,274 Target 2013 - 2,805 | Activity 1.1 :Strengthening management, coordination, monitoring and evaluation of the National Tuberculosis Programme
| 1.1.1 | Training of NTP management staff by attending international conferences abroad (2 participants per year) | Attendance of training courses in various aspects of NTP management and international conferences abroad (Warsaw and Sondalo training courses, European NTP managers' meetings, IUATLD conferences, etc.). Funding for 2 people attending 1 event per year. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 9604 | 9604
| 1.1.2 | Training of NTP Regional Units' staff in supervision, monitoring and evaluation | Training for staff of 5 Regional (velayat) NTP Units will be conducted at the NTP Central Unit in different aspects of NTP management (in particular in supervision, monitoring and evaluation) to strengthen capacities of NTP RUs and support decentralization / regionalisation of the NTP management. (10 participants, 1 training in Y3 -Y4) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 2620 | 2620
| 1.1.3 a | Quarterly supervision visits by the central NTP Unit ,1 round ( 3 specialists for 3 days in each of 5 regions) | Supervision visits will be conducted by the NTP Central Unit team to 5 velayat centres and selected districts (etraps): quarterly during Years 3-5. | M&E IA Code: 001981 Account: 71600 | UNDP | 6126.62 | 2448 | 2448 | 2448 | 13470.62
| 1.1.3 b - new | Quarterly monitoring meetings to discuss the results of monitoring visits | To discuss the key findings, plan the next steps and ensure effective implementation of recommendations of supervision / monitoring visits, quarterly meetings will be held at the CTTP. Participants: representatives of the MOH, regional Departments of Health, Ashgabat City Department of Health, CTTP, regional NTP units, Medical Department of the MoI, NRCS, and the UNDP/GF GIU staff. There will be 12 meetings in total (4 per year, in 2013-2015). | M&E IA Code: 001981 Account: 71600 | UNDP | 0 | 1110 | 1110 | 1110 | 3330
| 1.1.4 | Support to regional (velayat) NTP supervision | Regional (velayat level) supervision visits will be conducted by 5 Regional NTP Units to TB service and PHC facilities in peripheral districts.Visits will be done using the vehicles procured in Phase1, therefore, no budget is needed. | M&E IA Code: 001981 Account: 71600 | UNDP | 2466.97 | 0 | 0 | 0 | 2466.97
| 1.1.6-new | Procurement of PCs for statistics cabinets of the regional TB hospitals | 5 PC's will be procured for statistical units of the 5 regional TB hospitals, especially in view of the plans to introduce electronic TB manager. | IF IA Code: 001981 Account: 72400, 72800 | UNDP | 8567 | 0 | 0 | 0 | 8567
| 1.1.8 a-new | Procurement of air conditioner for the training center at Balkanabad Regional TB Hospital | 1 air conditioner will be procured for Balkanabad Regional TB hospital | IF IA Code: 001981 Account: 72200 | UNDP | 668 | 0 | 0 | 0 | 668
| 1.1.8 b-new | Refurbishment of training centers at Lebap and Balkan Regional TB Hospitals | Basic refurbishment is planned for training centers at Lebap ( separate a space within that hall and make minor repairs such as refresher pargeting and painting) and Balkan regions. | IF IA Code: 001981 Account: 72100 | UNDP | 0 | 17097.57 | 0 | 0 | 17097.57
| 1.1.8 c- new | Procurement of 5 printers for regional training facilities. | 5 printers will be procured for 5 regional training centers. Cost assumption is $300 per printer. | IF IA Code: 001981 Account: 72400 | UNDP | 0 | 1500 | 0 | 0 | 1500
| 1.1.9 | Operational expenses of the NTP Central Unit and Regional Units, 5 % price increase is forecasted starting from Y4 | Operational expenses of the NTP Central Unit and Regional (velayat) Units (communication expenses, internet / e-mail stationery, printing, etc.) | OVER IA Code: 001981 Account: 72500, 74200 | UNDP | 3260.6 | 2330 | 2330 | 2330 | 10250.6
| 1.1.11 | Training of NTP and TB service staff in upgraded TB recording and reporting system | Staff from the Central and Regional (velayat) NTP units, and key TB service facilities will be trained in the use of revised recording and reporting forms and database management. (15 participants,2 trainings in Y3 - Y5, totally 90 participants) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 4269 | 4269 | 8538
| 1.1.12 | Recruitment of national IT specialist for the management of the national TB database | Local IT specialist will be contracted to assist the NTP in management and maintenance of the national electronic TB database (starting Year 3). | HR IA Code: 002066 Account: 71400 | WHO | 0 | 2100 | 2100 | 2100 | 6300
| 1.1.13 | Printing of recording and reporting national TB forms | Revised recording and reporting forms and registers will be printed at the end of Year 3 (in quantities sufficient for 2 years) and distributed to all TB service delivery sites. Y3 needs were printed in Phase 1. | M&E IA Code: 001981 Account: 74200 | UNDP | 0 | 0 | 0 | 16465.3816 | 16465.3816
| 1.1.14 | Cost of revision and Russian-Turkmen translation of training materials | Training materials will be developed or revised for all training activities and made available in 2 languages (Turkmen, Russian). | P&A IA Code: 002066 Account: 71300 | WHO | 0 | 5050 | 0 | 0 | 5050
| 1.1.15 a | Conduct M&E training session for TB specialists from 5 velayats and Ashgabat at central level | M&E specialists at central and regional level will be trained and retrained on M&E (18 participants,1 training in Y3 and Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 5100 | 0 | 0 | 5100
| 1.1.5 b-new line | Printing of Ministry of Health order #109, which is a key document regulating all aspects of TB control in Turkmenistan | The new Order #109 includes updates on TB diagnostics, as well as control of MDR-TB. It is requested to print 1000 copies of the Order to distribute among central, regional and district level TB facilities; Ministry of Health and regional departments of health; TB department of Turkmen State University; PHC facilities, Sanitary-Epidemiology Service staff at all levels. The cost estimate is based on the market research done in September 2012. Unit cost $12.00 ( 1 order of approx.528 pages of A5 format , in Turkmen and Russian languages)*1000 units=$12,000. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 12000 | 0 | 0 | 12000
| 1.1.16 -new | External assessment of the TB surveillance system | Lumpsum of $100,000 was allocated for an external assessment of the completeness and quality of the national TB surveillance system and data to improve the estimates and trends of TB burden in the country and measurement of impact. | M&E IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 100000 | 0 | 100000
| 1.1.17 a - new | Development of the National TB M&E Plan | The National M&E Plan is required to provide a framework for implementing and strengthening systems and resources to monitor and evaluate the activities, outcomes, and impact of TB control interventions for years 2013-2015. The Plan will be developed with the assistance of an external consultant and a national expert. The draft Plan will be discussed at a workshop and presented for approval to the Government. | TA IA Code: 002066 Account: 71200 | WHO | 0 | 9490 | 0 | 0 | 9490
| 1.1.17 b- new | Printing of the National TB M&E Plan | Translation and printing of 500 copies of National TB M&E Plan. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 3940 | 0 | 0 | 3940
| 1.1.18 a- new | Development of monitoring check-lists for in-patient and out-patient TB facilities | It has been recommended by MESS workshop in September 2012 to develop separate check-lists for in-patient TB facilities and for out-patient facilities (TB cabinets) because of different scope of work and, respectively, different aspects to be monitored. In particular, the new check-lists will include specific component on infection control. 2 national experts will revise the check-lists #2B and 4. Separate check-lists will be developed, including IC and other relevant aspects by type of facility. | TA IA Code: 002066 Account: 71300 | WHO | 0 | 0 | 2400 | 0 | 2400
| 1.1.18 b- new | Development of separate check-lists for monitoring of peripheral (district level) and regional (velayat level) laboratories | Currently lab services are monitored using the check-list #1. However, in view of upgrade of regional labs for culture and DST, it is required to develop check-lists for monitoring of microscopy labs (district level) and culture and DST (velayat level). The existing check-list #1 will be divided to 1A and 1B and updated to incorporate new methods available at regional reference labs. 2 national experts will revise check-list #1 and develop check-lists 1A and 1B. | TA IA Code: 002066 Account: 71300 | WHO | 0 | 0 | 2400 | 0 | 2400
| 1.1.19- new | Technical assistance in revising definitions and TB recording and reporting forms in accordance to the latest WHO recommendations | In 2012, WHO issued the new recommendations for revision of the definitions of TB cases and treatment outcomes (for both sensitive and drug resistant TB cases) and proposed relevant changes in routine country recording and reporting systems. As suggested by the MESS workshop, Turkmenistan will adopt this new guidance and adjust the existing information system accordingly, especially in view of the starting MDR-TB treatment program with the project support. Technical assistance (by an external consultant and local expert) will be contracted in implementation of the new guidance and adjusting the existing recording and recording forms (in Year 1). | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 0 | 9090 | 9090
Activity 1.2 : Strengthening capacities for TB control in the penitentiary sector
| 1.2.1 | Recruitment of international consultant to provide technical assistance to improve accessibility of quality TB diagnosis and treatment for detainees in Y3. | In Year 3, technical assistance (by an external consultant) will be provided to the Medical Department of the Ministry of Internal Affairs to follow up recommendations of the TA in Phase 1, and planning further interventions to improve accessibility of quality TB diagnosis and treatment for detainees, in line with the human right approach. | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 12449 | 0 | 12449
| 1.2.2 | Training in TB management in prisons by attending international conferences abroad | Attendance of training courses in various aspects of TB control in prisons, international conferences abroad and study tours. (3 participants, 1 event in Y3-Y5) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 15606 | 0 | 15606
| 1.2.3 | Conduct quarterly supervision visits by the Medical department of MIA to the TB treatment site in the penitentiary sector (Mary Prison hospital MRK-15) | Quarterly supervision visits will be conducted by the Medical Department of the Ministry of Internal Affairs to the TB treatment site in the penitentiary sector (Mary velayat) and selected detention sites including pre-trial isolators to monitor case finding and case management practices. | M&E IA Code: 001981 Account: 71600 | UNDP | 510 | 510 | 510 | 510 | 2040
| 1.2.8 a - new | Monitor for stationary X-ray machine for Mary Prison Hospital | It is planned to procure monitor for the stationary X-Ray equipment which was procured in 2011 for Mary Prison Hospital with the GF grant, as the radiologist who performs investigation is located in a separate room, and monitor is required for control of the X-Ray procedure. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 14149 | 0 | 0 | 14149
| 1.2.8 b-new | PSM costs for monitor for x-ray for Mary Prison Hospital | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700 | UNDP | 0 | 3077.4075 | 0 | 0 | 3077.4075
Activity 1.3 : Strengthening TB laboratory network
| 1.3.1 b | Conduct training of TB regional laboratory staff on conducting culture investigations | Training of staff of regional microscopy laboratories will be conducted at the NRL on culture investigations (1 training in Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 9062 | 0 | 9062
| 1.3.2 a | Procurement of Reagents for Ziel-Nelsen Microscopy : Sputum smear microscopy investigations | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). ZN was calculated as 75% of this amount, 25% will be done with LED. | HP IA Code: 001981 Account: 72300 | UNDP | 17027.8228 | 0 | 0 | 0 | 17027.8228
| 1.3.2 c | PSM costs for Reagents for Ziel-Nelsen Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 3703.5515 | 0 | 0 | 0 | 3703.5515
| 1.3.2 b | Procurement of Reagents for LED Microscopy (Sputum smear microscopy investigations) | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). LED was calculated as 25% of this amount, 75% will be done with ZN. | HP IA Code: 001981 Account: 72300 | UNDP | 9132.8513 | 0 | 0 | 0 | 9132.8513
| 1.3.2 d | PSM costs for Reagents for LED Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1986.3952 | 0 | 0 | 0 | 1986.3952
| 1.3.3 a | Procurement of Reagents for Culture investigations (manual technique) | Culture investigations (manual technique on solid media) will be performed by the NRL and regional laboratories in Balkanabad,Lebap and Mary, and later in Dashoguz regions. For confirmation of TB 2 tubes and for monitoring of 1 line treatment -2 tubes,at the end of intensive phase (2-3 months), at 4-5 months and at the end of treatment. In 2013 the need in culture investigations is 11,980. It is estimated that the NTP can cover only 50% of this amount (5,990). In 2014 the esitmated need is 12,220 and the expected coverage - 70% or 8,554 .In 2015, the estimated need is 12,850 and the NTP should be able to perform 80% of the need, or 10,280. | HP IA Code: 001981 Account: 72300 | UNDP | 17047.8 | 0 | 0 | 0 | 17047.8
| 1.3.3 b | PSM costs for reagents for Culture investigations (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 3707.8965 | 0 | 0 | 0 | 3707.8965
| 1.3.7 a | Procurement of respirators for staff of TB laboratories (Individual measures for infection control) | Procurement of high protection respirators to ensure individual measures of infection control at TB laboratories. | HP IA Code: 001981 Account: 72300 | UNDP | 6219.2 | 0 | 0 | 0 | 6219.2
| 1.3.7 b | PSM costs for respirators for staff of TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1352.676 | 0 | 0 | 0 | 1352.676
| 1.3.8 a - new line | Development of Standard Operating Procedures (SOPs) for cultural and molecular diagnostic tests and Drug Susceptibility Testing. | 2 national experts will develop SOPs (based on SOPs already developed in other countries). SOPs will be revised by the Supra-National Lab in the Netherlands. Training on SOPs will be done within the lab training program planned for phase 2. | TA IA Code: 002066 Account: 71300 | WHO | 0 | 0 | 5640 | 0 | 5640
| 1.3.8 b-new line | Printing and translation of Standard Operating Procedures (SOPs) for cultural and molecular diagnostic tests and Drug Susceptibility Testing. | Translation from Russian to Turkmen and to English will be provided. 100 copies will be printed. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 0 | 0 | 5500 | 5500
Activity 1. 4 Improving TB case management
| 1.4.3 | Conduct training for TB nurses using standard DOTS module | DOTS initial training and refreshing training of nurses from TB service institutions (15 participants, 1 training in Y3, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 2515 | 2515
| 1.4.4 | Recruitment of international consultant to provide technical assistance to NTP in strengthening TB drugs' management in Y3 | Technical assistance (by an external consultant) will be provided to the NTP to strengthen the drug management system including forecasting, ordering, storage, stock monitoring, distribution, monitoring and management of side effects). 1 mission in Y3 | TA IA Code: 002066 Account: 71200 | WHO | 0 | 13049 | 0 | 0 | 13049
| 1.4.5 | Conduct training in TB drugs' management by the NTP Central Unit for TB specialists, key staff and drug managers from the regional level | Training in anti-TB drugs' management will be provided by the NTP Central Unit for TB specialists and drug managers (15 participants, 2 trainings in Y3- Y4) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 3705 | 3705 | 7410
| 1.4.6 b -new | Procurement of air conditioners for drug storage spaces at the DOTS cabinets to ensure adequate temperature for storage of TB drugs. | Procurement of air-conditioners for drug storage spaces at the DOTS cabinets is required to ensure adequate temperature for storage of TB drugs. As per NTP data, there are 160 service delivery points at district level of TB care. The unit price for air-conditioner is about $315. The required budget is therefore 160 * $315 = $50,400 | IF IA Code: 001981 Account: 72200 | UNDP | 0 | 0 | 0 | 50400 | 50400
| 1.4.7 a | Procurement of First Line Anti-TB Drugs , 5 % price increase is forecasted starting from Y4 | 1 line TB drugs will be procured for : Y3 - 4,500 patients (civil- 3,300 and penal- 1,200), Y4- 4,600 patients (civil-3,400 and penal -1,200), Y5- 4,600 patients (civil-3,500 and penal-1,100). For civil patients 87%- I, III category and 13%- II category. For penal patients 50%-I, III category, 50%-II category. | MED IA Code: 001981 Account: 72300 | UNDP | 0 | 0 | 0 | 77550.131 | 77550.131
| 1.4.7 b | PSM costs for First Line Anti-TB-Drugs (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 0 | 19387.5327 | 19387.5327
| 1.4.8 a | Procurement of (food parcels) for TB patients,as incentives (support to treatment adherence), 5 % price increase is forecasted starting from Y4 | TB patients on 1line treatment during continuation phase receive monthly food parcels. I, III category- 4 parcels per treatment course, II category - 5 parcels per treatment course. The coverage with support is 85%. | LS IA Code: 001981 Account: 72300 | UNDP | 41518.66 | 302940 | 0 | 0 | 344458.66
| 1.4.8 b | Salary of NRCS personnel (project coordinator,project assistant, 5 patronage nurses) 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. [delivery of food packages to DOTS cabinets and monitoring] | The National Red Crescent Society hired staff in Ashgabat and all regions to implement patient support countrywide. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | 9210.7944 | 9210.7944 | 9210.7944 | 9210.7944 | 36843.1776
| 1.4.8 c | Transportation of parcels до DOTS cabinets.[delivery of food packages to DOTS cabinets ] | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | 10106.775 | 10106.775 | 10106.775 | 10106.775 | 40427.1
| 1.4.8 d | Quarterly monitoring visits by central NRCS [delivery of food packages to DOTS cabinets and monitoring] | Central level of NRCS will conduct quarterly monitoring visits to verify reporting on number of patients receiving food parcels ( 3 days, 2 person to 2 regions) | M&E IA Code: 005742 Account: 71600 | NRCS | 2099.4053 | 2099.4053 | 2099.4053 | 2099.4053 | 8397.6211
| 1.4.8 e | Monthly monitoring visits by regional NRCS [delivery of food packages to DOTS cabinets and monitoring] | Regional level of NRCS will conduct monthly verification of number of patients receiving food parcels, survey on patient satisfaction, and provision of consultation to TB specialists on distribution of food parcels (3 days, 1 person, 2 etraps per month) | M&E IA Code: 005742 Account: 71600 | NRCS | 4059.0395 | 4059.0395 | 4059.0395 | 4059.0395 | 16236.1579
| 1.4.8 f | Procurement of 2 PCs for patronage nurses in Dashoguz and Mary regions .[delivery of food packages to DOTS cabinets and monitoring] | Office equipment is required for reporting and administrative needs, considering the increased workload compared to Phase 1( MDR-TB patients support is added) | IF IA Code: 001981 Account: 72400, 72800,74700 | UNDP | 0 | 2836.1667 | 0 | 0 | 2836.1667
| 1.4.8 g | Internet and telephone communication for NRCS personnel at 5 velayats and Ashgabat.[delivery of food packages to DOTS cabinets and monitoring] | Operational expenses of NRCS (communication expenses, internet) will be covered. | IF IA Code: 005742 Account: 72400 | NRCS | 421.0526 | 421.0526 | 421.0526 | 421.0526 | 1684.2105
| 1.4.8 h - new line | Procurement of furniture for NRCS patronage nurses offices | Furniture set ( table and cabinet) will be procured for Ashgabat and 4 regional NRCS offices. | IF IA Code: 001981 Account: 72200 | UNDP | 0 | 1755 | 0 | 0 | 1755
| 1.4.8 i-new line | Printing of journals for registration of TB patients receiving parcels | Total 90 journals planned to be printed for DOTS cabinets in all regions. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 2684.7 | 0 | 0 | 2684.7
| 1.4.9 a- new | Procurement of medical scales for TB facilities. | Medical scales for checking the patient weight for accurate adminitration of dosage of TB medicines are lacking at many TB treatment delivery sites, or the equipment is old and not reliable. It is required to equip TB facilities with medical scales for accurate administration of TB treatment. Mechanical medical scales will be procured for 5 regional TB hospitals (2 per hospital - 1 for MDR-TB and 1 for other patients), 56 district TB facilities (1 for each), and 11 for penitentiary TB facilities, totally 77 scales (estimated cost US$ 430 including delivery costs). | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 0 | 27194.86 | 0 | 27194.86
| 1.4.9 b- new | PSM costs for procurement of medical scales | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700 | UNDP | 0 | 0 | 5914.882 | 0 | 5914.882
| 1.4.9 c- new | Development of guidance on quantification and inventory for sputum smear microscopy reagents and consumables. | Lab specialists performing sputum smear microscopy need written guidance on quantification and inventory for reagents and consumables for Ziehl-Neelsen and luminescent methods. 2 national experts will develop the guideline and practical instructions based on internationally recommended practices. Training will be done within the lab training program planned for phase 2. | TA IA Code: 002066 Account: 71300 | WHO | 0 | 0 | 2400 | 0 | 2400
| 1.4.9 d-new | Printing of guidance on quantification and inventory for sputum smear microscopy reagents and consumables. | 250 copies of guidance will be printed. Unit cost is estimated as $10. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 0 | 0 | 2500 | 2500
Activity 1.5 :TB advocacy, communication and social mobilisation (ACSM)
| 1.5.3 | Conduct training workshops for mass media representatives on priority issues of TB control. | Training workshops will be organised for mass media representatives in priority issues of TB control to enhance public awareness and social mobilisation for effective TB control. 1 workshops will be organised for 20 participants in Y3-Y5, before the World TB day. | TR IA Code: 004520 Account: 75700 | Health Information Center | 0 | 910 | 0 | 0 | 910
| 1.5.4 | Development and printing of TB informational and educational materials. | During Y3, the materials will be redeveloped and printed for 3 and 4. Additionally, the materials will be printed in Y5. | COM IA Code: 001981 Account: 74200 | UNDP | 1519.72 | 0 | 0 | 30000 | 31519.72
| 1.5.5 | Design, produce and broadcast TB informational and educational materials: video (10% increase forecasted starting from Y4) | Video spots will be designed, produced and broadcasted that will aim at increasing public awareness and social mobilisation for better TB control (in Y3-Y5). | COM IA Code: 004520 Account: 74200 | Health Information Center | 0 | 0 | 0 | 3000 | 3000
| 1.5.6 | Operational costs for TB Resource Center at the Ministry of Health Information Centre (5 % increase is forecasted starting from Y4) | Operational expenses of TB resource center (communication expenses, internet) will be covered. | IF IA Code: 004520 Account: 72400 | Health Information Center | 4162.35 | 4140 | 2070 | 2070 | 12442.35
| 1.5.7 a | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | COM IA Code: 004520 Account: 74200 | Health Information Center | 0 | 2674.4311 | 0 | 0 | 2674.4311
| 1.5.7 b | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | TR IA Code: 004520 Account: 75700 | Health Information Center | 0 | 2047.5 | 0 | 0 | 2047.5
| 1.5.7 c- new | Informational and educational events and activities, including seminars and round-tables for public associations, media and educators | It is planned to conduct 4 trainings and 1 round table per quarter | TR IA Code: 004520 Account: 75700 | Health Information Center | 6211.56 | 0 | 0 | 0 | 6211.56
| 1.5.8 | Training workshops for community leaders on TB control | Trainings workshops for community activists will be held to generate public awareness and raise social commitment at community level for fighting TB, with emphasis on reducing TB-related stigmatization and using community and family levers to motivate the patients to complete treatment and avoid the development of drug resistance. NRCS will train 100 people per year (13 participants, 8 trainings in Y3-Y5). | TR IA Code: 005742 Account: 75700 | NRCS | 0 | 4943.15 | 6411 | 6411 | 17765.15
Activity 1.6 Collaborative activities for control of TB / HIV co-infection
| 1.6.4 | Training of TB service staff in diagnostic counselling and testing (DCT) for HIV | It is planned to train 90 TB specialists from all velayats and penitentiary sector in HIV diagnostic counselling and testing (DCT) among TB patients in order to improve access to and quality of the service.(15 participants,1 training in Y3, 3 trainings in Y4, 2 trainings in Y5) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 3469 | 3469
Objective 2 :To improve the health system performance for effective tuberculosis control | Activity 2.1 Strengthening Primary Health Care involvement in TB control
Number of TB and PHC services staff (doctors and nurses) trained and re-trained in DOTS, drug management and MDR-TB management. Baseline: 2011 – 1,168 Target 2013- 300 | 2.1.2 - new | The new national guidelines on TB control for PHC providers will be printed at the beginning of Year 2 and further distributed during training (number of copies needed: 6,000). | Cost of 1 copy: $ 3.0; totally $ 18 000 (in Year 2) for 6000 copies | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 0 | 18000 | 0 | 18000
| 2.1.3 | Conduct training of trainers for further training of PHC providers on TB control (20 participants in Y3) | The national team of trainers will be strengthened by conducting in-depth training at the NTP Central Unit for selected TB specialists from the regions (velayats) who will further conduct training for PHC providers on TB control. Totally 20 persons will be trained in Year 3. | TR IA Code: 002066 Account: 75700 | WHO | 0 | 15038 | 0 | 0 | 15038
| 2.1.4 | Conduct training of PHC doctors from all regions in TB control (3 days, 20 participants, Q9 - 6 trainings ; 3 days, 15 participants Q11- 1 training, Q 12 - 1 training; Y4-8 trainings, Y5-8 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants, 8 trainings ).Will include general doctors from the penitentiary sector. 1,060 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | 21486 | 0 | 3163 | 3163 | 27812
| 2.1.5 | Conduct training of PHC nurses from all regions and penitentiary sector in TB control (3 days, 20 participants, Q9-6 trainings; 3 days, 15 participants Q11- 2 training, Q 12 - 1 training; Y4-8 trainings, Y5- 5 trainings) | It is planned to train PHC nurses from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants).Will include nurses from the penitentiary sector. 1,030 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | 21486 | 0 | 6326 | 3163 | 30975
| 2.1.6 a | Printing TB suspects' logbooks for PHC institutions (TB 15) | TB suspects' logbooks (form TB-15) for family doctors will be printed and distributed among PHC institutions. 6000 copies (based on the number of PHC doctors in the country). | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 0 | 0 | 3621.0526 | 3621.0526
| 2.1.6 b -new | Printing of algorithm for PHC doctors (standard plan of treatment of TB patient) | It is requested to print additional 5000 copies of algorithm. Copies will be distributed to PHC doctors, administration of PHC facilities and TB facilities. Some copies will be reserved for distribution in 2014-2015 for new PHC doctors. Cost estimate is based on the previous similar procurement done in 2011 adjusted to the price fluctuation advised by supplier. The estimated unit cost is $1.03* 5,000 units=5,150. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 5150 | 0 | 0 | 5150
| 2.1.8-new | Monitoring of effectiveness of PHC trainings on DOTS | Members of the HSS working group will conduct mini-assessment of effectiveness of the PHC trainings. They will conduct visits to 3 velayats semiannually in Y3-Y4 and once in Y5. Trained PHC staff will be surveyed with the post-test questionnaire with aim to assess how the knowledge "survives" after 3,6, 12 months following training, how the PHC doctors use the knowledge in the daily practice, what gaps remain. The results will be communicated to the trainers and used for adjustment of training modules. | M&E IA Code: 002066 Account: 71600 | WHO | 0 | 0 | 1478.6667 | 1478.6667 | 2957.3333
Activity 2.2 Strengthening key health system functions for effective TB control
| 2.2.3 | Recruitment of international consultant to provide technical assistanceto the MOHMI and NTP in improving hospital performance in TB control in Y3 | TB hospitals have to develop and implement IC plans.Technical assistance (by an external and a local expert) will be provided to the Ministry of Health and NTP in improving effectiveness, efficiency and safety (with particular emphasis on infection control in TB hospitals for preventing cross-contamination and development of drug resistance) in in-patient TB hospitals and departments.One consultancy mission is planned in Y3. | TA IA Code: 002066 Account: 71200 | WHO | 0 | 14251 | 0 | 0 | 14251
Activity 2.3 : Introducing Practical Approach to Lung Health (PAL)
| 2.3.2 | Recruitment of local consultant to provide technical assistance in monitoring and evaluation of PAL implementation in the pilot area in Y4 | Local consultant will monitor implementation of PAL activities in the pilot regions. Cost includes fees, travel to pilot areas. | TA IA Code: 002066 Account: 71300 | WHO | 0 | 3000 | 1500 | 1500 | 6000
| 2.3.3 | Printing of national PAL guidelines | The national guidelines on PAL will be printed (in Year 3) and distributed among all PHC providers: 5,000 copies. | P&A IA Code: 001981 Account: 74200 | UNDP | 0 | 0 | 0 | 40043.8596 | 40043.8596
| 2.3.4 | Organize national workshops for the introduction of PAL inpilot regions, evaluation and further planning | One national workshops will be organised in Years 3 to evaluate project progress, plan future actions and develop recommendations to MOH and NTP for expansion of the approach in the country. | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 10924 | 0 | 10924
Objective 3 :To introduce and expand access to diagnosis and treatment of drug-resistant tuberculosis | Activity 3.1.Strengthening national capacities for management of drug-resistant tuberculosis
TB cases with results for diagnostic drug susceptibility testing for MDR-TB among those eligible Baseline: 2011 – 40.5% Target 2013 - 48% Confirmed MDR-TB cases enrolled on treatment: Laboratory-confirmed MDR-TB cases enrolled on 2nd line anti-TB treatment during the specified period of assessment (number) Baseline: N/a Target 2013- 92 Number of MDR-TB patients on out-patient treatment receiving patient support (food incentives) for better adherence to treatment. Baseline: N/a Target 2013- 17 | 3.1.1 | Support to the Green Light Committee operations (GLC Fee) | GLC monitoring missions and operational support to the GLC in accordance to agreement between the GLC and the Global Fund ($25,000 per year) | P&A IA Code: 001981 Account: 72100 | UNDP | 0 | 25000 | 0 | 0 | 25000
| 3.1.2 | Recruitment of international consultant to provide technical assistance in DR-TB management in Y3 | Technical assistance (by external consultants) will be provided on various aspects of the DR-TB management, such as laboratory diagnosis, clinical management of DR-TB cases, organization of treatment and follow-up during continuation phase, DR-TB treatment in the penitentiary sector, infection control planning (1 mission in Y3). | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 0 | 16793 | 16793
| 3.1.4 | Conduct TOT on DR-TB management | TOT will be conducted to train national trainers, who will then train TB and PHC specialists In their respective regions (20 participants , 1 training in Y3). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 15038 | 0 | 0 | 15038
| 3.1.5 | Conduct local training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff from DR-TB treatment delivery sites | Training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff DR-TB treatment delivery sites (15 participants,2 trainings in Y3-Y5, totally 90 participants) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 5210 | 5210 | 10420
| 3.1.6 | Conduct local training in MDR-TB management for Primary Health Care services, who will be involved in follow-up of DR-TB patients | Training in MDR-TB management for staff from PHC service who will be involved in follow-up of MDR-TB patients during out-patient phase of treatment with special emphasis on psychosocial support to ensure adherence. It is planned to train 300 PHC providers ( 15 participants,2 trainings in Y3, 8 trainings in Y4, 10 trainings in Y5). | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 3290 | 3290 | 6580
| 3.1.7 | Conduct training for staff from MDR-TB treatment sites and regional laboratories for infection control | Local training on infection control will be organised for staff from MDR-TB treatment delivery sites and regional laboratories: totally 120 persons to be trained (20 participants, 1 training - Y3, 3 trainings in Y4 , 2 trainings in Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 4394 | 4394
| 3.1.9 a | Renovation of regional reference laboratory in Dashoguz region | Support to infrastructure rehabilitation of the newly established regional reference laboratories which will be involved in DR-TB surveillance and diagnosis in Dashoguz (during Year 3), for ensuring proper workflow amd infection control including installation of the external negative pressure ventilation system. | IF IA Code: 001981 Account: 72100 | UNDP | 0 | 0 | 0 | 395154 | 395154
| 3.1.9 b -new | Procurement of tools for monitoring engineering measures of Infection Control (airflow, UV) | Procurement of anemometers, UV-radiometers and analyzers of voltage for Centre for TB Treatment and Prophylaxis, 5 regional TB hospitals, Project monitoring, Turkmenmedtechnika. | IF IA Code: 001981 Account: 72200, 74700 | UNDP | 10411.15 | 0 | 0 | 0 | 10411.15
| 3.1.10 a | Procurement of equipment for regional reference laboratory in Dashoguz region | A standard set of laboratory equipment will be procured for the newly established regional reference laboratories Dashoguz (delivery in Year 4). | HP IA Code: 001981 Account: | UNDP | 0 | 62223.1788 | 0 | 0 | 62223.1788
| 3.1.10 b | PSM costs for equipment for regional reference laboratory in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 13533.5414 | 0 | 0 | 13533.5414
| 3.1.10 c | Procurement of furniture for regional reference laboratory in Dashoguz region | A standard set of laboratory furniture will be procured for the newly established regional reference laboratories Dashoguz (delivery in Year 4). | HP IA Code: 001981 Account: | UNDP | 0 | 0 | 0 | 47633 | 47633
| 3.1.10 d | Transportation of furniture for regional reference laboratory in Dashoguz region | Transportation costs of 16.53% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 0 | 7873.7349 | 7873.7349
| 3.1.11 | Recruitment of international consultant for the development of Infection Control (IC) plans for MDR-TB sites and bacteriological laboratories in Y3 -Mary and Turkmenabad, Y4- Dashoguz | Technical assistance will be provided for development of IC plans at the regional TB laboratories of BSL 3. Cost includes consultant fees, travel to the regional laboratories and translation costs. | TA IA Code: 002066 Account: 71200 | WHO | 0 | 18341 | 18341 | 0 | 36682
| 3.1.13 | Training of NRCS personnel in infection control | Local training on infection control will be organised for the NRCS staff working with the MDR-TB patients (12 participants, 1 training in Y3-5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 2244 | 0 | 2244
Activity 3.2 Drug resistance surveillance and diagnosis of drug-resistant TB cases
| 3.2.5 a | Procurement of automated MGIT technology (including installation) equipment for DR-TB diagnosis for Dashoguz region (isolation of strains in liquid culture) | Procurement of automated MGIT technology equipment for rapid isolation of strains and liquid culture for accelerated DST to 1st line drugs (BD Bactec MGIT 960 System instrument): 1 machine will be procured for Dashoguz (Year 3). | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 44455.5 | 0 | 0 | 44455.5
| 3.2.5 b | MGIT technology equipment 12 month service contract | Maintence cost is budgeted for 4 MGIT machines ( 3 - procured within Grant and 1 -previously already in place at NRL). | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 37060 | 0 | 0 | 37060
| 3.2.5 c | PSM costs for MGIT technology in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 17729.6213 | 0 | 0 | 17729.6213
| 3.2.6 a | Procurement of laboratory equipment for DR-TB diagnosis (molecular line probe assay, PCR GenoType MTBDR Plus technology) for Dashoguz region | Procurement of equipment for DR-TB diagnosis (molecular line probe assay, PCR GenoType MTBDR Plus technology), 1 machine will be procured for Dashoguz . | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 14334.8344 | 0 | 0 | 14334.8344
| 3.2.6 b | PCR GenoType equipment 12 month service contract | Maintence cost is budgeted for 2 PCR machines. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 1433.4857 | 0 | 0 | 1433.4857
| 3.2.6 c | PSM costs for PCR GenoType MTBDR Plus technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 3429.6096 | 0 | 0 | 3429.6096
| 3.2.7 a | Procurement of GeneXperts for Balkan and Ahal regional TB laboratories | 1 GeneXpert machines will be procured for Balkan and 1 for Ahal regional TB hospitals for rapid identification of TB and resistance to rifampicin | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 44286.6095 | 0 | 0 | 44286.6095
| 3.2.7 b | GeneXpert 12 month service contract | Maintence cost is budgeted for 6 GeneXpert machines. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 13285.9829 | 0 | 0 | 13285.9829
| 3.2.7 c | PSM costs for GeneXperts for Balkan and Ahal regional TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 12522.0388 | 0 | 0 | 12522.0388
| 3.2.8 a | Culture and DST to 1st line drugs for DR-TB diagnosis (automated MGIT technique) | Culture investigations (automated technique on liquid media) will be performed by the NRL and regional laboratories.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | 21832.9524 | 0 | 0 | 0 | 21832.9524
| 3.2.8 b | PSM costs for Culture and DST to 1st line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 4748.6671 | 0 | 0 | 0 | 4748.6671
| 3.2.9 a | DST to 1st line drugs (manual technique) | DST to 1st line drugs will be performed in culture-positive cases using manual technique on solid media, for quality assurance of automated MGIT technique.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | 886.44 | 0 | 0 | 0 | 886.44
| 3.2.9 b | PSM costs for DST to 1st line drugs (manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 192.8007 | 0 | 0 | 0 | 192.8007
| 3.2.10 a | Tests for rapid identification of R/H resistance | Identification of strains and express testing for R/H resistance to be performed by the NRL and regional laboratories. In 2013 the estimated number of tests is 1380, in 2014 -2040, 2015-2400. | HP IA Code: 001981 Account: 72300 | UNDP | 22563 | 0 | 0 | 0 | 22563
| 3.2.10 b | PSM costs for tests for rapid identification of R/H resistance (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 4907.4525 | 0 | 0 | 0 | 4907.4525
| 3.2.11 a | Tests for rapid detection and MDR screening, GeneXpert technology | Procurement of supplies for tests by automated sample processing, detection of M. tuberculosis and screening for R resistance (GeneXpert technology).In 2013 the estimated number of tests is 2490, in 2014 -3540, 2015-3980) | HP IA Code: 001981 Account: 72300 | UNDP | 29940 | 0 | 0 | 0 | 29940
| 3.2.11 b | PSM costs for rapid detection and MDR screening GeneXpert technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 6511.95 | 0 | 0 | 0 | 6511.95
| 3.2.12 | Cost of missions of SRL experts to the NRL in Ashgabat. | Visits of SRL (National Mycobacteria Reference Laboratory, National Institute of Public Health and the Environment, Bilthoven, The Netherlands) to the NRL with the scope of technical assistance and external laboratory quality assurance (1 mission per Y3-Y5) | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 9897 | 0 | 9897
| 3.2.13 | Cost of on-site training of NRL specialists at the SRL, | NRL specialists will visit the SRL in Bilthoven, Netherlands, for for in-depth on-site training on new techniques (1 trainining for 3 participants per Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 15204 | 15204
| 3.2.14 | External laboratory quality assurance: shipment of strains to the Supranational Reference Laboratory | With the scope of external laboratory quality assurance of DST to 1st line and 2nd line TB drugs in support of the DR-TB management programme, strains will be shipped quarterly to the Supranational Reference Laboratory (SRL) in Bithoven, Netherlands. | P&A IA Code: 001981 Account: 72100 | UNDP | 4850 | 2750 | 2750 | 2750 | 13100
Activty 3.3 Treatment of drug-resistant TB cases
| 3.3.1 a | Procurement of reagents for culture investigations for MDR-TB patients on treatment (manual technique) | Cultures by manual technique on solid media will be performed for monitoring of treatment of MDR-TB patients.Calculations were done based on National MDR-TB Protocol. In 2013 the estimated number of tests is 660, in 2014 -2244, 2015-4356. | HP IA Code: 001981 Account: 72300 | UNDP | 1894.2 | 0 | 0 | 0 | 1894.2
| 3.3.1 b | PSM costs for reagents for culture investigations for MDR-TB patients on treatment ,manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 411.9885 | 0 | 0 | 0 | 411.9885
| 3.3.2 a | Procurement of reagents for DST to 2nd line drugs for DR-TB patients on treatment (manual technique) | DST to 2nd line drugs will be performed in all MDR-TB patients on treatment. DST to 2nd line will be conducted in accordance with National MDR-TB Protocol.In 2013 the estimated number of tests is 100, in 2014 -340, 2015-660 | HP IA Code: 001981 Account: 72300 | UNDP | 6566.2 | 0 | 0 | 0 | 6566.2
| 3.3.2 b | PSM costs for reagents for DST to 2nd line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1428.1485 | 0 | 0 | 0 | 1428.1485
| 3.3.3 a | Procurement of 2nd line anti-TB drugs for MDR-TB patients | 2nd line TB drugs will be procured for 550 patients (Y3-50, Y4-170, Y5-330 patients). The drugs and their quantities are based on the National MDR-TB Protocol. | MED IA Code: 001981 Account: 72300 | UNDP | 148568.784 | 0 | 0 | 0 | 148568.784
| 3.3.3 b | PSM costs for 2nd line anti-TB drugs for MDR-TB patients to the country (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 37142.196 | 0 | 0 | 0 | 37142.196
| 3.3.5 a -revised (distributed between 3 lines) | Cost of reagents for electrolyte analysis for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for hypokaliemia side effect of second line treatment. The budget was allocated for reagents, while the tests will be done using electrolyte analyzers, procured under Grant. | HP IA Code: 001981 Account: 72300 | UNDP | 0 | 146.9794 | 367.4484 | 734.8968 | 1249.3245
| 3.3.5 b- revised (distributed between 3 lines) | PSM costs for reagents for electrolyte analysis | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 31.968 | 79.92 | 159.8401 | 271.7281
| 3.3.5 c- revised (distributed between 3 lines) | Cost of clinical investigations for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for side effects of second line treatment: thyroid gland function, hypokaliemia and screened for viral hepatitis. The budget was allocated based on the number of patients and tests as required by the National MDR-TB Protocol. | LS IA Code: 001981 Account: 72100 | UNDP | 0 | 0 | 419.2982 | 1622.807 | 2042.1053
| 3.3.5 d-new | Procurement of electrolyte analyzers | Montlhy monitoring of levels of Kalium in blood is required during 2nd line treatment with injectable drugs. Currently the NTP has capacity to perform such tests only at central level. The grant will support procurement of electrolye anlyzers for 5 regional TB hosptials. Proxy price per 1 analyzer is $8,500. Thus, total amount required for 5 analyzers is $42,500. | HP IA Code: 001981 Account:72200 | UNDP | 0 | 34907.6 | 0 | 0 | 34907.6
| 3.3.5 e-new | PSM costs for electrolyte analyzers | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 7592.403 | 0 | 0 | 7592.403
| 3.3.7 а | Procurement of respirators for MDR-TB sites and BK+ departments [Individual measures for infection control] | High protection respirators will be procured for MDR-TB sites and BK+ departments to ensure individual measures of IC ( 69,000 per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | 55200 | 0 | 0 | 0 | 55200
| 3.3.7 b | Procurement of masks for MDR-TB patients | Masks will be procured for MDR-TB patients to ensure IC control measures as required by the National IC guidelines (total 116, 600 masks for 3 years of Phase 2) | HP IA Code: 001981 Account: 72300 | UNDP | 58300 | 0 | 0 | 0 | 58300
| 3.3.7 c | Procurement of respirators NRCS staff | High protection respirators will be procured for NRCS staff to ensure individual measures of IC ( 1,265 respirators per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | 1012 | 0 | 0 | 0 | 1012
| 3.3.7 d | PSM costs for respirators for MDR-TB sites and BK+ departments, NRCS staff and masks | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 24906.36 | 0 | 0 | 0 | 24906.36
| 3.3.9 a - new line | Procurement of respirator fit-testers | The grant provides the NTP with high-protection respirators. It is required to monitor that the medical staff wares respirators correctly. For monitoring this, the PR will procure kits for fit testing (quantitative). The need is 45 kits: 1 CTTP, 5 regional TB hospitals, 37 TB departments, 1 for Central Prison Hospital and 1 for the NRCS, totally 45 kits. Estimated cost of 1 kit is $143.74. | HP IA Code: 001981 Account: 72300 | UNDP | 0 | 0 | 6468.3 | 0 | 6468.3
| 3.3.9 b - new line | PSM costs of respirators fit-tester | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 1406.8553 | 0 | 1406.8553
Activity 3.4 Patient support programme for drug-resistant TB patients
| 3.4.3 a | Conduct MDR-TB patient patient education and counselling sessions by adherence counsellors | Patient education and counselling sessions will be conducted by adherence counsellors in out-patient basis.Estimated number of sessions: 2 quarter-6 sessions, 13 quarter- 12 sessions, 14-20 quarters- 36 sessions. | TR IA Code: 005742 Account: 75700 | NRCS | 0 | 0 | 0 | 1079.1579 | 1079.1579
| 3.4.3 b | Salary for 5 patronage nurses engaged in counselling sessions and DOT supporting 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. | The National Red Crescent Society plans to hire staff in Ashgabat and regions for councelling sevices. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | 0 | 0 | 5835.672 | 5835.672 | 11671.344
| 3.4.4 a | Procurement of incentives (food parcels) for DR-TB patients, 5 % price increase is forecasted starting from Y4 [Support to treatment adherence] | MDR-TB patients on continuation phase (16 month) will be given monthly food parcels as means of motivation to treatment adherence and prevention of hypokaliemia.It is estimated that 85- 90 % of patients will stay on treatment in the first year of treatment and 80-85% on the 2nd year of treatment. Since the country does not have experience with MDR-TB management, these estimates are subject to correction based on the actual needs. | LS IA Code: 001981 Account: 72300 | UNDP | 0 | 0 | 0 | 61560 | 61560
| 3.4.5 | Cost of transportation of visiting DOT supporters for visits DR-TB patients [Support to treatment adherence ] | Patient counsellors will visit MDR-TB patients to provide support. Cost includes transportation. Patients will be also supported by phone communication, which is budgeted under the activity 3.4.8 b. | PSM IA Code: 005742 Account: 72100 | NRCS | 0 | 0 | 0 | 547.3684 | 547.3684
| 3.4.8 a | Procurement of printers for 5 regional NRCS offices | Office equipment is required for reporting and administrative needs, considering the increased workload compared to Phase 1( MDR-TB patients support is added) | IF IA Code: 001981 Account: 72400 | UNDP | 0 | 750 | 0 | 0 | 750
| 3.4.8 b | Operational expenses -stationery, telephone communication | Operational expenses of the NRCS (stationery, office supplies) are covered by the Grant. | OVER IA Code: 005742 Account: 72500 | NRCS | 0 | 0 | 0 | 510.5263 | 510.5263
Objective 4 Project management and administration | 4.1 a | Salaries for Principal Recipient's PIU staff | The activity includes budget for GIU staff of 9 person (please see cost assumption 4.1) | HR IA Code: 001981 Account: 71400 | UNDP | 42274.8 | 42274.8 | 42274.8 | 42274.8 | 169099.2
| 4.1 b | Monitoring visits by GIU plan | Supervision visits will be conducted by quarterly by M&E team (M&E specialist and Senior TB Specialist) and by Construction Specialist to the renovation sites in Mary and Dashoguz. | M&E IA Code: 001981 Account: 71600 | UNDP | 1922 | 1922 | 1922 | 1922 | 7688
| 4.2 a | Cost of GIU unit operational expenses | Cost of GIU unit operation expenses- office rent, internet, telephone communication, 5 % increase is forecasted starting from Y4 | OVER IA Code: 001981 Account: 72400, 72500, 73100, 73500 | UNDP | 30125.96 | 12423.6 | 12423.6 | 12423.6 | 67396.76
| 4.2 b | Cost of GIU unit operational expenses | Cost of GIU unit operational expenses - office supplies, bank and translation charges, 5 % increase is forecasted starting from Y4 | P&A IA Code: 001981 Account: 74200, 74500 | UNDP | 2400 | 2400 | 2400 | 2400 | 9600
| 4.4 a | Cost of external SR audit | External audit will be conducted for 2 SR's on annual basis- NRCS and Health Information Center | P&A IA Code: 001981 Account: 74100 | UNDP | 0 | 0 | 2000 | 0 | 2000
| 4.4 b | SR capacity assesment by international consultant | Capacity assessment will be done by international consultant for the capacity assessment of NRCS ( MDR-TB support activities) | P&A IA Code: 001981 Account: 71200 | UNDP | 0 | 5410 | 0 | 0 | 5410
| 4.5 a | PR capacity building by attending various conferences, seminars, educational workshops for effective grant implementation | Trainings for capacity building of PR staff will be arranged in ( 2 trainings for 3 GIU staff members in Y3-Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 11406 | 0 | 11406 | 22812
| 4.5 b | SR capacity building by participation in seminars, educational workshops for effective grant implementation | Trainings in M&E and Finance for the SR's will be conducted annually during Y3-Y5. Training on monitoring of parcel distribution will be conducted annually in all 5 regions. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 8964 | 0 | 8964
| 4.5 c | SR (NRCS) staff capacity building by conducting study visit to MDR TB patient support (Belgrad or Tomsk, Russia) | Training in provision of MDR-TB support will be arranged for NRCS staff (3 participants in Y3) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 8808 | 0 | 0 | 8808
| 4.5 d | Cost of capacity development activities of national entities to implement national disease response | Lumpsum of $10,000 is foreseen for the capacity development of national entities, and will be detailed after development of plan by UNDP headqurters. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 10000 | 10000
| 4.6 | Quality assurance of the 1 and 2 line TB drugs | Quality assurance activities are planned according to QA action plan. Please refer to cost assumption 4.6 | PSM IA Code: 001981 Account: | UNDP | 20656 | 26874.5 | 0 | 0 | 47530.5
| 4.11 | WHO-remuneration for NPO (management and coordination) for 3 years | The salary of the NPO is budgeted for coordination of the activities under SR Agreement, $11,000 per quarter | HR IA Code: 002066 Account: 71400 | WHO | 0 | 22000 | 11000 | 11000 | 44000
| 4.12 | WHO- administrative charges-7% | 7% is budgeted as administrative charges under SR agreement with WHO | OVER IA Code: 002066 Account: 72100 | WHO | 0 | 8571.99 | 14359.2167 | 5293.5867 | 28224.7933
| 4.14 | Salary of TB project coordinator of Health Information center | The salary of TB project Health Information Center will be covered by MOHMI | HR IA Code: 004520 Account: 71400 | Health Information Center | 1418.21 | 0 | 0 | 0 | 1418.21
| 4.15 | Health Information Center - administrative charges- 5% | 5% is budgeted as administrative charges under SR agreement with Health Information Center | OVER IA Code: 004520 Account: 72100 | Health Information Center | 708.04 | 0 | 0 | 0 | 708.04
| 4.18 | UNDP Administrative charges- 7% according to the agreeement between GF and UNDP |  | OVER IA Code: 001981, 002066,004520, 005742 Account: 75100 | UNDP | 138187.9427 | 151133.4665 | 29887.311 | 70209.4877 | 389418.2079
|  | Grand Total |  |  |  | 884025.9824 | 1143294.7013 | 456848.8971 | 1073202.1688 | 3557371.7497
Note on B54: aylar.hayitjanova: quantities of parcels were revised
Note on B92: aylar.hayitjanova: previously was UNDP

## AWP 2014_X
ANNUAL WORK PLAN – YEAR 4 ( 1 October 2013 – 30 September 2014
EXPECTED OUTPUTS Add baseline, indica-tors including annual targets. Please use the numbering of outputs as they are in the RRF/ SRF of ProDoc | PLANNED ACTIVITIES List activity results and associated actions. Please use the numbering of outputs as they are in the RRF/SRF of ProDoc |  | Budget Description | Budget Codes | Responsible party | TIMEFRAME |  |  |  | PLANNED BUDGET
| # | Activity |  |  |  | Q 13 01/10/13 -01/12/13 | Q 14 01/01/14 - 31/03/14 | Q 15 01/04/14 - 30/06/14 | Q 16 01/07/14 - 30/09/14
Objective 1 : To consolidate DOTS framework through strengthening programme management, improving TB case detection and diagnosis and ensuring quality treatment
Number of new smear-positive TB cases notified to the national health authorities during the specified period. Baseline: 2011 – 1,137 Target 2014 - 1,550 Number of all TB cases notified to the national health authorities during the specified period Baseline: 2011 – 3,038 Target 2014 - 4,600 Number of staff from district and regional TB laboratories trained in microscopy techniques and culture methods. Baseline: 2012 - 29 Target 2014 - 30 Number of direct sputum microscopy investigations for TB diagnosis and treatment monitoring. Baseline: 2011 – 85,755 Target 2014 - 95.040 Number of culture investigations (manual technique) for confirmation of TB diagnosis and monitoring of treatment. Baseline: 2011 - 2,198 Target 2014 -10,800 Treatment success rate: new smear positive TB cases. Baseline 2010 – 74% Target 2014 - 82% Number of TB patients receiving incentives (food parcels) for better adherence to treatment during out-patient phase of 1st line treatment. Baseline 2011 – 2,274 Target 2014 - 2,890 | Activity 1.1 :Strengthening management, coordination, monitoring and evaluation of the National Tuberculosis Programme
| 1.1.1 | Training of NTP management staff by attending international conferences abroad (2 participants per year) | Attendance of training courses in various aspects of NTP management and international conferences abroad (Warsaw and Sondalo training courses, European NTP managers' meetings, IUATLD conferences, etc.). Funding for 2 people attending 1 event per year. | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 9604
| 1.1.2 | Training of NTP Regional Units' staff in supervision, monitoring and evaluation | Training for staff of 5 Regional (velayat) NTP Units will be conducted at the NTP Central Unit in different aspects of NTP management (in particular in supervision, monitoring and evaluation) to strengthen capacities of NTP RUs and support decentralization / regionalisation of the NTP management. (10 participants, 1 training in Y3 -Y4) | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 2620
| 1.1.3 a | Quarterly supervision visits by the central NTP Unit ,1 round ( 3 specialists for 3 days in each of 5 regions) | Supervision visits will be conducted by the NTP Central Unit team to 5 velayat centres and selected districts (etraps): quarterly during Years 3-5. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 9792
| 1.1.3 b - new | Quarterly monitoring meetings to discuss the results of monitoring visits | To discuss the key findings, plan the next steps and ensure effective implementation of recommendations of supervision / monitoring visits, quarterly meetings will be held at the CTTP. Participants: representatives of the MOH, regional Departments of Health, Ashgabat City Department of Health, CTTP, regional NTP units, Medical Department of the MoI, NRCS, and the UNDP/GF GIU staff. There will be 12 meetings in total (4 per year, in 2013-2015). | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 4440
| 1.1.9 | Operational expenses of the NTP Central Unit and Regional Units, 5 % price increase is forecasted starting from Y4 | Operational expenses of the NTP Central Unit and Regional (velayat) Units (communication expenses, internet / e-mail stationery, printing, etc.) | OVER IA Code: 001981 Account: 72500, 74200 | UNDP | x | x | x | x | 9786
| 1.1.11 | Training of NTP and TB service staff in upgraded TB recording and reporting system | Staff from the Central and Regional (velayat) NTP units, and key TB service facilities will be trained in the use of revised recording and reporting forms and database management. (15 participants,2 trainings in Y3 - Y5, totally 90 participants) | TR IA Code: 002066 Account: 75700 | WHO |  | x |  | x | 8538
| 1.1.12 | Recruitment of national IT specialist for the management of the national TB database | Local IT specialist will be contracted to assist the NTP in management and maintenance of the national electronic TB database (starting Year 3). | HR IA Code: 002066 Account: 71400 | WHO | x | x | x | x | 8400
Activity 1.2 : Strengthening capacities for TB control in the penitentiary sector
| 1.2.2 | Training in TB management in prisons by attending international conferences abroad | Attendance of training courses in various aspects of TB control in prisons, international conferences abroad and study tours. (3 participants, 1 event in Y3-Y5) | TR IA Code: 002066 Account: 75700 | WHO |  |  | x |  | 15606
| 1.2.3 | Conduct quarterly supervision visits by the Medical department of MIA to the TB treatment site in the penitentiary sector (Mary Prison hospital MRK-15) | Quarterly supervision visits will be conducted by the Medical Department of the Ministry of Internal Affairs to the TB treatment site in the penitentiary sector (Mary velayat) and selected detention sites including pre-trial isolators to monitor case finding and case management practices. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 2040
Activity 1.3 : Strengthening TB laboratory network
| 1.3.1 a | Conduct training of TB peripheral laboratory staff on standard DOTS microscopy modules. | Training and re-training of staff of peripheral microscopy laboratories using standard DOTS microscopy modules will be conducted at the NRL (2 trainings in Y4-Y5). | TR IA Code: 002066 Account: 75700 | WHO | x | 0 | x |  | 5240
| 1.3.1 b | Conduct training of TB regional laboratory staff on conducting culture investigations | Training of staff of regional microscopy laboratories will be conducted at the NRL on culture investigations (1 training in Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO |  | x |  |  | 9062
| 1.3.2 a | Procurement of Reagents for Ziel-Nelsen Microscopy : Sputum smear microscopy investigations | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). ZN was calculated as 75% of this amount, 25% will be done with LED. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 17208.8928
| 1.3.2 c | PSM costs for Reagents for Ziel-Nelsen Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 3742.9342
| 1.3.2 b | Procurement of Reagents for LED Microscopy (Sputum smear microscopy investigations) | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). LED was calculated as 25% of this amount, 75% will be done with ZN. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 9229.968
| 1.3.2 d | PSM costs for Reagents for LED Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 2007.518
| 1.3.3 a | Procurement of Reagents for Culture investigations (manual technique) | Culture investigations (manual technique on solid media) will be performed by the NRL and regional laboratories in Balkanabad,Lebap and Mary, and later in Dashoguz regions. For confirmation of TB 2 tubes and for monitoring of 1 line treatment -2 tubes,at the end of intensive phase (2-3 months), at 4-5 months and at the end of treatment. In 2013 the need in culture investigations is 11,980. It is estimated that the NTP can cover only 50% of this amount (5,990). In 2014 the esitmated need is 12,220 and the expected coverage - 70% or 8,554 .In 2015, the estimated need is 12,850 and the NTP should be able to perform 80% of the need, or 10,280. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 24452.4
| 1.3.3 b | PSM costs for reagents for Culture investigations (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 5318.397
| 1.3.7 a | Procurement of respirators for staff of TB laboratories (Individual measures for infection control) | Procurement of high protection respirators to ensure individual measures of infection control at TB laboratories. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 6219.2
| 1.3.7 b | PSM costs for respirators for staff of TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1352.676
Activity 1. 4 Improving TB case management
| 1.4.2 | Conduct refreshing training for TB doctors using standard DOTS modules | Refreshing training of doctors from TB service institutions using standard DOTS modules will be conducted by the national team of trainers at the central level (15 participants, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | x |  | x |  | 7410
| 1.4.3 | Conduct training for TB nurses using standard DOTS module | DOTS initial training and refreshing training of nurses from TB service institutions (15 participants, 1 training in Y3, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP |  | x |  | 2515 | 5030
| 1.4.4 | Recruitment of international consultant to provide technical assistance to NTP in strengthening TB drugs' management in Y3 | Technical assistance (by an external consultant) will be provided to the NTP to strengthen the drug management system including forecasting, ordering, storage, stock monitoring, distribution, monitoring and management of side effects). 1 mission in Y3 | TA IA Code: 002066 Account: 71200 | WHO |  |  |  |  | 0
| 1.4.5 | Conduct training in TB drugs' management by the NTP Central Unit for TB specialists, key staff and drug managers from the regional level | Training in anti-TB drugs' management will be provided by the NTP Central Unit for TB specialists and drug managers (15 participants, 2 trainings in Y3- Y4) | TR IA Code: 002066 Account: 75700 | WHO |  | x | x |  | 7410
| 1.4.7 a | Procurement of First Line Anti-TB Drugs , 5 % price increase is forecasted starting from Y4 | 1 line TB drugs will be procured for : Y3 - 4,500 patients (civil- 3,300 and penal- 1,200), Y4- 4,600 patients (civil-3,400 and penal -1,200), Y5- 4,600 patients (civil-3,500 and penal-1,100). For civil patients 87%- I, III category and 13%- II category. For penal patients 50%-I, III category, 50%-II category. | MED IA Code: 001981 Account: 72300 | UNDP |  |  |  | x | 200372.856
| 1.4.7 b | PSM costs for First Line Anti-TB-Drugs (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  |  | x | 50093.214
| 1.4.8 a | Procurement of (food parcels) for TB patients,as incentives (support to treatment adherence), 5 % price increase is forecasted starting from Y4 | TB patients on 1line treatment during continuation phase receive monthly food parcels. I, III category- 4 parcels per treatment course, II category - 5 parcels per treatment course. The coverage with support is 85%. | LS IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 327726
| 1.4.8 b | Salary of NRCS personnel (project coordinator,project assistant, 5 patronage nurses) 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. [delivery of food packages to DOTS cabinets and monitoring] | The National Red Crescent Society hired staff in Ashgabat and all regions to implement patient support countrywide. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | x | x | x | x | 40527.4954
| 1.4.8 c | Transportation of parcels до DOTS cabinets.[delivery of food packages to DOTS cabinets ] | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | x | x | x | x | 46491.165
| 1.4.8 d | Quarterly monitoring visits by central NRCS [delivery of food packages to DOTS cabinets and monitoring] | Central level of NRCS will conduct quarterly monitoring visits to verify reporting on number of patients receiving food parcels ( 3 days, 2 person to 2 regions) | M&E IA Code: 005742 Account: 71600 | NRCS | x | x | x | x | 9296.1665
| 1.4.8 e | Monthly monitoring visits by regional NRCS [delivery of food packages to DOTS cabinets and monitoring] | Regional level of NRCS will conduct monthly verification of number of patients receiving food parcels, survey on patient satisfaction, and provision of consultation to TB specialists on distribution of food parcels (3 days, 1 person, 2 etraps per month) | M&E IA Code: 005742 Account: 71600 | NRCS | x | x | x | x | 18509.22
| 1.4.8 g | Internet and telephone communication for NRCS personnel at 5 velayats and Ashgabat.[delivery of food packages to DOTS cabinets and monitoring] | Operational expenses of NRCS (communication expenses, internet) will be covered. | IF IA Code: 005742 Account: 72400 | NRCS | x | x | x | x | 1684.2105
Activity 1.5 :TB advocacy, communication and social mobilisation (ACSM)
| 1.5.3 | Conduct training workshops for mass media representatives on priority issues of TB control. | Training workshops will be organised for mass media representatives in priority issues of TB control to enhance public awareness and social mobilisation for effective TB control. 1 workshops will be organised for 20 participants in Y3-Y5, before the World TB day. | TR IA Code: 004520 Account: 75700 | Health Information Center |  | x |  |  | 910
| 1.5.5 | Design, produce and broadcast TB informational and educational materials: video (10% increase forecasted starting from Y4) | Video spots will be designed, produced and broadcasted that will aim at increasing public awareness and social mobilisation for better TB control (in Y3-Y5). | COM IA Code: 004520 Account: 74200 | Health Information Center |  |  | x |  | 3300
| 1.5.6 | Operational costs for TB Resource Center at the Ministry of Health Information Centre (5 % increase is forecasted starting from Y4) | Operational expenses of TB resource center (communication expenses, internet) will be covered. | IF IA Code: 004520 Account: 72400 | Health Information Center | x | x | x | x | 8694
| 1.5.7 a | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | COM IA Code: 004520 Account: 74200 | Health Information Center |  | x |  |  | 2674.4311
| 1.5.8 | Training workshops for community leaders on TB control | Trainings workshops for community activists will be held to generate public awareness and raise social commitment at community level for fighting TB, with emphasis on reducing TB-related stigmatization and using community and family levers to motivate the patients to complete treatment and avoid the development of drug resistance. NRCS will train 100 people per year (13 participants, 8 trainings in Y3-Y5). | TR IA Code: 005742 Account: 75700 | NRCS | x | x | x | x | 17096
Activity 1.6 Collaborative activities for control of TB / HIV co-infection
| 1.6.3 | Recruitment of international consultant to evaluate the progress of interventionas in strengthening diagnostic counselling and testing (DCT) for HIV among TB patients in Y4 [Technical assistance] | In Year 4, technical assistance (by an external consultant) will be provided to the NTP and National AIDS Prevention Centre to evaluate progress after Phase 1 mission and plan interventions and develop recommendations for future actions. | TA IA Code: 002066 Account: 71200 | WHO | x |  |  |  | 9928
| 1.6.4 | Training of TB service staff in diagnostic counselling and testing (DCT) for HIV | It is planned to train 90 TB specialists from all velayats and penitentiary sector in HIV diagnostic counselling and testing (DCT) among TB patients in order to improve access to and quality of the service.(15 participants,1 training in Y3, 3 trainings in Y4, 2 trainings in Y5) | TR IA Code: 002066 Account: 75700 | WHO | x | x | x |  | 10407
Objective 2 :To improve the health system performance for effective tuberculosis control
Number of TB and PHC services staff (doctors and nurses) trained and re-trained in DOTS, drug management and MDR-TB management. Baseline: 2011 – 1,168 Target 2014- 480 | Activity 2.1 Strengthening Primary Health Care involvement in TB control
| 2.1.1 | Recruitment of international consultant in strengthening the framework of PHC involvement in TB control in Y4 [Technical assistance] | In Year 4, external technical assistance will be provided to evaluate the project interventions in PHC performance in regard to TB control. | TA IA Code: 002066 Account: 71200 | WHO |  | x |  |  | 12112
| 2.1.4 | Conduct training of PHC doctors from all regions in TB control (3 days, 20 participants, Q9 - 6 trainings ; 3 days, 15 participants Q11- 1 training, Q 12 - 1 training; Y4-8 trainings, Y5-8 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants; Y4-8 trainings ).Will include general doctors from the penitentiary sector. 1,060 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | x | x | x | x | 25304
| 2.1.5 | Conduct training of PHC nurses from all regions and penitentiary sector in TB control (3 days, 20 participants, Q9-6 trainings; 3 days, 15 participants Q11- 2 training, Q 12 - 1 training; Y4-8 trainings, Y5- 5 trainings) | It is planned to train PHC nurses from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, Y4-8 trainings of 15 participants , Y5- 5 trainings of 15 participants).Will include nurses from the penitentiary sector. 1,030 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | x | x | x | x | 25304
| 2.1.7 | Organize national workshop in Y4 to review the performance of PHC services in relation to TB control and plan future actions | One national workshops will be organised in Years 4 to review performance of PHC services in relation to TB control and plan future actions. | TR IA Code: 002066 Account: 75700 | WHO |  |  | x |  | 10924
| 2.1.8-new | Monitoring of effectiveness of PHC trainings on DOTS | Members of the HSS working group will conduct mini-assessment of effectiveness of the PHC trainings. They will conduct visits to 3 velayats semiannually in Y3-Y4 and once in Y5. Trained PHC staff will be surveyed with the post-test questionnaire with aim to assess how the knowledge "survives" after 3,6, 12 months following training, how the PHC doctors use the knowledge in the daily practice, what gaps remain. The results will be communicated to the trainers and used for adjustment of training modules. | M&E IA Code: 002066 Account: 71600 | WHO |  | x |  | x | 2957.3333
Activity 2.2 Strengthening key health system functions for effective TB control
| 2.2.4 | Recruitment of international and local consultant to provide technical assistance in human resources planning for TB control in Y4. | Technical assistance (by an external and a local expert) will be provided to the Ministry of Health in mid-term and longer term manpower planning for TB control, to be aligned with the overall health system human resources development strategy. One consultancy mission is planned in Y4. | TA IA Code: 002066 Account: 71200 | WHO | x |  |  |  | 13994
Activity 2.3 : Introducing Practical Approach to Lung Health (PAL)
| 2.3.2 | Recruitment of local consultant to provide technical assistance in monitoring and evaluation of PAL implementation in the pilot area in Y4 | Local consultant will monitor implementation of PAL activities in the pilot regions. Cost includes fees, travel to pilot areas. | TA IA Code: 002066 Account: 71300 | WHO | x | x | x | x | 6000
| 2.3.5 | Conduct training of general health service doctors in PAL in the pilot regions (20 participants,Y4-7 trainings, Y5- 3 trainings) | Training of general health service doctors in PAL will be conducted in the pilot region during Years 4-5. Totally 200 specialists will be trained (20 participants,Y4-7 trainings, Y5- 3 trainings). | TR IA Code: 002066 Account: 75700 | WHO | x | x | x | x | 27174
Objective 3 :To introduce and expand access to diagnosis and treatment of drug-resistant tuberculosis
TB cases with results for diagnostic drug susceptibility testing for MDR-TB among those eligible Baseline: 2011 – 40.5% Target 2014- 63% Confirmed MDR-TB cases enrolled on treatment: Laboratory-confirmed MDR-TB cases enrolled on 2nd line anti-TB treatment during the specified period of assessment (number) Baseline: N/a Target 2014 - 210 Number of MDR-TB patients on out-patient treatment receiving patient support (food incentives) for better adherence to treatment. Baseline: N/a Target 2014 - 128 Interim results: culture conversion at six months: MDR-TB cases initiated on a 2nd line anti-TB treatment who have a negative culture at the end of six months of treat-ment during the specified period of assessment (number and percentage) Baseline: N/a Target 2014 - 76% | Activity 3.1.Strengthening national capacities for management of drug-resistant tuberculosis
| 3.1.1 | Support to the Green Light Committee operations (GLC Fee) | GLC monitoring missions and operational support to the GLC in accordance to agreement between the GLC and the Global Fund ($25,000 per year) | P&A IA Code: 001981 Account: 72100 | UNDP |  | x |  |  | 25000
| 3.1.5 | Conduct local training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff from DR-TB treatment delivery sites | Training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff DR-TB treatment delivery sites (15 participants,2 trainings in Y3-Y5, totally 90 participants) | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x | x | 10420
| 3.1.6 | Conduct local training in MDR-TB management for Primary Health Care services, who will be involved in follow-up of DR-TB patients | Training in MDR-TB management for staff from PHC service who will be involved in follow-up of MDR-TB patients during out-patient phase of treatment with special emphasis on psychosocial support to ensure adherence. It is planned to train 300 PHC providers ( 15 participants,2 trainings in Y3, 8 trainings in Y4, 10 trainings in Y5). | TR IA Code: 001981 Account: 75700 | UNDP | x | x | x | x | 26320
| 3.1.7 | Conduct training for staff from MDR-TB treatment sites and regional laboratories for infection control | Local training on infection control will be organised for staff from MDR-TB treatment delivery sites and regional laboratories: totally 120 persons to be trained (20 participants, 1 training - Y3, 3 trainings in Y4 , 2 trainings in Y5). | TR IA Code: 002066 Account: 75700 | WHO | x |  | x | x | 13182
| 3.1.8 | Installlation of ventilation system of MDR-TB in-patient department of penitentiary sector (MRK-15) | Limited support is requested for infrastructure rehabilitation at MDR-TB at Central Prison Hospital (for installation of the external negative pressure ventilation system, patient separation measures and ensuring proper drug storage conditions) for treatment of MDR-TB patients starting in the prison in 2014. | IF IA Code: 001981 Account: 72100 | UNDP | x |  |  |  | 296487
| 3.1.11 | Recruitment of international consultant for the development of Infection Control (IC) plans for MDR-TB sites and bacteriological laboratories in Y3 -Mary and Turkmenabad, Y4- Dashoguz | Technical assistance will be provided for development of IC plans at the regional TB laboratories of BSL 3. Cost includes consultant fees, travel to the regional laboratories and translation costs. | TA IA Code: 002066 Account: 71200 | WHO | x |  |  |  | 18084
| 3.1.12 | Installation of doors and windows in 4 MDR TB sites in 4 regions - Mary, Turkmenabad, Balkanabad, Dashoguz. Estimated unit cost $36,667 per department (Infection control in MDR TB sites) | Small MDR-TB departments will be renovated to ensure IC measures and ensure availability of MDR-TB beds at each regional TB hospital. Cost includes installation of windows and doors, ventilators, small repair works, ensuring uninterrupted electrical, heating and sanitaryware nets, and establishment of hall tambours -locks. | IF IA Code: 001981 Account: 72100 | UNDP | x |  |  |  | 150665.8125
| 3.1.13 | Training of NRCS personnel in infection control | Local training on infection control will be organised for the NRCS staff working with the MDR-TB patients (12 participants, 1 training in Y3-5) | TR IA Code: 001981 Account: 75700 | UNDP |  | x |  |  | 2244
Activity 3.2 Drug resistance surveillance and diagnosis of drug-resistant TB cases
| 3.2.5 b | MGIT technology equipment 12 month service contract | Maintence cost is budgeted for 4 MGIT machines ( 3 - procured within Grant and 1 -previously already in place at NRL). | HP IA Code: 001981 Account: 72200 | UNDP |  |  | x |  | 27795
| 3.2.5 c | PSM costs for MGIT technology in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  | x |  | 6045.4125
| 3.2.6 b | PCR GenoType equipment 12 month service contract | Maintence cost is budgeted for 2 PCR machines. | HP IA Code: 001981 Account: 72200 | UNDP |  |  | x |  | 2866.9714
| 3.2.6 c | PSM costs for PCR GenoType MTBDR Plus technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  | x |  | 623.5663
| 3.2.7 b | GeneXpert 12 month service contract | Maintence cost is budgeted for 6 GeneXpert machines. | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 8857.3219
| 3.2.7 c | PSM costs for GeneXperts for Balkan and Ahal regional TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 1926.4675
| 3.2.8 a | Culture and DST to 1st line drugs for DR-TB diagnosis (automated MGIT technique) | Culture investigations (automated technique on liquid media) will be performed by the NRL and regional laboratories.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 32223.3333
| 3.2.8 b | PSM costs for Culture and DST to 1st line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 7008.575
| 3.2.9 a | DST to 1st line drugs (manual technique) | DST to 1st line drugs will be performed in culture-positive cases using manual technique on solid media, for quality assurance of automated MGIT technique.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 1308.3
| 3.2.9 b | PSM costs for DST to 1st line drugs (manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 284.5553
| 3.2.10 a | Tests for rapid identification of R/H resistance | Identification of strains and express testing for R/H resistance to be performed by the NRL and regional laboratories. In 2013 the estimated number of tests is 1380, in 2014 -2040, 2015-2400. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 33354
| 3.2.10 b | PSM costs for tests for rapid identification of R/H resistance (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 7254.495
| 3.2.11 a | Tests for rapid detection and MDR screening, GeneXpert technology | Procurement of supplies for tests by automated sample processing, detection of M. tuberculosis and screening for R resistance (GeneXpert technology).In 2013 the estimated number of tests is 2490, in 2014 -3540, 2015-3980) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 39920
| 3.2.11 b | PSM costs for rapid detection and MDR screening GeneXpert technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 8682.6
| 3.2.12 | Cost of missions of SRL experts to the NRL in Ashgabat. | Visits of SRL (National Mycobacteria Reference Laboratory, National Institute of Public Health and the Environment, Bilthoven, The Netherlands) to the NRL with the scope of technical assistance and external laboratory quality assurance (1 mission per Y3-Y5) | TA IA Code: 002066 Account: 71200 | WHO |  |  | x |  | 9640
| 3.2.13 | Cost of on-site training of NRL specialists at the SRL, | NRL specialists will visit the SRL in Bilthoven, Netherlands, for for in-depth on-site training on new techniques (1 trainining for 3 participants per Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 15204
| 3.2.14 | External laboratory quality assurance: shipment of strains to the Supranational Reference Laboratory | With the scope of external laboratory quality assurance of DST to 1st line and 2nd line TB drugs in support of the DR-TB management programme, strains will be shipped quarterly to the Supranational Reference Laboratory (SRL) in Bithoven, Netherlands. | P&A IA Code: 001981 Account: 72100 | UNDP | x | x | x | x | 11000
Activty 3.3 Treatment of drug-resistant TB cases
| 3.3.1 a | Procurement of reagents for culture investigations for MDR-TB patients on treatment (manual technique) | Cultures by manual technique on solid media will be performed for monitoring of treatment of MDR-TB patients.Calculations were done based on National MDR-TB Protocol. In 2013 the estimated number of tests is 660, in 2014 -2244, 2015-4356. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 6440.28
| 3.3.1 b | PSM costs for reagents for culture investigations for MDR-TB patients on treatment ,manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1400.7609
| 3.3.2 a | Procurement of reagents for DST to 2nd line drugs for DR-TB patients on treatment (manual technique) | DST to 2nd line drugs will be performed in all MDR-TB patients on treatment. DST to 2nd line will be conducted in accordance with National MDR-TB Protocol.In 2013 the estimated number of tests is 100, in 2014 -340, 2015-660 | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 26264.8
| 3.3.2 b | PSM costs for reagents for DST to 2nd line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 5712.594
| 3.3.3 a | Procurement of 2nd line anti-TB drugs for MDR-TB patients | 2nd line TB drugs will be procured for 550 patients (Y3-50, Y4-170, Y5-330 patients). The drugs and their quantities are based on the National MDR-TB Protocol. | MED IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 505133.8656
| 3.3.3 b | PSM costs for 2nd line anti-TB drugs for MDR-TB patients to the country (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 126283.4664
| 3.3.5 a -revised (distributed between 3 lines) | Cost of reagents for electrolyte analysis for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for hypokaliemia side effect of second line treatment. The budget was allocated for reagents, while the tests will be done using electrolyte analyzers, procured under Grant. | HP IA Code: 001981 Account: 72300 | UNDP | x | x | x | x | 8766.2899
| 3.3.5 b- revised (distributed between 3 lines) | PSM costs for reagents for electrolyte analysis | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x | x | x | x | 1906.668
| 3.3.5 c- revised (distributed between 3 lines) | Cost of clinical investigations for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for side effects of second line treatment: thyroid gland function, hypokaliemia and screened for viral hepatitis. The budget was allocated based on the number of patients and tests as required by the National MDR-TB Protocol. | LS IA Code: 001981 Account: 72100 | UNDP | x | x | x | x | 15714.4342
| 3.3.6 b | Spare parts (filters and UV-C bulbs ) for UV lamps for 1 year non-stop operation | Spare parts will be procured for the 100 lamps procured in Phase 1 and 30 lamps in Y5. | HP IA Code: 001981 Account:72200 | UNDP | x |  |  |  | 7000
| 3.3.6 c | PSM costs for ultraviolet lamps (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1522.5
| 3.3.7 а | Procurement of respirators for MDR-TB sites and BK+ departments [Individual measures for infection control] | High protection respirators will be procured for MDR-TB sites and BK+ departments to ensure individual measures of IC ( 69,000 per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 55200
| 3.3.7 d | PSM costs for respirators for MDR-TB sites and BK+ departments, NRCS staff and masks | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 12006
Activity 3.4 Patient support programme for drug-resistant TB patients
| 3.4.3 a | Conduct MDR-TB patient patient education and counselling sessions by adherence counsellors | Patient education and counselling sessions will be conducted by adherence counsellors in out-patient basis.Estimated number of sessions: 2 quarter-6 sessions, 13 quarter- 12 sessions, 14-20 quarters- 36 sessions. | TR IA Code: 005742 Account: 75700 | NRCS | x | x | x | x | 21583.1579
| 3.4.3 b | Salary for 5 patronage nurses engaged in counselling sessions and DOT supporting 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. | The National Red Crescent Society plans to hire staff in Ashgabat and regions for councelling sevices. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | x | x | x | x | 25676.9568
| 3.4.4 b | Cost of delivery food parcels to DOTS cabinets | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS |  | x | x | x | 2538.9
| 3.4.5 | Cost of transportation of visiting DOT supporters for visits DR-TB patients [Support to treatment adherence ] | Patient counsellors will visit MDR-TB patients to provide support. Cost includes transportation. Patients will be also supported by phone communication, which is budgeted under the activity 3.4.8 b. | PSM IA Code: 005742 Account: 72100 | NRCS | x | x | x | x | 24631.5789
| 3.4.8 b | Operational expenses -stationery, telephone communication | Operational expenses of the NRCS (stationery, office supplies) are covered by the Grant. | OVER IA Code: 005742 Account: 72500 | NRCS | x | x | x | x | 2042.1053
Objective 4 Project management and administration
| 4.1 a | Salaries for Principal Recipient's PIU staff | The activity includes budget for GIU staff of 9 person (please see cost assumption 4.1) | HR IA Code: 001981 Account: 71400 | UNDP | x | x | x | x | 145377.24
| 4.1 b | Monitoring visits by GIU plan | Supervision visits will be conducted by quarterly by M&E team (M&E specialist and Senior TB Specialist) and by Construction Specialist to the renovation sites in Mary and Dashoguz. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 7688
| 4.2 a | Cost of GIU unit operational expenses | Cost of GIU unit operation expenses- office rent, internet, telephone communication, 5 % increase is forecasted starting from Y4 | OVER IA Code: 001981 Account: 72400, 72500, 73100, 73500 | UNDP | x | x | x | x | 52179.12
| 4.2 b | Cost of GIU unit operational expenses | Cost of GIU unit operational expenses - office supplies, bank and translation charges, 5 % increase is forecasted starting from Y4 | P&A IA Code: 001981 Account: 74200, 74500 | UNDP | x | x | x | x | 9600
| 4.4 a | Cost of external SR audit | External audit will be conducted for 2 SR's on annual basis- NRCS and Health Information Center | P&A IA Code: 001981 Account: 74100 | UNDP |  |  | x |  | 2000
| 4.5 a | PR capacity building by attending various conferences, seminars, educational workshops for effective grant implementation | Trainings for capacity building of PR staff will be arranged in ( 2 trainings for 3 GIU staff members in Y3-Y5) | TR IA Code: 001981 Account: 75700 | UNDP |  | x |  | x | 22812
| 4.5 b | SR capacity building by participation in seminars, educational workshops for effective grant implementation | Trainings in M&E and Finance for the SR's will be conducted annually during Y3-Y5. Training on monitoring of parcel distribution will be conducted annually in all 5 regions. | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x |  | 8964
| 4.5 d | Cost of capacity development activities of national entities to implement national disease response | Lumpsum of $10,000 is foreseen for the capacity development of national entities, and will be detailed after development of plan by UNDP headqurters. | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 10000
| 4.6 | Quality assurance of the 1 and 2 line TB drugs | Quality assurance activities are planned according to QA action plan. Please refer to cost assumption 4.6 | PSM IA Code: 001981 Account: | UNDP |  | x |  |  | 26874.5
| 4.11 | WHO-remuneration for NPO (management and coordination) for 3 years | The salary of the NPO is budgeted for coordination of the activities under SR Agreement, $11,000 per quarter | HR IA Code: 002066 Account: 71400 | WHO | x | x | x | x | 44000
| 4.12 | WHO- administrative charges-7% | 7% is budgeted as administrative charges under SR agreement with WHO | OVER IA Code: 002066 Account: 72100 | WHO | x | x | x | x | 17533.7633
| 4.18 | UNDP Administrative charges- 7% according to the agreeement between GF and UNDP |  | OVER IA Code: 001981, 002066,004520, 005742 Account: 75100 | UNDP | x | x | x | x | 209946.7629
|  | Grand Total |  |  |  | 2073456.1663 | 304491.0764 | 300754.4107 | 530484.5792 | 3209186.2326
Note on B35: aylar.hayitjanova: quantities of parcels were revised
Note on B55: aylar.hayitjanova: previously was UNDP

## AWP 2014
ANNUAL WORK PLAN – YEAR 4 ( 1 October 2013 – 30 September 2014
EXPECTED OUTPUTS Add baseline, indica-tors including annual targets. Please use the numbering of outputs as they are in the RRF/ SRF of ProDoc | PLANNED ACTIVITIES List activity results and associated actions. Please use the numbering of outputs as they are in the RRF/SRF of ProDoc |  | Budget Description | Budget Codes | Responsible party | TIMEFRAME |  |  |  | PLANNED BUDGET
| # | Activity |  |  |  | Q 13 01/10/13 -01/12/13 | Q 14 01/01/14 - 31/03/14 | Q 15 01/04/14 - 30/06/14 | Q 16 01/07/14 - 30/09/14
Objective 1 : To consolidate DOTS framework through strengthening programme management, improving TB case detection and diagnosis and ensuring quality treatment | [10 empty] | 2999239.4698
Number of new smear-positive TB cases notified to the national health authorities during the specified period. Baseline: 2011 – 1,137 Target 2014 - 1,550 Number of all TB cases notified to the national health authorities during the specified period Baseline: 2011 – 3,038 Target 2014 - 4,600 Number of staff from district and regional TB laboratories trained in microscopy techniques and culture methods. Baseline: 2012 - 29 Target 2014 - 30 Number of direct sputum microscopy investigations for TB diagnosis and treatment monitoring. Baseline: 2011 – 85,755 Target 2014 - 95.040 Number of culture investigations (manual technique) for confirmation of TB diagnosis and monitoring of treatment. Baseline: 2011 - 2,198 Target 2014 -10,800 Treatment success rate: new smear positive TB cases. Baseline 2010 – 74% Target 2014 - 82% Number of TB patients receiving incentives (food parcels) for better adherence to treatment during out-patient phase of 1st line treatment. Baseline 2011 – 2,274 Target 2014 - 2,890 |  | Activity 1.1 :Strengthening management, coordination, monitoring and evaluation of the National Tuberculosis Programme
| 1.1.1 | Training of NTP management staff by attending international conferences abroad (2 participants per year) | Attendance of training courses in various aspects of NTP management and international conferences abroad (Warsaw and Sondalo training courses, European NTP managers' meetings, IUATLD conferences, etc.). Funding for 2 people attending 1 event per year. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 9604 | 9604 | 0
| 1.1.2 | Training of NTP Regional Units' staff in supervision, monitoring and evaluation | Training for staff of 5 Regional (velayat) NTP Units will be conducted at the NTP Central Unit in different aspects of NTP management (in particular in supervision, monitoring and evaluation) to strengthen capacities of NTP RUs and support decentralization / regionalisation of the NTP management. (10 participants, 1 training in Y3 -Y4) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 2620 | 2620
| 1.1.3 a | Quarterly supervision visits by the central NTP Unit ,1 round ( 3 specialists for 3 days in each of 5 regions) | Supervision visits will be conducted by the NTP Central Unit team to 5 velayat centres and selected districts (etraps): quarterly during Years 3-5. | M&E IA Code: 001981 Account: 71600 | UNDP | 2448 | 2448 | 2448 | 2448 | 9792 | 0
| 1.1.3 b - new | Quarterly monitoring meetings to discuss the results of monitoring visits | To discuss the key findings, plan the next steps and ensure effective implementation of recommendations of supervision / monitoring visits, quarterly meetings will be held at the CTTP. Participants: representatives of the MOH, regional Departments of Health, Ashgabat City Department of Health, CTTP, regional NTP units, Medical Department of the MoI, NRCS, and the UNDP/GF GIU staff. There will be 12 meetings in total (4 per year, in 2013-2015). | M&E IA Code: 001981 Account: 71600 | UNDP | 1110 | 1110 | 1110 | 1110 | 4440
| 1.1.9 | Operational expenses of the NTP Central Unit and Regional Units, 5 % price increase is forecasted starting from Y4 | Operational expenses of the NTP Central Unit and Regional (velayat) Units (communication expenses, internet / e-mail stationery, printing, etc.) | OVER IA Code: 001981 Account: 72500, 74200 | UNDP | 2446.5 | 2446.5 | 2446.5 | 2446.5 | 9786
| 1.1.11 | Training of NTP and TB service staff in upgraded TB recording and reporting system | Staff from the Central and Regional (velayat) NTP units, and key TB service facilities will be trained in the use of revised recording and reporting forms and database management. (15 participants,2 trainings in Y3 - Y5, totally 90 participants) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 4269 | 0 | 4269 | 8538
| 1.1.12 | Recruitment of national IT specialist for the management of the national TB database | Local IT specialist will be contracted to assist the NTP in management and maintenance of the national electronic TB database (starting Year 3). | HR IA Code: 002066 Account: 71400 | WHO | 2100 | 2100 | 2100 | 2100 | 8400
Activity 1.2 : Strengthening capacities for TB control in the penitentiary sector
| 1.2.2 | Training in TB management in prisons by attending international conferences abroad | Attendance of training courses in various aspects of TB control in prisons, international conferences abroad and study tours. (3 participants, 1 event in Y3-Y5) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 15606 | 0 | 15606
| 1.2.3 | Conduct quarterly supervision visits by the Medical department of MIA to the TB treatment site in the penitentiary sector (Mary Prison hospital MRK-15) | Quarterly supervision visits will be conducted by the Medical Department of the Ministry of Internal Affairs to the TB treatment site in the penitentiary sector (Mary velayat) and selected detention sites including pre-trial isolators to monitor case finding and case management practices. | M&E IA Code: 001981 Account: 71600 | UNDP | 510 | 510 | 510 | 510 | 2040
Activity 1.3 : Strengthening TB laboratory network
| 1.3.1 a | Conduct training of TB peripheral laboratory staff on standard DOTS microscopy modules. | Training and re-training of staff of peripheral microscopy laboratories using standard DOTS microscopy modules will be conducted at the NRL (2 trainings in Y4-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 2620 | 0 | 2620 | 0 | 5240
| 1.3.1 b | Conduct training of TB regional laboratory staff on conducting culture investigations | Training of staff of regional microscopy laboratories will be conducted at the NRL on culture investigations (1 training in Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 9062 | 0 | 0 | 9062
| 1.3.2 a | Procurement of Reagents for Ziel-Nelsen Microscopy : Sputum smear microscopy investigations | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). ZN was calculated as 75% of this amount, 25% will be done with LED. | HP IA Code: 001981 Account: 72300 | UNDP | 17208.8928 | 0 | 0 | 0 | 17208.8928
| 1.3.2 c | PSM costs for Reagents for Ziel-Nelsen Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 3742.9342 | 0 | 0 | 0 | 3742.9342
| 1.3.2 b | Procurement of Reagents for LED Microscopy (Sputum smear microscopy investigations) | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). LED was calculated as 25% of this amount, 75% will be done with ZN. | HP IA Code: 001981 Account: 72300 | UNDP | 9229.968 | 0 | 0 | 0 | 9229.968
| 1.3.2 d | PSM costs for Reagents for LED Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 2007.518 | 0 | 0 | 0 | 2007.518
| 1.3.3 a | Procurement of Reagents for Culture investigations (manual technique) | Culture investigations (manual technique on solid media) will be performed by the NRL and regional laboratories in Balkanabad,Lebap and Mary, and later in Dashoguz regions. For confirmation of TB 2 tubes and for monitoring of 1 line treatment -2 tubes,at the end of intensive phase (2-3 months), at 4-5 months and at the end of treatment. In 2013 the need in culture investigations is 11,980. It is estimated that the NTP can cover only 50% of this amount (5,990). In 2014 the esitmated need is 12,220 and the expected coverage - 70% or 8,554 .In 2015, the estimated need is 12,850 and the NTP should be able to perform 80% of the need, or 10,280. | HP IA Code: 001981 Account: 72300 | UNDP | 24452.4 | 0 | 0 | 0 | 24452.4
| 1.3.3 b | PSM costs for reagents for Culture investigations (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 5318.397 | 0 | 0 | 0 | 5318.397
| 1.3.7 a | Procurement of respirators for staff of TB laboratories (Individual measures for infection control) | Procurement of high protection respirators to ensure individual measures of infection control at TB laboratories. | HP IA Code: 001981 Account: 72300 | UNDP | 6219.2 | 0 | 0 | 0 | 6219.2
| 1.3.7 b | PSM costs for respirators for staff of TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1352.676 | 0 | 0 | 0 | 1352.676
Activity 1. 4 Improving TB case management
| 1.4.2 | Conduct refreshing training for TB doctors using standard DOTS modules | Refreshing training of doctors from TB service institutions using standard DOTS modules will be conducted by the national team of trainers at the central level (15 participants, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 3705 | 0 | 3705 | 0 | 7410
| 1.4.3 | Conduct training for TB nurses using standard DOTS module | DOTS initial training and refreshing training of nurses from TB service institutions (15 participants, 1 training in Y3, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 2515 | 0 | 2515 | 5030
| 1.4.4 | Recruitment of international consultant to provide technical assistance to NTP in strengthening TB drugs' management in Y3 | Technical assistance (by an external consultant) will be provided to the NTP to strengthen the drug management system including forecasting, ordering, storage, stock monitoring, distribution, monitoring and management of side effects). 1 mission in Y3 | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 0 | 0 | 0
| 1.4.5 | Conduct training in TB drugs' management by the NTP Central Unit for TB specialists, key staff and drug managers from the regional level | Training in anti-TB drugs' management will be provided by the NTP Central Unit for TB specialists and drug managers (15 participants, 2 trainings in Y3- Y4) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 3705 | 3705 | 0 | 7410
| 1.4.7 a | Procurement of First Line Anti-TB Drugs , 5 % price increase is forecasted starting from Y4 | 1 line TB drugs will be procured for : Y3 - 4,500 patients (civil- 3,300 and penal- 1,200), Y4- 4,600 patients (civil-3,400 and penal -1,200), Y5- 4,600 patients (civil-3,500 and penal-1,100). For civil patients 87%- I, III category and 13%- II category. For penal patients 50%-I, III category, 50%-II category. | MED IA Code: 001981 Account: 72300 | UNDP | 0 | 0 | 0 | 200372.856 | 200372.856
| 1.4.7 b | PSM costs for First Line Anti-TB-Drugs (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 0 | 50093.214 | 50093.214
| 1.4.8 a | Procurement of (food parcels) for TB patients,as incentives (support to treatment adherence), 5 % price increase is forecasted starting from Y4 | TB patients on 1line treatment during continuation phase receive monthly food parcels. I, III category- 4 parcels per treatment course, II category - 5 parcels per treatment course. The coverage with support is 85%. | LS IA Code: 001981 Account: 72300 | UNDP | 327726 | 0 | 0 | 0 | 327726
| 1.4.8 b | Salary of NRCS personnel (project coordinator,project assistant, 5 patronage nurses) 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. [delivery of food packages to DOTS cabinets and monitoring] | The National Red Crescent Society hired staff in Ashgabat and all regions to implement patient support countrywide. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | 10131.8738 | 10131.8738 | 10131.8738 | 10131.8738 | 40527.4954
| 1.4.8 c | Transportation of parcels до DOTS cabinets.[delivery of food packages to DOTS cabinets ] | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | 11622.7912 | 11622.7912 | 11622.7912 | 11622.7912 | 46491.165
| 1.4.8 d | Quarterly monitoring visits by central NRCS [delivery of food packages to DOTS cabinets and monitoring] | Central level of NRCS will conduct quarterly monitoring visits to verify reporting on number of patients receiving food parcels ( 3 days, 2 person to 2 regions) | M&E IA Code: 005742 Account: 71600 | NRCS | 2324.0416 | 2324.0416 | 2324.0416 | 2324.0416 | 9296.1665
| 1.4.8 e | Monthly monitoring visits by regional NRCS [delivery of food packages to DOTS cabinets and monitoring] | Regional level of NRCS will conduct monthly verification of number of patients receiving food parcels, survey on patient satisfaction, and provision of consultation to TB specialists on distribution of food parcels (3 days, 1 person, 2 etraps per month) | M&E IA Code: 005742 Account: 71600 | NRCS | 4627.305 | 4627.305 | 4627.305 | 4627.305 | 18509.22
| 1.4.8 g | Internet and telephone communication for NRCS personnel at 5 velayats and Ashgabat.[delivery of food packages to DOTS cabinets and monitoring] | Operational expenses of NRCS (communication expenses, internet) will be covered. | IF IA Code: 005742 Account: 72400 | NRCS | 421.0526 | 421.0526 | 421.0526 | 421.0526 | 1684.2105
Activity 1.5 :TB advocacy, communication and social mobilisation (ACSM)
| 1.5.3 | Conduct training workshops for mass media representatives on priority issues of TB control. | Training workshops will be organised for mass media representatives in priority issues of TB control to enhance public awareness and social mobilisation for effective TB control. 1 workshops will be organised for 20 participants in Y3-Y5, before the World TB day. | TR IA Code: 004520 Account: 75700 | Health Information Center | 0 | 910 | 0 | 0 | 910
| 1.5.5 | Design, produce and broadcast TB informational and educational materials: video (10% increase forecasted starting from Y4) | Video spots will be designed, produced and broadcasted that will aim at increasing public awareness and social mobilisation for better TB control (in Y3-Y5). | COM IA Code: 004520 Account: 74200 | Health Information Center | 0 | 0 | 3300 | 0 | 3300
| 1.5.6 | Operational costs for TB Resource Center at the Ministry of Health Information Centre (5 % increase is forecasted starting from Y4) | Operational expenses of TB resource center (communication expenses, internet) will be covered. | IF IA Code: 004520 Account: 72400 | Health Information Center | 2173.5 | 2173.5 | 2173.5 | 2173.5 | 8694
| 1.5.7 a | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | COM IA Code: 004520 Account: 74200 | Health Information Center | 0 | 2674.4311 | 0 | 0 | 2674.4311
| 1.5.8 | Training workshops for community leaders on TB control | Trainings workshops for community activists will be held to generate public awareness and raise social commitment at community level for fighting TB, with emphasis on reducing TB-related stigmatization and using community and family levers to motivate the patients to complete treatment and avoid the development of drug resistance. NRCS will train 100 people per year (13 participants, 8 trainings in Y3-Y5). | TR IA Code: 005742 Account: 75700 | NRCS | 4274 | 4274 | 4274 | 4274 | 17096
Activity 1.6 Collaborative activities for control of TB / HIV co-infection
| 1.6.3 | Recruitment of international consultant to evaluate the progress of interventionas in strengthening diagnostic counselling and testing (DCT) for HIV among TB patients in Y4 [Technical assistance] | In Year 4, technical assistance (by an external consultant) will be provided to the NTP and National AIDS Prevention Centre to evaluate progress after Phase 1 mission and plan interventions and develop recommendations for future actions. | TA IA Code: 002066 Account: 71200 | WHO | 9928 | 0 | 0 | 0 | 9928
| 1.6.4 | Training of TB service staff in diagnostic counselling and testing (DCT) for HIV | It is planned to train 90 TB specialists from all velayats and penitentiary sector in HIV diagnostic counselling and testing (DCT) among TB patients in order to improve access to and quality of the service.(15 participants,1 training in Y3, 3 trainings in Y4, 2 trainings in Y5) | TR IA Code: 002066 Account: 75700 | WHO | 3469 | 3469 | 3469 | 0 | 10407
Objective 2 :To improve the health system performance for effective tuberculosis control
Number of TB and PHC services staff (doctors and nurses) trained and re-trained in DOTS, drug management and MDR-TB management. Baseline: 2011 – 1,168 Target 2014- 480 |  | Activity 2.1 Strengthening Primary Health Care involvement in TB control
| 2.1.1 | Recruitment of international consultant in strengthening the framework of PHC involvement in TB control in Y4 [Technical assistance] | In Year 4, external technical assistance will be provided to evaluate the project interventions in PHC performance in regard to TB control. | TA IA Code: 002066 Account: 71200 | WHO | 0 | 12112 | 0 | 0 | 12112
| 2.1.4 | Conduct training of PHC doctors from all regions in TB control (3 days, 20 participants, Q9 - 6 trainings ; 3 days, 15 participants Q11- 1 training, Q 12 - 1 training; Y4-8 trainings, Y5-8 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants; Y4-8 trainings ).Will include general doctors from the penitentiary sector. 1,060 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | 6326 | 6326 | 6326 | 6326 | 25304
| 2.1.5 | Conduct training of PHC nurses from all regions and penitentiary sector in TB control (3 days, 20 participants, Q9-6 trainings; 3 days, 15 participants Q11- 2 training, Q 12 - 1 training; Y4-8 trainings, Y5- 5 trainings) | It is planned to train PHC nurses from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, Y4-8 trainings of 15 participants , Y5- 5 trainings of 15 participants).Will include nurses from the penitentiary sector. 1,030 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | 6326 | 6326 | 6326 | 6326 | 25304
| 2.1.7 | Organize national workshop in Y4 to review the performance of PHC services in relation to TB control and plan future actions | One national workshops will be organised in Years 4 to review performance of PHC services in relation to TB control and plan future actions. | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 10924 | 0 | 10924
| 2.1.8-new | Monitoring of effectiveness of PHC trainings on DOTS | Members of the HSS working group will conduct mini-assessment of effectiveness of the PHC trainings. They will conduct visits to 3 velayats semiannually in Y3-Y4 and once in Y5. Trained PHC staff will be surveyed with the post-test questionnaire with aim to assess how the knowledge "survives" after 3,6, 12 months following training, how the PHC doctors use the knowledge in the daily practice, what gaps remain. The results will be communicated to the trainers and used for adjustment of training modules. | M&E IA Code: 002066 Account: 71600 | WHO | 0 | 1478.6667 | 0 | 1478.6667 | 2957.3333
Activity 2.2 Strengthening key health system functions for effective TB control
| 2.2.4 | Recruitment of international and local consultant to provide technical assistance in human resources planning for TB control in Y4. | Technical assistance (by an external and a local expert) will be provided to the Ministry of Health in mid-term and longer term manpower planning for TB control, to be aligned with the overall health system human resources development strategy. One consultancy mission is planned in Y4. | TA IA Code: 002066 Account: 71200 | WHO | 13994 | 0 | 0 | 0 | 13994
Activity 2.3 : Introducing Practical Approach to Lung Health (PAL)
| 2.3.2 | Recruitment of local consultant to provide technical assistance in monitoring and evaluation of PAL implementation in the pilot area in Y4 | Local consultant will monitor implementation of PAL activities in the pilot regions. Cost includes fees, travel to pilot areas. | TA IA Code: 002066 Account: 71300 | WHO | 1500 | 1500 | 1500 | 1500 | 6000
| 2.3.5 | Conduct training of general health service doctors in PAL in the pilot regions (20 participants,Y4-7 trainings, Y5- 3 trainings) | Training of general health service doctors in PAL will be conducted in the pilot region during Years 4-5. Totally 200 specialists will be trained (20 participants,Y4-7 trainings, Y5- 3 trainings). | TR IA Code: 002066 Account: 75700 | WHO | 7764 | 7764 | 3882 | 7764 | 27174
Objective 3 :To introduce and expand access to diagnosis and treatment of drug-resistant tuberculosis
TB cases with results for diagnostic drug susceptibility testing for MDR-TB among those eligible Baseline: 2011 – 40.5% Target 2014- 63% Confirmed MDR-TB cases enrolled on treatment: Laboratory-confirmed MDR-TB cases enrolled on 2nd line anti-TB treatment during the specified period of assessment (number) Baseline: N/a Target 2014 - 210 Number of MDR-TB patients on out-patient treatment receiving patient support (food incentives) for better adherence to treatment. Baseline: N/a Target 2014 - 128 Interim results: culture conversion at six months: MDR-TB cases initiated on a 2nd line anti-TB treatment who have a negative culture at the end of six months of treat-ment during the specified period of assessment (number and percentage) Baseline: N/a Target 2014 - 76% |  | Activity 3.1.Strengthening national capacities for management of drug-resistant tuberculosis
| 3.1.1 | Support to the Green Light Committee operations (GLC Fee) | GLC monitoring missions and operational support to the GLC in accordance to agreement between the GLC and the Global Fund ($25,000 per year) | P&A IA Code: 001981 Account: 72100 | UNDP | 0 | 25000 | 0 | 0 | 25000
| 3.1.5 | Conduct local training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff from DR-TB treatment delivery sites | Training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff DR-TB treatment delivery sites (15 participants,2 trainings in Y3-Y5, totally 90 participants) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 5210 | 5210 | 10420
| 3.1.6 | Conduct local training in MDR-TB management for Primary Health Care services, who will be involved in follow-up of DR-TB patients | Training in MDR-TB management for staff from PHC service who will be involved in follow-up of MDR-TB patients during out-patient phase of treatment with special emphasis on psychosocial support to ensure adherence. It is planned to train 300 PHC providers ( 15 participants,2 trainings in Y3, 8 trainings in Y4, 10 trainings in Y5). | TR IA Code: 001981 Account: 75700 | UNDP | 6580 | 6580 | 6580 | 6580 | 26320
| 3.1.7 | Conduct training for staff from MDR-TB treatment sites and regional laboratories for infection control | Local training on infection control will be organised for staff from MDR-TB treatment delivery sites and regional laboratories: totally 120 persons to be trained (20 participants, 1 training - Y3, 3 trainings in Y4 , 2 trainings in Y5). | TR IA Code: 002066 Account: 75700 | WHO | 4394 | 0 | 4394 | 4394 | 13182
| 3.1.8 | Installlation of ventilation system of MDR-TB in-patient department of penitentiary sector (MRK-15) | Limited support is requested for infrastructure rehabilitation at MDR-TB at Central Prison Hospital (for installation of the external negative pressure ventilation system, patient separation measures and ensuring proper drug storage conditions) for treatment of MDR-TB patients starting in the prison in 2014. | IF IA Code: 001981 Account: 72100 | UNDP | 296487 | 0 | 0 | 0 | 296487
| 3.1.11 | Recruitment of international consultant for the development of Infection Control (IC) plans for MDR-TB sites and bacteriological laboratories in Y3 -Mary and Turkmenabad, Y4- Dashoguz | Technical assistance will be provided for development of IC plans at the regional TB laboratories of BSL 3. Cost includes consultant fees, travel to the regional laboratories and translation costs. | TA IA Code: 002066 Account: 71200 | WHO | 18084 | 0 | 0 | 0 | 18084
| 3.1.12 | Installation of doors and windows in 4 MDR TB sites in 4 regions - Mary, Turkmenabad, Balkanabad, Dashoguz. Estimated unit cost $36,667 per department (Infection control in MDR TB sites) | Small MDR-TB departments will be renovated to ensure IC measures and ensure availability of MDR-TB beds at each regional TB hospital. Cost includes installation of windows and doors, ventilators, small repair works, ensuring uninterrupted electrical, heating and sanitaryware nets, and establishment of hall tambours -locks. | IF IA Code: 001981 Account: 72100 | UNDP | 150665.8125 | 0 | 0 | 0 | 150665.8125
| 3.1.13 | Training of NRCS personnel in infection control | Local training on infection control will be organised for the NRCS staff working with the MDR-TB patients (12 participants, 1 training in Y3-5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 2244 | 0 | 0 | 2244
Activity 3.2 Drug resistance surveillance and diagnosis of drug-resistant TB cases
| 3.2.5 b | MGIT technology equipment 12 month service contract | Maintence cost is budgeted for 4 MGIT machines ( 3 - procured within Grant and 1 -previously already in place at NRL). | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 0 | 27795 | 0 | 27795
| 3.2.5 c | PSM costs for MGIT technology in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 6045.4125 | 0 | 6045.4125
| 3.2.6 b | PCR GenoType equipment 12 month service contract | Maintence cost is budgeted for 2 PCR machines. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 0 | 2866.9714 | 0 | 2866.9714
| 3.2.6 c | PSM costs for PCR GenoType MTBDR Plus technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 623.5663 | 0 | 623.5663
| 3.2.7 b | GeneXpert 12 month service contract | Maintence cost is budgeted for 6 GeneXpert machines. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 8857.3219 | 0 | 0 | 8857.3219
| 3.2.7 c | PSM costs for GeneXperts for Balkan and Ahal regional TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 1926.4675 | 0 | 0 | 1926.4675
| 3.2.8 a | Culture and DST to 1st line drugs for DR-TB diagnosis (automated MGIT technique) | Culture investigations (automated technique on liquid media) will be performed by the NRL and regional laboratories.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | 32223.3333 | 0 | 0 | 0 | 32223.3333
| 3.2.8 b | PSM costs for Culture and DST to 1st line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 7008.575 | 0 | 0 | 0 | 7008.575
| 3.2.9 a | DST to 1st line drugs (manual technique) | DST to 1st line drugs will be performed in culture-positive cases using manual technique on solid media, for quality assurance of automated MGIT technique.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | 1308.3 | 0 | 0 | 0 | 1308.3
| 3.2.9 b | PSM costs for DST to 1st line drugs (manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 284.5553 | 0 | 0 | 0 | 284.5553
| 3.2.10 a | Tests for rapid identification of R/H resistance | Identification of strains and express testing for R/H resistance to be performed by the NRL and regional laboratories. In 2013 the estimated number of tests is 1380, in 2014 -2040, 2015-2400. | HP IA Code: 001981 Account: 72300 | UNDP | 33354 | 0 | 0 | 0 | 33354
| 3.2.10 b | PSM costs for tests for rapid identification of R/H resistance (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 7254.495 | 0 | 0 | 0 | 7254.495
| 3.2.11 a | Tests for rapid detection and MDR screening, GeneXpert technology | Procurement of supplies for tests by automated sample processing, detection of M. tuberculosis and screening for R resistance (GeneXpert technology).In 2013 the estimated number of tests is 2490, in 2014 -3540, 2015-3980) | HP IA Code: 001981 Account: 72300 | UNDP | 39920 | 0 | 0 | 0 | 39920
| 3.2.11 b | PSM costs for rapid detection and MDR screening GeneXpert technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 8682.6 | 0 | 0 | 0 | 8682.6
| 3.2.12 | Cost of missions of SRL experts to the NRL in Ashgabat. | Visits of SRL (National Mycobacteria Reference Laboratory, National Institute of Public Health and the Environment, Bilthoven, The Netherlands) to the NRL with the scope of technical assistance and external laboratory quality assurance (1 mission per Y3-Y5) | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 9640 | 0 | 9640
| 3.2.13 | Cost of on-site training of NRL specialists at the SRL, | NRL specialists will visit the SRL in Bilthoven, Netherlands, for for in-depth on-site training on new techniques (1 trainining for 3 participants per Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 15204 | 15204
| 3.2.14 | External laboratory quality assurance: shipment of strains to the Supranational Reference Laboratory | With the scope of external laboratory quality assurance of DST to 1st line and 2nd line TB drugs in support of the DR-TB management programme, strains will be shipped quarterly to the Supranational Reference Laboratory (SRL) in Bithoven, Netherlands. | P&A IA Code: 001981 Account: 72100 | UNDP | 2750 | 2750 | 2750 | 2750 | 11000
Activity 3.3 Treatment of drug-resistant TB cases
| 3.3.1 a | Procurement of reagents for culture investigations for MDR-TB patients on treatment (manual technique) | Cultures by manual technique on solid media will be performed for monitoring of treatment of MDR-TB patients.Calculations were done based on National MDR-TB Protocol. In 2013 the estimated number of tests is 660, in 2014 -2244, 2015-4356. | HP IA Code: 001981 Account: 72300 | UNDP | 6440.28 | 0 | 0 | 0 | 6440.28
| 3.3.1 b | PSM costs for reagents for culture investigations for MDR-TB patients on treatment ,manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1400.7609 | 0 | 0 | 0 | 1400.7609
| 3.3.2 a | Procurement of reagents for DST to 2nd line drugs for DR-TB patients on treatment (manual technique) | DST to 2nd line drugs will be performed in all MDR-TB patients on treatment. DST to 2nd line will be conducted in accordance with National MDR-TB Protocol.In 2013 the estimated number of tests is 100, in 2014 -340, 2015-660 | HP IA Code: 001981 Account: 72300 | UNDP | 26264.8 | 0 | 0 | 0 | 26264.8
| 3.3.2 b | PSM costs for reagents for DST to 2nd line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 5712.594 | 0 | 0 | 0 | 5712.594
| 3.3.3 a | Procurement of 2nd line anti-TB drugs for MDR-TB patients | 2nd line TB drugs will be procured for 550 patients (Y3-50, Y4-170, Y5-330 patients). The drugs and their quantities are based on the National MDR-TB Protocol. | MED IA Code: 001981 Account: 72300 | UNDP | 505133.8656 | 0 | 0 | 0 | 505133.8656
| 3.3.3 b | PSM costs for 2nd line anti-TB drugs for MDR-TB patients to the country (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 126283.4664 | 0 | 0 | 0 | 126283.4664
| 3.3.5 a -revised (distributed between 3 lines) | Cost of reagents for electrolyte analysis for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for hypokaliemia side effect of second line treatment. The budget was allocated for reagents, while the tests will be done using electrolyte analyzers, procured under Grant. | HP IA Code: 001981 Account: 72300 | UNDP | 1216.9891 | 1772.5711 | 2575.5193 | 3201.2104 | 8766.2899
| 3.3.5 b- revised (distributed between 3 lines) | PSM costs for reagents for electrolyte analysis | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 264.6951 | 385.5342 | 560.1754 | 696.2633 | 1906.668
| 3.3.5 c- revised (distributed between 3 lines) | Cost of clinical investigations for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for side effects of second line treatment: thyroid gland function, hypokaliemia and screened for viral hepatitis. The budget was allocated based on the number of patients and tests as required by the National MDR-TB Protocol. | LS IA Code: 001981 Account: 72100 | UNDP | 2059.4737 | 3181.3158 | 4625.4868 | 5848.1579 | 15714.4342
| 3.3.6 b | Spare parts (filters and UV-C bulbs ) for UV lamps for 1 year non-stop operation | Spare parts will be procured for the 100 lamps procured in Phase 1 and 30 lamps in Y5. | HP IA Code: 001981 Account:72200 | UNDP | 7000 | 0 | 0 | 0 | 7000
| 3.3.6 c | PSM costs for ultraviolet lamps (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1522.5 | 0 | 0 | 0 | 1522.5
| 3.3.7 а | Procurement of respirators for MDR-TB sites and BK+ departments [Individual measures for infection control] | High protection respirators will be procured for MDR-TB sites and BK+ departments to ensure individual measures of IC ( 69,000 per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | 55200 | 0 | 0 | 0 | 55200
| 3.3.7 d | PSM costs for respirators for MDR-TB sites and BK+ departments, NRCS staff and masks | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 12006 | 0 | 0 | 0 | 12006
Activity 3.4 Patient support programme for drug-resistant TB patients
| 3.4.3 a | Conduct MDR-TB patient patient education and counselling sessions by adherence counsellors | Patient education and counselling sessions will be conducted by adherence counsellors in out-patient basis.Estimated number of sessions: 2 quarter-6 sessions, 13 quarter- 12 sessions, 14-20 quarters- 36 sessions. | TR IA Code: 005742 Account: 75700 | NRCS | 2158.3158 | 6474.9474 | 6474.9474 | 6474.9474 | 21583.1579
| 3.4.3 b | Salary for 5 patronage nurses engaged in counselling sessions and DOT supporting 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. | The National Red Crescent Society plans to hire staff in Ashgabat and regions for councelling sevices. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | 6419.2392 | 6419.2392 | 6419.2392 | 6419.2392 | 25676.9568
| 3.4.4 b | Cost of delivery food parcels to DOTS cabinets | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | 0 | 846.3 | 846.3 | 846.3 | 2538.9
| 3.4.5 | Cost of transportation of visiting DOT supporters for visits DR-TB patients [Support to treatment adherence ] | Patient counsellors will visit MDR-TB patients to provide support. Cost includes transportation. Patients will be also supported by phone communication, which is budgeted under the activity 3.4.8 b. | PSM IA Code: 005742 Account: 72100 | NRCS | 2189.4737 | 4378.9474 | 7115.7895 | 10947.3684 | 24631.5789
| 3.4.8 b | Operational expenses -stationery, telephone communication | Operational expenses of the NRCS (stationery, office supplies) are covered by the Grant. | OVER IA Code: 005742 Account: 72500 | NRCS | 510.5263 | 510.5263 | 510.5263 | 510.5263 | 2042.1053
Objective 4 Project management and administration
| 4.1 a | Salaries for Principal Recipient's PIU staff | The activity includes budget for GIU staff of 9 person (please see cost assumption 4.1) | HR IA Code: 001981 Account: 71400 | UNDP | 36344.31 | 36344.31 | 36344.31 | 36344.31 | 145377.24
| 4.1 b | Monitoring visits by GIU plan | Supervision visits will be conducted by quarterly by M&E team (M&E specialist and Senior TB Specialist) and by Construction Specialist to the renovation sites in Mary and Dashoguz. | M&E IA Code: 001981 Account: 71600 | UNDP | 1922 | 1922 | 1922 | 1922 | 7688
| 4.2 a | Cost of GIU unit operational expenses | Cost of GIU unit operation expenses- office rent, internet, telephone communication, 5 % increase is forecasted starting from Y4 | OVER IA Code: 001981 Account: 72400, 72500, 73100, 73500 | UNDP | 13044.78 | 13044.78 | 13044.78 | 13044.78 | 52179.12
| 4.2 b | Cost of GIU unit operational expenses | Cost of GIU unit operational expenses - office supplies, bank and translation charges, 5 % increase is forecasted starting from Y4 | P&A IA Code: 001981 Account: 74200, 74500 | UNDP | 2400 | 2400 | 2400 | 2400 | 9600
| 4.4 a | Cost of external SR audit | External audit will be conducted for 2 SR's on annual basis- NRCS and Health Information Center | P&A IA Code: 001981 Account: 74100 | UNDP | 0 | 0 | 2000 | 0 | 2000
| 4.5 a | PR capacity building by attending various conferences, seminars, educational workshops for effective grant implementation | Trainings for capacity building of PR staff will be arranged in ( 2 trainings for 3 GIU staff members in Y3-Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 11406 | 0 | 11406 | 22812
| 4.5 b | SR capacity building by participation in seminars, educational workshops for effective grant implementation | Trainings in M&E and Finance for the SR's will be conducted annually during Y3-Y5. Training on monitoring of parcel distribution will be conducted annually in all 5 regions. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 8964 | 0 | 8964
| 4.5 d | Cost of capacity development activities of national entities to implement national disease response | Lumpsum of $10,000 is foreseen for the capacity development of national entities, and will be detailed after development of plan by UNDP headqurters. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 10000 | 10000
| 4.6 | Quality assurance of the 1 and 2 line TB drugs | Quality assurance activities are planned according to QA action plan. Please refer to cost assumption 4.6 | PSM IA Code: 001981 Account: | UNDP | 0 | 26874.5 | 0 | 0 | 26874.5
| 4.11 | WHO-remuneration for NPO (management and coordination) for 3 years | The salary of the NPO is budgeted for coordination of the activities under SR Agreement, $11,000 per quarter | HR IA Code: 002066 Account: 71400 | WHO | 11000 | 11000 | 11000 | 11000 | 44000
| 4.12 | WHO- administrative charges-7% | 7% is budgeted as administrative charges under SR agreement with WHO | OVER IA Code: 002066 Account: 72100 | WHO | 5239.71 | 3952.1767 | 4818.8 | 3523.0767 | 17533.7633
| 4.18 | UNDP Administrative charges- 7% according to the agreeement between GF and UNDP |  | OVER IA Code: 001981, 002066,004520, 005742 Account: 75100 | UNDP | 135646.6651 | 19919.977 | 19675.5222 | 34704.5986 | 209946.7629
|  | Grand Total |  |  |  | 2073456.1663 | 304491.0764 | 300754.4107 | 530484.5792 | 3209186.2326
Note on B35: aylar.hayitjanova: quantities of parcels were revised
Note on B55: aylar.hayitjanova: previously was UNDP

## AWP 2015_X
ANNUAL WORK PLAN – YEAR 5 ( 1 October 2014 – 30 September 2015
EXPECTED OUTPUTS Add baseline, indica-tors including annual targets. Please use the numbering of outputs as they are in the RRF/ SRF of ProDoc | PLANNED ACTIVITIES List activity results and associated actions. Please use the numbering of outputs as they are in the RRF/SRF of ProDoc |  | Budget Description | Budget Codes | Responsible party | TIMEFRAME |  |  |  | PLANNED BUDGET
| # | Activity |  |  |  | Q 17 01/10/14 -01/12/14 | Q 18 01/01/15 - 31/03/15 | Q 19 01/04/15 - 30/06/15 | Q 20 01/07/15 - 30/09/15
Objective 1 : To consolidate DOTS framework through strengthening programme management, improving TB case detection and diagnosis and ensuring quality treatment
Number of new smear-positive TB cases notified to the national health authorities during the specified period. Baseline: 2011 – 1,137 Target 2015 - 1,575 Number of all TB cases notified to the national health authorities during the specified period Baseline: 2011 – 3,038 Target 2015- 4,600 Number of staff from district and regional TB laboratories trained in microscopy techniques and culture methods. Baseline: 2012 - 29 Target 2015- 20 Number of direct sputum microscopy investigations for TB diagnosis and treatment monitoring. Baseline: 2011 – 85,755 Target 2015- 103,760 Number of culture investigations (manual technique) for confirmation of TB diagnosis and monitoring of treatment. Baseline: 2011 - 2,198 Target 2015- 14,600 Treatment success rate: new smear positive TB cases. Baseline 2010 – 74% Target 2015- 85% Number of TB patients receiving incentives (food parcels) for better adherence to treatment during out-patient phase of 1st line treatment. Baseline 2011 – 2,274 Target 2015- 2975 | Activity 1.1 :Strengthening management, coordination, monitoring and evaluation of the National Tuberculosis Programme
| 1.1.1 | Training of NTP management staff by attending international conferences abroad (2 participants per year) | Attendance of training courses in various aspects of NTP management and international conferences abroad (Warsaw and Sondalo training courses, European NTP managers' meetings, IUATLD conferences, etc.). Funding for 2 people attending 1 event per year. | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 9604
| 1.1.3 a | Quarterly supervision visits by the central NTP Unit ,1 round ( 3 specialists for 3 days in each of 5 regions) | Supervision visits will be conducted by the NTP Central Unit team to 5 velayat centres and selected districts (etraps): quarterly during Years 3-5. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 9792
| 1.1.3 b - new | Quarterly monitoring meetings to discuss the results of monitoring visits | To discuss the key findings, plan the next steps and ensure effective implementation of recommendations of supervision / monitoring visits, quarterly meetings will be held at the CTTP. Participants: representatives of the MOH, regional Departments of Health, Ashgabat City Department of Health, CTTP, regional NTP units, Medical Department of the MoI, NRCS, and the UNDP/GF GIU staff. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 4440
| 1.1.9 | Operational expenses of the NTP Central Unit and Regional Units, 5 % price increase is forecasted starting from Y4 | Operational expenses of the NTP Central Unit and Regional (velayat) Units (communication expenses, internet / e-mail stationery, printing, etc.) | OVER IA Code: 001981 Account: 72500, 74200 | UNDP | x | x | x | x | 9786
| 1.1.11 | Training of NTP and TB service staff in upgraded TB recording and reporting system | Staff from the Central and Regional (velayat) NTP units, and key TB service facilities will be trained in the use of revised recording and reporting forms and database management. (15 participants,2 trainings) | TR IA Code: 002066 Account: 75700 | WHO | x | x | x | x | 8538
| 1.1.12 | Recruitment of national IT specialist for the management of the national TB database | Local IT specialist will be contracted to assist the NTP in management and maintenance of the national electronic TB database (starting Year 3). | HR IA Code: 002066 Account: 71400 | WHO | x | x | x | x | 8400
| 1.1.15 a | Conduct M&E training session for TB specialists from 5 velayats and Ashgabat at central level | M&E specialists at central and regional level will be trained and retrained on M&E (18 participants,1 training in Y3 and Y5). | TR IA Code: 002066 Account: 75700 | WHO |  | x |  |  | 5100
| 1.1.20 | Cost NTP review mission by the international consultants at the end of the Y5 | NTP review mission will be conducted in Y5 to assess impact of the Grant. | TA IA Code: 002066 Account: 71200 | WHO |  |  |  | x | 66879.53
Activity 1.2 : Strengthening capacities for TB control in the penitentiary sector
| 1.2.2 | Training in TB management in prisons by attending international conferences abroad | Attendance of training courses in various aspects of TB control in prisons, international conferences abroad and study tours. (3 participants, 1 event in Y3-Y5) | TR IA Code: 002066 Account: 75700 | WHO |  |  | x |  | 15606
| 1.2.3 | Conduct quarterly supervision visits by the Medical department of MIA to the TB treatment site in the penitentiary sector (Mary Prison hospital MRK-15) | Quarterly supervision visits will be conducted by the Medical Department of the Ministry of Internal Affairs to the TB treatment site in the penitentiary sector (Mary velayat) and selected detention sites including pre-trial isolators to monitor case finding and case management practices. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 2040
Activity 1.3 : Strengthening TB laboratory network
| 1.3.1 a | Conduct training of TB peripheral laboratory staff on standard DOTS microscopy modules. | Training and re-training of staff of peripheral microscopy laboratories using standard DOTS microscopy modules will be conducted at the NRL (2 trainings in Y4-Y5). | TR IA Code: 002066 Account: 75700 | WHO | x |  | 2620 |  | 5240
| 1.3.1 b | Conduct training of TB regional laboratory staff on conducting culture investigations | Training of staff of regional microscopy laboratories will be conducted at the NRL on culture investigations (1 training in Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO |  | x |  |  | 9062
| 1.3.2 a | Procurement of Reagents for Ziel-Nelsen Microscopy : Sputum smear microscopy investigations | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). ZN was calculated as 75% of this amount, 25% will be done with LED. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 18787.8232
| 1.3.2 c | PSM costs for Reagents for Ziel-Nelsen Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 4086.3515
| 1.3.2 b | Procurement of Reagents for LED Microscopy (Sputum smear microscopy investigations) | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). LED was calculated as 25% of this amount, 75% will be done with ZN. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 10080.71
| 1.3.2 d | PSM costs for Reagents for LED Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 2192.5544
| 1.3.3 a | Procurement of Reagents for Culture investigations (manual technique) | Culture investigations (manual technique on solid media) will be performed by the NRL and regional laboratories in Balkanabad,Lebap and Mary, and later in Dashoguz regions. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 29503.6
| 1.3.3 b | PSM costs for reagents for Culture investigations (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 6417.033
| 1.3.7 a | Procurement of respirators for staff of TB laboratories (Individual measures for infection control) | Procurement of high protection respirators to ensure individual measures of infection control at TB laboratories. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 6219.2
| 1.3.7 b | PSM costs for respirators for staff of TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 1352.676
Activity 1. 4 Improving TB case management
| 1.4.2 | Conduct refreshing training for TB doctors using standard DOTS modules | Refreshing training of doctors from TB service institutions using standard DOTS modules will be conducted by the national team of trainers at the central level (15 participants, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | x |  | x |  | 7410
| 1.4.3 | Conduct training for TB nurses using standard DOTS module | DOTS initial training and refreshing training of nurses from TB service institutions (15 participants, 1 training in Y3, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP |  | x | x |  | 5030
| 1.4.7 a | Procurement of First Line Anti-TB Drugs , 5 % price increase is forecasted starting from Y4 | 1 line TB drugs will be procured for : Y3 - 4,500 patients (civil- 3,300 and penal- 1,200), Y4- 4,600 patients (civil-3,400 and penal -1,200), Y5- 4,600 patients (civil-3,500 and penal-1,100). For civil patients 87%- I, III category and 13%- II category. For penal patients 50%-I, III category, 50%-II category. | MED IA Code: 001981 Account: 72300 | UNDP |  |  |  | x | 297411.6696
| 1.4.7 b | PSM costs for First Line Anti-TB-Drugs (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  |  |  | x | 74352.9174
| 1.4.8 a | Procurement of (food parcels) for TB patients,as incentives (support to treatment adherence), 5 % price increase is forecasted starting from Y4 | TB patients on 1line treatment during continuation phase receive monthly food parcels. I, III category- 4 parcels per treatment course, II category - 5 parcels per treatment course. The coverage with support is 85%. | LS IA Code: 001981 Account: 72300 | UNDP | x |  |  | x | 337365
| 1.4.8 b | Salary of NRCS personnel (project coordinator,project assistant, 5 patronage nurses) 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. [delivery of food packages to DOTS cabinets and monitoring] | The National Red Crescent Society hired staff in Ashgabat and all regions to implement patient support countrywide. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | x | x | x | x | 44580.2449
| 1.4.8 c | Transportation of parcels до DOTS cabinets.[delivery of food packages to DOTS cabinets ] | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | x | x | x | x | 53464.8397
| 1.4.8 d | Quarterly monitoring visits by central NRCS [delivery of food packages to DOTS cabinets and monitoring] | Central level of NRCS will conduct quarterly monitoring visits to verify reporting on number of patients receiving food parcels ( 3 days, 2 person to 2 regions) | M&E IA Code: 005742 Account: 71600 | NRCS | x | x | x | x | 10329.0739
| 1.4.8 e | Monthly monitoring visits by regional NRCS [delivery of food packages to DOTS cabinets and monitoring] | Regional level of NRCS will conduct monthly verification of number of patients receiving food parcels, survey on patient satisfaction, and provision of consultation to TB specialists on distribution of food parcels (3 days, 1 person, 2 etraps per month) | M&E IA Code: 005742 Account: 71600 | NRCS | x | x | x | x | 21107.0053
| 1.4.8 g | Internet and telephone communication for NRCS personnel at 5 velayats and Ashgabat.[delivery of food packages to DOTS cabinets and monitoring] | Operational expenses of NRCS (communication expenses, internet) will be covered. | IF IA Code: 005742 Account: 72400 | NRCS | x | x | x | x | 1684.2105
Activity 1.5 :TB advocacy, communication and social mobilisation (ACSM)
| 1.5.1 | Conduct Knowledge, Attitude and Practices (KAP) survey to evaluate impact of ACSM interventions implemented by Round 9 Grant for TB in Y5. | KAP survey will be provided in Y5 and findings will be compared to KAP survey results from Phase 1 in order to evaluate ACSM interventions. Cost includes TA mission, interviewer's fees and training costs. | M&E IA Code: 002066 Account: 72100 | WHO |  |  | x |  | 34993
| 1.5.3 | Conduct training workshops for mass media representatives on priority issues of TB control. | Training workshops will be organised for mass media representatives in priority issues of TB control to enhance public awareness and social mobilisation for effective TB control. 1 workshops will be organised for 20 participants in Y3-Y5, before the World TB day. | TR IA Code: 004520 Account: 75700 | Health Information Center |  | x |  |  | 910
| 1.5.4 | Development and printing of TB informational and educational materials. | During Y3, the materials will be redeveloped and printed for 3 and 4. Additionally, the materials will be printed in Y5. | COM IA Code: 001981 Account: 74200 | UNDP |  | x |  |  | 15000
| 1.5.5 | Design, produce and broadcast TB informational and educational materials: video (10% increase forecasted starting from Y4) | Video spots will be designed, produced and broadcasted that will aim at increasing public awareness and social mobilisation for better TB control (in Y3-Y5). | COM IA Code: 004520 Account: 74200 | Health Information Center |  |  | x |  | 3630
| 1.5.6 | Operational costs for TB Resource Center at the Ministry of Health Information Centre (5 % increase is forecasted starting from Y4) | Operational expenses of TB resource center (communication expenses, internet) will be covered. | IF IA Code: 004520 Account: 72400 | Health Information Center | x | x | x | x | 8694
| 1.5.7 a | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | COM IA Code: 004520 Account: 74200 | Health Information Center |  | x |  |  | 2674.4311
| 1.5.8 | Training workshops for community leaders on TB control | Trainings workshops for community activists will be held to generate public awareness and raise social commitment at community level for fighting TB, with emphasis on reducing TB-related stigmatization and using community and family levers to motivate the patients to complete treatment and avoid the development of drug resistance. NRCS will train 100 people per year (13 participants, 8 trainings in Y3-Y5). | TR IA Code: 005742 Account: 75700 | NRCS | x | x | x | x | 17096
Activity 1.6 Collaborative activities for control of TB / HIV co-infection
| 1.6.4 | Training of TB service staff in diagnostic counselling and testing (DCT) for HIV | It is planned to train 90 TB specialists from all velayats and penitentiary sector in HIV diagnostic counselling and testing (DCT) among TB patients in order to improve access to and quality of the service.(15 participants,1 training in Y3, 3 trainings in Y4, 2 trainings in Y5) | TR IA Code: 002066 Account: 75700 | WHO | x | x |  |  | 6938
Objective 2 :To improve the health system performance for effective tuberculosis control
Number of TB and PHC services staff (doctors and nurses) trained and re-trained in DOTS, drug management and MDR-TB management. Baseline: 2011 – 1,168 Target 2015 - 330 | Activity 2.1 Strengthening Primary Health Care involvement in TB control
| 2.1.4 | Conduct training of PHC doctors from all regions in TB control (3 days, 20 participants, Q9 - 6 trainings ; 3 days, 15 participants Q11- 1 training, Q 12 - 1 training; Y4-8 trainings, Y5-8 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants, 8 trainings of 15 participants ).Will include general doctors from the penitentiary sector. 1,060 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | x | x | x | x | 25304
| 2.1.5 | Conduct training of PHC nurses from all regions and penitentiary sector in TB control (3 days, 20 participants, Q9-6 trainings; 3 days, 15 participants Q11- 2 training, Q 12 - 1 training; Y4-8 trainings, Y5- 5 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants,Y5- 5 trainings of 15 participants).Will include nurses from the penitentiary sector. 1,030 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | x | x | x | x | 15815
| 2.1.8-new | Monitoring of effectiveness of PHC trainings on DOTS | Members of the HSS working group will conduct mini-assessment of effectiveness of the PHC trainings. They will conduct visits to 3 velayats semiannually in Y3-Y4 and once in Y5. Trained PHC staff will be surveyed with the post-test questionnaire with aim to assess how the knowledge "survives" after 3,6, 12 months following training, how the PHC doctors use the knowledge in the daily practice, what gaps remain. The results will be communicated to the trainers and used for adjustment of training modules. | M&E IA Code: 002066 Account: 71600 | WHO |  |  | x |  | 1478.6667
Activity 2.2 Strengthening key health system functions for effective TB control
| 2.2.2 | Recruitment of an international consultant to provide technical assistance to MOHMI and NTP in assessment of financial needs of the NTP and developing financial sustainability plan for TB control | Technical assistance (by an external and a local expert) will be provided to the Ministry of Health and NTP in assessment of financial needs and development of a financial sustainability plan for TB control, e.g. in view of the need of take over by the Government beyond the Global Fund and other external support. | TA IA Code: 002066 Account: 71200, 71300 | WHO | x |  |  |  | 11512
Activity 2.3 : Introducing Practical Approach to Lung Health (PAL)
| 2.3.2 | Recruitment of local consultant to provide technical assistance in monitoring and evaluation of PAL implementation in the pilot area in Y4 | Local consultant will monitor implementation of PAL activities in the pilot regions. Cost includes fees, travel to pilot areas. | TA IA Code: 002066 Account: 71300 | WHO | x | x | x | x | 6000
| 2.3.5 | Conduct training of general health service doctors in PAL in the pilot regions (20 participants,Y4-7 trainings, Y5- 3 trainings) | Training of general health service doctors in PAL will be conducted in the pilot region during Years 4-5. Totally 200 specialists will be trained (20 participants, Y5- 3 trainings). | TR IA Code: 002066 Account: 75700 | WHO | x | x | x |  | 11646
Objective 3 :To introduce and expand access to diagnosis and treatment of drug-resistant tuberculosis
TB cases with results for diagnostic drug susceptibility testing for MDR-TB among those eligible Baseline: 2011 – 40.5% Target 2015- 68% Confirmed MDR-TB cases enrolled on treatment: Laboratory-confirmed MDR-TB cases enrolled on 2nd line anti-TB treatment during the specified period of assessment (number) Baseline: N/a Target 2015- 248 Number of MDR-TB patients on out-patient treatment receiving patient support (food incentives) for better adherence to treatment. Baseline: N/a Target 2015- 236 Interim results: culture conversion at six months: MDR-TB cases initiated on a 2nd line anti-TB treatment who have a negative culture at the end of six months of treat-ment during the specified period of assessment (number and percentage) Baseline: N/a Target 2015 - 77% | Activity 3.1.Strengthening national capacities for management of drug-resistant tuberculosis
| 3.1.1 | Support to the Green Light Committee operations (GLC Fee) | GLC monitoring missions and operational support to the GLC in accordance to agreement between the GLC and the Global Fund ($25,000 per year) | P&A IA Code: 001981 Account: 72100 | UNDP |  | x |  |  | 25000
| 3.1.5 | Conduct local training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff from DR-TB treatment delivery sites | Training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff DR-TB treatment delivery sites (15 participants,2 trainings) | TR IA Code: 001981 Account: 75700 | UNDP |  | x | x |  | 10420
| 3.1.6 | Conduct local training in MDR-TB management for Primary Health Care services, who will be involved in follow-up of DR-TB patients | Training in MDR-TB management for staff from PHC service who will be involved in follow-up of MDR-TB patients during out-patient phase of treatment with special emphasis on psychosocial support to ensure adherence. 15 participants10 trainings in Y5). | TR IA Code: 001981 Account: 75700 | UNDP | x | x | x | x | 32900
| 3.1.7 | Conduct training for staff from MDR-TB treatment sites and regional laboratories for infection control | Local training on infection control will be organised for staff from MDR-TB treatment delivery sites and regional laboratories. 20 participants, 2 trainings in Y5. | TR IA Code: 002066 Account: 75700 | WHO |  | x | x |  | 8788
| 3.1.13 | Training of NRCS personnel in infection control | Local training on infection control will be organised for the NRCS staff working with the MDR-TB patients (12 participants, 1 training in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | x |  |  |  | 2244
Activity 3.2 Drug resistance surveillance and diagnosis of drug-resistant TB cases
| 3.2.5 b | MGIT technology equipment 12 month service contract | Maintence cost is budgeted for 4 MGIT machines ( 3 - procured within Grant and 1 -previously already in place at NRL). | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 37060
| 3.2.5 c | PSM costs for MGIT technology in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 8060.55
| 3.2.6 b | PCR GenoType equipment 12 month service contract | Maintence cost is budgeted for 2 PCR machines. | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 2866.9714
| 3.2.6 c | PSM costs for PCR GenoType MTBDR Plus technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 623.5663
| 3.2.7 b | GeneXpert 12 month service contract | Maintence cost is budgeted for 6 GeneXpert machines. | HP IA Code: 001981 Account: 72200 | UNDP |  | x |  |  | 13285.9829
| 3.2.7 c | PSM costs for GeneXperts for Balkan and Ahal regional TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP |  | x |  |  | 2889.7013
| 3.2.8 a | Culture and DST to 1st line drugs for DR-TB diagnosis (automated MGIT technique) | Culture investigations (automated technique on liquid media) will be performed by the NRL and regional laboratories.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 37878.8571
| 3.2.8 b | PSM costs for Culture and DST to 1st line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 8238.6514
| 3.2.9 a | DST to 1st line drugs (manual technique) | DST to 1st line drugs will be performed in culture-positive cases using manual technique on solid media, for quality assurance of automated MGIT technique.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 1537.92
| 3.2.9 b | PSM costs for DST to 1st line drugs (manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 334.4976
| 3.2.10 a | Tests for rapid identification of R/H resistance | Identification of strains and express testing for R/H resistance to be performed by the NRL and regional laboratories. In 2013 the estimated number of tests is 1380, in 2014 -2040, 2015-2400. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 39240
| 3.2.10 b | PSM costs for tests for rapid identification of R/H resistance (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 8534.7
| 3.2.11 a | Tests for rapid detection and MDR screening, GeneXpert technology | Procurement of supplies for tests by automated sample processing, detection of M. tuberculosis and screening for R resistance (GeneXpert technology).In 2013 the estimated number of tests is 2490, in 2014 -3540, 2015-3980) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 49900
| 3.2.11 b | PSM costs for rapid detection and MDR screening GeneXpert technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 10853.25
| 3.2.12 | Cost of missions of SRL experts to the NRL in Ashgabat. | Visits of SRL (National Mycobacteria Reference Laboratory, National Institute of Public Health and the Environment, Bilthoven, The Netherlands) to the NRL with the scope of technical assistance and external laboratory quality assurance (1 mission per Y3-Y5) | TA IA Code: 002066 Account: 71200 | WHO |  |  | x |  | 10040
| 3.2.13 | Cost of on-site training of NRL specialists at the SRL, | NRL specialists will visit the SRL in Bilthoven, Netherlands, for for in-depth on-site training on new techniques (1 trainining for 3 participants per Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO |  |  |  | x | 15204
| 3.2.14 | External laboratory quality assurance: shipment of strains to the Supranational Reference Laboratory | With the scope of external laboratory quality assurance of DST to 1st line and 2nd line TB drugs in support of the DR-TB management programme, strains will be shipped quarterly to the Supranational Reference Laboratory (SRL) in Bithoven, Netherlands. | P&A IA Code: 001981 Account: 72100 | UNDP | x | x | x | x | 11000
Activty 3.3 Treatment of drug-resistant TB cases
| 3.3.1 a | Procurement of reagents for culture investigations for MDR-TB patients on treatment (manual technique) | Cultures by manual technique on solid media will be performed for monitoring of treatment of MDR-TB patients.Calculations were done based on National MDR-TB Protocol. In 2013 the estimated number of tests is 660, in 2014 -2244, 2015-4356. | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 12501.72
| 3.3.1 b | PSM costs for reagents for culture investigations for MDR-TB patients on treatment ,manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 2719.1241
| 3.3.2 a | Procurement of reagents for DST to 2nd line drugs for DR-TB patients on treatment (manual technique) | DST to 2nd line drugs will be performed in all MDR-TB patients on treatment. DST to 2nd line will be conducted in accordance with National MDR-TB Protocol.In 2013 the estimated number of tests is 100, in 2014 -340, 2015-660 | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 45963.4
| 3.3.2 b | PSM costs for reagents for DST to 2nd line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 9997.0395
| 3.3.3 a | Procurement of 2nd line anti-TB drugs for MDR-TB patients | 2nd line TB drugs will be procured for 550 patients (Y3-50, Y4-170, Y5-330 patients). The drugs and their quantities are based on the National MDR-TB Protocol. | MED IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 980553.9744
| 3.3.3 b | PSM costs for 2nd line anti-TB drugs for MDR-TB patients to the country (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 245138.4936
| 3.3.5 a -revised (distributed between 3 lines) | Cost of reagents for electrolyte analysis for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for hypokaliemia side effect of second line treatment. The budget was allocated for reagents, while the tests will be done using electrolyte analyzers, procured under Grant. | HP IA Code: 001981 Account: 72300 | UNDP | x | x | x | x | 22473.2908
| 3.3.5 b- revised (distributed between 3 lines) | PSM costs for reagents for electrolyte analysis | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x | x | x | x | 4887.9408
| 3.3.5 c- revised (distributed between 3 lines) | Cost of clinical investigations for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for side effects of second line treatment: thyroid gland function, hypokaliemia and screened for viral hepatitis. The budget was allocated based on the number of patients and tests as required by the National MDR-TB Protocol. | LS IA Code: 001981 Account: 72100 | UNDP | x | x | x | x | 42593.25
| 3.3.6 a | Procurement of ultraviolet lamps [environment measures for infection control] | Procurement of UV lamps for two in-patient DR-TB treatment sites in the civilian and penitentiary sectors, NRL and reference laboratories (100 lamps were procured in Phase 1 and additional 30 lamps in Year 5 to replace the broken / failed ones) | HP IA Code: 001981 Account:72200 | UNDP | x |  |  |  | 11728
| 3.3.6 b | Spare parts (filters and UV-C bulbs ) for UV lamps for 1 year non-stop operation | Spare parts will be procured for the 100 lamps procured in Phase 1 and 30 lamps in Y5. | HP IA Code: 001981 Account:72200 | UNDP | x |  |  |  | 9100
| 3.3.6 c | PSM costs for ultraviolet lamps (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | x |  |  |  | 4530.09
| 3.3.7 а | Procurement of respirators for MDR-TB sites and BK+ departments [Individual measures for infection control] | High protection respirators will be procured for MDR-TB sites and BK+ departments to ensure individual measures of IC ( 69,000 per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | x |  |  |  | 55200
| 3.3.7 d | PSM costs for respirators for MDR-TB sites and BK+ departments, NRCS staff and masks | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 12006 |  |  |  | 12006
Activity 3.4 Patient support programme for drug-resistant TB patients
| 3.4.3 a | Conduct MDR-TB patient patient education and counselling sessions by adherence counsellors | Patient education and counselling sessions will be conducted by adherence counsellors in out-patient basis.Estimated number of sessions: 2 quarter-6 sessions, 13 quarter- 12 sessions, 14-20 quarters- 36 sessions. | TR IA Code: 005742 Account: 75700 | NRCS | x | x | x | x | 25899.7895
| 3.4.3 b | Salary for 5 patronage nurses engaged in counselling sessions and DOT supporting 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. | The National Red Crescent Society plans to hire staff in Ashgabat and regions for councelling sevices. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | x | x | x | x | 28244.6525
| 3.4.4 a | Procurement of incentives (food parcels) for DR-TB patients, 5 % price increase is forecasted starting from Y4 [Support to treatment adherence] | MDR-TB patients on continuation phase (16 month) will be given monthly food parcels as means of motivation to treatment adherence and prevention of hypokaliemia.It is estimated that 85- 90 % of patients will stay on treatment in the first year of treatment and 80-85% on the 2nd year of treatment. Since the country does not have experience with MDR-TB management, these estimates are subject to correction based on the actual needs. | LS IA Code: 001981 Account: 72300 | UNDP |  | x |  |  | 119906.325
| 3.4.4 b | Cost of delivery food parcels to DOTS cabinets | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | x | x | x | x | 5225.9025
| 3.4.5 | Cost of transportation of visiting DOT supporters for visits DR-TB patients [Support to treatment adherence ] | Patient counsellors will visit MDR-TB patients to provide support. Cost includes transportation. Patients will be also supported by phone communication, which is budgeted under the activity 3.4.8 b. | PSM IA Code: 005742 Account: 72100 | NRCS | x | x | x | x | 78821.0526
| 3.4.8 b | Operational expenses -stationery, telephone communication | Operational expenses of the NRCS (stationery, office supplies) are covered by the Grant. | OVER IA Code: 005742 Account: 72500 | NRCS | x | x | x | x | 2042.1053
Objective 4 Project management and administration
| 4.1 a | Salaries for Principal Recipient's PIU staff | The activity includes budget for GIU staff of 9 person (please see cost assumption 4.1) | HR IA Code: 001981 Account: 71400 | UNDP | x | x | x | x | 145377.24
| 4.1 b | Monitoring visits by GIU plan | Supervision visits will be conducted by quarterly by M&E team (M&E specialist and Senior TB Specialist) and by Construction Specialist to the renovation sites in Mary and Dashoguz. | M&E IA Code: 001981 Account: 71600 | UNDP | x | x | x | x | 7688
| 4.2 a | Cost of GIU unit operational expenses | Cost of GIU unit operation expenses- office rent, internet, telephone communication, 5 % increase is forecasted starting from Y4 | OVER IA Code: 001981 Account: 72400, 72500, 73100, 73500 | UNDP | x | x | x | x | 52179.12
| 4.2 b | Cost of GIU unit operational expenses | Cost of GIU unit operational expenses - office supplies, bank and translation charges, 5 % increase is forecasted starting from Y4 | P&A IA Code: 001981 Account: 74200, 74500 | UNDP | x | x | x | x | 9600
| 4.4 a | Cost of external SR audit | External audit will be conducted for 2 SR's on annual basis- NRCS and Health Information Center | P&A IA Code: 001981 Account: 74100 | UNDP |  |  | x |  | 2000
| 4.5 a | PR capacity building by attending various conferences, seminars, educational workshops for effective grant implementation | Trainings for capacity building of PR staff will be arranged in ( 2 trainings for 3 GIU staff members in Y3-Y5) | TR IA Code: 001981 Account: 75700 | UNDP |  | x |  | x | 22812
| 4.5 b | SR capacity building by participation in seminars, educational workshops for effective grant implementation | Trainings in M&E and Finance for the SR's will be conducted annually during Y3-Y5. Training on monitoring of parcel distribution will be conducted annually in all 5 regions. | TR IA Code: 001981 Account: 75700 | UNDP |  |  | x |  | 8964
| 4.5 d | Cost of capacity development activities of national entities to implement national disease response | Lumpsum of $10,000 is foreseen for the capacity development of national entities, and will be detailed after development of plan by UNDP headqurters. | TR IA Code: 001981 Account: 75700 | UNDP |  |  |  | x | 10000
| 4.6 | Quality assurance of the 1 and 2 line TB drugs | Quality assurance activities are planned according to QA action plan. Please refer to cost assumption 4.6 | PSM IA Code: 001981 Account: | UNDP |  | x |  |  | 26874.5
| 4.11 | WHO-remuneration for NPO (management and coordination) for 3 years | The salary of the NPO is budgeted for coordination of the activities under SR Agreement, $11,000 per quarter | HR IA Code: 002066 Account: 71400 | WHO | x | x | x | x | 44000
| 4.12 | WHO- administrative charges-7% | 7% is budgeted as administrative charges under SR agreement with WHO | OVER IA Code: 002066 Account: 72100 | WHO | x | x | x | x | 18859.7638
| 4.18 | UNDP Administrative charges- 7% according to the agreeement between GF and UNDP |  | OVER IA Code: 001981, 002066,004520, 005742 Account: 75100 | UNDP | x | x | x | x | 255663.8672
|  | Grand Total |  |  |  | 2322461.7461 | 518980.8109 | 323097.3567 | 743464.913 | 3908004.8267
3908004.8267
Note on B15: aylar.hayitjanova: previously was budgeted under 4.4 c
Note on B35: aylar.hayitjanova: quantities of parcels were revised

## AWP 2015
ANNUAL WORK PLAN – YEAR 5 ( 1 October 2014 – 30 September 2015
EXPECTED OUTPUTS Add baseline, indica-tors including annual targets. Please use the numbering of outputs as they are in the RRF/ SRF of ProDoc | PLANNED ACTIVITIES List activity results and associated actions. Please use the numbering of outputs as they are in the RRF/SRF of ProDoc |  | Budget Description | Budget Codes | Responsible party | TIMEFRAME |  |  |  | PLANNED BUDGET
| # | Activity |  |  |  | Q 17 01/10/14 -01/12/14 | Q 18 01/01/15 - 31/03/15 | Q 19 01/04/15 - 30/06/15 | Q 20 01/07/15 - 30/09/15
Objective 1 : To consolidate DOTS framework through strengthening programme management, improving TB case detection and diagnosis and ensuring quality treatment
Number of new smear-positive TB cases notified to the national health authorities during the specified period. Baseline: 2011 – 1,137 Target 2015 - 1,575 Number of all TB cases notified to the national health authorities during the specified period Baseline: 2011 – 3,038 Target 2015- 4,600 Number of staff from district and regional TB laboratories trained in microscopy techniques and culture methods. Baseline: 2012 - 29 Target 2015- 20 Number of direct sputum microscopy investigations for TB diagnosis and treatment monitoring. Baseline: 2011 – 85,755 Target 2015- 103,760 Number of culture investigations (manual technique) for confirmation of TB diagnosis and monitoring of treatment. Baseline: 2011 - 2,198 Target 2015- 14,600 Treatment success rate: new smear positive TB cases. Baseline 2010 – 74% Target 2015- 85% Number of TB patients receiving incentives (food parcels) for better adherence to treatment during out-patient phase of 1st line treatment. Baseline 2011 – 2,274 Target 2015- 2975 | Activity 1.1 :Strengthening management, coordination, monitoring and evaluation of the National Tuberculosis Programme
| 1.1.1 | Training of NTP management staff by attending international conferences abroad (2 participants per year) | Attendance of training courses in various aspects of NTP management and international conferences abroad (Warsaw and Sondalo training courses, European NTP managers' meetings, IUATLD conferences, etc.). Funding for 2 people attending 1 event per year. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 9604 | 9604
| 1.1.3 a | Quarterly supervision visits by the central NTP Unit ,1 round ( 3 specialists for 3 days in each of 5 regions) | Supervision visits will be conducted by the NTP Central Unit team to 5 velayat centres and selected districts (etraps): quarterly during Years 3-5. | M&E IA Code: 001981 Account: 71600 | UNDP | 2448 | 2448 | 2448 | 2448 | 9792
| 1.1.3 b - new | Quarterly monitoring meetings to discuss the results of monitoring visits | To discuss the key findings, plan the next steps and ensure effective implementation of recommendations of supervision / monitoring visits, quarterly meetings will be held at the CTTP. Participants: representatives of the MOH, regional Departments of Health, Ashgabat City Department of Health, CTTP, regional NTP units, Medical Department of the MoI, NRCS, and the UNDP/GF GIU staff. | M&E IA Code: 001981 Account: 71600 | UNDP | 1110 | 1110 | 1110 | 1110 | 4440
| 1.1.9 | Operational expenses of the NTP Central Unit and Regional Units, 5 % price increase is forecasted starting from Y4 | Operational expenses of the NTP Central Unit and Regional (velayat) Units (communication expenses, internet / e-mail stationery, printing, etc.) | OVER IA Code: 001981 Account: 72500, 74200 | UNDP | 2446.5 | 2446.5 | 2446.5 | 2446.5 | 9786
| 1.1.11 | Training of NTP and TB service staff in upgraded TB recording and reporting system | Staff from the Central and Regional (velayat) NTP units, and key TB service facilities will be trained in the use of revised recording and reporting forms and database management. (15 participants,2 trainings) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 4269 | 4269 | 8538
| 1.1.12 | Recruitment of national IT specialist for the management of the national TB database | Local IT specialist will be contracted to assist the NTP in management and maintenance of the national electronic TB database (starting Year 3). | HR IA Code: 002066 Account: 71400 | WHO | 2100 | 2100 | 2100 | 2100 | 8400
| 1.1.15 a | Conduct M&E training session for TB specialists from 5 velayats and Ashgabat at central level | M&E specialists at central and regional level will be trained and retrained on M&E (18 participants,1 training in Y3 and Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 5100 | 0 | 0 | 5100
| 1.1.20 | Cost NTP review mission by the international consultants at the end of the Y5 | NTP review mission will be conducted in Y5 to assess impact of the Grant. | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 0 | 66879.53 | 66879.53
Activity 1.2 : Strengthening capacities for TB control in the penitentiary sector
| 1.2.2 | Training in TB management in prisons by attending international conferences abroad | Attendance of training courses in various aspects of TB control in prisons, international conferences abroad and study tours. (3 participants, 1 event in Y3-Y5) | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 15606 | 0 | 15606
| 1.2.3 | Conduct quarterly supervision visits by the Medical department of MIA to the TB treatment site in the penitentiary sector (Mary Prison hospital MRK-15) | Quarterly supervision visits will be conducted by the Medical Department of the Ministry of Internal Affairs to the TB treatment site in the penitentiary sector (Mary velayat) and selected detention sites including pre-trial isolators to monitor case finding and case management practices. | M&E IA Code: 001981 Account: 71600 | UNDP | 510 | 510 | 510 | 510 | 2040
Activity 1.3 : Strengthening TB laboratory network
| 1.3.1 a | Conduct training of TB peripheral laboratory staff on standard DOTS microscopy modules. | Training and re-training of staff of peripheral microscopy laboratories using standard DOTS microscopy modules will be conducted at the NRL (2 trainings in Y4-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 2620 | 0 | 2620 | 0 | 5240
| 1.3.1 b | Conduct training of TB regional laboratory staff on conducting culture investigations | Training of staff of regional microscopy laboratories will be conducted at the NRL on culture investigations (1 training in Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 9062 | 0 | 0 | 9062
| 1.3.2 a | Procurement of Reagents for Ziel-Nelsen Microscopy : Sputum smear microscopy investigations | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). ZN was calculated as 75% of this amount, 25% will be done with LED. | HP IA Code: 001981 Account: 72300 | UNDP | 18787.8232 | 0 | 0 | 0 | 18787.8232
| 1.3.2 c | PSM costs for Reagents for Ziel-Nelsen Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 4086.3515 | 0 | 0 | 0 | 4086.3515
| 1.3.2 b | Procurement of Reagents for LED Microscopy (Sputum smear microscopy investigations) | Procurement of glassware, reagents and other supplies for direct sputum smear microscopy (DSM) investigations for TB diagnosis and treatment monitoring. DSM will be performed in accordance with national standards. (3 smears for detection and 2 for monitoring of 1 line treatment). In 2013 - 94,040 investigations, in 2014 - 95,040, and in 2015 - 103,756 (or 77,820 by 30 September 2015). LED was calculated as 25% of this amount, 75% will be done with ZN. | HP IA Code: 001981 Account: 72300 | UNDP | 10080.71 | 0 | 0 | 0 | 10080.71
| 1.3.2 d | PSM costs for Reagents for LED Microscopy (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 2192.5544 | 0 | 0 | 0 | 2192.5544
| 1.3.3 a | Procurement of Reagents for Culture investigations (manual technique) | Culture investigations (manual technique on solid media) will be performed by the NRL and regional laboratories in Balkanabad,Lebap and Mary, and later in Dashoguz regions. | HP IA Code: 001981 Account: 72300 | UNDP | 29503.6 | 0 | 0 | 0 | 29503.6
| 1.3.3 b | PSM costs for reagents for Culture investigations (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 6417.033 | 0 | 0 | 0 | 6417.033
| 1.3.7 a | Procurement of respirators for staff of TB laboratories (Individual measures for infection control) | Procurement of high protection respirators to ensure individual measures of infection control at TB laboratories. | HP IA Code: 001981 Account: 72300 | UNDP | 6219.2 | 0 | 0 | 0 | 6219.2
| 1.3.7 b | PSM costs for respirators for staff of TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 1352.676 | 0 | 0 | 0 | 1352.676
Activity 1. 4 Improving TB case management
| 1.4.2 | Conduct refreshing training for TB doctors using standard DOTS modules | Refreshing training of doctors from TB service institutions using standard DOTS modules will be conducted by the national team of trainers at the central level (15 participants, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 3705 | 0 | 3705 | 0 | 7410
| 1.4.3 | Conduct training for TB nurses using standard DOTS module | DOTS initial training and refreshing training of nurses from TB service institutions (15 participants, 1 training in Y3, 2 trainings in Y4, 2 trainings in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 2515 | 2515 | 0 | 5030
| 1.4.7 a | Procurement of First Line Anti-TB Drugs , 5 % price increase is forecasted starting from Y4 | 1 line TB drugs will be procured for : Y3 - 4,500 patients (civil- 3,300 and penal- 1,200), Y4- 4,600 patients (civil-3,400 and penal -1,200), Y5- 4,600 patients (civil-3,500 and penal-1,100). For civil patients 87%- I, III category and 13%- II category. For penal patients 50%-I, III category, 50%-II category. | MED IA Code: 001981 Account: 72300 | UNDP | 0 | 0 | 0 | 297411.6696 | 297411.6696
| 1.4.7 b | PSM costs for First Line Anti-TB-Drugs (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 0 | 0 | 74352.9174 | 74352.9174
| 1.4.8 a | Procurement of (food parcels) for TB patients,as incentives (support to treatment adherence), 5 % price increase is forecasted starting from Y4 | TB patients on 1line treatment during continuation phase receive monthly food parcels. I, III category- 4 parcels per treatment course, II category - 5 parcels per treatment course. The coverage with support is 85%. | LS IA Code: 001981 Account: 72300 | UNDP | 337365 | 0 | 0 | 0 | 337365
| 1.4.8 b | Salary of NRCS personnel (project coordinator,project assistant, 5 patronage nurses) 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. [delivery of food packages to DOTS cabinets and monitoring] | The National Red Crescent Society hired staff in Ashgabat and all regions to implement patient support countrywide. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | 11145.0612 | 11145.0612 | 11145.0612 | 11145.0612 | 44580.2449
| 1.4.8 c | Transportation of parcels до DOTS cabinets.[delivery of food packages to DOTS cabinets ] | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | 13366.2099 | 13366.2099 | 13366.2099 | 13366.2099 | 53464.8397
| 1.4.8 d | Quarterly monitoring visits by central NRCS [delivery of food packages to DOTS cabinets and monitoring] | Central level of NRCS will conduct quarterly monitoring visits to verify reporting on number of patients receiving food parcels ( 3 days, 2 person to 2 regions) | M&E IA Code: 005742 Account: 71600 | NRCS | 2582.2685 | 2582.2685 | 2582.2685 | 2582.2685 | 10329.0739
| 1.4.8 e | Monthly monitoring visits by regional NRCS [delivery of food packages to DOTS cabinets and monitoring] | Regional level of NRCS will conduct monthly verification of number of patients receiving food parcels, survey on patient satisfaction, and provision of consultation to TB specialists on distribution of food parcels (3 days, 1 person, 2 etraps per month) | M&E IA Code: 005742 Account: 71600 | NRCS | 5276.7513 | 5276.7513 | 5276.7513 | 5276.7513 | 21107.0053
| 1.4.8 g | Internet and telephone communication for NRCS personnel at 5 velayats and Ashgabat.[delivery of food packages to DOTS cabinets and monitoring] | Operational expenses of NRCS (communication expenses, internet) will be covered. | IF IA Code: 005742 Account: 72400 | NRCS | 421.0526 | 421.0526 | 421.0526 | 421.0526 | 1684.2105
Activity 1.5 :TB advocacy, communication and social mobilisation (ACSM)
| 1.5.1 | Conduct Knowledge, Attitude and Practices (KAP) survey to evaluate impact of ACSM interventions implemented by Round 9 Grant for TB in Y5. | KAP survey will be provided in Y5 and findings will be compared to KAP survey results from Phase 1 in order to evaluate ACSM interventions. Cost includes TA mission, interviewer's fees and training costs. | M&E IA Code: 002066 Account: 72100 | WHO | 0 | 0 | 34993 | 0 | 34993
| 1.5.3 | Conduct training workshops for mass media representatives on priority issues of TB control. | Training workshops will be organised for mass media representatives in priority issues of TB control to enhance public awareness and social mobilisation for effective TB control. 1 workshops will be organised for 20 participants in Y3-Y5, before the World TB day. | TR IA Code: 004520 Account: 75700 | Health Information Center | 0 | 910 | 0 | 0 | 910
| 1.5.4 | Development and printing of TB informational and educational materials. | During Y3, the materials will be redeveloped and printed for 3 and 4. Additionally, the materials will be printed in Y5. | COM IA Code: 001981 Account: 74200 | UNDP | 0 | 15000 | 0 | 0 | 15000
| 1.5.5 | Design, produce and broadcast TB informational and educational materials: video (10% increase forecasted starting from Y4) | Video spots will be designed, produced and broadcasted that will aim at increasing public awareness and social mobilisation for better TB control (in Y3-Y5). | COM IA Code: 004520 Account: 74200 | Health Information Center | 0 | 0 | 3630 | 0 | 3630
| 1.5.6 | Operational costs for TB Resource Center at the Ministry of Health Information Centre (5 % increase is forecasted starting from Y4) | Operational expenses of TB resource center (communication expenses, internet) will be covered. | IF IA Code: 004520 Account: 72400 | Health Information Center | 2173.5 | 2173.5 | 2173.5 | 2173.5 | 8694
| 1.5.7 a | World TB Day informational campaigns at national and local levels | Different informational and educational events at the national and local levels will be organised by the NTP and MOH Information Centre with participation of national and international NGOs on occasions of World TB Day 24 March | COM IA Code: 004520 Account: 74200 | Health Information Center | 0 | 2674.4311 | 0 | 0 | 2674.4311
| 1.5.8 | Training workshops for community leaders on TB control | Trainings workshops for community activists will be held to generate public awareness and raise social commitment at community level for fighting TB, with emphasis on reducing TB-related stigmatization and using community and family levers to motivate the patients to complete treatment and avoid the development of drug resistance. NRCS will train 100 people per year (13 participants, 8 trainings in Y3-Y5). | TR IA Code: 005742 Account: 75700 | NRCS | 4274 | 4274 | 4274 | 4274 | 17096
Activity 1.6 Collaborative activities for control of TB / HIV co-infection
| 1.6.4 | Training of TB service staff in diagnostic counselling and testing (DCT) for HIV | It is planned to train 90 TB specialists from all velayats and penitentiary sector in HIV diagnostic counselling and testing (DCT) among TB patients in order to improve access to and quality of the service.(15 participants,1 training in Y3, 3 trainings in Y4, 2 trainings in Y5) | TR IA Code: 002066 Account: 75700 | WHO | 3469 | 3469 | 0 | 0 | 6938
Objective 2 :To improve the health system performance for effective tuberculosis control
Number of TB and PHC services staff (doctors and nurses) trained and re-trained in DOTS, drug management and MDR-TB management. Baseline: 2011 – 1,168 Target 2015 - 330 | Activity 2.1 Strengthening Primary Health Care involvement in TB control
| 2.1.4 | Conduct training of PHC doctors from all regions in TB control (3 days, 20 participants, Q9 - 6 trainings ; 3 days, 15 participants Q11- 1 training, Q 12 - 1 training; Y4-8 trainings, Y5-8 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants, 8 trainings of 15 participants ).Will include general doctors from the penitentiary sector. 1,060 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | 6326 | 6326 | 6326 | 6326 | 25304
| 2.1.5 | Conduct training of PHC nurses from all regions and penitentiary sector in TB control (3 days, 20 participants, Q9-6 trainings; 3 days, 15 participants Q11- 2 training, Q 12 - 1 training; Y4-8 trainings, Y5- 5 trainings) | It is planned to train PHC doctors from all regions in TB control (training of new staff) to strengthen participation in it with emphasis on case detection, treatment follow up and community work. (3 days, 15 participants,Y5- 5 trainings of 15 participants).Will include nurses from the penitentiary sector. 1,030 PHC doctors will be trained over the Grant. | TR IA Code: 001981 Account: 75700 | UNDP | 3163 | 3163 | 3163 | 6326 | 15815
| 2.1.8-new | Monitoring of effectiveness of PHC trainings on DOTS | Members of the HSS working group will conduct mini-assessment of effectiveness of the PHC trainings. They will conduct visits to 3 velayats semiannually in Y3-Y4 and once in Y5. Trained PHC staff will be surveyed with the post-test questionnaire with aim to assess how the knowledge "survives" after 3,6, 12 months following training, how the PHC doctors use the knowledge in the daily practice, what gaps remain. The results will be communicated to the trainers and used for adjustment of training modules. | M&E IA Code: 002066 Account: 71600 | WHO | 0 | 0 | 1478.6667 | 0 | 1478.6667
Activity 2.2 Strengthening key health system functions for effective TB control
| 2.2.2 | Recruitment of an international consultant to provide technical assistance to MOHMI and NTP in assessment of financial needs of the NTP and developing financial sustainability plan for TB control | Technical assistance (by an external and a local expert) will be provided to the Ministry of Health and NTP in assessment of financial needs and development of a financial sustainability plan for TB control, e.g. in view of the need of take over by the Government beyond the Global Fund and other external support. | TA IA Code: 002066 Account: 71200, 71300 | WHO | 11512 | 0 | 0 | 0 | 11512
Activity 2.3 : Introducing Practical Approach to Lung Health (PAL)
| 2.3.2 | Recruitment of local consultant to provide technical assistance in monitoring and evaluation of PAL implementation in the pilot area in Y4 | Local consultant will monitor implementation of PAL activities in the pilot regions. Cost includes fees, travel to pilot areas. | TA IA Code: 002066 Account: 71300 | WHO | 1500 | 1500 | 1500 | 1500 | 6000
| 2.3.5 | Conduct training of general health service doctors in PAL in the pilot regions (20 participants,Y4-7 trainings, Y5- 3 trainings) | Training of general health service doctors in PAL will be conducted in the pilot region during Years 4-5. Totally 200 specialists will be trained (20 participants, Y5- 3 trainings). | TR IA Code: 002066 Account: 75700 | WHO | 3882 | 3882 | 3882 | 0 | 11646
Objective 3 :To introduce and expand access to diagnosis and treatment of drug-resistant tuberculosis
TB cases with results for diagnostic drug susceptibility testing for MDR-TB among those eligible Baseline: 2011 – 40.5% Target 2015- 68% Confirmed MDR-TB cases enrolled on treatment: Laboratory-confirmed MDR-TB cases enrolled on 2nd line anti-TB treatment during the specified period of assessment (number) Baseline: N/a Target 2015- 248 Number of MDR-TB patients on out-patient treatment receiving patient support (food incentives) for better adherence to treatment. Baseline: N/a Target 2015- 236 Interim results: culture conversion at six months: MDR-TB cases initiated on a 2nd line anti-TB treatment who have a negative culture at the end of six months of treat-ment during the specified period of assessment (number and percentage) Baseline: N/a Target 2015 - 77% | Activity 3.1.Strengthening national capacities for management of drug-resistant tuberculosis
| 3.1.1 | Support to the Green Light Committee operations (GLC Fee) | GLC monitoring missions and operational support to the GLC in accordance to agreement between the GLC and the Global Fund ($25,000 per year) | P&A IA Code: 001981 Account: 72100 | UNDP | 0 | 25000 | 0 | 0 | 25000
| 3.1.5 | Conduct local training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff from DR-TB treatment delivery sites | Training in managerial, clinical and laboratory aspects of DR-TB management for TB service staff DR-TB treatment delivery sites (15 participants,2 trainings) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 5210 | 5210 | 0 | 10420
| 3.1.6 | Conduct local training in MDR-TB management for Primary Health Care services, who will be involved in follow-up of DR-TB patients | Training in MDR-TB management for staff from PHC service who will be involved in follow-up of MDR-TB patients during out-patient phase of treatment with special emphasis on psychosocial support to ensure adherence. 15 participants10 trainings in Y5). | TR IA Code: 001981 Account: 75700 | UNDP | 9870 | 6580 | 9870 | 6580 | 32900
| 3.1.7 | Conduct training for staff from MDR-TB treatment sites and regional laboratories for infection control | Local training on infection control will be organised for staff from MDR-TB treatment delivery sites and regional laboratories. 20 participants, 2 trainings in Y5. | TR IA Code: 002066 Account: 75700 | WHO | 0 | 4394 | 4394 | 0 | 8788
| 3.1.13 | Training of NRCS personnel in infection control | Local training on infection control will be organised for the NRCS staff working with the MDR-TB patients (12 participants, 1 training in Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 2244 | 0 | 0 | 0 | 2244
Activity 3.2 Drug resistance surveillance and diagnosis of drug-resistant TB cases
| 3.2.5 b | MGIT technology equipment 12 month service contract | Maintence cost is budgeted for 4 MGIT machines ( 3 - procured within Grant and 1 -previously already in place at NRL). | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 37060 | 0 | 0 | 37060
| 3.2.5 c | PSM costs for MGIT technology in Dashoguz region (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 8060.55 | 0 | 0 | 8060.55
| 3.2.6 b | PCR GenoType equipment 12 month service contract | Maintence cost is budgeted for 2 PCR machines. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 2866.9714 | 0 | 0 | 2866.9714
| 3.2.6 c | PSM costs for PCR GenoType MTBDR Plus technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 623.5663 | 0 | 0 | 623.5663
| 3.2.7 b | GeneXpert 12 month service contract | Maintence cost is budgeted for 6 GeneXpert machines. | HP IA Code: 001981 Account: 72200 | UNDP | 0 | 13285.9829 | 0 | 0 | 13285.9829
| 3.2.7 c | PSM costs for GeneXperts for Balkan and Ahal regional TB laboratories (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 0 | 2889.7013 | 0 | 0 | 2889.7013
| 3.2.8 a | Culture and DST to 1st line drugs for DR-TB diagnosis (automated MGIT technique) | Culture investigations (automated technique on liquid media) will be performed by the NRL and regional laboratories.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | 37878.8571 | 0 | 0 | 0 | 37878.8571
| 3.2.8 b | PSM costs for Culture and DST to 1st line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 8238.6514 | 0 | 0 | 0 | 8238.6514
| 3.2.9 a | DST to 1st line drugs (manual technique) | DST to 1st line drugs will be performed in culture-positive cases using manual technique on solid media, for quality assurance of automated MGIT technique.In 2013 the estimated number of tests is 1660, in 2014 -2450, 2015-2880. | HP IA Code: 001981 Account: 72300 | UNDP | 1537.92 | 0 | 0 | 0 | 1537.92
| 3.2.9 b | PSM costs for DST to 1st line drugs (manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 334.4976 | 0 | 0 | 0 | 334.4976
| 3.2.10 a | Tests for rapid identification of R/H resistance | Identification of strains and express testing for R/H resistance to be performed by the NRL and regional laboratories. In 2013 the estimated number of tests is 1380, in 2014 -2040, 2015-2400. | HP IA Code: 001981 Account: 72300 | UNDP | 39240 | 0 | 0 | 0 | 39240
| 3.2.10 b | PSM costs for tests for rapid identification of R/H resistance (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 8534.7 | 0 | 0 | 0 | 8534.7
| 3.2.11 a | Tests for rapid detection and MDR screening, GeneXpert technology | Procurement of supplies for tests by automated sample processing, detection of M. tuberculosis and screening for R resistance (GeneXpert technology).In 2013 the estimated number of tests is 2490, in 2014 -3540, 2015-3980) | HP IA Code: 001981 Account: 72300 | UNDP | 49900 | 0 | 0 | 0 | 49900
| 3.2.11 b | PSM costs for rapid detection and MDR screening GeneXpert technology (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 10853.25 | 0 | 0 | 0 | 10853.25
| 3.2.12 | Cost of missions of SRL experts to the NRL in Ashgabat. | Visits of SRL (National Mycobacteria Reference Laboratory, National Institute of Public Health and the Environment, Bilthoven, The Netherlands) to the NRL with the scope of technical assistance and external laboratory quality assurance (1 mission per Y3-Y5) | TA IA Code: 002066 Account: 71200 | WHO | 0 | 0 | 10040 | 0 | 10040
| 3.2.13 | Cost of on-site training of NRL specialists at the SRL, | NRL specialists will visit the SRL in Bilthoven, Netherlands, for for in-depth on-site training on new techniques (1 trainining for 3 participants per Y3-Y5). | TR IA Code: 002066 Account: 75700 | WHO | 0 | 0 | 0 | 15204 | 15204
| 3.2.14 | External laboratory quality assurance: shipment of strains to the Supranational Reference Laboratory | With the scope of external laboratory quality assurance of DST to 1st line and 2nd line TB drugs in support of the DR-TB management programme, strains will be shipped quarterly to the Supranational Reference Laboratory (SRL) in Bithoven, Netherlands. | P&A IA Code: 001981 Account: 72100 | UNDP | 2750 | 2750 | 2750 | 2750 | 11000
Activity 3.3 Treatment of drug-resistant TB cases
| 3.3.1 a | Procurement of reagents for culture investigations for MDR-TB patients on treatment (manual technique) | Cultures by manual technique on solid media will be performed for monitoring of treatment of MDR-TB patients.Calculations were done based on National MDR-TB Protocol. In 2013 the estimated number of tests is 660, in 2014 -2244, 2015-4356. | HP IA Code: 001981 Account: 72300 | UNDP | 12501.72 | 0 | 0 | 0 | 12501.72
| 3.3.1 b | PSM costs for reagents for culture investigations for MDR-TB patients on treatment ,manual technique (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 2719.1241 | 0 | 0 | 0 | 2719.1241
| 3.3.2 a | Procurement of reagents for DST to 2nd line drugs for DR-TB patients on treatment (manual technique) | DST to 2nd line drugs will be performed in all MDR-TB patients on treatment. DST to 2nd line will be conducted in accordance with National MDR-TB Protocol.In 2013 the estimated number of tests is 100, in 2014 -340, 2015-660 | HP IA Code: 001981 Account: 72300 | UNDP | 45963.4 | 0 | 0 | 0 | 45963.4
| 3.3.2 b | PSM costs for reagents for DST to 2nd line drugs (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 9997.0395 | 0 | 0 | 0 | 9997.0395
| 3.3.3 a | Procurement of 2nd line anti-TB drugs for MDR-TB patients | 2nd line TB drugs will be procured for 550 patients (Y3-50, Y4-170, Y5-330 patients). The drugs and their quantities are based on the National MDR-TB Protocol. | MED IA Code: 001981 Account: 72300 | UNDP | 980553.9744 | 0 | 0 | 0 | 980553.9744
| 3.3.3 b | PSM costs for 2nd line anti-TB drugs for MDR-TB patients to the country (transportation,procurement handling and insurance fees) | PSM costs of 25% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 245138.4936 | 0 | 0 | 0 | 245138.4936
| 3.3.5 a -revised (distributed between 3 lines) | Cost of reagents for electrolyte analysis for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for hypokaliemia side effect of second line treatment. The budget was allocated for reagents, while the tests will be done using electrolyte analyzers, procured under Grant. | HP IA Code: 001981 Account: 72300 | UNDP | 4194.6439 | 5194.6915 | 6139.1808 | 6944.7747 | 22473.2908
| 3.3.5 b- revised (distributed between 3 lines) | PSM costs for reagents for electrolyte analysis | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 912.335 | 1129.8454 | 1335.2718 | 1510.4885 | 4887.9408
| 3.3.5 c- revised (distributed between 3 lines) | Cost of clinical investigations for DR-TB patients on treatment | MDR-TB patients on treatment will be monitored for side effects of second line treatment: thyroid gland function, hypokaliemia and screened for viral hepatitis. The budget was allocated based on the number of patients and tests as required by the National MDR-TB Protocol. | LS IA Code: 001981 Account: 72100 | UNDP | 7654.2237 | 9773.0132 | 11719.9342 | 13446.0789 | 42593.25
| 3.3.6 a | Procurement of ultraviolet lamps [environment measures for infection control] | Procurement of UV lamps for two in-patient DR-TB treatment sites in the civilian and penitentiary sectors, NRL and reference laboratories (100 lamps were procured in Phase 1 and additional 30 lamps in Year 5 to replace the broken / failed ones) | HP IA Code: 001981 Account:72200 | UNDP | 11728 | 0 | 0 | 0 | 11728
| 3.3.6 b | Spare parts (filters and UV-C bulbs ) for UV lamps for 1 year non-stop operation | Spare parts will be procured for the 100 lamps procured in Phase 1 and 30 lamps in Y5. | HP IA Code: 001981 Account:72200 | UNDP | 9100 | 0 | 0 | 0 | 9100
| 3.3.6 c | PSM costs for ultraviolet lamps (transportation,procurement handling and insurance fees) | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 4530.09 | 0 | 0 | 0 | 4530.09
| 3.3.7 а | Procurement of respirators for MDR-TB sites and BK+ departments [Individual measures for infection control] | High protection respirators will be procured for MDR-TB sites and BK+ departments to ensure individual measures of IC ( 69,000 per Y3-Y5) | HP IA Code: 001981 Account: 72300 | UNDP | 55200 | 0 | 0 | 0 | 55200
| 3.3.7 d | PSM costs for respirators for MDR-TB sites and BK+ departments, NRCS staff and masks | PSM costs of 21.75% | PSM IA Code: 001981 Account: 74700, 74200 | UNDP | 12006 | 0 | 0 | 0 | 12006
Activity 3.4 Patient support programme for drug-resistant TB patients
| 3.4.3 a | Conduct MDR-TB patient patient education and counselling sessions by adherence counsellors | Patient education and counselling sessions will be conducted by adherence counsellors in out-patient basis.Estimated number of sessions: 2 quarter-6 sessions, 13 quarter- 12 sessions, 14-20 quarters- 36 sessions. | TR IA Code: 005742 Account: 75700 | NRCS | 6474.9474 | 6474.9474 | 6474.9474 | 6474.9474 | 25899.7895
| 3.4.3 b | Salary for 5 patronage nurses engaged in counselling sessions and DOT supporting 10% increase forecasted compared to Y3 in Y4, and in Y5 compared to Y4. | The National Red Crescent Society plans to hire staff in Ashgabat and regions for councelling sevices. Full costs of salaries are budgeted, as these positions were created to directly support the project activities. | HR IA Code: 005742 Account: 71400 | NRCS | 7061.1631 | 7061.1631 | 7061.1631 | 7061.1631 | 28244.6525
| 3.4.4 a | Procurement of incentives (food parcels) for DR-TB patients, 5 % price increase is forecasted starting from Y4 [Support to treatment adherence] | MDR-TB patients on continuation phase (16 month) will be given monthly food parcels as means of motivation to treatment adherence and prevention of hypokaliemia.It is estimated that 85- 90 % of patients will stay on treatment in the first year of treatment and 80-85% on the 2nd year of treatment. Since the country does not have experience with MDR-TB management, these estimates are subject to correction based on the actual needs. | LS IA Code: 001981 Account: 72300 | UNDP | 0 | 119906.325 | 0 | 0 | 119906.325
| 3.4.4 b | Cost of delivery food parcels to DOTS cabinets | Delivery of food parcels from regional NRCS offices to all DOTS cabinets countrywide. | PSM IA Code: 005742 Account: 72100 | NRCS | 846.3 | 1459.8675 | 1459.8675 | 1459.8675 | 5225.9025
| 3.4.5 | Cost of transportation of visiting DOT supporters for visits DR-TB patients [Support to treatment adherence ] | Patient counsellors will visit MDR-TB patients to provide support. Cost includes transportation. Patients will be also supported by phone communication, which is budgeted under the activity 3.4.8 b. | PSM IA Code: 005742 Account: 72100 | NRCS | 14778.9474 | 17515.7895 | 21347.3684 | 25178.9474 | 78821.0526
| 3.4.8 b | Operational expenses -stationery, telephone communication | Operational expenses of the NRCS (stationery, office supplies) are covered by the Grant. | OVER IA Code: 005742 Account: 72500 | NRCS | 510.5263 | 510.5263 | 510.5263 | 510.5263 | 2042.1053
Objective 4 Project management and administration
| 4.1 a | Salaries for Principal Recipient's PIU staff | The activity includes budget for GIU staff of 9 person (please see cost assumption 4.1) | HR IA Code: 001981 Account: 71400 | UNDP | 36344.31 | 36344.31 | 36344.31 | 36344.31 | 145377.24
| 4.1 b | Monitoring visits by GIU plan | Supervision visits will be conducted by quarterly by M&E team (M&E specialist and Senior TB Specialist) and by Construction Specialist to the renovation sites in Mary and Dashoguz. | M&E IA Code: 001981 Account: 71600 | UNDP | 1922 | 1922 | 1922 | 1922 | 7688
| 4.2 a | Cost of GIU unit operational expenses | Cost of GIU unit operation expenses- office rent, internet, telephone communication, 5 % increase is forecasted starting from Y4 | OVER IA Code: 001981 Account: 72400, 72500, 73100, 73500 | UNDP | 13044.78 | 13044.78 | 13044.78 | 13044.78 | 52179.12
| 4.2 b | Cost of GIU unit operational expenses | Cost of GIU unit operational expenses - office supplies, bank and translation charges, 5 % increase is forecasted starting from Y4 | P&A IA Code: 001981 Account: 74200, 74500 | UNDP | 2400 | 2400 | 2400 | 2400 | 9600
| 4.4 a | Cost of external SR audit | External audit will be conducted for 2 SR's on annual basis- NRCS and Health Information Center | P&A IA Code: 001981 Account: 74100 | UNDP | 0 | 0 | 2000 | 0 | 2000
| 4.5 a | PR capacity building by attending various conferences, seminars, educational workshops for effective grant implementation | Trainings for capacity building of PR staff will be arranged in ( 2 trainings for 3 GIU staff members in Y3-Y5) | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 11406 | 0 | 11406 | 22812
| 4.5 b | SR capacity building by participation in seminars, educational workshops for effective grant implementation | Trainings in M&E and Finance for the SR's will be conducted annually during Y3-Y5. Training on monitoring of parcel distribution will be conducted annually in all 5 regions. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 8964 | 0 | 8964
| 4.5 d | Cost of capacity development activities of national entities to implement national disease response | Lumpsum of $10,000 is foreseen for the capacity development of national entities, and will be detailed after development of plan by UNDP headqurters. | TR IA Code: 001981 Account: 75700 | UNDP | 0 | 0 | 0 | 10000 | 10000
| 4.6 | Quality assurance of the 1 and 2 line TB drugs | Quality assurance activities are planned according to QA action plan. Please refer to cost assumption 4.6 | PSM IA Code: 001981 Account: | UNDP | 0 | 26874.5 | 0 | 0 | 26874.5
| 4.11 | WHO-remuneration for NPO (management and coordination) for 3 years | The salary of the NPO is budgeted for coordination of the activities under SR Agreement, $11,000 per quarter | HR IA Code: 002066 Account: 71400 | WHO | 11000 | 11000 | 11000 | 11000 | 44000
| 4.12 | WHO- administrative charges-7% | 7% is budgeted as administrative charges under SR agreement with WHO | OVER IA Code: 002066 Account: 72100 | WHO | 2525.81 | 2835.49 | 6431.7867 | 7066.6771 | 18859.7638
| 4.18 | UNDP Administrative charges- 7% according to the agreeement between GF and UNDP |  | OVER IA Code: 001981, 002066,004520, 005742 Account: 75100 | UNDP | 151936.7497 | 33952.0157 | 21137.2103 | 48637.8915 | 255663.8672
|  | Grand Total |  |  |  | 2322461.7461 | 518980.8109 | 323097.3567 | 743464.913 | 3908004.8267
Note on B15: aylar.hayitjanova: previously was budgeted under 4.4 c
Note on B35: aylar.hayitjanova: quantities of parcels were revised