## NHRAP Eng
UNDP component Annual Work Plan
UN-Turkmenistan Joint Programme | "Assistance in the realization of the National Action Plan of Turkmenistan in the field of human rights for 2021-2025"
Period: | 01-JAN-2021 - 31-DEC-2023
Budget 2021: | 85058.64
Source: | Government of Turkmenistan-SDG fund
JP Outcome 1: | [13 empty] | 72600-Grants |  |  | 0
[14 empty] | 74200-Audio, Visual, Translation |  |  | 7502 | 574 | 574 | 912 | 442 | 5000
JP Outcome: Of the framework program for cooperation in the field of sustainable development between Turkmenistan and the United Nations for 2021-2025. “By 2025, the population of Turkmenistan has access to a more efficient, innovative and transparent public administration system based on the rule of law, respect for human rights, gender equality and labor rights, and quality data” | [13 empty] | 75700-Learning Cost |  |  | 15735 | 1015 | 2457 | 2332 | 2332 | 933 | 1866 | 3600 | 1200
[14 empty] | 71600-Travel |  |  | 15790 | 2267 | 2217 | 2267 | 4616 | 2167 | 1410 | 846
[14 empty] | 72100-Contractual Services-Companies |  |  | 0
[14 empty] | 71300-Local Consultants |  |  | 0
[14 empty] | 71200-International Consultant |  |  | 23650 | 5000 | 7500 | 3500 | 7650
[14 empty] | 71400-Service contracts |  |  | 13000 | 6000 | 7000
[14 empty] | 73100-Office rental cost |  |  | 0
[14 empty] | 72400-Connectivity |  |  | 1500 | 1500
[14 empty] | 75100-Facilities & Administration (GMS) |  |  | 5106.64 | 1928.01 | 908.46 | 1745.17 | 525
[14 empty] | 74500-Miscellaneous Expenses |  |  | 2775 | 1275 | 750 | 750
[14 empty] | Total |  |  | 85058.64
EXPECTED INTERIM RESULTS | PLANNED ACTIVITIES | TIMEFRAME | [12 empty] | PLANNED BUDGET
|  | January | February | March | April | May | June | July | August | September | October | November | December | RESPONSIBLE PARTIES | Budget Code | Amount Budget 2021 per code | Amount Budgeted in 2021 | Actual Spending | Saving
Result 1: Assistance in the implementation and monitoring of the implementation of the activities of the National Action Plan for Human Rights for 2021-2025 (NHRAP) . | Funds avaiblable from 1st transh 2021 | [15 empty] | 34174.79 | $27174.79 (Gov.TKM - 95,11.77 TMT)+$7000 (UNDPs)
Result 2: International experience studied and potential increased of the Interagency Commission for the preparation of national periodic reports to the UN human rights treaty bodies. | Funds form the 2nd transh available | [15 empty] | 50883.85
Result 3: Promotion of human rights education at various levels of educational institutions and professional training courses. | Total Funds budgeted for 2021 | [15 empty] | 85058.64
IR: 1.1. 25% of NHRAP activities completed Assistance in the implementation and monitoring of the implementation of activities of the National Action Plan for Human Rights 2021-2025 (NHRAP) | Presentation of the NHRAP (2021-2025) - completed online | [12 empty] | Government of Turkmenistan | 75700-Learning Cost | 1015 | 1015 | 0 | 1015 | to be allocated to activity 3.2 (3)
IR: 1.2. A reporting form on the implementation of the NHRAP has been adopted and is used by national authorities. | Conducting a two-day workshop on international standards for the measurement and implementation of human rights indicators. | [12 empty] | Project Team | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 5,000.00 2,267.00 2,457.00. 574.00 | 10298 | 10298 | 0
| Development of a reporting form for monitoring the implementation of the NHRAP (2021-2025). | [12 empty] | Project Team | 75700-Learning Cost | 2332 | 2332 | 2332 | 0
IR: 1.3. Analysis of the mid-term review of the implementation of UPR recommendations (2018) completed. | Conduct mid-term review of the implementation of UPR recommendations (2018). Conducting a two-day workshop with members of the Working Group. | [12 empty] | Project Team | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 7,500 .00 2,217.00 2,332.00 574.00 | 12623 | 12623 | 0
IR: 2.1. 10 representatives of the Turkmen delegation prepared to participate in the Dialogue with the UN Treaty Bodies | Conducting a simulation workshop to prepare for the Dialogue with the UN Treaty Bodies (according to the schedule). | [12 empty] | Project Team | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 3,500.00 2,267.00 933.00 912.00 | 7612 | 7612 | 0
| Participation in international conferences to study the regional experience of national human rights institutions on human rights. (2 members of the Working Group of the Interagency Commission). | [12 empty] | Project Team | 71600-Travel | 4616 | 4616 | 420 | 4196 | to be allocated to next year trip
IR: 3.1. 500 copies of developed and disseminated information and educational materials on human rights, including the NHRAP (2021-2025). | Publishing and distribution of NHRAP 2021-2025 (completed) | [12 empty] | Project Team | 74200-Printing | 5000 | 5000 | 4, 887 | 113 | to be allocated to activity 3.2 (3) | 320 copies (96 pages)
IR: 3.2. 100 civil servants, law enforcement officers, judges, lawyers who took part in information events dedicated to human rights and the implementation of Turkmenistan's international obligations in the field of human rights. | Conducting a review of educational programs in order to prepare recommendations for the integration of educational materials on human rights at the Faculty of International Law of the Institute of International Relations of MFA of Turkmenistan. - Two-day seminar for educators on the study of international experience. | [12 empty] | Project Team | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200 -Audio, Visual, Translation | 7,650.00 2,167.00. 1,866.00 442.00 | 12125 | 12125
| Conducting presentations of the NHRAP 2021-2025 for the law enforcement officials, judges, lawyers. Three seminars will be held at the human rights resource centers in the velayats. Total: 3 workshops. 2 national Experts will conduct sessions. (completed) | [12 empty] | Project Team | 71600-Travel 75700-Learning Cost | 1,410.00 3,600.00 | 5010 | 5010
| Conducting information sessions for the government officials and representatives of local authorities on the rights of persons with disabilities. Three seminars will be held at the human rights resource centers in the velayats. 2 national Experts will conduct workshops. | [12 empty] | Project Team | 71600-Travel 75700-Learning Cost | 846.00 1,200.00 | 2046 | 2046
Project Management
| Project staff salary: Project Manager (50%), | [12 empty] | Project Team | 71400-Service contracts | 13000 | 13000 | 3799
| DPC: General operating and other direct costs | [12 empty] | Project Team | 74500-Miscellaneous Expenses | 2775 | 2775
| Connectivity Charges (phones, email) 6 months | [13 empty] | 72400-Connectivity | 1500 | 1500 | 622
| Office rental, other expenses | [13 empty] | 73100 - Office rental cost | 0 |  | 210
| GMS: (Max. 7%)- | [12 empty] | Project Team | 75100-Facilities & Administration (GMS) | 5106.64 | 5106.64 | 573
[14 empty] | Total Expected Expenses |  |  | 85058.64
Note on Q24: lartykova17@gmail.com:
Note on R24: lartykova17@gmail.com:

## IR. 1.2-1.3
Ac | OCTOBER 7-8, 2021 |  |  |  | ACTUAL COST | SAVING
| Conducting a two-day workshop on international standards for the measurement and implementation of human rights indicators. | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 5,000.00 2,267.00 2,457.00. 574.00 | 10298 | 6155 1864 574 1840 200
| Development of a reporting form for monitoring the implementation of the NHRAP (2021-2025). | 75700-Learning Cost | 2332 | 2332
|  |  |  | 12630 | 10233 | 2397
David Johnson

## IR.1.4
OCTOBER 27-28, 2021 |  |  |  | ACTUAL COST | SAVING
Conduct mid-term review of the implementation of UPR recommendations (2018). Conducting a two-day workshop with members of the Working Group. | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 7,500 .00 2,217.00 2,332.00 574.00 | 12623 | 4500 1954 194 | 5975
|  |  |  | 6648 |  | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 7,500 .00 2,217.00 2,332.00 574.00 | 12623
Nato Alhazishvilli

## I.R 2.1-2.2
November 16-17 |  |  |  | EXPECTED | SAVING | NOTES
Conducting a simulation workshop to prepare for the Dialogue with the UN Treaty Bodies (according to the schedule). INSTEAD - Analysis on Compliance of National Legislation with the Provisions of the International Covenant on Civil and Political Rights (ICCPR) and deliver a two-day workshop | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200-Audio, Visual, Translation | 3,500.00 2,267.00 933.00 912.00 | 7612 | 8000 | 0,00
Participation in international conferences to study the regional experience of national human rights institutions on human rights. (2 members of the Working Group of the Interagency Commission). | 71600-Travel | 4616 | 4616 | 388 | 4228

## I.R 3.1
NOVEMBER 29-30 |  |  |  | EXPECTED COST
Conducting a review of educational programs in order to prepare recommendations for the integration of educational materials on human rights at the Faculty of International Law of the Institute of International Relations of MFA of Turkmenistan. - Two-day seminar for educators on the study of international experience. | 71200-International Consultant 71600-Travel 75700-Learning Cost 74200 -Audio, Visual, Translation | 7,650.00 2,167.00. 1,866.00 442.00 | 12125 | 12125
|  |  |  | Peter Liskola | 6000
1900 taken for I.R.3.3

## I.R 3.2
JULY 23-29 |  |  |  | SPENT | SAVING
Conducting presentations of the NHRAP 2021-2025 for the law enforcement officials, judges, lawyers. Three seminars will be held at the human rights resource centers in the velayats. Total: 3 workshops. 2 national Experts will conduct sessions. | 71600-Travel 75700-Learning Cost | 1,410.00 3,600.00 | 5010 | 2607 | 2403

## I.R 3.3
2021-10-21 |  |  |  | SPENT | SAVING
Conducting information sessions for the government officials and representatives of local authorities on the rights of persons with disabilities. Three seminars will be held at the human rights resource centers in the velayats. 2 national Experts will conduct workshops. | 71600-Travel 75700-Learning Cost | 846.00 1,200.00 | 2046 | 2046 2403 1900
6349

## I.R.3.4
2021-10-21 |  |  | SPENT | SAVING
Publishing and distribution of NHRAP 2021-2025 - amount 500. | 74200 | 5000 | 4571 315 | 114
4886

## SAVING
TOTAL
RESULT 1 | 1015 | 2397 | 5975 | 9387
RESULT 2 |  |  | 4228 | 4228
RESULT 3 |  |  |  | 0
13615
84% Dileverable