## Costed WorkplanYEAR1
INSTRUCTIONS: CHOOSE ACTIVITY, COST CATEGORY AND FILL IN THE YELLOW CELLS
CCM Name: | CCM Turkmenistan
Starting Date: | 2017-07-01 | [6 empty] | GRAND TOTAL (Fixed Costs + Activities) = |  |  |  |  | 50000.03
Year of Agreement: | Year 1
Currency: | USD
|  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| Activities | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Total | Budget | Assumptions* | Comments | Cost Category | Performance Area
General | CCM Plenary/General Assembly meeting | [12 empty] | 4 | 1450 | See the worksheet "встречи СКК и рабоч группы". The budget includes travel of members from the regions, water, printouts. | Regular meetings of CMM: 1) in May to get informed about Secretariat funding and the selected Secretary; 2) in August to review the draft funding request; 3) in Nov - 2017 year end meeting; March 2018 - for 2017 report by the PR and agreeing the 2018 work plan. | Meeting, Trainings, Workshops, consultations | Oversight | bar: Q1 Aug; Q2 Nov; Q3 Feb; Q4 Jun
| CCM Induction | [12 empty] | 1 | 1760 | See the worksheet "ориентационн тренинг". The budget includes rent of hall, travel expenses for the CCM members from the regions, water, meals, stationery and printouts. | CCM induction training by an international expert: the current CCM eligibility and how to improve it. | Meeting expenses, Training, Workshops, Consultations | Capacity Building/Gender | bar: Q3 Feb
| Technical Support | [12 empty] | 1 | 3120 | See the worksheet "тех поддержка" cell F10. The budget includes travel expenses, fee for 1 expert. | Technical support by an an international expert for induction session. | Technical Assistance | Capacity Building/Gender | bar: Q3 Feb
Oversight | Site Visits / Monitoring Visits | [12 empty] | 2 | 210 | See the worksheet "надзорные визиты". The budget includes travel expenses for 1 day for 2 staff of the oversight committee. | Oversight visits 2 times for the funding year. 2 regions per visit, 4 regions in the funding year. | Others (Please specify in comments) | Oversight | bar: Q1 Aug; Q3 Feb
Funding Request Preparation | Technical Support | [12 empty] | 1 | 10185 | See the worksheet "тех поддержка" cell F19. The budget includes travel expenses, fee for 1 expert. | 1 expert will be engaged to work 10 days in-country and 6 days remotely. | Meeting expenses, Training, Workshops, Consultations | bar: Q2 Oct
| Technical Working groups meetings | Q1 Aug: 1; Q1 Sep: 2; Q2 Oct: 2; Q2 Nov: 2; Q3 Jan: 1 | 8 | 2112 | See the worksheet "встречи СКК и рабоч группы". The budget includes water, printouts, coffee breaks. | Technical working group for development of funding request will meet in May-Aug, and then in Oct/Nov for the TRP comments | Meeting expenses, Training, Workshops, Consultations | Constituency Engagement
0
Others | CCM capacity building by participation in international events, experience exchange | [12 empty] | 1 | 5312 | See the worksheet "междун поездка". The budget includes travel expenses for 2 CCM members | CCM Turkmenistan has not participated in any international CCM-related meetings since 2010. The current funding request includes possibility for 1 event to be attended by 2 CCM members | Meeting, Trainings, Workshops, consultations | Capacity Building/Gender | bar: Q3 Mar
| Printing of the CCM Statute, 30 copies, $5 each | Q3 Jan: 30 | 30 | 150 | Revised CCM Statute to be printed in 30 copies, each for estimated $10. | CCM Statute needs to be revised and printed for the CCM members. | Communication materials | Constituency Engagement
| Development and printing of communication materials | Q2 Oct: 5500 | 5500 | 6150 | Approximately 5,500 copies of simple leaflets, booklets, etc. More precise prices will be known later. 2 experts and 1 designer will develop the information materials in Turkmen and Russian languages. See the worksheet "распечатки". | There is need to print out various information materials. Therefore this CCM funding request includes it. | Communication materials | Sustainability and Transition
0
0
0
30449
* Has to be detailed if the yearly budget is over 10'000 per annum.
| Fixed Costs | Q1 July: Total Year; Q1 Sep: Cost Category (Read-only); Q3 Mar: CCM Secretariat positions
| Human Resources (Secretariat staffs) | Q1 July: 6000; Q1 Sep: Human Resources; Q3 Mar: Executive Secretary; Q4 Jun: 0.5
| Office rental and supplies (including equipement) | Q1 July: 7373.2; Q1 Sep: Planning and Administration; Q4 Jun: 0
| Vehicule maintenance | Q1 July: 0; Q1 Sep: Others (Please specify in comments); Q4 Jun: 0
| Other | Q1 July: 2677.83; Q1 Sep: Planning and Administration; Q4 Jun: 0
| Other | Q1 July: 3500; Q1 Sep: Planning and Administration
| Total | Q1 July: 19551.03; Q4 Jun: 0.5
50000.03
-0.03
Note on C24: Lale Chopanova: See worksheet "персонал" - 1 Secretary 50% engagement
Note on C25: Lale Chopanova: See worksheet "офис"
Note on C26: Lale Chopanova: This will be covered by the driver remuneration
Note on C27: Lale Chopanova: UNDP charges for PO, vouchers, contracts etc - see worksheet "ПРООН"
Note on C28: Lale Chopanova: 7% GMS

## персонал
| зарплата в мес | занятость | кол-во месяцев | итого | в манатах
Секретарь СКК, зарплата включает 20% социальных выплат | 1000 | 0.5 | 12 | 6000 | 1750 | манат, до выплат, в мес
|  |  |  | 6000 | 1400 | манат, после выплат, в мес
[5 empty] | 400 | после выплат, в мес

## офис
| в мес | кол-во | итого
Закупка компьютера | 1000 | 1 | 1000
Закупка принтер 4 в 1 | 500 | 1 | 500
Канц.товары, на квартал | 45 | 4 | 180
Картридж, раз в 6 мес | 100 | 2 | 200
Мобильный телефон, на квартал | 20 | 4 | 80
Аренда водителя с машиной. Включает 20% социальные выплаты и расходы на бензин, масло, тех ремонт и другие нужды | 300 | 12 | 3600 | 240 | зарплата водителя в мес после социальных выплат | 840 | в манатах
Интернет, в месяц | 151.1 | 12 | 1813.2
7373.2
Машина (бензин, масло, колодки, итп) на квартал | 300 | 4 | 1200
1000
285.7143

## междун поездка
| цена | кол-во людей | кол-во дней | стоимость
авиа билет | 1000 | 2 | 1 | 2000
такси в аэропорт | 152 | 2 | 1 | 304
суточные | 350 | 2 | 4 | 2800
виза и страховка | 100 | 2 | 1 | 200
5312

## встречи СКК и рабоч группы
собрания СКК
кол-во людей | 25
| цена | кол-во | стоимость
Вода | 0.5 | 25 | 12.5
билеты участникам из велаятов | 55 | 4 | 220
суточные участникам из велаятов | 20 | 4 | 80
Распечатки | 2 | 25 | 50
362.5
Встречи рабочей группы
Nr of people | 9
| цена | кол-во | стоимость
Кофе-брейк | 7 | 15 | 105
Распечатки | 3 | 9 | 27
Вода | 0.5 | 30 | 132
264

## ориентационн тренинг
кол-во людей | 20
| цена | кол-во | дней | стоимость
аренда зала | 150 | 1 | 2 | 300
Вода | 0.5 | 40 | 2 | 40
билеты участникам из велаятов | 55 | 5 | 1 | 275
суточные участникам из велаятов | 50 | 5 | 2 | 250
Распечатки | 5 | 20 | 1 | 100
канц товары | 3 | 25 | 1 | 75
Кофе брейк | 7 | 40 | 2 | 280
Обед | 22 | 20 | 2 | 440
разное
1760

## тех поддержка
| цена | кол-во людей | кол-во дней | стоимость
авиа билет | 1000 | 1 | 1 | 1000
такси в аэропорт | 152 | 1 | 1 | 152
суточные | 249 | 1 | 3 | 747
гонорар | 300 | 1 | 4 | 1200
виза | 21 | 1 | 1 | 21
3120
| цена | кол-во людей | кол-во дней | стоимость
авиа билет | 1122 | 1 | 1 | 1122
такси в аэропорт | 152 | 1 | 1 | 152
суточные | 249 | 1 | 10 | 2490
гонорар | 400 | 1 | 16 | 6400
виза | 21 | 1 | 1 | 21
10185

## надзорные визиты
| цена | кол-во людей | стоимость
авиа билет | 55 | 2 | 110
такси в аэропорт (2) | 30 | 2 | 60
суточные | 20 | 2 | 40
210

## распечатки
| цена в мес | кол-во людей | кол-во мес | стоимость
гонорар экспертов | 500 | 2 | 2 | 2000
дизайнер | 600 | 1 | 0.5 | 300
материал 1 | 0.7 | 2000 | 1 | 1400
материал 2 | 0.7 | 2000 | 1 | 1400
материал 3 | 0.7 | 1500 | 1 | 1050
6150

## ПРООН
Project starff |  |  | 0
Transactions:
PO | 2112.55 | 2112.55 | 2677.83
Vouchers | 379.28 | 379.28
AR management | 186 | 186
Customs clearance | 0 | 0
2677.83

## LISTS
Cost Categories | CCM Secretariat positions | Activities | Fixed Costs
Human Resources | Executive Secretary | Annual CCM retreat | Human Resources (Secretariat staffs)
Technical Assistance | Oversight Officer | CCM Elections | Office rental and supplies (including equipement)
Planning and Administration | Finance Officer | CCM Induction | Other
Meeting, Trainings, Workshops, consultations | Admin Assistant | CCM Plenary/General Assembly meeting | Overhead cost (i.e. fees to manage CCM funding)
Communication materials |  | Constituency consultations for non-governmental constituencies only (e.g. civil society and private sector) and processes to promote and improve the quality of stakeholder participation, including travel costs and per diems for civil society participation. | Vehicule maintenance
Equipment |  | Constituency engagement meetings (specify in comments)
Overhead |  | Oversight Committee meetings | Performance Area
Indirect Costs |  | Site Visits / Monitoring Visits | Alilgnment
Others (Please specify in comments) | CCM Secretariat positions | Technical Support | Oversight
| Executive Secretary | Technical Working groups meetings | Constituency Engagement
| Oversight Officer | Workshop/Meeting for funding request development | Capacity Building/Gender
|  | Others….(Please specify) | Sustainability and Transition
Dialogue
Currency
USD
EUR