Human Resource Management Information System and Support to the Civil Service Census

Combined Inception Report and Implementation Plan

8 November 2010

Objective

By March 2011, to have accurate Ministry of Education (ME) personnel records, stored securely on a sustainable Human Resources Management Information System (HRMIS) that maintains the accuracy of its data.  This objective is consistent with Result 9.2 of the National Education Strategic Plan 2011-2030: By 2011 an Integrated Human Resource Management System is in place.

Development Context and Issues

Personnel Information Management

The Government of Timor-Leste (GoTL) has three main databases that store information about ME personnel, located as described in the table below.

Table 1: Current location of GoTL databases containing key ME personnel data

| Name of Database | LOCATION |
| --- | --- |
|  | Agency | National Directorate |
| Education Management Information System (EMIS) | Ministry of Education | Policy, Planning & Development |
| Personnel Management Information System (PMIS) | Civil Service Commission | Human Resources Policy & Practice |
| Government Payroll | Ministry of Finance | Treasury |

Apart from these electronic databases, ME personnel records are also kept as paper files in the archives section of the Human Resources Department in the National Directorate of Administration, Finance and Logistics (AFLA) of the Ministry of Education.

Issues

There are many information management issues both within and between the GoTL databases that could compromise the effectiveness of the National Education Strategic Plan (NESP), and education management generally. The examples below give a general indication of the four most basic problems.

- Basic inconsistencies in ME personnel records on PMIS and Payroll can have financial costs to ME

Each of the databases mentioned above contains various types or fields of information. Where these fields have similar labels, the contents do not match for even the most basic information such as numbers, names and location of employees and their birthdates.  An analysis of the ME payroll for October 2010, suggests that the financial cost of inconsistencies between the PMIS and Payroll databases may have been as high as $43,592.00, where 39 staff were actually based in other agencies; implying an annual total cost of $523,104 to the ME salaries and wages budget.

- Current EMIS data cannot be used to support or verify implementation of the Teacher Career Regime

This issue will impact negatively on the ability of ME to support planning and verify progress in the implementation of the National Education Strategic Plan.  Successful implementation of the Teacher Career Regime (TCR) requires accurate information on the academic and teaching qualifications of teachers. While the EMIS has a field for recording the educational level (edu_level_name) of ME personnel outside of the central ministry and regional offices, the values are confusing. For example, the difference between the values to classify self-reported data on qualifications: college graduate, completed tertiary, and university degree is unclear. Also unclear is how these labels can be used to describe the range of qualifications encountered in Timor-Leste.  By comparison the values in the corresponding PMIS field (Nível habilitacional) are clearer, but the added clarity is compromised by the fact that there is no information for about a third of the ME staff (Not stated). Consider the information in Table 2 below.

| Table 2: Comparison of values for EMIS and PMIS fields on ME staff qualifications |
| --- |
| EMIS Field: edu_level_name % Value Labels College Graduate 26.7 Completed Tertiary 1.4 None 1.3 NULL .6 Pre Sec (Complete) 2.7 Pre Sec (Incomplete) .2 Primary (Complete) 5.1 Primary (Incomplete) 1.0 Secondary (Complete) 47.6 Secondary (Incomplete) .6 University Graduate 12.8 Total 100.0 | PMIS Field: Nível habilitacional % Value Labels Not Stated 32.0 Ensino Básico 1.1 6 anos de escolaridade 1.7 9 anos de escolaridade 1.6 12º Ano 49.1 Diploma 1 .2 Diploma 2 4.8 Diploma 3 2.6 Diploma 4 .1 Bacharelato .8 Licenciatura 4.7 Mestrado .5 Doutoramento .0 Pos-Graduacao .0 Other .8 Total 100.0 |

3. Job categories used in the GoTL databases differ and are not yet consistent with the TCR

While all GoTL databases mentioned above distinguish between temporary and permanent staff, they do not share a common field for job categories.  And they do not yet have fields consistent with the TCR (Professor Sénior, Professor, Assistente).

- The EMIS field for staff categories is useful insofar as it distinguishes within teachers, and between teachers and “other staff”. It can therefore be expected to capture data about non-teaching staff, but only for support staff (security guards and administrative assistants) working in schools. It does not include records on staff working in the Ministry or Regional offices.

- The PMIS includes aggregated information on ME staff; it does not distinguish between teachers and non-teachers, but does include staff working in the Ministry or Regional offices. Job titles in  PMIS refer to the civil service grade (A to G) and their corresponding titles (Technical Superior, Technical Professional, Technical Assistant, Administrative, Assistant Administrative), using labels that combine title and grade (TPGrauC, TAGrauE). The range of values for this field also includes management positions, like ChefeDep, DirNacional.

- The Payroll uses rough English translations of the Portuguese civil service grade title followed by the Ministry; but no grade (for example, Intermediate Technician/Ministry of Education).

4. All GoTL databases contain unwanted duplicate records and require cleaning.

Project Description and Methodology

The MECBP HRM projects, HRMIS and Support to the Civil Service Census (SCSC), will reconcile ME staff data on the GoTL databases and assist in improving the functionality of the EMIS, so that it can better support the implementation and monitoring of the NESP and TCR. Together the HRMIS and SCSC projects have six components:

| C.1 Inception C.2 Data Entry and Document Scanning C.3 Field Data Collection | C.4 Data Analysis And Reporting C.5 Integration of HRM Information Systems C.6 Document Management System |
| --- | --- |

Component Description

Component 1 (C.1) refers to the Inception Phase of the HRMIS and Support to the Civil Service Census, which lasted throughout October 2010 starting with the mobilisation of the respective Project Coordinators (PCs). During the Inception Phase the PCs analysed the current situation to determine issues and set benchmarks for monitoring and evaluating progress.

C.2 through C.4 refers mainly to what was originally called the ME Staff Census Project. During the Inception phase (C.1), the name was changed to Support to the Civil Service Census (SCSC). This was done to acknowledge that the MECBP contribution is only one part (albeit a very important part) of the wider Civil Service Census, currently being conducted by the Civil Service Commission, with assistance from the UNDP Support to the Civil Service Reform Project (SCSRP).

Civil Service Census

Primary data collection, the activity most popularly associated with a “census”, is proceeding efficiently district by district. The CSC field team started in Lautem in May 2010 and is due to complete data collection on schedule, in Dili District by the end of December 2010. The aim of this exercise is to enumerate and validate basic data like: names, faces (via digital photograph to be matched with a unique civil service number), age, years of service; and most importantly for current ME priorities, the validation of qualifications (via certified copies) and place of work – schools in the case of teachers.

Component 2: Data Entry and Document Scanning

As per normal PMIS practice, Census Data is entered by trained staff from all GoTL agencies at CSC’s PMIS Unit. It cannot be done from a remote location or by untrained staff. ME data operators are allotted two computer terminals from Monday to Friday (smaller agencies are allotted one computer terminal). Attendance of the ME data operators is not optimal, and their choice of district census data is random. One day they may enter data from Lautem, another day from Manufahi or some other district.

Accelerated Data Entry (ADE)

This component facilitates cooperation between the CSC and the ME to accelerate census data entry. Accelerated Data Entry (ADE) is needed because only 10% of data collected since May 2010 had been entered by mid-October. Without SCSC assistance the estimated completion date for data entry is 30 June 2011. In cooperation with the ME and CSC, SCSC Project will mobilize more data operators from with the ME and from the CSC for entering ME personnel data (500 person days divided by 15 persons = 33 days), and bring the estimated completion date forward, from June 2011 to January 2011.

ADE will be conducted after office hours (6pm to 10pm) and on Saturdays and Sundays (8am to 1pm and 2pm to 5pm), regardless of public holidays. Lunch and snacks will be provided on site to optimise time utilization. Meanwhile, data entry during weekdays will be optimized with no extra subsidy, by improving supervision of attendance and accuracy and increasing the number of data operators whenever possible; for instance, when data operators from other Agencies are absent.

To ensure quality of data entry (and to avoid duplicated, inaccurate or missing entries which made the census necessary in the first place), the Project will recruit a quality controller (referred to as “Data Entry Checker” or DEC) for 70 working days. The DEC’s duties will include supervision of data operators’ attendance and monitoring the accuracy and speed of all data entries, recording output and number of errors for each data operator. This information will be use in a system of rewards and sanctions to motivate data operators to pay attention to quality and to ensure that the subsidy paid for working provides value for money. The rewards will consist of prizes awarded weekly for the most accurate and fastest data operator.  The sanctions will include debiting the hourly subsidy for each data entry error after the first three mistakes in any session. Data operators who are shown to be consistently inaccurate or too slow will be dropped from the roster.

Scan ME personnel documents

The project will procure document management scanners to record soft copies of the certified documents for all ME staff, collected by the CSC field team during the Enumeration phase of the Civil Service Census. Priority will be given to scanning teacher qualifications, needed to inform the ME’s transitional certification framework for assessing entry points into the TCR and the rapid bacharelato program, by giving appropriate credit for existing qualifications.

Component 3: Field Data Collection

Field data collection will follow up on the CSC visits, targeting gaps in their data. Such gaps may happen where ME staff did not attend the Census Enumeration meetings as scheduled in their District Offices, and where the ME requires other information to support priority programs in the NESP. Field data collection will be conducted by three post-enumeration survey teams (PEST) from ME’s HR Department. The Head of the Department is the Field Operations Manager. These field visits are intended as cost-effective surveys to collect, confirm or clarify teacher-specific data (e.g. class contact hours, attendance, teacher-student ratios, etc.). This information will be needed to answer questions arising from three possible sources: the Civil Service Census, or EMIS and PMIS data cleaning, or from the 2011 teacher schedules requested by the Ministry in late November or early December 2010 with a submission deadline set in the second week of January 2011.

Component 4: Data Analysis and Reporting

An early activity under Component 5 was the extraction and analysis of existing data from PMIS, EMIS and Payroll databases in October 2010. Analysis of this existing data during the inception phase was necessary to establish benchmarks to inform three monitoring and evaluation purposes:

1.  Measurement of progress in the reconciliation of data within and between these databases during    the project;

2.   Assessment of the effectiveness of ADE, as described under Component 3; and

3.  Basis for comparison of findings for an independent audit, mentioned under Component 5 below (Activity C.5.14 in Attachment A:  Joint Implementation Plan).

Computer Applications

The GoTL databases all use different applications. Payroll uses Crystal, PMIS uses a propriety program owned and operated by a Portuguese company Quidgest, and EMIS uses SQL server. Extraction of data from these databases is via Microsoft Office Excel to IBM SPSS 19 for data analysis and production of standard tables for project reporting to the Steering Committee and other stakeholders. An SPSS Codebook will be produced under this component to define new variables (the SPSS term for fields), and to recode values into existing fields.

Component 5: Integration of GoTL HRM Information Systems

Components 5 and 6 refer specifically to the HRMIS project. Successful implementation of the HRMIS project is critical to achieving sustainable results in the SCSC project. Component 5 includes measures to promote national ownership, by standardizing  HRMIS protocols between the EMIS, PMIS, and Payroll and establishing an inter-ministerial Steering Committee, to supervise the joint implementation of the HRMIS and SCSC Projects initially, and then to ensure compliance with the agreed protocols across the organizations where the databases are located. This is intended to ensure that regular reconciliation of records continues after the project ends. Under Component 5, existing data from the various GoTL databases will be integrated and new fields added as new types of information are required by ME. It is for this purpose also that protocols between the various GoTL organizations that manage the databases must be agreed. Therefore, the proposed steering committee must have representatives from all stakeholder organizations.

Methodology

| Key Steps | Outputs |
| --- | --- |
| 1. Describe the structure of current ME HR data in EMIS, PMIS, Payroll, and Personnel Files in the archive section of the ME HR Department. | Report to the Steering Committee |
| 2. Identify the following, for the PMIS, EMIS and Payroll information systems respectively. |
| Objective | Content | Data managers | Report to the Steering Committee |
| Who uses (or should use) the data |  |
| Data collection method | Linkages to other databases |  |
| Protocols, security & backup | Issues |  |
| 3. Data Analysis and Verification (Component 4) to identify inter alia: Records that are unique to each database Records that are common to more than one database Statistics on data records, e.g. number of permanent & contract staff | Data fields matrix, statistics on errors, duplications and gaps. |
| 4. Joint Project Steering Committee (and Work Group) Establish a steering committee to monitor the operation of HRMIS into the future. Recommended membership: Directorate-General of Corporative Services, National Director of Human Resources, National Director of Finance & Logistics, National Director of Planning, Statistics & Information Technology, EMIS Chief of Department and the ME Payroll team-leader, a representative from the Ministry of Finance Payroll Department and PMIS in the Civil Service Commission. | ToR Roles and responsibilities for ongoing accuracy of HRMIS data is clarified Progress reports to the Ministers of Education, Finance and the President of the Civil Service Commission |
| 5. Establish protocols for the integration of HRMIS Determine who will be the authority for individual data, e.g. PMIS for name, qualifications, employment status; EMIS for subjects and timetables; Payroll for salary payments; HR Department for teacher attendance and annual leave Determine what the relationship between each database should be and implications for operational staff Develop protocol procedures Manual for each database Develop shared systems for such things as alerting operators to data entry errors, and for locking certain data fields e.g. names Conduct a review of the purpose of each database with the aim to improve reliability Develop training plan and conduct training in the new procedures | HRMIS Procedures Manual Operational staff trained in HRMIS protocols Efficiency improved |
| 6. Entering SCSC Project data Assist to establish new fields in EMIS to for census and PES data. Arrange to input data to EMIS from the SCSC Project Verify existing data in EMIS against the census data | EMIS includes data fields for the SCSC Project data entry EMIS data accuracy verified against PMIS census records |
| 7. Merge EMIS staff records with PMIS Match selected data fields and values in PMIS and EMIS (e.g Names, IDs number, DoB, Qualifications) and reconcile data between EMIS and PMIS | Reconciled key data between PMIS and EMIS |
| 8. Identify which fields created in Step 7 require changes in the Payroll database, and reconcile duplications and information gaps | Errors, duplications and gaps identified and reconciled |
| 9. Regional and District roles in HRMIS Steering Committee to determine the role of the regional and district offices in the capture and input of HRMIS data, having considered the protocols and inter-relationships | Allocation of regional and district roles and responsibilities |

Component 6: Document Management System for Personnel Files

Under this  component, the a document management system will be purchased by the ME for storing personnel files within the Human Resource Department, for 15,000 box files containing  information on each ME employee. This will be a commercial quality “compactus” design and must be installed in a secure location where access is controlled and conditions suitable for long term storage. Plans will be developed for the implementation of the hard copy system (leaving a project plan, for example) that the ME can implement with technical support. The project will include planning for eventual digital scanning equipment/ software to enable a soft copy of all personnel files to be generated and stored. If time and/or budget allocations impede progress it will be feasible to purchase and install the storage facility first and the digital scanning component can done in the future, once the hard copy files are completed.

Methodology

| Key Steps | Outputs |
| --- | --- |
| Situation analysis and Data Verification of personnel files will be conducted in Part 1 (HRMIS) | Report, Data matrix, statistics, errors, duplications and gaps |
| Document Management System Work Group Establish work group to oversee the project and to provide progress reports to the National Director TOR to be drafted for National Director’s approval Determine the allocation of responsibilities for maintaining the personnel files in the future | ToRs |
| Protocols for the integration of Personnel Filing System with other databases. To be determined in Component 5 | HRMIS Procedures Manual Operational staff trained in HRMIS protocols and efficiency improved |
| Regional and District roles in Document Management To be determined in Component 5 | Allocation of regional and district roles and responsibilities clear Training in document management |
| Specifications for quotations Filing cabinets supply and installation Box files supply and delivery Scanning and electronic imaging equipment supply with Automatic Document Feeder, 20 pages per minute, and dpi of 600. Price to include installation along with document management software installation and training | Request for Quotations produced CPVs produced Staff trained in document management system Operations manual produced |

Language support required

English to Tetun interpretation will be required for meetings with the Steering Committee and training presentations.  English to Tetun translation for documentation will be required for HRMIS Guidelines and Protocols, and related Training Powerpoint and handouts, and for Terms of Reference.

Project Governance and Personnel

The project will be implemented by the Ministry of Education with assistance provided by the New Zealand Embassy Aid Programme Ministry of Education Capacity Building Programme (CBP).  The Steering Committee will be responsible for implementing the HRMIS Project and a Work Group is responsible for implementing the Document Management System

Attachments

- Joint Implementation Plan

- Joint Activity Schedule

- Joint Project Budget