United Nations Development Programme

Country: Vanuatu

Project Document

| Project Title | Vanuatu MDG Acceleration Framework: Improving Access to Reproductive Health Services |
| --- | --- |
| UNDAF Outcome: | Regional UNDAF Outcome 3.1: Inclusive economic growth is enhanced, poverty is reduced, sustainable Decent Work is improved and increased, livelihood opportunities and food security are expanded for women, youth and vulnerable groups and social safety nets are enhanced for all citizens. |
| Expected CP Outcome(s): | Vanuatu UNDAF Outcome 3.1: Alleviation of poverty and increased inclusive growth, employment and livelihoods with a focus on women and youth |
| Expected Output(s): | Vanuatu UNDAF Output 3.1.2: Cross sectoral coordination mechanisms are functioning effectively in order to facilitate the implementation of national strategic priorities towards poverty reduction, youth employment and inclusive economic growth and social safety nets |
| Implementing Partner: | UNDP |
| Responsible Parties: | Department of Strategic Policy, Planning & Aid Coordination (DSPPAC) |

Agreed by: 							Date:

Government of Vanuatu

Agreed by: 							Date:

UNDP Resident Representative

# Situation Analysis

This section deals with the socio-economic context and progress of MDG in Vanuatu. Vanuatu was one of the three Pacific countries selected to prepare the MAF in the run-up to the December 2012 Summit. The UNDP’s MDG Acceleration Framework (MAF) provides United Nations Member States a methodological framework to assist countries in identifying obstacles and solutions to achievement of the goals. It is recognised that there is a need to develop a programme strategy that focuses on the continued strengthening of national institutions and focus on a tailored MDG target. The MAF is a strategic vehicle for prioritization, focus, streamlining, cohesive programming, considers the best possible combination for highest impact. The MDG Acceleration Framework in Vanuatu  has  focused  on a tailored MDG 5: which is to address the target of improving reproductive health (MDG 5.B) with emphasis on reducing the adolescent birth rate (Indicator 5.4), especially in rural areas, and reducing the unmet need for family planning (Indicator 5.6).

Socio-economic context:

The Republic of Vanuatu comprises a chain of more than 80 islands in a ‘Y’ shaped chain, of which 65 are permanently inhabited. These islands extend 1,300 km along a north—south axis between latitudes 13O and 22O degrees south, with an exclusive economic zone (EEZ) of 700,000 km². The volcanic and coral platform islands are young, small and highly disturbed as a result of frequent cyclone, seismic and volcanic activity. There are nine active volcanoes, seven of which are terrestrial and two under sea. Because of the rugged and mountainous terrain most of the population live on the narrow coastal strip.

The country has a reasonable natural resource base for achieving sustainable development and 76% of the population live in rural areas, mainly living by subsistence although there is increasing ‘formal’ economic activity in all of the islands. An estimated 41% of the land is suitable for cultivation, but these amounts vary considerably from island to island. Over 90% of the land is held in customary land tenure for use by family members while the remaining 10% is freehold and public land.

Research conducted by UNICEF on the 2006 poverty data examined the incidence of poverty for children aged 17 years and under. While the national incidence of poverty as measured by $1.25 a day was 5% for all children there was considerable variation between provinces (see Table 1 ). The incidence of poverty ranged from 14% of children living in households that managed on less than $1.25 a day in Torba to 2% in Malampa. In Luganville 1% of children lived in households with income of less than $1.25 a day and 2% in Port Vila lived in poverty using this definition.

Table 1: Children living on less than $1.25 per day, 2006

| Province / urban area | Total number of children | Number. below $1.25 poverty line | % below $1.25 poverty line |
| --- | --- | --- | --- |
| Torba | 4,420 | 628 | 14.2 |
| Sanma (rural) | 11,673 | 123 | 1.1 |
| Penama | 15,059 | 244 | 1.6 |
| Malampa | 13,081 | 307 | 2.3 |
| Shefa (rural) | 12,067 | 1,294 | 10.7 |
| Tafea | 15,786 | 1,867 | 11.8 |
| Luganville | 4,408 | 46 | 1.0 |
| Port Vila | 11,492 | 232 | 2.0 |
| Vanuatu | 87,986 | 4,740 | 5.4 |

Source: UNICEF (2006 HIES data). Children defined as aged 17 years and under.

### Rural and urban differences

From the 2006 HIES data the incidence of poverty using the $1.25 (PPP) poverty line was 9% for the population and 8% for households (Table 2). It was highest in the rural areas, although there are concerns about the under—estimation of the value of subsistence production and consumption in rural areas which has resulted in a higher level of poverty than that which occurs.

Table 2: Incidence of poverty (IP) using the $1.25 (PPP) poverty line, 2006

|  | Households | IP | Population | IP |
| --- | --- | --- | --- | --- |
| Vanuatu | 1,838 | 7.7% | 10,857 | 9.2% |
| Rural | 1,703 | 5.0% | 10,179 | 6.4% |
| Urban | 136 | 2.7% | 678 | 2.8% |
| Port Vila | 107 | 1.5% | 553 | 1.7% |
| Luganville | 28 | 1.2% | 125 | 1.2% |

Source: VNSO

## National poverty lines

Most Ni—Vanuatu live in ‘subsistence affluence’, enjoying plentiful natural resources in an unspoilt environment providing that they are able to contribute labour and have access to land and marine resources. Yet the rural majority suffer from what is often called ‘poverty of opportunity’—a lack of access to services (education, health, regular water supply, transport, communications, energy) and income—earning opportunities that would enable them to improve their living standards. Most major new developments still occur in, or near, the urban areas.

Lack of opportunity in rural areas is contributing to rapid urbanisation. If the "urban fringe" around Port Vila is included, the urban population is now around 30% of the total population in Vanuatu. Gradually Port Vila has acquired densely populated squatter settlements lacking basic services, creating a new urban poverty. Land disputes between groups of immigrants to Efate and the indigenous communities are a potential source of conflict. A range of social problems are emerging among the new urban generation, with high rates of unemployment contributing to substance abuse, property—related crime, transactional sex and teenage pregnancy.

The Government considers the HIES of 2006 the source of the first nationally reliable estimates for poverty for Vanuatu. National food and basic needs poverty lines were derived using the regional ‘standard’ method used by UNDP and the ADB in their regional assistance programmes. A limitation of this method is that poverty lines are derived from the HIES expenditure data for food, subsistence production and other non—food expenditure in the lowest 30% of households rather than the cost of a ‘model’ diet or the actual costs of other expenses essential for life. This has lead to some criticism of this method.

The HIES data indicated that the average adult in Vanuatu needs Vt 3,064 a month (Vt 102 a day) for food and a further Vt 1,651 (Vt 55 per day) for non—food items such as shelter, clothing, household supplies etc. The Basic Needs Poverty Line (BNPL) in 2006 for Vanuatu was the total of the food and non—food monthly expenditure: Vt 4,715. Applying this BNPL to expenditure reported in the HIES resulted in 6% of households or 7% of the population experiencing food poverty or hardship and 13% of households or 16% of the population in basic needs poverty or hardship. The BNPL for Port Vila was Vt 11,075 and for Luganville it was Vt 6,110 while for rural areas it was much lower at Vt 3,366 per average adult per month. In Port Vila 33% of the population had per capita incomes (average adult) below the BNPL of Vt 11,075 and were defined as poor using this definition of poverty.

MDG Acceleration and approach: The MAF approach is based on four points: identification of the strategic interventions required to accelerate MDGs that are presently not on target for 2015; analysis of key bottlenecks that have delayed implementation of the interventions; selection of cost-efficient solutions and development of an action and monitoring plan including a precise definition of the roles of institutions and partners in implementation. In this way, the MAF seeks to identify practical, targeted, short-term solutions to accelerate achievement of MDGs. The MAF is a strategic vehicle for prioritization, focus, streamlining, cohesive programming, considers the best possible combination for highest impact. The MAF is not intended to replace current policy preparation processes in this respect; on the contrary, it forms part of such processes by providing deeper analysis of problems and helping to identify solutions and the stakeholders who could carry them out.

The MDG target to accelerate was chosen based on the following selection criteria: “Should have the potential to achieve significant results within the next two years”, “should have strong political and community support” and “should have the potential to accelerate and impact other targets that are also lagging (i.e. cross sectoral impact)”. Based on these criteria the government of Vanuatu has chosen to address the target of improving reproductive health (MDG 5.B) with emphasis on reducing the adolescent birth rate (Indicator 5.4), especially in rural areas, and reducing the unmet need for family planning (Indicator 5.6).

MDG 5, Maternal Health: The challenges to be addressed: The population of Vanuatu is expected to double by 2030. And, the government will face significant challenges to provide essential services, especially maternal and child health and basic services, to its fairly fertile population. Use of family planning methods is important not only for fertility control, but also for the health of mothers and children by preventing pregnancies that are too early or too late, extending the period between births, and limiting the number of children.

The main indicators relating to unmet need for family planning and adolescent birth rate show that Vanuatu is unable to guarantee an adequate access to reproductive health to the whole population. In addition to the lack of access to family planning in certain remote areas, the adolescent birth rate per 1,000 women aged 15-19 years is relatively high in the country, especially in rural areas. Very early childbearing brings with it heightened health risks for mothers and their infants. Early childbearing is also linked to outcomes such as lower educational attainment and poverty. Adolescent Sexual and Reproductive Health is a priority area for the Ministry of Health as part of its overall national Reproductive Health programme 2008-2010.

Adolescent birth rate is one of the two MDG indicators selected by the Government of Vanuatu during the MAF process. The latest Vanuatu MDG report that was released in 2010 found a high adolescent birth rate compared to the Pacific region and the rest of the developing regions. The Adolescent Birth Rate measures the annual number of births to women 15 to 19 years of age per 1,000 women in that age group. It represents the risk of childbearing among adolescent women 15 to 19 years of age.

In Vanuatu, the rate has decreased from 92 per 1,000 live births in 1999 to 64 per 1,000 live births in 2009. But this adolescent birth rate is still relatively high (especially in rural areas) by regional standards. The Pacific as a region recorded an adolescent birth rate, on average, of 52 per 1,000 live births to women aged 15-19 years. The rate varies from 18 per 1,000 births in Palau (2007) to 138 per 1,000 births in the Marshalls Islands (2007).

Another frequently-used indicator is the teenage (or adolescent) fertility rate, which is the number of births per 1,000 women aged 15-19. The 2009 Census estimated that the teenage fertility rate in rural areas was 77 births per 1,000 women aged 15-19 and 40 in urban area). The high teenage fertility in Vanuatu is primarily a rural phenomenon. In 2009 the urban teenage fertility rate is almost half the rural rate and is only one third of the rate observed in Torba province (the most northern province). The relatively low rate in Shefa is obviously related to the high level of urbanization in this province. In Vanuatu, early child-bearing is incompatible with educational achievement at higher secondary and tertiary levels. This suggests that education and access to services are key elements in reducing teenage fertility (Prime Minister’s Office, 2011: 24).

The second MDG indicator selected by the Government as part of the MDG acceleration framework process is the Contraceptive Prevalence Rate (CPR). The CPR is the proportion of women of reproductive age who are using (or whose partner is using) a contraceptive method.  Although the CPR has shown a “slight improvement” in Vanuatu over the years from an estimated 28% in 1999 to 30% in 2005 it is still low by global standards. The latest Multiple Indicator Cluster Survey (UNICEF and DSPPAC, 2008) underlines subnational disparities whereby urban women are more likely to use modern family planning methods than rural women (41.4% vs. 37.5%). The contraceptive prevalence rate also varies widely across the provinces, ranging from 25% in Malampa to 53% in Torba.

# Strategy

UNDP has a strong and long-standing development partnership with the Government of Vanuatu and the previous support provided in the achievement of MDG, in particular. UNDP has been engaging with the Office of the Prime Minister since 2008 through the MDG Capacity Building Project which resulted in the development of the 2nd National MDG report and mainstreaming MDGs into the PAA/PLAS as well as relevant sectoral development plans and government corporate plans amongst other initiatives.

Key areas of interventions identified during the MAF formulation process to reduce the unmet need for Family Planning and Adolscent birth rate include: (1) Delivery of quality family planning services, (2) Family Life Education  Programme, (3) Youth Friendly Services (YFS). Vanuatu is challenged with many bottlenecks related to the identified key areas of intervention. These bottlenecks have been identified by the MAF expert working group during MAF workshop sessions and fit within the following categories: policy and planning, budget and financing, service delivery (Supply) and service utilization (Demand).

The principal bottlenecks identified under key priority area Delivery of Quality Family Planning Services are:

- Irregular availability and accessibility of contraceptive commodities (especially pills and injections) at all levels

- Shortage of staff allocated to running RH services

- Gvt/Donor funds not allocated and dispersed at  Dispensaries & Health centers (where RH services are delivered) to support FP outreach programmes

- Inadequate skilled service providers (RH nurses)

- Restriction of Emergency Contraceptive Pills (Postino) to hospitals

- Low coverage of HIS reports

- Poor coordination between services providers (at national and provincial levels) to plan and implement FP services (poor resource mobilization)

- Fear, misconceptions and lack of appropriate FP knowledge by local communities

- Limited involvement of male in reproductive health (male involvement)

The three principal bottlenecks identified under key priority area Family Life Education (FLE) Programme are:

- No local expert at VITE and schools to deliver FLE programme

- Possible fear and misconceptions of parents and school committee members in implementing the FLE programme in schools

- No funding for Monitoring and Evaluation FLE programme

The principal bottlenecks identified under key priority area Youth Friendly Services (YFS) are:

- Inadequate skilled YFS service providers (RH nurses)

- Inadequate funding to expand YFS by NGOs and CBOs through 30 Health Centers and 103 dispensaries across Vanuatu (only 7 YFS operating at the moment)

- Low demand creation for YFS utilization

- No definition, standardization and accreditation of YFS to ease Monitoring and Evaluation

- Irregular availability of YFS

- Inadequate skilled peer educators for YFS

Further to the acceleration of the achievement of MDG 5.B, the government of Vanuatu and development partners have identified three key priority areas and prioritized interventions to address the main bottlenecks, these are:

- Strengthen and improve delivery of quality family planning services

- Improving supply and distribution of FP commodities;

- Extending reach of family planning services into community by improving FP Outreach Programmes (recruit more staff, disperse funds);

- Improving quality of FP services by training adequate skilled service providers, extending access to Emergency Contraceptive Pills, improving coordination between services providers;

- Improving community awareness and understanding of reproductive health (develop appropriate knowledge, improve male involvement).

- Establish school based Family Life Education (FLE) Programme

- Ensuring delivery of quality FLE course of study by training adequate skilled teachers and reproducing FLE materials;

- Improving community support for FLE Programme; and

- Improving Monitoring and Evaluation of FLE Programme.

- Increase access and utilization of Youth Friendly Services (YFS)

- Extending reach of Youth Friendly Services into community by expanding YFS across Vanuatu;

- Improving quality of Youth Friendly Services by training adequate skilled service providers and peer educators and assuring regular availability of YFS;

- Improving demand creation for YFS utilization by including other youth initiative and implementing innovative ideas; and

- Improving Monitoring and Evaluation of Youth Friendly Services.

UNDP will assist the Government of Vanuatu to implement the MDG Acceleration Framework for Vanuatu by providing support following areas relating to the identified key priority areas and related selected interventions:

- Policy Advisory Services

- MDG Planning and Monitoring

- Resource Mobilization for the Implementation of the MAF

- Programme Management and M&E

- MAF Advocacy and Awareness Raising

- Policy Advisory Services

Targeted interventions to address leadership and coordination gaps as well as health system bottlenecks need to be combined with longer-term efforts to address social, cultural and economic determinants of maternal and reproductive health. These factors include, among others, widespread poverty, gender inequalities and harmful cultural norms, inadequate promotion and protection of human rights, marginalization and exclusion, food insecurity and poor nutrition, low levels of social capita, long distances from health facilities, and inadequate infrastructure and transport services, particularly in rural areas.  Appropriate laws and policies, that are multi-sectoral in nature and human rights based, to address the social, cultural and economic determinants of maternal and reproductive health are an essential ingredient to address these social, cultural and economic factors and can impact, directly and indirectly, maternal mortality and improving access to reproductive health services.

As part of this component UNDP provided in-depth analysis and appropriate policy design to address the social, cultural and economic determinants of maternal and reproductive health through the following initiatives:

- Analyze the social, cultural and economic determinants of maternal and reproductive health;

- Design appropriate policy responses;

- Assist the Government to allocate sufficient financial resources for an effective implementation of the policy response;

- Assess the extent to which the governments respond to the identified bottlenecks that are hastening the achievement of the MDG 5; and

- Encourage South-south collaboration and knowledge-sharing on MDG 5.

UNDP will either provide direct policy advisory services to the MAF expert group and/or relevant implementing agency or coordinate amongst relevant UN agencies and/or development partner/s to provide the necessary policy advisor service for policies identified in the MAF implementation plan either for review of formulation relating to three key priority areas and prioritized interventions.

- MDG Planning and Aid Coordination

Within this component UNDP will assist the National MDG Taskforce, MAF expert working group and relevant implementing partners to monitor and report on the MDG indicators and MDG targets that the MAF action plan is striving towards. This component will also focus on assisting relevant Government Ministries and Departments to plan and budget for interventions outlined in the MAF implementation plan to address the MDG target selected for acceleration. Support will also be provided in monitoring the overall MDG framework, both at the national and sub-national as much as possible, focusing on the targets and indicators that are off track or showing no progress.

UNDP will provide support in terms of creating and enabling environment for resource mobilization to cover the funding gap for the MAF implementation plan. This will be in the form of conducting donor round table and/or bilateral meetings, preparing and proposals relating to the MAF funding gap for funding consideration.

As part of this component UNDP will mainstream maternal and reproductive health as a human rights and development issue through the following initiatives:

- Ensure the MDG 5 is appropriately reflected in national, sector and local development plans and processes, which adequately relate to the relevant public expenditure frameworks;

- Ensure national, sectoral or local result frameworks include MDG indicators and other appropriate indicators that are relevant for achieving MDG 5;

- Ensure MDG 5 and corresponding indicators are reflected in UNDAFs and CPAPs; and

- Foster national dialogue for developing appropriate macroeconomic policy responses that can trigger sustained and well managed increased aid flows for maternal and reproductive health and the larger health system.

The government of Vanuatu will take the lead in organizing and liaising directly with the donors whereas UNDP will provide technical and financial support to the Government to facilitate the process.

- MAF Advocacy & Post 2015 Agenda

Efforts to improve maternal and reproductive health cannot succeed where they are not nationally owned and prioritized. Where appropriate UNDP will provide funding assistance to promote the objectives of the MAF as well as the progress and planned activities of the MAF implementation plan. As much as possible UNDP will report on stores that relate to the human face of the MDGs acceleration framework. For example, how the MAF has or intends to improve the lives of individuals or communities that are part of the population that are off track in the selected MDG target. This component will also look at facilitating national consultations among all relevant stakeholders on the pertinent issues for consideration in the post 2015 development agenda. This will be a major opportunity for a wide variety of stakeholders to influence the shape of the next agenda from both a country and global perspective. Furthermore, this builds a shared vision and ownership of how global, regional, national and sub-national governance and accountability should be integrated within the intergovernmental process to inform on the post-2015 development agenda; The results of these efforts particularly the findings of consultations related to governance and accountability frameworks are directly linked to and feedback into   national consultations, as well as into ongoing global processes. This is crucial to ensure that neither time nor momentum on development is lost in the transition to post 2015 development framework.

As part of this component UNDP will encourage local ownership of the MAF through the following initiatives:

- Coordinate and engage in advocacy activities with leaders within and outside of government (Parliament, civil society organizations, religious leaders, and others);

- Work with civil society organizations and the media to highlight the importance of maternal and reproductive health;

- Train local media and government Information and Communication Officers in identifying and developing stories that relate to the achievement of the MDGs;

- Assist the government in setting out the flows of information from Government to communities via the media and other outlets; and

- Organize consultations with all relevant stakeholders at all levels to identify the pertinent development issues for consideration in the post 2015 development agenda dialogue.

- Programme Management and M&E

A MAF Programme Coordinator will be based in the UNDP MCO to coordinate and provide oversight management of the various MAF projects in the Pacific Island countries that are implementing MAF projects. UNDP will provide a MAF National Project Coordinator to be based within DSSPAC to support the implementation of the MDG acceleration Framework for Vanuatu.

The key functions of the MAF Project Coordinator would be to coordinate MAF implementation activities by convening meetings of the MAF expert groups, implementing partners and relevant stakeholders to discuss progress and implementation arrangements for planned activities. Convene annual review meetings of the MAF project board. Report on a quarterly basis and annual basis on the progress, risks, issues and mitigation actions of MAF implementation plan in the required UNDP reporting format. Report on a quarterly and annual basis on the financial delivery of the MAF implementation plan. Provide logistical support and technical support where possible to the relevant government agencies to implement their respective activities of the MDG Acceleration Framework.

The MAF National Project Coordinator is also required to provide assistance in terms of identifying and responding to governance, institutional and management capacity bottlenecks that impact on the health sector through the following initiatives:

- Coordinate multiple partners for action on MDG 5;

- Strengthen the capacity of local development partners and local government to work with communities to identify and deliver localized approaches to improve maternal and reproductive health as well as monitor and evaluate results;

- Strengthen ministerial capacities, particularly in public sector management, to implement the MAF action plan;

- Explore innovative policies and technologies to enhance service delivery and improve capacities of national and local governments to implement the MAF action plan; and

- Support legal and policy reforms to address implementation gaps

5.  Resource Mobilizations for the MAF Action Plan

UNDP will provide support in terms of creating and enabling environment for resource mobilization to cover the funding gap for the MAF implementation plan - this will be in the form of conducting donor round table and/or bilateral meetings, and preparing proposals relating to the MAF funding gap for funding consideration. This can include assisting with the formulation of proposals for the components of the MAF to be implemented by NGOs and CBOs for donor consideration.

The government of Vanuatu will take the lead in organizing and liaising directly with the donors whereas UNDP will provide technical and financial support to the Government to facilitate the process. UNDP will support a review of the aid management architecture.

Cross collaboration: As much as possible the project will collaborate with existing and new UN and UNDP projects that are providing similar services in the areas of policy advice, advocacy and capacity building of reproductive health service providers. Such projects could include the UNFPA support to the implementation of the population policy, (focusing on improving the supply chain and effective utilization of contraceptive commodities to the most vulnerable communities as well as family planning counselling services) and the joint UNICEF and UNDP project on strengthening community resilience to climate change (focusing on providing relevant training on reproductive health to the most vulnerable communities) and the UNDP Parliament Strengthening project (focusing on the provision of pro-poor policy advisory services relating to improving the quality and outreach of reproductive health services especially to the most vulnerable communities).

# Results and Resources Framework

| INTENDED OUTCOME AS STATED IN THE COUNTRY PROGRAMME RESULTS AND RESOURCES FRAMEWORK Outcome 3.1. By 2017, inclusive economic growth is enhanced, poverty is reduced, sustainable employment is improved, livelihood opportunities and food security are expanded for women, youth and vulnerable groups and social safety |
| --- |
| OUTCOME INDICATORS AS STATED IN THE VANUATU COUNTRY PROGRAMME (UNDAF COUNTRY MATRIX): Vanuatu UNDAF Outcome 3.1. Alleviation of poverty and increased inclusive growth, employment and livelihoods with a focus on women and youth nets are enhanced for all citizens. Baseline: Vanuatu is on track in only MDG 4 & 6 Target: Vanuatu is on track in at least 4 goals by 2015 |
| Applicable Key Result Area (from current Strategic Plan): Poverty Reduction and Achievement of the MDGs |
| Partnership Strategy: UNDP will implement the project in close consultation with the Department of Strategic Policy, Planning & Aid Coordination - Office of the Prime Minister. The joint presence office in Vanuatu will provide support to in country coordination and quality assurance. Relevant regional and UN Agencies will provide technical support to the project implementation. |
| Project title: Vanuatu Support to MAF Implementation |
| INTENDED OUTPUTS | OUTPUT TARGETS FOR (YEARS) | INDICATIVE ACTIVITIES | RESPONSIBLE PARTIES | INPUTS |
| Output: Improved enabling environment access to family planning and reproductive health services through effective implementation of MAF Action Plan. Related CP outcome: 3.1. Alleviation of poverty and increased inclusive growth, employment and livelihoods with a focus on women and youth. Baselines: Weak policy framework to achieve the MAF objectives of reducing adolescent pregnancies and improving access to reproductive health services Limited sex disaggregated data available for capacity building programs.(workshops) Absence of communication strategy. Indicator 1.1.: # of policies either reviewed or formulated relating to the 3 key areas of priority intervention. Target for indicator 1.1: At least 2 policies either reviewed or formulated relating to the 3 key areas of priority intervention. Indicator 1.2.: # of analytical research undertaken relating to the feasibility of establishing formal social protection programmes targeting the proportion of the population living under the basic needs poverty line i.e. conditional cash transfer programmes Targets for indicator 1.2.: At least 1 analytical research undertaken relating to the feasibility of establishing formal social protection programme targeting the proportion of the population under the basic needs poverty line At least 40% of women and youth participate in workshops at national and sub-national level. At least 40% of women and youth participation. At least 30% of the women and youths participate in advocacy programs which results in reduced rate of unwanted pregnancies and unmet need for family planning. | Targets (2013) - Formulate new and strengthen existing policies relating to improving reproductive health - Targets (2014) - Formulate new and strengthen existing policies relating to improving reproductive health - | Activity Result 1: Strengthened Policy Framework on improving Reproductive Health Action 1.1. Review existing policies and assist with the formulation of new policies or policy papers relating to the identified priority interventions of; Improving the delivery of quality family planning services; Developing and Implementing Family Life Education Programme in School Curriculum; and, Improving access to youth friendly reproductive health services providers; Action 1.2. Coordinate amongst relevant UN agencies to provide policy advise relating to the 3 key areas and identified interventions; and Action 1.3. Undertake analytical research on the feasibility and institutional requirements for the establishment of the formal social protection programmes i.e. direct cash transfer programme to ensure that the poorest of the poor receive adequate financial support to sustain their basic needs Action 1.4. Undertake analytical research on the feasibility and institutional requirements for the establishment a National Employment Centre and National Volunteer Scheme for the purpose of achieving full and productive employment and decent work for all, especially the poor and vulnerable population (under and just above the poverty line. | MAF National Project Coordinator, DSSPAC, DSSPAC, Line Ministries, MAF expert working group, MDG taskforce, UNDP MCO, relevant UN agencies and Development partners | Reproductive health Technical Advisor – 20,000 Social Protection Analyst – 20,000 Travel – 3,000 Workshops costs-4,000 Sub –total: 47,000 |
| Baseline: Lack of capacity to monitor the progress towards the MAF and the MDGs on an annual basis; No centralized data collection and dissemination systems to accurately monitor the progress of MDGs; Limited sex disaggregated data available for capacity building programs; Limited sex disaggregated data on the poor and vulnerable women and men, boys and girls Indicator 2.1.: Production of NSDS annual progress report; Target for indicator 2.1.: 1 NSDS annual report produced Indicator 2.2.: MAF mainstreamed into Government corporate plans and annual work plans; Target for indicator 2.2.: At least government departments have MDGs 3 mainstreamed into respective corporate plans. | Targets (2013) - Training Government planners and Statisticians on MDG data collection, reporting and planning conducted; -Annual Report on MDG progress, challenges and mitigation actions produced; -Review of budget preparation process and recommendations for evidence based policy formulation and budget allocations provided Targets (2014) - Capacity to monitor MDG Targets and Indicators Strengthen; -Capacity to disseminate MDG data for policy formulation and implementation strengthened; - Link between MDG data collection and budget allocation strengthened | Activity Result 2: National capacity for MDG monitoring and reporting strengthened Action 2.1. Workshop on MDG data collection and dissemination for government planners and statisticians Action 2.2. National MDG web-based database populated and launched using DevInfo software Action 2.3. Strengthen capacity of government to analyse macro-economic and poverty related data for the formulation of appropriate pro-poor policies for the achievement of the MDGs Action 2.4. Conduct analysis on hardship and poverty (based on HIES results) to determine the poor and vulnerable for evidence based pro-poor policy formulation/targeting Action 2.5. Integrate MAF into Corporate Plans, Annual Management Plans of Relevant Government Ministries and Departments and State Owned Enterprises Action 2.6. Review budget preparation process and assist relevant government departments to incorporate MAF in 2014 and 2015 national budget | MAF National Project Coordinator, DSSPAC, DSSPAC, MAF expert working group, MDG taskforce, UNDP MCO | Workshop costs – 5,000 IT Equipment – 2,000 Poverty Analysis-10,000 Budget and Planning Technical advisor – 10,000 Printing and Publication of MDG Report Card -5,000 Sub-total: 32,000 |
| Baseline: lack of awareness of the MDGs (progress and challenges) as well as MAF (objectives and implementation strategy) Indicator 3.1.: Number of press releases and stories relating to the MAF and MDGs in Vanuatu Targets for indicator 3.1: At least 4 press releases relating to MAF or MDGs published. Indicator 3.2. Number of media and government officers trained on reporting on the MAF and disseminating information relating to the MAF and MDGs in Vanuatu Targets for indicator 3.1: At least 12 media and government officers trained on reporting on MAF implementation and MDG achievement. At least 40% of those participating in capacity building programs are women and youths. At least 50% of boys and girls participating in MDG awareness are girls. | Targets (2013) - Raised awareness and ownership of the MAF and overall MDG achievement at the community and political level Targets (2014) - Capacity of local media and government information officers to report on progress and challenges of the MAF (and the MDGs overall) officers strengthened - Awareness on the pertinent issues for the post 2015 development agenda debate | Activity Result 3: General Public Awareness and national ownership of the MAF Regular press releases and awareness raising campaigns on the objectives of the MAF, implementation strategy and key achievement on an on-going basis Action 3.1. Regularly consult with members of parliament, NGOs and CBOs on MAF related policies for review and/or formulation Action 3.2. Train local media and government information officers to identify and report on stories relating to MDG achievement as well as the human face of the MDGs i.e. local examples of individuals or communities who are lagging behind in the MDGs and/or individuals or communities that are benefiting from the MAF Action 3.3. Regular MDG awareness raising campaigns i.e. essay and poster competitions, oratory contests etc targeting the general public Action 3.4. National consultations to identify the pertinent development issues for contributions into the Post 2015 development agenda | MAF National Project Coordinator,, Local Media, Ministry of Information and Communication, DSSPAC, DSSPAC, MAF expert working group, MDG taskforce, UNDP icomms | Printing and Publications- 8,000 Advocacy and Awareness Raising- 5,000 Workshop costs – 4,000 Sub-total: 17,000 |
| Baseline: MAF action plan yet to be implemented Indicator 4.1.: Proportion of project work plan activities completed Targets for indicator 4.1.: At least 70% of funded MAF activities completed. Achieve at least 80% of “support to MAF implementation” project delivery | Targets (2013) - MAF Management Structure and Project Board Formalized -MAF implementation and institutional arrangements established and operationalized - MAF initiation workshop for implementing partners and major stakeholders conducted -MAF 2013 Annual Work plan formulated - MAF board meetings held in a timely manner Targets (2014) - MAF 2014 Annual Work Plan formulated - MAF 2014 Annual Work Plan implemented | Activity Result 4: Effective Implementation, Monitoring and Evaluation of MAF action plan Action 4.1. MAF National Project Coordinator recruited Action 4.2. MAF Annual Work Plans formulated in a timely manner Action 4.3. MAF expert group meetings conducted once a month and MAF executive board meeting conducted once a quarter Action 4.4. Quarterly and annual financial and performance reports provided in a timely manner. Action 4.5. Communications Strategy formulated and implementing in a timely manner to beneficiaries and policy makers Action 4.6. Monitoring and evaluation missions to assess and impact of deliverables conducted at least every 6 months Action 4.7. Project audit effectively conducted and any audit gaps addressed in a timely manner Action 4.8. Documentation of delivery of impact, lessons learnt and best practices of the formulation of the MAF report and implementation of the MAF action plan (UNDP Pacific Centre) | MAF National project Coordinator, DSSPAC, MAF expert working group, MDG taskforce, UNDP MCO | MAF Programme Coordinator – 30,000 Project Coordinator – 80,000 M&E- 5,000 Programme Evaluation costs – 10,000 Project Audit – 5,000 Equipment and Furniture – 8,000 Communication & Knowledge Management- 6,000 Inception & Initiation – 10,000 Sub-total: 154,000 |
| Baseline: lack of financial resources to fully achieve the MAF Indicator 5.1.: Number of donor round table meetings to address the MAF funding gap; Target for indicator 5.1.: At least 2 donor round tables conducted | Targets (2013) - Identify Resource gap (Financial and Technical) for the full implementation of the MAF Action Plan; - Conduct Donor round table meetings for donor consideration to cover funding gap of the MAF Action Plan; Targets (2014) - Assist with the formulation of proposals for the components of the MAF to be implemented by NGOs and CBOs for donor consideration | Activity Result 5: Enabling Environment provided to mobilize resources to address the MAF funding gap Action 5.1. Mapping exercise to identify funding gap for the MAF action plan Action 5.2. Draft MAF funding gap proposal for donor consideration Action 5.3. Conduct donor round table as well as donor bilateral meetings to address MAF action plan funding gap Action 5.4. Review aid management architecture and formulate/review National Aid Management Policy Action 5.5. Recommend and implement an appropriate aid Information Management System based on international best practises and designed in accordance with the global principles on aid effectiveness emanating from Paris, Accra and Bussan | MAF National Project Coordinator, DSSPAC, DSSPAC, Line Ministries, Development Partner, Resident Donors, MAF expert working group, MDG taskforce, UNDP MCO | Donor round tables – 10,000 Aid Management technical Advisor – 10,000 Sub-total: 20,000 |
|  |  |  |  | Total: 270,000 |

# Annual Work Plan

Year: 2013

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output: Improved access to family planning and reproductive health services through effective implementation of MAF Action Plan. Related CP outcome: 3.1. Alleviation of poverty and increased inclusive growth, employment and livelihoods with a focus on women and youth. Baseline: MAF action plan yet to be implemented Indicator 4.1.: Proportion of funded MAF activities completed; Target for indicator 4.1.: At least 70% of funded MAF activities implemented | Activity Result 4: MAF Management Structure operational Action 4.1. MAF Project Coordinator recruited Action 4.2. MAF expert meeting group meetings conducted once a month Action 4.3. MAF Executive board meeting conducted at least once a quarter Action 4.4. Quarterly and annual financial and performance reports provided in a timely manner Action 4.5. Communications Strategy formulated and implemented in a timely manner Action 4.6. Monitoring and evaluation Missions conducted every 6 months |  |  |  | X X X X X X | MAF National Project Coordinator, DSSPAC, MAF expert working group, MDG taskforce, UNDP MCO | UNDP TRAC | MAF Project Coordinator - 71200 Equipment and Furniture-72200 Inception & Initiation-75700 & 71600 | 10,000 3,000 7,000 Sub-total:20,000 |
| TOTAL |  |  |  |  |  |  |  |  | 20,000 |

Year: 2014

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Output: Improved access to family planning and reproductive health services through effective implementation of MAF Action Plan. Indicator 1.1.: # of policies either reviewed or formulated relating to the 3 key areas of priority intervention. Target for indicator 1.1: At least 2 policies either reviewed or formulated relating to the 3 key areas of priority intervention. Indicator 1.2.: # of analytical research undertaken relating to the feasibility of establishing formal social protection programmes targeting the proportion of the population living under the basic needs poverty line i.e. conditional cash transfer programmes Targets for indicator 1.2.: At least 1 analytical research undertaken relating to the feasibility of establishing formal social protection programme targeting the proportion of the population under the basic needs poverty line At least 40% of women and youth participate in workshops at national and sub-national level. At least 40% of women and youth participation. At least 30% of the women and youths participate in advocacy programs which results in reduced rate of unwanted pregnancies and unmet need for family planning. | Activity result 1: Strengthened Policy Framework on improving Reproductive health Action 1.1. Review existing policies and assist with the formulation of new policies relating to the identified priority interventions of improving the delivery of quality family planning services. Action 1.2. Undertake analytical research on the feasibility and institutional requirements for the establishment of the formal social protection programmes i.e. direct cash transfer programme to ensure that the poorest of the poor receive adequate financial support to sustain their basic needs. Action 1.3. Undertake analytical research on the feasibility and institutional requirements for the establishment a National Employment Centre and National Volunteer Scheme for the purpose of achieving full and productive employment and decent work for all, especially the poor and vulnerable population (under and just above the poverty line | X X X | X X X | X X X | X X X | MAF National Project Coordinator DSSPAC, DSSPAC, Line Ministries, MAF expert working group, MDG taskforce, UNDP MCO, relevant UN agencies and Development partners | UNDP TRAC | Reproductive health Technical Advisor-71200 Social Protection Analyst-71200 Workshop costs-75700 Trave-71600 Poverty Analyst-71200 | 20,000 20,000 4,000 3,000 10,000 2,000 Sub-total:59,000 |
| Baseline: Lack of capacity to monitor the progress towards the MAF and the MDGs on an annual basis; Indicator 2.1.: Production of NSDS annual progress report; Target for indicator 2.1.: 1 NSDS annual report produced Indicator 2.2.: MAF mainstreamed into Government corporate plans and annual work plans; Target for indicator 2.2.: At least government departments have MDGs 3 mainstreamed into respective corporate plans. | Activity result 2: National capacity for MDG monitoring and reporting strengthened Action 2.1. Workshop on MDG data collection and dissemination for Government planners and statisticians Action 2.2. Review budget preparation process and assist relevant government departments to incorporate MAF in 2015 national budget Action 2.3. Strengthen capacity of Government to analyse macro-economic and poverty related data for the formulation of appropriate pro-poor policies for the achievement of the MDGs planners and statisticians Action 2.4. Conduct analysis on hardship and poverty (based on HIES results) to determine the poor ad vulnerable for evidence based pro-poor policy formulation/targeting |  |  | X X X X | X X X X | MAF National Project Coordinator, DSSPAC, DSSPAC, MAF expert working group, MDG taskforce, UNDP MCO | UNDP TRAC | Workshop costs-75700 IT Equipment-72800 Budget and planning advisor-71200 Printing and publication of MDG report card-74200 | 3,000 2,000 10,000 5,000 Sub-total:20,000 |
| Baseline: Lack of awareness of the MDGs as well as MDG Acceleration Framework Indicator 3.1.: Number of press releases and stories relating to the MAF and MDGs in Vanuatu Targets for indicator 3.1: At least 4 press releases relating to MAF or MDGs published. Indicator 3.2. Number of media and government officers trained on reporting on the MAF and disseminating information relating to the MAF and MDGs in Vanuatu Targets for indicator 3.1: At least 12 media and government officers trained on reporting on MAF implementation and MDG achievement. At least 40% of those participating in capacity building programs are women and youths. At least 50% of boys and girls participating in MDG awareness are girls. | Activity result 3: General public awareness and national ownership of the MAF Action 3.1. Regular press releases and awareness raising campaigns promoting awareness and local ownership of the MAF Action 3.2. Regularly consult with member of parliament, NGOs, and CBOs on MAF activities and policies for review/formulation Action 3.3. Media and Government communication officers trained on reporting on MAF implementation and overall MDG progress and challenges Action 3.4. Train local media and government information officers to identify and report on stories relating to MDG achievement as well as the human face of the MDGs i.e. local examples of individuals or communities who are lagging behind in the MDGs and/or individuals or communities that are benefiting from the MAF Action 3.5. Regular MDG awareness raising campaigns i.e. essay and poster competitions, oratory contests etc targeting the general public | X X X | X X X | X X X X X | X X X X X | MAF National Project Coordinator Local Media, Ministry of Information and Communication, DSSPAC, DSSPAC, MAF expert working group, MDG taskforce, UNDP incomes | UNDP TRAC | Printing and Publications-74200 MAF Advocacy and Awareness Raising campaign-74215 Workshop costs-75700 | 5,000 3,000 2,000 Sub-total:10,000 |
| Baseline: MAF action plan yet to be implemented Indicator 4.1.: Proportion of project work plan activities completed Targets for indicator 4.1.: At least 70% of funded MAF activities completed. Achieve at least 80% of “support to MAF implementation” project delivery | Activity Result 4: MAF Management Structure operational Action 4.1. MAF expert meeting group meetings conducted once a month Action 4.2. MAF Executive board meeting conducted at least once a quarter Quarterly and annual financial and performance reports provided in a timely manner Action 4.3. Communications Strategy formulated and implemented in a timely manner Action 4.4. Monitoring and evaluation Missions conducted every 6 months | X X X X | X X X X X | X X X X | X X X X X | MAF National Project Coordinator, DSSPAC, MAF expert working group, MDG taskforce, UNDP MCO | UNDP TRAC | Programme coordinator-71300 Project Coordinator-71300 Equipment and furniture-72200 UNDP M&E-71600 Inception & Initiation-71600 | 20,000 40,000 5,000 5,000 3,000 Sub-total:73,000 |
| Baseline: lack of financial resources to fully achieve the MAF Indicator 5.1.: Number of donor round table meetings to address the MAF funding gap; Target for indicator 5.1.: At least 2 donor round tables conducted | Activity result 5: Enabling environment provided to mobilize resources to address the MAF funding gap Action 5.1. Mapping exercise to identify funding gap for the MAF action plan Action 5.2. Draft MAF funding gap proposal for donor consideration Action 5.3. Conduct donor round table meeting as well as bilateral meetings to mobilize resources for the MAF funding gap | X X | X X X | X | X | MAF National Project Coordinator,, DSPPAC, DSSPAC, Line Ministries, Development Partner, Resident Donors, MAF expert working group, MDG taskforce, UNDP MCO | UNDP TRAC | MAF Donor round tables-75700 | 5,000 Sub-total:5,000 |
| TOTAL |  |  |  |  |  |  |  |  | 167,000 |

Year: 2015

| EXPECTED OUTPUTS And baseline, indicators including annual targets | PLANNED ACTIVITIES List activity results and associated actions | TIMEFRAME | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount |
| Baseline: Lack of awareness of the MDGs as well as MDG Acceleration Framework Indicator 3.1.: Number of press releases and stories relating to the MAF and MDGs in Vanuatu Targets for indicator 3.1: At least 4 press releases relating to MAF or MDGs published. Indicator 3.2. Number of media and government officers trained on reporting on the MAF and disseminating information relating to the MAF and MDGs in Vanuatu Targets for indicator 3.1: At least 12 media and government officers trained on reporting on MAF implementation and MDG achievement. At least 40% of those participating in capacity building programs are women and youths. At least 50% of boys and girls participating in MDG awareness are girls. | Activity result 3: General public awareness and national ownership of the MAF Action 3.1. Regular press releases and awareness raising campaigns promoting awareness and local ownership of the MAF Action 3.2. Regularly consult with members of parliament, NGOs, and CBOs on MAF activities and policies for review/formulation Action 3.3. Regular MDG awareness raising campaigns i.e. essay and poster competitions, oratory contests etc targeting the general public | X X X | X X X | X X X | X X X | MAF National Project Coordinator, Local Media, Ministry of Information and Communication, DSSPAC, DSSPAC, MAF expert working group, MDG taskforce, UNDP i-comms team. | UNDP TRAC | Printing and Publications-74210 MAF Advocacy and Awareness Raising campaign-74200 Workshop costs-75700 | 3,000 2,000 2,000 Sub-total:7,000 |
| Baseline: MAF action plan yet to be implemented Indicator 3.2.: Proportion of funded MAF activities completed; Targets for indicator 3.2.: At least 70% of funded MAF activities completed. Achieve at least 80% of “support to MAF implementation” project delivery | Activity result 4: MAF Management Structure operational and effective Action 4.1. MAF Project Coordinator recruited Action 4.2. MAF expert meeting group meetings conducted once a month Action 4.3. MAF Executive board meeting conducted at least once a quarter Action 4.4. Quarterly and annual financial and performance reports provided in a timely manner Action 4.5. Communications Strategy formulated and implemented in a timely manner Action 4.6. Monitoring and evaluation Missions conducted every 6 months Action 4.7. Documentation of MAF formulation and implementation process | X X X X X | X X X X X X | X X X X X X | X X X X X X X | MAF National Project Coordinator, DSSPAC, MAF expert working group, MDG taskforce, UNDP MCO | UNDP TRAC | Programme coordinator-71300 Project Coordinator-71200 Programme Evaluation-71400 Project Audit-71400 Communications & Knowledge management-71600 & 74200 | 10,000 30,000 10,000 5,000 6,000 Sub-total:61,000 |
| Baseline: lack of financial resources to fully achieve the MAF Indicator 5.1.: Number of donor round table meetings to address the MAF funding gap; Target for indicator 5.1.: At least 2 donor round tables conducted | Activity result 5: Enabling environment provided to mobilize resources to address the MAF funding gap Action 5.1. Dialogue with donors and development partners to address the resource gaps identified in the MAF action plan. Action 5.2. Review aid management architecture and formulate/review national Aid Management policy | X | X X | X X | X X | MAF National Project Coordinator,, DSPPAC, DSSPAC, Line Ministries, Development Partner, Resident Donors, MAF expert working group, MDG taskforce, UNDP MCO | UNDP TRAC | Aid Management TA-71200 Donor Roundtables-75700 | 10,000 5,000 Sub-total:15,000 |
| TOTAL |  |  |  |  |  |  |  |  | 83,000 |

# Management Arrangements

A MAF Programme Coordinator will be based in the UNDP MCO to coordinate and provide oversight management of the various MAF projects in the Pacific Island countries that are implementing MAF projects.  This project will be managed by UNDP using the Directly Implementation Modality (DIM), under the guidance of a Project Board. The Project Board will be co-chaired by the chair of the MDG Taskforce and UNDP Resident Representative. Under the DIM modality, the UNDP Resident Representative is responsible to the UNDP Administrator for reporting on progress towards achievement of results including the documenting of prudent and proper use of resources.  Use of the DIM modality will reduce the administrative burden to the Government of Vanuatu to coordinate and report on the various project components.

The project will benefit both operationally and substantively from the UN Joint Presence Initiative in Vanuatu led by UNICEF and the UNDP Programme Analyst based in the UN Joint Presence Office.

## Project Management

While each responsible party will be accountable to UNDP for the delivery of the components, a project coordinator will be recruited to provide support with the coordination of an annual project work plan and quarterly update; six monthly progress reports to the project board (Annex 2). The MAF national project coordinator will work in close collaboration with the responsible parties on a day-to-day basis and be responsible for the management of the project teams on behalf of the Project Board. The project coordinator’s prime responsibility is to ensure the efficient delivery of project results and to ensure that the results are of satisfactory quality and delivered within budget and on time. The MAF national project coordinator reports to the Project Board through the UNDP Resident Representative.

Project outcome will be monitored against a set of quantitative and qualitative indicators as described in the results and resources framework and the monitoring and evaluation framework. The project coordinator will coordinate inputs and prepare financial management reports for each component.

## Project Board – Refer Annex 2 for TOR

All responsible parties will be responsible to a project board which will function under the joint chairmanship of the Government of Vanuatu (DSSPAC and Office of the Prime Minister) and UNDP and include the national MDG taskforce and representatives from the Ministry of Health, Ministry of Education and the national implementing partner (DSSPAC):

The project board consists of three different types of members with roles defined as follows:

- The executive which represents the project ownership and co-chair responsibility (Government of Vanuatu and UNDP)

- The senior supplier is the MAF Expert Group and National MDG Taskforce with responsibility for providing guidance and oversight on project delivery.

- The senior beneficiary role represented by the responsible parties, Office of the Prime Minister and DSSPAC.

The project board’s responsibilities are defined as follows:

- To ensure that adequate mechanisms are in place to guarantee the transparency and accountability as well as the efficiency of project operations,

- Build consensus around the project strategies and planned results, including the links between its outputs and the intended outcomes,

- Provide advice when substantive changes are needed in the project’s planned activities, strategies or implementation arrangements,

- Oversee progress, consult with beneficiaries, and ensure that potential opportunities and risks, including lessons learned from experience, are taken into account by the project management unit,

- Assess project performance and endorse project annual work-plan for approval by UNDP and the respective implementing partners, and

- To provide guidance to the implementing partners through the project management unit.

The Project Board will meet every six months or as and when required by the chairpersons. The first meeting will be held within the first six months following the recruitment of the project coordinator. The chairpersons may call for special meetings should the need arise for these. UNDP in consultation with the responsible parties and the Project Coordinator will prepare the Agenda and circulate this at least two weeks in advance of the Project Board meeting. UNDP will also circulate the Minutes of the Meeting within two weeks after a meeting is held.

## MAF Expert Group

In addition to the project board, the MAF Expert Group shall act as an advisory mechanism to the Vanuatu MAF Project to ensure adequate consideration is taken to address all aspects of the project implementation in Vanuatu. The advisory committee will meet at least every three months and provide advice and guidance on technical issues relevant to project implementation to the responsible parties and the project coordinator.

## Programme Support by UNDP

UNDP will provide strategic guidance and programme management support to the Project coordinator & the DSSPAC to ensure procurement, financial and human resource management and reporting for the Project is in accordance with UNDP rules and procedures.  A key role for UNDP will be to ensure that development partners and stakeholders are kept fully informed of project’s progress.

Exit Strategy

A local counterpart will be appointed within DSSPAC, Office of the Prime Minister to understudy the project coordinator. The project coordinator will be required to transfer project coordination skills including knowledge gained from the various short term technical consultancies outlined in the results and resources framework and annual work plans of the project throughout the course of the implementation period. The skills will be transferred through both on-the-job as well as face-to-face training. The counterpart will assume the coordination role of the implementation of the MAF action plan 3 months prior to the project completion date.

Such roles will include coordinating meetings with MAF implementing partners – government ministries and development partners, meetings with donors to address the resource gap identified in the MAF action plan. Report (through the relevant government machinery) on the progress, challenges and opportunities for the way forward on the implementation of the MAF Action Plan.

This is consistent with the primary objective of the “Support to MAF Implementation” project which is to strengthen existing institutional capacity of Government coordinating agencies such Department of Strategic Policy, planning and Aid Coordination as well as Government implementing agencies to effectively implement the MAF action plan.

# Monitoring Framework And Evaluation

## Within the Annual Cycle

On a quarterly basis, a results assessment exercise shall record progress towards the completion of key results. An Issue Log shall be activated in Atlas and updated by the MAF national Project coordinator to facilitate tracking and resolution of potential problems or requests for change.

Based on the initial risk analysis submitted (Annex 1), a risk log shall be activated in Atlas and regularly updated after reviewing the external environmental risks that may affect project implementation. The MAF national project coordinator shall be responsible for updating the relevant section of the results/progress, issues and risk logs in ATLAS. Based on the above information recorded in Atlas, a Quarterly Progress Reports (QPR) shall be submitted by the project management unit to the project board using the standard reporting format available in the Executive Snapshot by the project coordinator.

A project Lesson-learned log shall be activated and regularly updated to ensure on-going learning and adaptation within the implementing partner, and to facilitate the preparation of the Lessons-learned Report at the end of the project. A Monitoring Schedule (Annex 4) Plan shall be activated in Atlas and updated to track key monitoring and management actions/events.

## Annual Report and Review

Annual Review Report: an Annual Review Report shall be prepared by the project coordinator and shared with the Project Board and the steering committee. As minimum requirement, the Annual Review Report shall consist of the Atlas standard format for the QPR covering the whole year with updated information for each of the above element of the QPR as well as a summary of results achieved against pre-defined annual targets at the output level.

Annual Project Review: based on the above report, an annual project review shall be conducted during the fourth quarter of the year or soon after, to assess the performance of the project and appraise the Annual Work Plan (AWP) for the following year. In the last year, this review will be a final assessment. This review is driven by the Project Board and may involve other stakeholders as required. It shall focus on the extent to which progress is being made towards the delivery of activities and its contribution to the achievement of the project out.

## Monitoring Visits

The project will include in-country monitoring visits by UNDP to be facilitated by the project coordinator in consultation with the responsible partners.

| Output: Improved enabling environment access to family planning and reproductive health services through effective implementation of MAF Action Plan. |
| --- |
| ACTIVITY 1: MAF Policy Advisory Services and South-south cooperation |
| Activity Result 1 | Strengthened Policy Framework on reducing the unwanted pregnancies | Start Date: 2014 End Date: 2015 |
| Purpose | Strengthen Policy Framework on the 3 key areas of intervention to improve maternal and reproductive health through reducing unwanted pregnancies and increasing the use of contraceptives: (1) Delivery of quality family planning services, (2) Family Life Education (FLE) Programme, (3) Youth Friendly Services (YFS). |
| Description | Action: Review existing policies and assist with the formulation of new policies relating to the identified key areas of intervention: (1) Delivery of quality family planning services, (2) Family Life Education (FLE) Programme, (3) Youth Friendly Services (YFS). Action: Coordinate amongst relevant UN agencies to provide policy advise or policy papers relating to the 3 key areas and identified interventions; and Action: Undertake analytical research on the feasibility and institutional requirements for the establishment of the formal social protection programmes i.e. direct cash transfer programme to ensure that the poorest of the poor receive adequate financial support to sustain their basic needs Action: Undertake analytical research on the feasibility and institutional requirements for the establishment a National Employment Centre and National Volunteer Scheme for the purpose of achieving full and productive employment and decent work for all, especially the poor and vulnerable population (under and just above the poverty line. Action: Undertake analytical research on the feasibility and institutional requirements for the establishment a National Employment Centre and National Volunteer Scheme for the purpose of achieving full and productive employment and decent work for all, especially the poor and vulnerable population (under and just above the poverty line. |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of policies either formulated or reviewed relating to the key priority areas and related priority interventions | MAF expert working group including UN technical agencies to provide quality assurance before it is submitted to cabinet for endorsement | 2014-2015 |
| Analytical research on the feasibility of establishing a cash transfer scheme for the poorest of the poor | MAF expert working group including UN technical agencies to provide quality assurance before it is submitted to cabinet for endorsement | 2014-2015 |
| Analytical research on the feasibility of establishing a National Employment Centre and National Volunteer Scheme | MAF expert working group including UN technical agencies to provide quality assurance before it is submitted to cabinet for endorsement | 2014-2015 |

| ACTIVITY 2: National Planning and Monitoring MDG Acceleration |
| --- |
| Activity Result 2 | MAF mainstreamed into National Planning Framework and National capacity for MAF planning and monitoring strengthened | Start Date: 2014 End Date: 2015 |
| Purpose | Strengthen national capacity for MDG and MAF planning and monitoring |
| Description | Action: Workshop on MDG data collection and dissemination for government planners and statisticians Action: National MDG web-based database populated and launched using DevInfo software Action: Strengthen capacity of government to analyse macro-economic and poverty related data for the formulation of appropriate pro-poor policies for the achievement of the MDGs Action: Conduct analysis on hardship and poverty (based on HIES results) to determine the poor and vulnerable for evidence based pro-poor policy formulation/targeting Action: Integrate MAF into Corporate Plans, Annual Management Plans of Relevant Government Ministries and Departments and State Owned Enterprises Action: Review budget preparation process and assist relevant government departments to incorporate MAF in 2014 and 2015 national budget |
| Quality Criteria | Quality Method | Date of Assessment |
| MDG data collection and analysis workshop conducted | MDG data collection workshop report to be review by MAF expert working group including relevant UN agencies | 2014-2015 |
| Formulation of centralized MDG data collection system | Centralized data collection system established to be review by MAF expert working group including relevant UN agencies | 2014-2015 |
| MDGs reported in Annual NSDS progress report | Annual NSDS progress report produced to be review by MAF expert working group including relevant UN agencies | 2014-2015 |
| MAF mainstreamed into relevant sector development plans and Government corporate plans | Sector Development Plans and Government Corporate Plans to be review by MAF expert working group including relevant UN agencies | 2014-2015 |

| ACTIVITY 3: Resource Mobilization for the MAF Implementation Plan |
| --- |
| Activity Result 3 | Enabling environment to address MAF funding gap | Start Date: 2014 End Date: 2015 |
| Purpose | Strengthen Aid Management Architecture to mobile resources to address the MAF funding gap and other MDG targets that are lagging behind |
| Description | 1. Activity Result: Enabling Environment provided to mobilize resources to address the MAF funding gap Action: Mapping exercise to identify funding gap for the MAF action plan Action: Draft MAF funding gap proposal for donor consideration Action: Conduct donor round table as well as donor bilateral meetings to address MAF action plan funding gap 2. Activity Result: Aid Management Architecture strengthened Action: Review aid management architecture and formulate/review National Aid Management Policy Action: Recommend and implement an appropriate aid Information Management System based on international best practises and designed in accordance with the global principles on aid effectiveness emanating from Paris, Accra and Bussan |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of donor round table meetings conducted (to address MAF funding gap) | Donor roundtable workshop reports reviewed by MAF expert working group | 2014-2015 |
| ODA Management policy formulated/reviewed | Aid Management policy reviewed by MAF expert working group and relevant UN agencies; Amount of donor funding mobilized to implementing the MAF funding gap | 2014-2015 |

| ACTIVITY 4: MAF Project Management |
| --- |
| Activity Result 4 | MAF Project Management | Start Date: 2013 End Date: 2015 |
| Purpose | Coordinate the implementation and Monitoring & Evaluation of the MAF Implementation Plan |
| Description | Activity Result: Effective Implementation, Monitoring and Evaluation of MAF action plan Action: MAF national project coordinator recruited Action: MAF Annual Work Plans formulated in a timely manner Action: MAF expert group meetings conducted once a month and MAF executive board meeting conducted once a quarter Action: Quarterly and annual financial and performance reports provided in a timely manner. Action: Communications Strategy formulated and implementing in a timely manner to beneficiaries and policy makers Action: Monitoring and evaluation missions to assess and impact of deliverables conducted at least every 6 months Action: Project audit effectively conducted and any audit gaps addressed in a timely manner Action: Documentation of delivery of impact, lessons learnt and best practices of the formulation of the MAF report and implementation of the MAF action plan (UNDP Pacific Centre) |
| Quality Criteria | Quality Method | Date of Assessment |
| Proportion of funded MAF action plan that is implemented effectively | Progress reports, financial delivery reports, mission reports, audit reports and evaluation reports. | Quarterly, annually and at the end of the project. |

| ACTIVITY 5: MAF Advocacy and Awareness Raising |
| --- |
| Activity Result 5 | MAF Advocacy and Awareness Raising | Start Date: 2013 End Date: 2015 |
| Purpose | Raise Awareness and strengthen national ownership of the MAF and MDGs |
| Description | Action: Regular press releases and awareness raising campaigns on the objectives of the MAF, implementation strategy and key achievement on an on-going basis Action: Regularly consult with members of parliament, NGOs and CBOs on MAF related policies for review and/or formulation Action: Train local media and government information officers to identify and report on stories relating to MDG achievement as well as the human face of the MDGs i.e. local examples of individuals or communities who are lagging behind in the MDGs and/or individuals or communities that are benefiting from the MAF Action: Regular MDG awareness raising campaigns i.e. essay and poster competitions, oratory contests etc targeting the general public |
| Quality Criteria | Quality Method | Date of Assessment |
| Number of press releases, stories and awareness raising campaigns on the MAF undertaken | Number of press releases, stories and awareness raising campaigns that is approved and verified by the MAF expert working group and National MDG Taskforce | 2014-2015 |
| Number of media and Government information officers trained on reporting and disseminating information relating to the MAF and MDGs | Media Training Workshop reports reviewed by MAF expert working group | 2014-2015 |
| Number of sectors consulted on the pertinent issues for consideration in the post 2015 development agenda dialogue | National consultation workshop outcome report on the priority development issues for the post 2015 development agenda dialogue. | 2014-2015 |

# Legal Context

This project support document shall be the instrument referred to as project support document in Article 1 of the Standard Basic Assistance Agreement (SBAA) between the Governments of Vanuatu and the United Nations Development Programme, signed by the parties on 27 March 1983, 4 April 1986 and 7 April 1981 respectively. The host country’s implementing Agency shall, for the purposes the Standard Basic Agreement, refer to the Government co-operating Agency described in that agreement.

The following types of revisions may be made to this project document with the signature of the UNDP Resident Representative only, provided that he is assured that The Government has no objections to the proposed changes:

(a)	Revisions in, or in addition to, any of the annexes of the project document;

(b)	Revisions which do not involve significant changes in the immediate objectives, outputs or activities of a project but are caused by re-arrangement of inputs already agreed to or by cost increases due to inflation.

Consistent with the Article III of the Standard Basic Assistance Agreement, the responsibility for the safety and security of the implementing partner and its personnel and property, and of UNDP’s property in the implementing partner’s custody, rests with the implementing partner.

The implementing partner shall:

- put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the project is being carried;

- Assume all risks and liabilities related to the implementing partner’s security, and the full implementation of the security plan.

UNDP reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this agreement.

The implementing partner agrees to undertake all reasonable efforts to ensure that none of the UNDP funds received pursuant to the Project Document are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNDP hereunder do not appear on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via http://www.un.org/Docs/sc/committees/1267/1267ListEng.htm. This provision must be included in all sub-contracts or sub-agreements entered into under this Project Document”.

# ANNEXES

Annex 1: Risk Log

Annex 2: Project Board – Terms of Reference

Annex 3: Project Coordinator – Terms of Reference

Annex 4: Monitoring Plan

| ANNEX1: Risk Log |
| --- |
| 1. | Type of risk: Financial | Project Formulation Stage: 21/03/2013 | Funds not disbursed to project on time | Impact: Implementation of project activities will be delayed Probability: Medium Counter Measures: Regular training on financial reporting, drafting work plans and budgets and audit requirements. | Status: Date: | UNDP, National Executing Agency, National Implementing Partner, DSSPAC, Treasury, UNDP MCO |
| 2. | Type of risk: Operational and Technical | Project Document Stage: 21/03/2013 | - Suitable short-term technical consultants not available to execute technical activities of the project. | Impact: Project will have to be delayed to accommodate suitable consultant OR quality of project delivered is compromised. Probability: Would be determined during tendering process, but project execution may take longer than proposed if approval process takes longer than anticipated. Counter Measures: Ensure ToRs are advertised extensively to minimize the probability of the risk. Ensure adequate budget to cover this activity in order to attract qualified and competent consultants. |  | Office of Budget and Planning & UNDP |
| 3. | Political | Project Document Stage: 21/03/2013 | Government does not endorse policies that are either reviewed or newly formulated relating to the key areas of intervention. | Impact: Delay in achieving the MDG target that was selected for acceleration. Probability: Low based on commitment of country to the achievement of the MDGs as part of the Millennium Declaration. Counter Measures: Continuously involve | Public outreach and advocacy on the MDGs built into the implementation strategy to raise awareness and seek input/ownership at all levels. Regular briefings to the MDG taskforce on progress of policy review/formulation. | Project Coordinator, National Implementing Agency, MDG Task Force, Parliament, & UNDP |

ANNEX 2: Terms of Reference-Project Board

The project board consists of three different types of members with roles defined as follows:

- The executive which represents the project ownership and co-chair responsibility (Government of Vanuatu and UNDP)

- The senior supplier role is the MAF Expert Group and the National MDG Taskforce with responsibility for providing guidance and oversight on project delivery.

- The senior beneficiary role represented by the Parliament.

The project board’s responsibilities are defined as follows:

- To ensure that adequate mechanisms are in place to guarantee the transparency and accountability as well as the efficiency of project operations,

- Build consensus around the project strategies and planned results, including the links between its activities and the intended results,

- Provide advice when substantive changes are needed in the project’s planned project’s planned activities, strategies or implementation arrangements,

- Oversee progress, consult with beneficiaries, and ensure that potential opportunities and risks, including lessons learned from experience, are taken into account by the project coordinator,

- Assess project performance and endorse project annual work-plan for approval by UNDP and the respective implementing partners, and

- To provide guidance to the implementing partners through the project coordinator.

The Project Board will meet annually or as and when required by the chairpersons. The first meeting will be held within the first six following the recruitment of the MAF National Project Coordinator. The chairpersons may call for special meetings should the need arise for these. UNDP in consultation with the responsible parties and the project coordinator will prepare the Agenda and circulate this at least two weeks in advance of the Project Board meeting. UNDP will also circulate the Minutes of the Meeting within two weeks after a meeting is held.

ANNEXE 3: Terms of Reference: Vanuatu MAF National Project Coordinator

1.  Post Title:	Vanuatu MAF National Project Coordinator

2.  Project Title:		MDG Acceleration Framework

3.  Duration:			2 Years

4.   Location, Country: 	Port Vila, Vanuatu

5.  Expected starting date:	June 2013

- Brief Project Description:

The project seeks to assist the Government of Vanuatu to implement the MDG Acceleration Framework by providing support in the following areas relating to the identified key priority areas and related selected interventions in the Vanuatu MAF:

- Programme Management and M&E

- MDG Planning and Monitoring

- Policy Advisory Services

- Resource Mobilization for the Implementation of the MAF

- MAF Advocacy and Awareness Raising

7. Host Agency/Host Institute: DSSPAC,

- Description of Duties:

Project management

- Consult with government implementing agencies and development partners to map out what activities have already been implemented in the MAF action plan, what activities are currently being undertaken and what is the resource gap to be mobilized by development partners and donors.

- Based on the mapping exercise prioritize activities in the MAF action plan to be undertaken within the new 12 months of project implementation.

- With guidance from the MAF expert group, develop and outcome and output results based M&E framework to measure the progress of the objective of the MAF action plan (to reduce the prevalence of adolescent unplanned pregnancies by XXX% by the year XXX).

- Coordinate and plan for the delivery of project inputs; including international experts, national experts, training and equipment, and sub-contracts. Prepare annual/quarterly work plans based on inputs from stakeholders.

- Assist with the National Execution of the project based on UNDP procedures, rules and regulations.

- Manage all project staff including identifying training needs and providing such training or where necessary helping to identify courses or providers of training.

- Draft TORs for project activities and assist with recruitment of all project staff through close liaison Government and UNDP Suva.

- Monitor and assist the delivery of inputs to achieve activitiess according to UNDP procedures and produce quarterly costed work plans.

- Work closely with the MAF technical working group and National MDG taskforce, Government counterparts, other technical assistance projects and UNDP Suva on technical aspects of the project.

- Produce project progress reports and plan and implement technical reviews, and tripartite review meetings of project. Ensure that project reports, including the final report, include documentation on best practices and lessons learnt.

- Assist the implementing partner with the management and accounting for all project finances, including quarterly financial reporting and maintain project budget in liaison with the UNDP Fiji Country Office.

- Provide substantive technical guidance and support on data collection, planning and budgeting systems and undertake all activities identified in the project work-plan for which external support has not been identified through national/international consultants.

- Assist in documenting outstanding project experiences for dissemination to all stakeholders, including national policymakers, planners and donors.

- Coordinate work plans and work with other technical assistance projects to maximize the impact of the assistance.

Technical duties

- Act as secretariat and resource person to the national MDG Task Force and MAF expert working group;

- Coordinate amongst relevant implementing agencies to report on progress on MAF implementation;

- Regularly collect, analyze, monitor and report on disaggregated data that will reveal trends towards progress (or lack thereof) on the MDGs and the MAF in particular.

- Take stock of existing analytical work or assessments related to the MDGs and MAF implementation plan;

- Draft progress reports on the current state of MAF implementation and identify institutional and technical capacity development needs,

- Facilitate closer linkages between the MAF implementation and national budget allocation;

    - Train relevant government statisticians to:

  - Regularly collect, analyze, monitor and report on disaggregated data that will reveal trends towards progress (or lack thereof) on the MDGs and the MAF in particular.

  - Make better use of available data as a basis for evidence-based policy making

  - Work with relevant state & national departments, especially Health & Social Services, Education and Emergency and Environmental Management to implement respective components of the MAF,

  - Provide support for the formulation of pro-poor policies that will help to ensure the most vulnerable and most needy are adequately targeted by government programmes, interventions and resources,

9.  Results /Expected Output

- Successful implementation of the MAF implementation plan;

- Regular reporting on the progress of MAF implementation;

- Building Capacity for data collection and analysis to report on the progress  and bottlenecks relating to MDG and MAF achievement at the state and national level;

- Mainstream MDG and MAF into national planning and budgeting framework

10.  Qualifications/Requirements:

- A university degree in statistics and/or sociology and/or economics;

- 5 years of relevant work experience;

- Relevant hands-on experience in development planning at sector and/or provincial and/or national level;

- Experience in compiling and analyzing social statistics from line ministries  and from Census, HIES and Demographic surveys is preferable but not mandatory;

- Ability to work in a small island context;

- Ability and maturity to relate to and work confidentially with officials at the highest levels in government, private sector and NGOs and advocate for change; and

- Cultural and gender sensitivity and ability to actively promote gender equity in all aspects of professional work.

- Sound knowledge of the MDG Framework and relevant work experience in terms of coordinating MDG reporting and mainstreaming MDGs in National Planning and Budget frameworks

## Annex 4:  Monitoring Plan

| Monitoring Action | Due Date | Milestone description | Comments | Responsibility |
| --- | --- | --- | --- | --- |
| Quarterly financial reporting (FACE) Reports | End of each quarter (Mar/Jun/Sept/Dec) | Accurately complied FACE form reflecting national expenditure for the quarter submitted to UNDP | To be received by UNDP within 15 days of end of each qtr; Expenditure to be reconciled with and endorsed by MOF | National Project Coordinator /Country Development Manager |
| Quarterly progress reports | End of each quarter (Mar/Jun/Sept/Dec) | Progress to be reported in the template provided by UNDP | Measurement of progress/ indicators Explanations for slippage and variance against budget Risk Log Issue log | National Project Coordinator,/Country Development Manager |
| Review of Progress | Mid Jan/Apr/Jul/Oct | Progress to be reviewed by the Project board including monitoring of the Capacity Development Plan | Risks/issues/ progress reviewed and analysed Action recommended | Project Board UNDP |
| Bi-annual reports to UNDP | December 31 each year | Report in prescribed format by UNDP | Report to be compiled by the UNDP MCO and submitted through Project Board for review and approval | National Project Coordinator |
| Annual Reports | Q4 each year | Annual report in the format prescribed in the Prodoc/Mgt Arrangements | Annual report based on QPRs to be compiled for review by an Annual Review Mtg | National Project Coordinator |
| Capacity Development | End of each quarter (Mar/Jun/Sept/Dec) | Update of CD Plan | Review CD Plan and sustainability | UNDP Country Focal point, in conjunction with all PMs in country |
| Annual audits | Mar/Apr each year | Annual DIM audit for Prior financial year | Audit of expenditure and project implementation | UNDP MCO in coordination with DSSPAC |
| Project evaluation | End of Project | Project evaluation | Independent Evaluator | Evaluator with support from UNDP MCO in coordination with DSSPAC |
| UNDP Monitoring Missions | 2 per year | Project monitoring, audit spot check Project Mgt training | Timing variable dependent on project/UNDP Requirements | UNDP Country Focal Point/UNDP MCO |

# Footnotes

For further information about the 2006 poverty estimates see VNSO, 2008, Report on the Estimation of Basic Needs Poverty Lines, and the Incidence and Characteristics of Poverty, Port Vila, Vanuatu.

The HIES of 1998 used by some regional and international agencies is not reliable because its sample design is not nationally representative and is biased for the urban areas.

2011 Pacific MDG tracking report

# Text boxes

Total resources required

Total allocated resources:	270,000

- Regular			270,000

Unfunded budget:		Nil

TRAC (2013)			20,000

In-kind Contributions		Nil

Programme Period:		                2013-2017

Key Result Area (Strategic Plan)	Poverty Reduction and the achievement of MDGs

Atlas Award ID:			00075001

Start date:		     	October  2013

End Date			               December 2015

PAC Meeting Date		               October 2013

Management Arrangements	DIM

Brief Description

The government of Vanuatu with assistance from UNDP has chosen to address the MDG target 5.B: on improving reproductive health with emphasis on reducing the adolescent birth rate (Indicator 5.4), especially in rural areas, and reducing the unmet need for family planning (Indicator 5.6).

UNDP will assist the Government of Vanuatu to implement the MDG Acceleration Framework for Vanuatu by providing support in the following areas relating to the identified key priority areas and related selected interventions in the Vanuatu MAF:

- Policy Advisory Services

- MDG Planning and Monitoring

- MAF Advocacy & the Post 2015 agenda

- Programme Management and M&E

- Resource Mobilization for the Implementation of the MAF

- MAF Advocacy and Awareness Raising

MAF National Project Coordinator & UNDP

Project Board

Senior Beneficiary

Office of the Prime Minister

Executive

Chair of MDG Taskforce/UNDP RR

Senior Supplier

MAF Expert Group & MDG Taskforce

Project Assurance

UNDP MCO & PC

Project Support

UNDP, UN Agencies & other development partners

Project Organisation Structure

TEAM A

DSSPAC,

Office of the PM

TEAM C

Other Government Agencies, Civil Society, SOEs, Academia and Private Sector

TEAM B

Ministry of Health