PROJECT NARRATIVE and FINANCIAL progress report TEMPLATE

PROJECT NAME AND ID: TURKEY’s engıneer gırls

REPORTING PERIOD: January 2017 – march 2017

Project Synopsis

| Project Name | Turkey’s Engineer Girls |
| --- | --- |
| Location | Ankara, Turkey |
| Project Duration | 5 years |
| Project Start Date | August 2016 |
| Project End Date | December 2020 |
| Reporting Period | January 2017 – March 2017 |
| Overall Objective | Overall the Project targets to develop models to support promotion of engineering profession, high quality women employment and inclusive business models while analyzing the regulatory framework to create enabling environment to support and adopt inclusive business practices with a strong emphasis on gender mainstreaming and gender equality. |
| Direct Beneficiary | Ministry of Family and Social Policies |
| Target Groups | Female engineering students in universities, female high school students, corporate staff of Limak |
| Final Beneficiaries | Female engineering students in universities, high school teachers, high school students, parents of high school students, corporate staff of Limak |
| Expected Results | Professional women employment in leading services and manufacturing sectors supported with scalable models contributing to transformation to more inclusive business environment |
| Main Activities | An analysis framework developed on assessment of challenges and barriers. A support program to empower and encourage female students for engineering designed. Corporate inclusive business models to adopt, implement and advocate gender sensitive approaches developed |

# EXECUTIVE SUMMARY

During the reporting period Project Board (PB) meetings took place frequently in order to accelerate the high school program to be conducted with the 2016-2017 academic year.

Within the scope of the project, a Gender Equality Training was held for the employees of Limak Holding on 24 February 2017. Within the context of the 2nd component of the project; the partnership with METU Interdisciplinary Design Studio has been completed and the board game was created by the METU IDS team for the Turkey’s Engineer Girls Project to be used for the high school programmes.

Project consultant carried out the focus group meetings and reported the outputs of these meetings.

# Purpose

The project has two expected results:

- A support program to empower and encourage female students for engineering designed: This activity will identify challenges for female students to prefer engineering faculties and design two-fold support program. a. To increase participation from female students to engineering departments

b. To empower female engineering students through scholarship, capacity building, awareness raising activities.

- Corporate models to adopt, implement and advocate gender sensitive approaches developed: Benefiting from the experience of the assessments carried out in first result internal analysis will be carried out in Limak Holding for corporate principles on gender equality. Internationally recognized tools will be used and internal capacity building programs will be developed along with the advocacy plan.

# Results

- Narrative reporting on results:

- Outcomes:

The long term outcome of the Project is to increase women’s high quality employment and advocate gender equality principles in the leading services and manufacturing sectors to improve inclusiveness of economic growth in a sustainable manner. Advocating gender equality principles within the private sector companies has been started by holding meetings and engaging the consultants professionalized on gender studies to the project.

- Outputs:

Within the scope of the project, a Gender Equality Training was held for the employees of Limak Holding on 24 February 2017. Training aimed to help implement the strategy for implementation of knowledge accumulation on gender equality as well as realization of the project within the context of Component 2. The concept of gender equality in education was discussed in general and at the same time project-specific contribution to the preparation of a conscious work environment for female engineers to take place in the sector. An overview of the Gender Equality Seal, a certificate program supported by UNDP for public and private sector organizations, was also introduced.

Within the scope of the project, focus group meetings / negotiations were held with various sections to contribute to the program aimed at encouraging and supporting the participation of female students in high school education to engineering professions. Three main groups were identified for focus group meetings. The first group consisted of students, teachers and parents, the second group of female engineers, and the last group consisted of female students studying in engineering faculties of universities. The reason for the selection of these groups is that the program that will be prepared for the high school is composed of sections where information can be taken to determine the purpose, the target groups, the content and the method. As it is stated in the report of the consultant; “Common points in all three groups; The fact that gender equality and its importance are not known by a large majority of participants, that gender plays an important role in choosing a profession, that many aspects of school life are shaped / influenced by the gender concept and that this is not adequately known and questioned by many, especially teachers, The fact that this is still considered a "male" profession because of the engineering profession and gender relation, which leads to a contradiction in the number of female students in engineering faculties and the number of female engineers in business life.”

A TV commercial has been telecasted. The commercial aimed to encourage girl students to select engineering as a profession as well as touching parents of these students to support them in selecting engineering.

The analysis of the current scholarship program was conducted by a consultant and during the reporting period the Baseline Report and the Evaluation Report have been delivered.

- Explain, if any delays in implementation, challenges, lessons learned & best practices:

Project Risks:

| Type | Date Identified | Description | Comment or Management Response |
| --- | --- | --- | --- |
| OPERATIONAL | August 2016 | Change in the operational priorities of the partner institutions | Establishing strong communication channels with partners |
| ECONOMIC | August 2016 | Lack of interest from high schools to be a part of the awareness program | Training of trainers will be in place. |

Using the Project Results Framework from Logframe of the Project Document - provide an update on the achievement of indicators at both the output and outcome level in the table below. Where it has not been possible to collect data on indicators, clear explanation should be given explaining why, as well as plans on how and when this data will be collected.

|  | Indicative Activities | Achieved Indicator Targets | Reasons for Variance with Planned Target (if any) | Source of Verification |
| --- | --- | --- | --- | --- |
| Output 1 Professional women employment in leading services and manufacturing sectors supported with scalable models contributing to transformation to more inclusive business environment Indicator: 1. Support program 2. # of employees trained 3. # of women engineers benefited from support programs developed 4. # of models to support inclusive business and gender sensitive approaches 5. # of assessments and reports Baseline: 1. Assessment on challenges for women in engineering intense sectors-services and manufacturing- limited 2. Awareness on gender equality and women’s empowerment among service sector and manufacturing sector is low 3. Programs support female engineering students and their capacity development, limited 4. Corporate models supporting gender sensitive inclusive business models, limited Planned Target: Analysis Framework ready Evaluation Programme Initial corporate gender analysis | 1.1 An analysis framework developed on assessment of challenges and barriers 1.1.1 Identification of research methodology and tools 1.1.2 Development of evaluation plan for the long term program 1.2 A support program to empower and encourage female students for engineering designed. 1.2.1 Pilot Support Program for engineering students for capacity improvement (i.e. Scholarship program, engineering management, social engineering programs) 1.2.2 Pilot Support Program for high school students 1.2.3 Pilot Capacity Building for corporate staff 1.3 Corporate inclusive business models to adopt, implement and advocate gender sensitive approaches developed 1.3.1 Institutional Needs Assessment 1.3.2.Gender Equality Mainstreaming Studies in Holding Company (or selected companies) 1.3.3 Capacity Building for corporate staff 1.3.4. Assessment of international recognized tools promoting gender equality for inclusive business 1.3.5 Policy Advocacy on scaling the exercise in different sectors within the Limak holding 1.3.6 Promotion and Communication Plan of the Overall Programme | 1.1. For the Identification of research methodology and tools under the preparation of the analysis framework, a consultant was contracted. 1.2.1 Baseline Report and the Evaluation Report have been delivered. 1.2.2 The partnership with METU IDS continued and the board game has been prepared and submitted to UNDP to be used in high school program. 1.2.3 Not started 1.3.1 Not started 1.3.2, A representative from Limak participated in the Panama meeting of UNDP on Gender Seal for private sector. They will participate on 21-22-23 November 2016. Gender training was held within Limak by the Gender Advisor of UNDP Turkey. 1.3.3 Not started 1.3.4 Gender Equality Seal document of UNDP translated in Turkish 1.3.5 Not started 1.3.6 A TV commercial was telecasted for 1 week on Turkish TV channels. |  | Deliverables of consultants The board game designed for the high school program |

- Programmatic Revisions (if applicable)

N/A

- Budget and Financial Progress

| Fiscal Year | Fund | Donor | Responsible Party | Budget | Encumbrances | Expenditure | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2017 | 30000 | 12704 | 000639 | 73,440.00 | 9,600.00 | 44,758.59 | 19081.41 |

Report Submitted By:…

Name/Surname: Ceyda Alpay

Title: Project Manager

Date: 15/04/2017

Signature:

# Footnotes

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document/ specific so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

# Text boxes

ii) Indicator Based Performance Assessment: