## Sheet1
Project Time Plan | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2022-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01
|  |  |  | 1900-01-20 | [5 empty] | 1900-01-20 |  | 1900-01-21
Planning
Signing the Project Contract
Preparation Meetings
Determination of the Project Provinces
Determination of the Cooperatives
Procurement Processes
Implementation
1.SERVICES FOR INVENTORY OF LOCAL PRODUCTS
1.1.Roadmap and Inventory Study
1.2.Product Identification Cards
1.3.Digital Platform Design
1.4.Local Products Identification Card Preparation
2. BUSINESS DEVELOPMENT SERVICES FOR WOMEN COOPERATIVES
2.1.Inception Report
2.2.Needs Analysis for Women’s Cooperatives
2.3.Provision of Business Development Consultancy
2.4.Identification of Grant Areas and Provision of Grants
3. BOOTCAMPS AND BUSINESS DEVELOPMENT SERVICES FOR ENTRE.
3.1.Inception Report
3.2.Organization of the Bootcamps
3.3.Selection of Beneficiaries for in-kind Support
3.4.Provision of Business Development Consultancy
3.5.Identification of Grant Areas and Provision of Grants
Monitoring & Evaluation
Follow-up
Final Report